| Meeting Date | 25 March 2025 |  | Agenda Item |  |  | 4.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Performance and Finance Committee |  |  |  |  |  |
| Report Title | Cancer Performance Update |  |  |  |  |  |
| Report Author | Marisa Bennett, Cancer Performance & Information Manager |  |  |  |  |  |
| Report Sponsor | Craige Wilson, Deputy Chief Operating Officer |  |  |  |  |  |
| Presented by | Deb Lewis, Chief Operating Officer |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The report provides an update on the delivery of the Single Cancer Pathway for Swansea Bay UHB patients. It focusses on recovery plans in place for the top tumour sites: - Lower Gastrointestinal - Breast - Upper Gastrointestinal - Gynaecological - Urological - Skin |  |  |  |  |  |
| Key Issues | This report will highlight current performance for both backlog and Single Cancer Pathway. Demonstrates by tumour sites current performance to meet 10-day outpatient; 31-day Decision to Treat internal targets and 5-day pathology turnaround. Identifies key service delivery challenges and mitigating actions. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - Acknowledge the performance and backlog volumes in the main tumour sites. - Acknowledge the additional work required to improve both performance and backlog. |  |  |  |  |  |

CANCER PERFORMANCE UPDATE

- INTRODUCTION

In October 2022 Welsh Government (WG) initiated the enhanced monitoring (EM) intervention process for the Health Board (HB) due to quality issues relating poor performance and long waiting times.  In January 2024 the HB was escalated to targeted intervention (TI) within several areas, including performance against the Suspected Cancer Pathway (SCP). The HB meets with WG TI on a monthly basis.  The areas of greatest focus both locally and nationally for improvement are:

- Lower Gastrointestinal, Gynaecological and Urological

In addition, the HB has identified other key tumour sites for improvement, including:

- Lung, Upper Gastrointestinal, Breast and Skin

Whilst performance for skin cancer regularly meets the 75% compliance target; as a high-volume tumour site any improvement or deterioration of the position impacts significantly on the HB’s performance as demonstrated within this report.

In order to be de-escalated from TI, 60% of patients must be treated within 62 days for three consecutive months.  Following quarterly resubmissions, the HB achieved 60% for six consecutive months, April 2024 to September 2024.

- BACKGROUND

The HB monitors two primary metrics for the single cancer pathway:

- % Performance within the 62-day target

- Backlog volumes (patients waiting over 62 days)

Performance 2023-2025

Graph 1 – SCP Performance 23-25

The graph above shows the HB’s SCP performance since April 2023.  It represents the patients receiving first definitive treatment (FDT) within the 62-day target against the target of 75%.

Performance fell to a very disappointing 52% in January 2025.  As demonstrated below, most tumour groups fell short of required delivery.  At least 14% of patients treated had some form of patient unavailability recorded, this number is likely be higher with closer scrutiny.  Performance would be in the region of a minimum 55% if adjusted pathways were reportable.

| Tumour Site | Total No. of patients treated | No. of patients treated within target | % | Tumour Site | Total No. of patients treated | No. of patients treated within target | % |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Head and neck | 14 | 5 | 36% | Breast | 32 | 19 | 59% |
| Upper GI | 24 | 12 | 50% | Gynaecological | 10 | 1 | 10% |
| Lower GI | 29 | 7 | 24% | Urological | 31 | 9 | 29% |
| Lung | 21 | 10 | 48% | Haematological | 14 | 6 | 43% |
| Sarcoma | 2 | 0 | 0% | Acute Leukaemia | 2 | 2 | 100% |
| Skin | 77 | 61 | 79% | Children's | 0 | 0 | - |
| Brain/CNS | 0 | 0 | - | Other | 4 | 3 | 75% |
|  |  |  |  | TOTAL | 260 | 135 | 52% |

The backlog trajectories were developed based on the anticipated improvement for individualised tumour site, whilst reflecting traditionally what happened for previous bank holidays and holiday period.  Some tumour groups targets were set at zero for backlog throughout the year: Children’s Cancer, Acute Leukaemia and Brain/CNS, the reason for this is that referrals trigger backlog infrequently and volumes do not impact on the overall position.

The table above shows the detail of the most recently reported backlog position, which stands at 192 patients, this is a reduction of 43% since the last reported position to the Committee.

The highest percentage of patients are in Lower GI (21%) this is inclusive of Bowel Screening Wales referrals, Skin (17%) and Urological (16%).  The position demonstrates a gap to trajectory of 88 patients.

In response to the performance escalation to Targeted Intervention (TI), the Health Board continues weekly TI meetings with both clinical and service leads, chaired by the Deputy Chief Operating Officer, attended by the Medical Director and supported by the Cancer Performance and Information Manager.  The agenda for these meetings include:

- Discussion of tumour site or service action plans

- A review of performance against first outpatient waits and diagnostic turnaround times

- A review of the last 10 breaches to identify themes and trends for a summarised visual presentation.

The Health Board continues to focus efforts on the front end of pathway.  Three pathway milestones previously identified by the Chief Operating Officer to further improve the SCP performance that we are monitoring are:

- First outpatient attendance must be within two weeks of receipt of referral.

The Planned Care Vitals Dashboard is used to report the waits based on activity within any month; this does not reflect patient choice/unavailability.  Additional monitoring arrangements and scrutiny is in place via tracking data and weekly review meetings with the services.  Every service saw an improvement in waiting times or percentage achieving the 2 week wait.

- That decision to treat must be attained by day 31 of pathway

The chart below demonstrates the median wait days from suspicion to decision to treat from September 2023 to January 2025 for closed (treated) pathways and percentage meeting 31 days.  November 2024 the only month where this metric has been achieved.  It is expected February will see some improvement.

- That cellular pathology reports will be available within 5 days

The cellular pathology service remains under extreme pressure and whilst there has been some improvement in reporting USC cases, there is very much a need for improvement.  The chart below demonstrates the specimen turnaround times within cellular pathology for those labelled ‘USC’.

Overall, there is little change.  Pathology remains an area of significant challenge, particularly from a consultant workforce perspective with vacancy, retirement and a known capacity gap.  The service is reliant on what has become routine outsourcing and non-recurrent funding.  Further mitigating actions include WLI’s and a recently retired consultant providing sessions via Bank and the HCSE team are working with the service.  A vacancy is due to be advertised imminently for a consultant post and a further post to go through the vacancy control process whilst also seeking locum cover.

In addition to USC monitoring, we are also monitoring the ‘CAN5’ waiting times, these are specimens identified for accelerated diagnostic turnaround (highly suspicious of malignancy endoscopically).  Performance of reporting turnaround times for this cohort is overall good.

- Treatment waits

In addition to the above three measures, treatment waits are included in monitoring arrangements.  The graph below demonstrates the median wait days and percentage of patients achieving treatment within 21 and 31 days of decision to treat to first definitive treatment (FDT) by month treated.

This wait however is skewed significantly when FDT includes pathways where treatments include ‘active monitoring’ or ‘hormone therapy’.

As such, waits for the three primary anti-cancer therapy modalities are separated as follows:

- Surgery:

- Systemic Anti-Cancer Therapy (SACT)

- Radiotherapy

A decline in SACT performance is clearly demonstrated above and whilst surgical and radiotherapy waits are relatively stable, they are above National Optimal Pathway (NOP) recommended 21 days; waits between services and tumour groups varies across modalities and this detail is available and shared with service teams.

The timely access to SACT is an increasing concern with the growing incidence rates of cancer, coupled with treatment advances and an increasing maintenance approach to treatment; waiting times continue to rise.

Multiple rounds of Quality Improvement (QI) work in South West Wales Cancer Centre (SWWCC) have resulted in a streamlined SACT processes resulting in improved chair utilisation and efficiency.

SACT capacity is also limited by the specialist pharmacy and nursing workforce required to safely prepare, check and administer therapy.

- Short-term actions to mitigate the acutely deteriorated Time to SACT position that has increased the HB risk register on this are being enacted.

- A business case outlining a medium-term plan to increase oncology SACT capacity by 2 chairs (15%) and decrease Time to SACT towards those set out in the Welsh QPI have been accepted and being worked through.

- A 3-year plan is in development to sustainably manage increasing demand.

- GOVERNANCE AND RISK ISSUES

Improvement action plans have been developed across a number of tumour sites and diagnostic specialties; the key actions related to these are outlined below.

Breast

This tumour group maintains excellent waiting times for first appointment/triple assessment, and waiting times to decision to treat have been 31 days of less since August 2024.

This has directly contributed to improved performance of the SCP.  Despite the decline in January, looking ahead to February, we anticipate a closing position of approx. 75% for this site.

Gynaecology

- First outpatient waits are maintained under 2 weeks since May 2024.

- PMB clinic waits at around 2 weeks or less currently

  - Long term plan to train 2 additional nurse hysteroscopists.  Training commenced September 2024.

- Gaps in consultant workforce is affecting component waits and overall performance.

  - Medical Director led discussions with Cardiff & Vale UHB

  - To advertise for gynaecologist to include Unit Lead, post is in final stages of approval with Royal College.

  - Insourcing to support gynae-oncology surgical capacity.

Urology

- New outpatient waits are consistently within 10 days.

- Haematuria waits in January were above 2 weeks for the first time since July 2024, primarily due to patient deferrals over the holiday period.  The position improved again in February with the addition of WLI’s for mitigation.

- Pathology turnaround times continue to impact progress for this high-volume tumour group.

- Additional Robotic capacity to include other urological cancer work has commenced however waits remain longer than desired.

- Enhanced surgical capacity to reduce waiting times for treatment.

- Development of a business case end of Q3, to support service expansion to include additional Clinical Nurse Specialist (CNS), administrative support and a 2nd Surgical Care Practitioner.

- Development of a high care unit (2 beds) for Urology at NPTH, increasing acuity of patients able to be operated on at NPTH and increasing capacity at Morriston.

Lower GI

- Collaboration between with the digital team, consultant surgeon and cancer performance manager to improve tracking arrangements, highlighting patients that are not at their desired points along the NOP timelines, developing a more ‘intelligent tracking’ process, work tentatively begun mid-February, and is progressing well.

- The NHS Executive have been working with Public Health Wales (PHW) to produce a Bowel Screening Wales Primary Target List (PTL), this will outline steps and pathway progress to the point of referral to the HB.  This is expected to be available to HB within several weeks.

- TI meeting with lead consultants has taken place. As demonstrated below, surgical waits in this tumour group are too long.  Escalation of surgical capacity through the TI process is under review.

Upper GI

- Appointment of a new MDT Lead for the Hepatobiliary (HPB) MDT in July 2024.  The MDT Lead has met with cancer information and service lead managers to discuss MDT meeting efficiencies, reducing discussion burden that impacts the overall MDT meeting, timely patient discussion and the impact secondary reporting of tertiary scans etc has on individuals and job plans.  Clinical Lead is presented at an NHS Executive HPB forum in November, and the MDT has begun the work to repatriate surveillance to local HBs.

Skin

- Skin has been the tumour site of biggest concern over recent months, with waits at start of pathway particularly within Dermatology leading to increased waits overall, a compounded backlog position and additional breaches. Waiting List Initiatives (WLIs) are being held to mitigate and recover the position in both dermatology and plastic surgery.

- As demonstrated in the above graphs. The median wait to a dermatology first appointment is now around 30 days, waits last seen in May-June 2024.  Plastic surgery also demonstrated a marked improvement in waiting times, with the median wait at 14 days, the lowest since December 2023. This has directly improved the backlog position as demonstrated below

:

- A Locum Consultant started in post 7th November 2024 and a further locum post was advertised, and interviews held in December and an appointment made, however for reasons beyond the HB’s control, is now not able to start until August 2025.

- FINANCIAL IMPLICATIONS

There are no direct financial implications associated with this paper.  The outputs from the modelling work or service initiatives and improvements will inform the development of the Health Board’s IMTP and financial plans for sustainable services.

- RECOMMENDATION

The Committee is asked to:

- Acknowledge the performance and backlog volumes in the main tumour sites.

- Acknowledge the additional work required to improve both performance and backlog

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Accurate, comprehensive demand and capacity plans can increase safety and quality whilst reducing risk and can lead to efficiency gains within clinical services. They will also facilitate more timely treatment of patients and enhance patient experience. |  |  |  |
| Financial Implications |  |  |  |
| There are no direct financial implications associated with this paper. Inputs (additional activity) into the demand and capacity models are funded via Recovery Money. However, the outputs from the modelling will inform the development of the Health Board’s IMTP and financial plans for sustainable services. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| There are no legal implications to consider. |  |  |  |
| Staffing Implications |  |  |  |
| There are no immediate staffing implications as a result of this paper but there is a need to be mindful that this is a very specialist area and we need to build robust and sustainable capacity in this area. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Report History |  | Previous reports have been presented to Management Board in November 2021 and February / August 2022 / October 2023 / February 2024 |  |
| Appendices |  | None. |  |