## Slide 1
Regional Partnership Board
11th Feb 2025
Update on RIF Evaluation and Review Process and Allocations for 25-26
Notes: Purpose of the report today
Update the regional funding position for 25-26
Outline the process for the RIF review and evaluation for all regionally funded schemes
Note the key lessons learned and endorse the key actions

## Slide 2
Summary of Regional Integration Fund (RIF) 25-26
Allocated as a flat rate of funding over 5 financial years from April 2022 to March 2027
Notes: Flat rate of RIF funding
short break funding for carers only until March 2026

## Slide 3
Summary of other Regional Funding 25-26
Other Sources of Regional Funding | Duration of Funding | Funding
Health Board MH Service Improvement Funding | Recurrent | £ 392,047
Dementia Connector Funding | Recurrent | £ 100,000
IRCF Revenue for Capital | 31 March 2026 | £ 669,500
Neurodiverse Funding: |  | 
Sustaining Existing Services (Health Board) | 31 March 2025 | £ 182,840
Transformation | 31 March 2025 | £ 307,556
Other Regional Funding |  | £ 1,651,943
Notes: And Dementia Connector Funding recently allocated to BRC - £100k recurrent funding
Awaiting confirmation of ND funding
Total regional funding of £20.3m

## Slide 4
RIF Review and Evaluation Process 24-25
All regionally funded projects funded on a yearly basis
RIF review and evaluation process is currently undertaken on an annual basis after quarter 2 reports submitted
Basis of the evaluation and review utilise the following
  Performance Measures (How much, how well, difference made)
  Story of Change (Narrative) Report
Funding panel / extra-ordinary board held with representatives from Board to review all schemes
All panels / Boards were quorate
All schemes were approved in Steering and Advisory Board on 17th December, so that all project leads could be notified of funding for 25-26

## Slide 5
Programme | No of Projects Reviewed 24-25 | No of Projects Approved 25-26 | Projects Not Approved
Carers | 22 | 22 | All projects approved
Children and Young People | 21 | 21 | All projects approved
Learning Disability | 19 | 15 | 2 projects not approved 2 projects completed
Communities and Older People | 22 | 20 | 1 project not approved 1 project, decision TBC
Neuro-diverse | 2 | 2 | All projects approved
Mental Health | 27 | 26 * | 1 project not supported
Dementia | 16 | 14 | 2 projects not supported
Social / Micro Enterprise | 2 | 2 | All projects approved
TOTAL | 131 | 122 | 9 less projects
Notes: All funded schemes are included in attached spreadsheet
* 4 third sector schemes approved only 6 months under MH

## Slide 6
Summary of Investment 24/25 & 25/26
Programme | Funding 24-25 | Funding 25-26 | Difference | Comments
Carers | £919,791 | £919,791 | £0 | 
CYP | £2,898,533 | £2,898,533 | £0 | 
LD | £621,428 | £507,446 | £113,982 | 6 schemes due full year costs in 25-25
Communities and Older People | £9,380,332 | £9,352,549 | £27,783 | 
Mental Health | £1,006,791 | £950,353 | * £56,437 | Full year costs for programme lead in 25/26
Dementia | £1,614,392 | £1,539,797 | £74,595 | Westfield House outstanding
Neurodiverse (ND) | £16,096 | £16,096 | £0 | 
Social /Micro Enterprise | £148,848 | £148,848 | £0 | 
TOTAL | £16,606,211 | £16,333,413 | £272,797 | 

## Slide 7
Chart: Total REGIONAL Funding 25/26 Regional/local SPLIT
| Local – NPT | Local – Swansea | Regional
Total | 769435.81 | 1428254.46 | 14533724.0628
Notes: All regional funding confirmed for 25-26 - £16.333m + £0.398m for IAS = £16,731m
Includes: RIF, RIF – Dementia, Memory Assessment, WG Carers, IAS, HB MH Service Improvement Funding, Dementia Connector Funding
NPT – 35% / Swansea – 65%

## Slide 8
Chart: Total Funding 25/26 Regional/local
Chart: Total Regional Funding 25/26 per Programme
| SM/SE | ND | LD | Carers | Mental Health | Dementia | Childrens | Communities & Older People
Sum of Total Funding 25/26 | 148848 | 414096 | 507446.48 | 919791 | 950353.5 | 1539797.06 | 2898533.2928 | 9352549
Percentage | 0.0088963 | 0.02475 | 0.030329 | 0.054974 | 0.056801 | 0.09203 | 0.17324 | 0.55898
Notes: All regional funding confirmed for 25-26 - £16.333m + £0.398m for IAS = £16,731m
Includes: RIF, RIF – Dementia, Memory Assessment, WG Carers, IAS, HB MH Service Improvement Funding, Dementia Connector Funding

## Slide 9
Chart: Total Funding 25/26 Regional/local
Includes: RIF, RIF – Dementia, Memory Assessment, WG Carers, IAS, HB MH Service Improvement Funding, Dementia Connector Funding
Chart: Total Regional Funding 25/26
| Statutory | Third Sector
Total | 12366280.67 | 4365133.6628
Notes: Excludes any funding not yet confirmed: Short break funding (carers trust), ND, IRCF revenue
Excludes regional infrastructure and PM costs

## Slide 10
Chart: Total Funding 25/26 Regional/local
Includes: RIF, RIF – Dementia, Memory Assessment, WG Carers, IAS
Chart: Total RIF Funding 25/26
| Statutory | Third Sector
Total | 13560355.67 | 4392361.6628
Notes: All RIF
Does not include short break funding (which comes under RIF)
Greater reduction in stat schemes
Number of LD schemes that have proportionally more funding in 25/26 given they are full year costs
Does not include un-allocated

## Slide 11
Key Lessons Learned and Actions from RIF Review & Evaluation Process
Theme | Lessons Learned | Action
Strategic Framework | Current process lacks a strategic framework, instead focusing on individual schemes. | Panel members requested assurance future plans will adopt a more strategic approach, promoting a cohesive and integrated service offering. Currently developing strategic approach in EW & MH Programme around new commissioning model for 3rd sector and single point of access for services.
RIF Funding Impact | Flat rate of RIF funding and additional NI costs will affect projects in terms of the scope, reach and impact | Collate impact from project leads to collate and escalate to Programme Boards to understand scale of the impact. Ensure correspondence to 3rd Sector provides assurance that reduction in service offer is expected
Significant Resource required for current process | Substantial time commitment from regional and local staff for RIF review and evaluation process, leading to decision to discontinue funding for 7 projects in 2025-26 period | Full review of process for 26-27 ensuring links with the national evaluation
Notes: A lessons learned document was developed and updated throughout the process. There are a number of actions that will need to be undertaken and monitored by West Glamorgan and Programme Boards.

## Slide 12
Key Point / Lessons Learned
Theme | Lessons Learned | Action
Proportionate process | Current reporting and monitoring process is not proportionate to amount of funding allocated | Full review of process for 26-27 to ensure a more proportionate process is followed
Return on Investment | Further work required to develop consistent process for identifying and demonstrating cost avoidance and social value performance. | Develop process for ROI, linking in with national work to ensure consistent approach adopted
Regional Project Support | Low support numbers in NPT for some regional schemes. (Usual split is 60/40, Swansea/NPT) | Review the regional / NPT numbers, whilst over-laying demographic data. Liaise with regional projects to understand accessibility for NPT residents, plans to ensure accessibility, and how they promote schemes to NPT residents

## Slide 13
Recommendations
Note the approach for funding for RIF schemes for 2025-26 and the schemes detailed in Appendix 1
Endorse the actions in line with the key lessons learned
Note discussions are underway with RPB Leads and WG to develop the next iteration of the regional funding. This presents an opportunity to shape future funding based on the lessons learned so far