| Meeting Date | 27 May 2025 |  | Agenda Item |  |  | 2.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Performance and Finance Committee |  |  |  |  |  |
| Report Title | Monthly Recovery & Sustainability Programme Update |  |  |  |  |  |
| Report Author | Brian Owens – Director Recovery and Sustainability |  |  |  |  |  |
| Report Sponsor | Darren Griffiths – Director Finance and Performance |  |  |  |  |  |
| Presented by | Brian Owens, Director Recovery and Sustainability |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The report is provided to update the committee on the current actions and work in progress of the Recovery & Sustainability programme. |  |  |  |  |  |
| Key Issues | - The savings plans have not delivered as required resulting in £4.1m deviation from the expected position. - There are significant gaps in the Service Groups savings plans - Variable pay continues at levels comparable to the previous year despite an improvement in agency expenditure - Agency expenditure achieved the required reduction to delivery against the ‘enabling action’ from the Cabinet Secretary |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - - RECEIVE the updated report for ASSURANCE of ongoing delivery associated with the Recovery and Sustainability Programme |  |  |  |  |  |

MONTHLY RECOVERY & SUSTAINABILITY PROGRAMME UPDATE

- INTRODUCTION

The paper provides the monthly formal update to the committee regarding the actions and progress within the Recovery and Sustainability programme.

- BACKGROUND

The Recovery and Sustainability (R&S) board met on 14th May 2025, with the second monthly meeting set for 28th May 2025.

The meeting commenced with a presentation by the Director of Finance on the month one financial position. The presentation and discussion emphasised the need for urgent remedial action to address the significant gaps in the savings plan and to recover the £4.1m overspend in the coming months.

Additionally, expenditure on variable pay has continued with the month one variable pay cost at the same levels as the previous year despite the additional controls and executive level scrutiny of agency requests, this is covered more fully later in this report.

Table 1, provides a summary position of the savings as of 7th May.

Table 1.

£17.04m of savings have been identified, £12.99m is classified as ‘red’, £1.66m ‘amber’ and £2.38m as ‘green’ schemes.

The largest unidentified savings gap is within the Primary Community and Therapies (PCT) group, where £0.5m (4%) of the required savings have been identified.

Service Groups were advised they needed to identify additional recurrent savings and progress the ‘red’ schemes so that they moved into the ‘green’ delivery categorisation.

a. Agency Reduction

Month one was the first ‘official’ reporting from each of the four service groups on the delivery of their plans to achieve the 30% reduction on last years outturn expenditure which forms part of the Cabinet Secretaries enabling actions.

To achieve the 30% reduction each of the service groups have a monthly maximum expenditure requirement they must not exceed to enable the delivery of the 30% reduction in agency expenditure.

Table 2 shows month one performance against the maximum expenditure plan.

Table 2

At an aggregated position the requirement to spend no more than £1.1m on agency was achieved. The NPTS and PCT service groups were under the maximum expenditure, MHLD up to the maximum whilst Morriston service group exceeded the maximum threshold.

b. Other Variable Pay

Whilst agency expenditure has reduced, other forms of variable pay have increased offsetting any benefit against the total variable pay cost.

Although the planned care recovery programme costs for variable pay are included in the overall expenditure an assessment of the likely costs associated with the planned care recovery has identified that c.£146k could be attributed to this area.

The enhanced scrutiny processes are continuing with agency scrutiny led by the respective clinical executives and nurse bank usage via triumvirate nurse directors.

The executive director for workforce articulated within the R&S board an approximate guide to the maximum levels of variable pay they would expect to see across the nursing workforce. At the time of writing, the analysis is yet to be finalised however, it appears to evidence that bank usage is c.3% higher than they would typically expect. Further detailed analysis is required to confirm the position however, it correlates with the increasing bank usage experienced over recent months.

Additionally, overtime expenditure in month one was £841k. We have not implemented enhanced senior scrutiny over this area of variable pay however, at these levels of expenditure additional scrutiny process will need to be considered.

c. Service Groups Absence Management Plan

The service groups presented their absence plan updates at the recent R&S board, the purpose was to demonstrate compliance and delivery against the corporate absence plan that has been previously presented.

Whilst each of the service groups are making some progress in this vitally important area, noting that absence is one of the primary drivers to the current levels of staffing unavailability. It was apparent from the presentations that further focus is required in this area. Further presentations will be required to provide assurance, and clarity will be provided to the service groups regarding the expectations.

d. R&S Programme Update

The board received a verbal update regarding progress on the main over arching workstreams. Of the eleven work streams 10 have completed project initiation documents (PIDs) and the project plans are currently being completed.

The Enabling Actions work stream does not yet have a PID or work plan however, considerable work and support has been deployed on this area working in collaboration with colleagues from strategy, performance and planned care as there remains a number of points of clarity from Welsh Government on how some of these can be measured.

In respect of the R&S team, there has been a successful appointment into the Head of Recovery and Sustainability post, the individual is currently completing a secondment with Health Education Improvement Wales (HEIW) and will commence in post on 9th June. Additionally, 3 further support programme manager posts are currently being advertised for recruitment. Once in post the team will be more equipped to provide consistent support to the agreed workstreams.

Additionally, as reported last month, an NHS graduate trainee has also commenced a six-month placement within the team with a second graduate commencing in November for a further six months.

e. Executive Led Themes

The above diagram sets out the previously shared executive led themes to support delivery of the savings schemes. The committee has requested updates from the respective executives regarding progress and delivery against each of the themes. The table below sets out an indicative timetable for consideration of the committee, subject to the establish planned work programme of the committee.

N.B. the timetable is indicative and subject to change as it has not been shared with the executive prior to inclusion in this paper.

| Theme | Exec Lead | Proposed Update Date to PFC |
| --- | --- | --- |
| Medicines Management | MD | Jun-25 |
| Clinical Variation | MD |  |
| UEC | COO | Jul-25 |
| Planned Care | D COO |  |
| Digital Enabled Changes | DD | Aug-25 |
| Things to Stop | DOTHS / DONPE |  |
| Workforce Redesign | DOWOD | Sep-25 |
| Variable Pay | DOWOD |  |
| CHC | DOPP | Oct-25 |
| Pathway Redesign | DOPP |  |
| Demand Management | DOPH / MD | Nov-25 |
| Commissioning / Contracting | DOPP |  |
| Non Pay / Procurement | DOF | Jan-26 |
| General House Keeping | DOF |  |
| Utilisation of Estate | DOF |  |

- GOVERNANCE AND RISK ISSUES

The establishment of the team will ensure resources are available to support the delivery of the main workstreams in a consistent manner. The Service Group savings plans however, have significant gaps and of those identified the largest elements have been classified as ‘red’ schemes, until those plans have identified the short fall risk remains to the delivery of the savings plan.

- FINANCIAL IMPLICATIONS

The financial implication of this report are included within its contents.

- RECOMMENDATION

Members are asked to:

- RECEIVE the updated report for ASSURANCE of ongoing delivery associated with the Recovery and Sustainability Programme

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| No Implications |  |  |  |
| Financial Implications |  |  |  |
| No Implications |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| No Implications |  |  |  |
| Staffing Implications |  |  |  |
| No Implications |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| No Implications |  |  |  |
| Report History |  | Routine report to Performance and Finance Committee |  |
| Appendices |  | none |  |