| Date | 27 May 2025 |  | Agenda Item |  |  | 4.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Meeting | Performance and Finance Committee |  |  |  |  |  |
| Report Title | Annual Plan 24/25 Delivery: Quarter 4 Progress Report |  |  |  |  |  |
| Report Author | Charlotte Edwards, Planning Project Support Ruth Tovey, Head of Strategic Planning Ffion Ansari, Head of IMTP Development & Implementation |  |  |  |  |  |
| Report Sponsor | Marie Davies, Executive Director of Planning & Partnerships Karen Stapleton, Deputy Director of Planning & Partnerships Deb Lewis, Chief Operating Officer |  |  |  |  |  |
| Presented by | Marie Davies, Executive Director of Planning & Partnerships |  |  |  |  |  |
| FOI | Open |  |  |  |  |  |
| Purpose of the Report | This paper provides the reported Quarter 4 status of the priorities for delivery, as set out in the Health Board Annual Plan 24/25 as Goals Methods Outcomes (GMOs). |  |  |  |  |  |
| Key Issues | - High-level summary provided of the position at the end of Q4 (1st January 2025 – 31st March 2025) in respect of delivery against Annual Plan priorities (Goals and Methods). Where Methods are reported as off-track, mitigating actions and revised delivery timescales are highlighted as approved by the Annual Plan Oversight Group on 30th April 2025. - Performance against Annual Plan System Indicators (aligned to the Key Performance Indicators set by Welsh Government) are highlighted at the end of Q4. - As per above, the Minimum Data Set (MDS) has been updated with actual data against the required metrics, as requested by Welsh Government as part of the NHS Wales planning process. This will be presented to the Performance & Finance Committee and Board in March for approval to submit to Welsh Government. |  |  |  |  |  |
| Specific Action Required | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☒ |  |
| Recommendations | The Board is asked to: - CONSIDER the areas of achievement in delivering the Annual Plan in Q4. - CONSIDER mitigating actions against GMOs which are off-track. - CONSIDER the mitigations and next steps where delivery is off track. |  |  |  |  |  |

ANNUAL PLAN 24/25 DELIVERY: QUARTER 4 PROGRESS REPORT

1. INTRODUCTION

This paper provides the reported status against the priorities for delivery in Quarter 4 24/25, as set out in the Annual Plan as Goals Methods Outcomes (GMOs). Any changes from the plan submitted to Welsh Government, including revisions to quarterly milestones, are presented for the assurance of the Performance & Finance Committee.

2. BACKGROUND

The Health Board has a statutory duty to submit a financially balanced Integrated Medium-Term Plan (IMTP) annually. The Health Board approved and submitted to Welsh Government its Annual Plan for 24/25 in March 2024. Subsequently, the Health Board resubmitted the Annual Plan for 2024-25 to WG on 31st May 2024. Whilst the Plan remained unchanged in terms of planning assumptions, the HB advised Welsh Government that further work at speciality/divisional level had been undertaken to refine the 24/25 demand and capacity profiles, leading to revised performance trajectories for several Welsh Government Key Performance Indicators (KPIs). As such, the respective Ministerial Templates and Minimum Data Set (MDS) were resubmitted as revised based on the updated trajectories set against new targets from Welsh Government.

The Annual Plan is structured in ‘systems’-based programmes of work that have key deliverables (GMOs) outlined. The responsibility for GMO operational delivery and performance sits with the Service Groups.  However, the accountability in providing direction and monitoring the delivery progress of System GMOs is via Programme Boards (or equivalent group). The Exec Lead/SROs for the system areas are set out in Table 1, below:

| System /Programme | SRO/ Exec Lead |
| --- | --- |
| Urgent & Emergency Care | Chief Operating Officer |
| Planned Care | Chief Operating Officer |
| Cancer | Executive Medical Director |
| Children and Young People | Executive Director of Nursing and Patient Experience |
| Maternity and Women’s Health | Executive Director of Nursing and Patient Experience |
| Mental Health and Learning Disabilities | Group Service Director for Mental Health and Learning Disabilities (reporting to Chief Operating Officer) |
| Primary Care | Group Service Director for Primary, Community, and Therapies (reporting to Chief Operating Officer) |
| Workforce | Executive Director of Workforce and Organisational Development |
| Digital | Director of Digital |

The Annual Plan Oversight Group (APOG), chaired by the Executive Director of Strategy, received an update on Q4 position from all areas on 30th April 2025.

It should be noted that the 2024/25 Annual Plan has now been superseded by the 2025/26 Annual plan. Outstanding actions not delivered in Q4 of 24/25 have been incorporated where appropriate into the 2025.26 Annual Plan reviewed by Board on 27th March 2025.

3. ANNUAL PLAN 24/25 DELIVERY UPDATE

3.1 PROGRESS AGAINST PLAN – SUMMARY

SROs were asked to update on the Q4 status of the Method (Action) component of the GMOs, assessed against delivery of Q4 milestones, using the definitions outlined in Table 2:

| METHODS STATUS | Definitions |
| --- | --- |
| Green | ON TRACK - Progressing as planned /to agreed timelines |
| Amber | OFF TRACK – Not progressing as planned/ to original timelines, however this is manageable & mitigating actions are in place |
| Red | OFF TRACK – Not progressing as planned/ to original timelines, there are significant issues which require escalating |

Q4 Highlight Reports were also provided to inform discussions at the APOG meeting.

Service Group reporting on the GMOs that they own and lead (as agreed through the GMO Mapping and Governance exercise, undertaken by Strategy in May 2024) were extracted into the System Highlight Reports. The Service Group Directors provided their review and sign off on the resulting System Plan Highlight Reports related to their areas.

Table 3, below, summarises performance by reporting area, reflecting cross-cutting (Service Group and Programme Board reporting group) GMOs in the figures of each area to which they are relevant:

| Reporting Area: | Q4 status METHODS: |
| --- | --- |
| Primary Care, Community & Therapies | 2 12888 |
| Neath Port Talbot Singleton | 1 |
| Morriston |  |
| Mental Health & Learning Disabilities |  |
| Outpatients |  |
| Urgent & Emergency Care |  |
| Digital |  |
| Workforce & Operational Development |  |
| Population Health |  |
| One Bay Way |  |
| Overall performance against Q4 milestones: |  |

Table 4, below, summarises performance of systems included in the figures reported by service, above:

| Reporting System: | Q4 status METHODS: |
| --- | --- |
| Cancer |  |
| Children & Young People |  |
| Maternity & Women’s Health |  |
| Planned Care |  |

3.2 Q4 ACHIEVEMENTS

Q4 achievements are outlined in Appendix 1.

3.3 Off-Track Methods

Table 5, below, details red, ‘significantly off-track,’ methods reported, including reasons for delay and the mitigating actions being undertaken. The Management Board are asked to note these mitigations and proposed next steps.

| GMO (Reference number and Method) | Off-track Milestone for Q4 | Reason for delay and what is being done to bring activity back ‘on track’ (Mitigating actions) | Change to Plan & Proposed Next Steps |
| --- | --- | --- | --- |
| NEATH PORT TALBOT SINGLETON (NPTS) Service Group Lead: Ceri Gimblett |  |  |  |
| Chemo Car (Cancer/Digital), led by Nicki Davies NPTS_15: Ensure Cancer Services have a robust electronic prescribing and administration (ePMA) system for Systemic Anti-Cancer Therapy (SACT) across the South West Wales Cancer Centre region | Responses to CEO letter from network received to agree support for national project | Due to key staff leaving/unavailable, no tangible progress made since. | . Escalated by Martin Rolles to Wales Cancer Network. Rolled over/ redefined for 25/26 Annual Plan (D_18: Engage with the National Programme on the replacement of the Systemic Anti-Cancer Therapy SACT e-prescribing system) |
| MORRISTON Service Group Lead: Sue Moore |  |  |  |
| M_23: Creation of a new Thoracic centre in Morriston Hospital | Welsh Government approval | Approval outstanding | With Welsh Government regarding Capital next steps – not included in prioritisation. Rolled over/ Redefined for 25/26 Annual Plan as Year 1 Planning item (MGH_19a: Develop single centre for Thoracic Surgery) |
| M_24: Creation of a new 6-day service pathway for Acute Coronary Syndrome (ACS) within an ARCH project with Hywel Dda UHB to achieve the 72-hour treatment target which is best practice - Year 1 Planning | Agreement with Hywel Dda UHB | No engagement | Will not proceed without funding agreement from Hywel Dda UHB GMO closed and not included in 25/26 Annual Plan |
| M_05: Stroke Develop a cohesive and compliant approach to the delivery of Stroke services for SBUHB | Further progress and recruitment have not taken place due lack of funding. However, A stroke improvement action plan is in place which currently monitors compliance and details progress against some key issue faced by the service. Actions within this improvement plan will be monitored and implemented moving into 2025/2026. KPI performance continues to be monitored on a weekly basis and within bi-monthly stroke board meetings. | Lack of financial support has delayed the 2nd and 3rd phases of agreed monies are received we are unable to progress this further. | - No funding allocated for the forthcoming years. - Stroke pathway progress is hindered because some areas are not progressing the acute part of the pathway. The focus is on rehab. - Awaiting further discussions and a meetings with the stroke team to address the situation. Rolled over/ redefined for 25/26 Annual Plan (M_06: Deliver the Stroke Service Improvement Plan that aims to transform stroke pathways, expand clinical roles and support early discharge) |
| M_06: Introduce a Comprehensive Regional Stroke Centre (CRSC) to Morriston Hospital | Unable to progress with the dedicated stroke rota and regional ARCH work. Work is however taking place to monitor increase in trajectories via stroke board and work is taking place to look at ensuring we can protect ringfenced stroke beds which is not currently possible due to front door constraints. | Lack of financial support has prevented progress with the dedicated stroke rota and regional ARCH work. |  |
| M_18: Development of 3 theatres in Singleton | Approval from WG | On hold | On hold – not included in Capital prioritisation with WG GMO closed and not included in 25/26 Annual Plan |
| MENTAL HEALTH & LEARNING DISABILITIES Service Group Lead: Dermot Nolan |  |  |  |
| MHLD_11: Adult Mental Health - To fully embed the hybrid clinical model into the assessment and treatment wards in Caswell Clinic. | Evaluation of clinical model to start following recruitment of consultant appointments. | Original plan compromised by the fire (i.e., subsequent loss of Tenby Ward). | Timescales have been delayed due to repairs required. Revised plan being drafted by the Division to repurpose Ogmore Ward as a mixed acuity ward. Rolled over/ redefined for 25/26 Annual Plan (MHLD_04: Joint Commissioning Committee (JCC) Mental Health Specialist Strategy; Progress implementation of Mental Health Specialist Strategy (held by the JCC), recommendations with impact on Caswell Clinic (Medium Secure Unit) and Taith Newydd (Low Secure Unit) |
| MHLD_12: Adult Mental Health Workforce planning to commence in 24/25 following JCC strategic planning to define role and function of wards in Caswell Clinic | Once feedback has been received from JCC, workforce plan can be developed. | JCC have yet to progress delivery of the MH Specialist Services Strategy. | JCC Decision Awaited. Workforce development plans on hold. Rolled over/ redefined for 25/26 Annual Plan (MHLD_04: Joint Commissioning Committee (JCC) Mental Health Specialist Strategy; Progress implementation of Mental Health Specialist Strategy (held by the JCC), recommendations with impact on Caswell Clinic (Medium Secure Unit) and Taith Newydd (Low Secure Unit) |
| MHLD_16: Adult Mental Health (Inpatient) – New Build Centralised inpatient model of service within a purposed built environment meeting the needs of the patient population for the Health Board area. Development of Adult Mental Inpatient provision business case. | If successful - develop outline business case for approval. | OBC for Adult Inpatient Reprovision was not prioritised for capital funding in 25.26 | Capital Funding TBC Rolled over/ redefined for 25/26 Annual Plan as Year 1 Planning item (MHLD_12: New Build Adult Mental Health – Progress Capital Business Case for Modernising Adult Mental Health Inpatient Services |
| MHLD_26: Older Peoples Mental Health (Inpatient) - Renovation of Suite 4, Tonna Hospital Continue with the redesign of the Older Peoples Mental Health Inpatient Services across the Service Group and input into the wider West Glamorgan regional work | Awaiting confirmation of capital funding. | Funding for suite 4 renovation was not prioritised for capital funding in 25.26 | Capital Funding TBC Rolled over/ redefined for 25/26 Annual Plan (MHLD_07: Redesign Older Peoples Mental Health Inpatient Services |
| MHLD_41: Psychology (MH&LD) Meeting therapeutic demand in a timely manner | Paper being submitted to RPB for consideration in relation to potential pump priming | Exceedingly elevated levels of demand. | Workforce Issues -Meeting with DAPH to discuss potential plan. Rolled over/ redefined for 25/26 Annual Plan as a cost neutral delivery action (MHLD_20: Manage Psychological Therapies demand, mitigate risks associated with increased waiting times) |
| OUTPATIENTS Lead: Ceri Gimblett |  |  |  |
| OP_02: Reduce the number of patients on a Follow Up waiting list by 30% (on the March 2019 baseline) | Anyone waiting up to two years to be transferred to Patient Initiated Follow Up (PIFU) pathway and informed of decision and rights of appeal | This milestone is reporting red because a decision to transfer patients onto the PIFU pathway (if waiting on the Follow-Up list for 2 years) has not been progressed. The programme has focused on validating the Follow-Up waiting list to ensure the lists are accurate for implementing the Follow-Up Transformation Programme | A plan has been developed and approved. Baseline assessment sent to all services and completed. All See on Symptom (SOS) and PIFU pathways agreed in the CIN groups have now been mandated in SBUHB. The project team is now in the process of establishing the Clinical Committee that will oversee this programme of work Rolled over/ redefined for 25/26 Annual Plan (OP_05/06: Modernise outpatient redesign (new to follow-up care)- including role of SoS and PIFU, and active discharge, virtual reviews, exploring use of high-volume clinic model |
| OP_05: Show an annual increase in the number of pathways where virtual appointments and reviews are carried out virtually | Demonstrate an annual increase in virtual appointments. | This Milestone is reporting red as whilst there have been some increases in month during 2024/25 for both Follow-Up and New virtual attendances, there was a decrease in the position at end of Q4: April 2024 New - 8.56% Follow-Up - 13.27% March 2025 New - 6.95% Follow-Up - 12.73% This has not been a priority in the outpatients programme for 2024/25 and will be considered as part of the follow-up programme in 2025/26. | This has not been a priority in the outpatients programme for 2024/25 and will be considered as part of the follow-up programme in 2025/26. Rolled over/ redefined for 25/26 Annual Plan (OP_05/06: Modernise outpatient redesign (new to follow-up care)- including role of SoS and PIFU, and active discharge, virtual reviews, exploring use of high-volume clinic model |
| Urgent and Emergency Care Lead: Deb Lewis |  |  |  |
| UEC_01: Predictive identification of future high users of Urgent and Emergency Care - Data analysis & interpretation | Delivery/ Development •Synthesis of data sources into a form for use by key decision makers | Lack of available resource to deliver in 24/ 25 | Project/ GMO was suggested as deferred to 25/ 26 and resource reviewed at that that time to confirm what is deliverable Closed and not included in Annual Plan 25/26 |
| UEC_07: Expansion of District Nursing Out of Hours/ Single Point of Access - Enhance the Community Nursing Service over 24hrs to support End of Life care | Noted that no funding available during 24/ 25 for activity – GMO/ project closed at end of Q2 (non-delivery) | Lack of resource/ funding to deliver | Project/ GMO has been closed for 24/ 25 – no funding available to deliver (non-delivery) Closed and not included in Annual Plan 25/26 |
| Create a Mental Health Emergency Department | Development of strategy | Noted that model of having Section 136 beds at Morriston site unsuitable with mental health beds located at Neath Port Talbot | Recommendation to close project/ GMO in 24/ 25 (non-delivery) Closed and not included in Annual Plan 25/26 |
| UEC_12: Evaluation of current Home First discharge support and subsequent agreement/ development of future intermediate bed provision | Noted that no funding available or support of evaluation during 24/ 25 – GMO/ project closed at end of Q2 (non-delivery) | Flagged that Home First programme board has been discontinued by the Regional Partnership Board – work is continuing but has been incorporated into the older persons group – no plans noted to develop an evaluation or extend the programme (in current financial environment) | Project/ GMO had no support to be taken forward (due to changing structures and no resource to deliver) – project/ GMO closed (non-delivery) Closed and not included in Annual Plan 25/26 |
| WORKFORCE Executive Lead: Tina Ricketts |  |  |  |
| Increase flexible working opportunities for our people through enabling self-rostering | Evaluate self-rostering pilot and look to expand to other service areas | Waiting for service area to define their parameters before being able to go live | Discussions are ongoing Closed and not included in Annual Plan 25/26 |
| DIGITAL Executive Lead: Matt John |  |  |  |
| D_18: Welsh Intensive Care Information System (WICIS)- Implementation | TBC, based upon the National Programme Board decision | An Independent Assessment has been undertaken by WG to assess WICIS as a solution for Intensive Care | Awaiting outcome of Independent Assessment from WG. Rolled over/ redefined for 25/26 Annual Plan: (D_16: Implement WICIS in line with national implementation plan - however noting nationally this is currently ON HOLD)_ |

3.4 SYSTEM INDICATORS PERFORMANCE

Table 6 below details the key system indicators reported for Q4 which are aligned to the NHS Wales Key Performance Indicators and national targets, including those set by Targeted Intervention. Performance in Q4 is correct as at May 2025, encompassing the latest performance trajectories submitted to the Welsh Government, and are rated accordingly:

- Green, if the outcome measure has met or exceeded the original target/ trajectory,

- Amber, if the measure is moving away from the baseline position in the desired direction, has not yet reached the target / trajectory, but the trajectory indicated that it is likely to do so,

- Red, if the measure is not moving in the desired direction, or the trajectory indicates that it will not meet the target. Mitigating actions being undertaken for off track outcomes are routinely reported to P&F Committee and the Board and are therefore not duplicated in this report.

| System | System Indicator | Target | Baseline Position (March 2024) | October 24 FORECAST | October 24 ACTUAL | November 24 FORECAST | November 24 ACTUAL | December 24 FORECAST | December 24 ACTUAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| URGENT AND EMERGENCY CARE | Number of ambulance patient handovers >1 hr | National target: 30% reduction by December 2024 Targeted Intervention Target: A continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on quarter 2 and 3 2023 baseline) | 629 | 500 | 638 | 450 | 632 | 441 | 616 |
|  | Number of patients who spend 12 hrs or more in all major and minor emergency care facilities from arrival until admission | National target: 20% reduction by September 202, Further 20% reduction by March 2025 Targeted Intervention Target: Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across the health board | 1,132 | 875 | 1,234 | 850 | 1,279 | 825 | 1,391 |
| PLANNED CARE | Number of patients waiting more than 52 weeks for a new outpatient appointment | National target: 40% reduction by end of September 2024 Zero by March 2025 Targeted Intervention Target: 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months | 0 | 0 | 0 | 0 | 1 | 0 | 0 |
|  | Number of patients waiting more than 104 weeks for referral to treatment | National target: Zero end of December 2024 Targeted Intervention Target: 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months | 1,832 | 997 | 1,285 | 776 | 1,145 | 460 | 981 |
|  | Number of patients waiting over 8 weeks for a specified diagnostic | National target: 95% to be zero by December 2024 Targeted Intervention Target: - 80% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months. - 80% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 months. - 80% of patients waiting for a NOUS and non-cardiac MRI to be waiting less than 8 weeks and maintained for 3 months | 3,687 | 2,944 | 3,156 | 2,777 | 3,017 | 2,529 | 2,969 |
| CANCER | Percentage of patients starting their first definitive treatment within 62 days from point of suspicion (regardless of the referral route) | National target: 60% performance by December 2024 70% performance by March 2025 Targeted Intervention Target: 60% performance maintained for 3 months against the SCP target | 56% | 62% | 56% | 64% | 66% | 65% |  |
| MENTAL HEALTH | Percentage of therapeutic interventions started within (up to and including) 28 days following an assessment by LPMHSS for people age under 18 years | National target: 80% by December 2024 Targeted Intervention Target: 65% of therapeutic interventions started within 28 days following an assessment by LPMHSS | 100% | 90% | 98% | 90% | 97% | 90% | 94% |
|  | Percentage of therapeutic interventions started within (up to and including) 28 days following an assessment by LPMHSS for adults age 18 years and over | National target: 80% by December 2024 | 98% | 95% | 100% | 98% | 100% | 100% | 99% |

3.5 MINIMUM DATA SET UPDATE FOR QUARTER 4

Welsh Government has requested formal submission of the Minimum Data Set, updated for Quarter 4 24/25. A copy of the Q4 actual data as provided, to date, is included as Appendix 2 and will be submitted to Welsh Government following approval by the Board.

4. FINANCIAL IMPLICATIONS

The Health Board submitted an Annual Plan on 28th March 2024 which reported a deficit of £50.1m. On the 26th of September 2024 the Health Board submitted a revised Financial Assessment for 2024/25, as a result of the operational pressures driving the variance from the £50.1m deficit plan. The September assessment and accompanying letter summarised a high degree of confidence in the delivery of £64.1m deficit position by the 31st March 2025, with further opportunities of £13.3m giving the Health Board line of sight to £50.8m. Recognising the risks around the delivery of the £50.8m but with a line of sight to £50.8m the forecast remained at £50.1m. In early December 2024 Welsh Government (WG) issued an additional £6.4m of recurrent funding to the Health Board, which has reduced the deficit plan to £43.7m.

On the 19th of December 2024 a Special Board meeting was provided with a further assessment of the position based on the information available following Month 8 closedown. In summary the financial assessment showed a possible outturn to end March 2025 of £57.9m against the £43.7m, and so there was a gap to the deficit plan figure of £14.3m. Through Quarter 4 details on the work and options to deliver the gap and achieve the deficit plan were provided in the WG Monthly Monitoring Return submissions.

The Draft Annual Accounts were submitted to WG on 2nd May 2025, which reported a £42.5m overspend deficit against the Revenue Resource Limit, which was £1.2m below the £43.7m Deficit Plan. This will remain a draft position pending the full review by Audit Wales and submission of final accounts on 30th June 2025.

5. WORKFORCE IMPLICATIONS

Several services, including those within planned care and children and young people services, have made good progress with recruitment, training and role development in Q4. However, some workforce challenges were reported by others, including those within mental health and learning disabilities and primary and community services, due to difficulties filling key roles, delays in recruitment processes, and reliance on temporary staffing affecting service continuity. Uncertainty around funding continues to be a challenge especially for capital and digital initiatives. Some areas have also reported challenges in aligning workforce capacity with service demands, particularly in specialist and high-demand areas, highlighted the need for more robust planning and support.

To address workforce challenges, services are implementing a range of strategic and operational responses. These include accelerating recruitment efforts, developing detailed workforce plans, and embedding successful initiatives into business-as-usual operations. Services are also progressing business cases to secure funding, particularly for digital and capital projects, and are aligning with national programmes to ensure consistency and support. Short-term mitigations, such as outsourcing and interim staffing, are being used where necessary, while long-term solutions focus on sustainable service models, enhanced training, and improved infrastructure. Collaborative planning, stakeholder engagement, and targeted investment are central to overcoming systemic barriers and ensuring workforce resilience.

| The Board is asked to: - CONSIDER the areas of achievement in delivering the Annual Plan in Q4. - CONSIDER mitigating actions against GMOs which are off-track. - CONSIDER the mitigations and next steps where delivery is off track. |  |  |
| --- | --- | --- |
| Governance and Assurance |  |  |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |
| No direct implications of this report, however the Annual Plan is predicated on improving quality, safety and patient experience. |  |  |
| Financial Implications |  |  |
| No direct financial implications of this report, see financial implication section for detail on the Finance Plan. |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |
| A Quality Impact Assessment and Equality Impact Assessment process will be part of the broader planning arrangements to ensure that service models detailed in the Plan are quality and equality/ diversity impact assessed. |  |  |
| Staffing Implications |  |  |
| No direct impact outlined in this report however there will be significant staffing implications as a result of new service models outlined in the Annual Plan – risks and implications to workforce form an integral part to planning arrangements. |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |
| The Annual Plan aims to deliver Strategic Objectives aligned to our Wellbeing Objectives through development of the Organisational Strategy. This paper sets out the alignment of the approved Health Board Wellbeing Objectives directly to the Annual Plan Deliverables. |  |  |
| Report History |  | Previous version to Management Board 21st May 2025. |
| Appendices |  | Appendix 1: Q4 Achievements Appendix 2: Minimum Data Set Q4 (Resources and available via Email if required) |