| Meeting Date | 28 November 2023 |  | Agenda Item |  |  | 5.4 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Getting it Right First Time – Elective Optimisation Programme |  |  |  |  |  |
| Report Author | Deb Lewis, Chief Operating Officer |  |  |  |  |  |
| Report Sponsor | Deb Lewis Chief Operating Officer |  |  |  |  |  |
| Presented by | Deb Lewis Chief Operating Officer |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | On 10th October 2023, the Health Board received communication from the Minister for Health regarding participation in the Getting it Right First Time (GIRFT) Elective Optimisation Programme. This report describes the Health Board’s approach to ensuring engagement in the programme. |  |  |  |  |  |
| Key Issues | The main area that the programme is covering is the efficient use of theatres and specifically ensuring that elective day-case rates are optimised, to 85%. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☒ | ☒ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to: To note the arrangements put in place to address the requirements of the GIRFT – Elective Optimisation Programme. |  |  |  |  |  |

Getting it Right First Time – Elective Optimisation Programme

- INTRODUCTION

On 10th October 2023, the Health Board received communication from the Minister for Health regarding participation in the Getting it Right First Time (GIRFT) Elective Optimisation Programme.  This report describes the Health Board’s approach to ensuring engagement in the programme.

- BACKGROUND

The Getting it Right First Time (GIRFT) Elective Optimisation Programme has been running in pilot form over the summer in both Cwm Taf Morgannwg and Betsi Cadwaladr UHBs and early indications are that there are some simple actions that health boards can take to improve theatre efficiency.

These include looking at late starts and early finishes, improvement in the number of High-Volume Low-Complexity (HVLC) cases undertaken, reducing the number of on the day postponements, which will come about through better pre-operative assessment, and improving turnaround times between cases.

The GiRFT recommendation is that 85% of all procedures should be undertaken as a day-case procedure.  The expectation of the Minister for Health and Social Services is that the Health Board provides the leadership to clinical and managerial teams to ensure the Health Board is working towards achievement of the 85% target.  Expectation is that this reporting on this agenda will become part of monthly reporting processes.

- Governance Arrangements

The Health Board is currently participating in GIRFT reviews in the following specialty areas:

- Orthopaedics

- Gynaecology

- Urology

- Ophthalmology

Due to the number of services involved across the Health Board, the Chief Operating Officer had already requested an over-arching programme within the Health Board to support the delivery of the work and to ensure a consistent approach for all.  The GIRFT Review Group (GRG) will feed into the Health Board’s Planned Care Programme Board and will be led by Gordon Staple, Assistant Medical Director for Healthcare Systems Engineering and Service Transformation.

Each of the services participating in the national GIRFT programme will be represented at the GRG by a lead clinician and a support manager.  The Terms of Reference for this group will be finalised by the end of November.

- Current Performance against efficiency metrics

A priority focus for the GIRFT Elective Optimisation Programme is standardisation of the definitions used for the key metrics.  Benchmarking currently is challenging due to variation in the rationale used across Health Boards and between NHS Wales and NHS England.

However, the metrics noted within the programme are currently measured by the Health Board and the current position is noted below for the first six months of 2023/24 (Qtrs 1 & 2 combined).

| Metric | Performance |  |
| --- | --- | --- |
| Late starts (hours lost) | 762 | Median - 44 mins per session |
| Early finishes (mins lost) | 2725 |  |
| On the day cancellations | 1278/15362 | 8.3% |
| Day-case rates | Unable to baseline |  |
| Theatre utilisation | 70% (inc cancellations | 84% (exc cancellations) |

- Next Steps

As the Health Board commences participation in the Elective Optimisation Programme, the next steps are to:

- Initiate the internal SBUHB GIRFT oversight group – first meeting will take place in November

- Receive the GIRFT data definitions for the key metrics as above

- Ensure dataset produced that matches the GIRFT data definitions

- RECOMMENDATION

To note the plans being developed to participate in the GIRFT Elective Optimisation Programme as outlined by the Minister for Health and Social Care.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| Participation in this programme has the ability to improve the quality and safety of services and in turn patient experience. |  |  |  |
| Financial Implications |  |  |  |
| There is are no financial implications as a direct result of this report. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| There are no legal implications to consider as a direct result of this report. |  |  |  |
| Staffing Implications |  |  |  |
| There are no staffing implications to consider as a direct result of this report. . |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Participation in this programme has the ability to positively impact on the Well-being of Future Generations. |  |  |  |
| Report History |  | First Report |  |
| Appendices |  | Appendix 1 – SBUHB Delivery Trajectory |  |

Appendix 1

| SBUHB Trajectory - Delivery of 104 Weeks by End of March 2024 Target: 800 (to achieve 99%) |  |  | Monthly (Aug 23 - March 24) |  |  |  |  |  |  |  | Variance |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | August | September | October | November | December | January | February | March | Total | Variance | Variance Core + Additional |  |
| STARTING BACKLOG POSITION - STAGE 5 | 8178 | BREACH NUMBER PER SERVICE |  |  |  |  |  |  |  |  |  |  |  |  |
| STARTING BACKLOG POSITION - STAGE 2/3 | 878 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY TYPE | SERVICE |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CORE | ENT | 662 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 224 | -438 |  |  |
| CORE | GASTRO | 565 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 136 | -429 |  |  |
| CORE | GENERAL SURGERY | 1304 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 464 | -840 |  |  |
| CORE | GYNAE | 918 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 352 | -566 |  |  |
| CORE | NEURO | 6 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 6 | 0 |  |  |
| CORE | OPHTHALMOLOGY | 99 | 29 | 29 | 29 | 12 | 0 | 0 | 0 | 0 | 99 | 0 |  |  |
| CORE | OMFS | 249 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 48 | -201 |  |  |
| CORE | PLASTICS | 734 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 304 | -430 |  |  |
| CORE | ORTHOPAEDICS | 3047 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 109 | 872 | -2175 |  |  |
| CORE | UROLOGY | 213 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 152 | -61 |  |  |
| CORE | VASCULAR | 3 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 3 | 0 |  |  |
| CORE | CLEFT | 3 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 3 | 0 |  |  |
| CORE | SPINAL | 375 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 80 | -295 |  |  |
| ADDITIONAL | ENT |  | 42 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 546 |  | -108 |  |
| ADDITIONAL | GENERAL SURGERY |  | 16 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 457 |  | 383 |  |
| ADDITIONAL | OMFS |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 192 |  | 9 |  |
| ADDITIONAL | ORTHOPAEDICS |  | 0 | 181 | 181 | 181 | 181 | 181 | 181 | 181 | 1267 |  | 2652 |  |
| ADDITIONAL | GYNAE |  | 0 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 154 |  | 412 |  |
| ADDITIONAL | SPINAL |  | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 88 |  | 284 |  |
| ADDITIONAL | PLASTICS |  | 0 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 483 |  | -53 |  |
| ADDITIONAL | UROLOGY |  | 0 | 14 | 14 | 0 | 14 | 5 | 0 | 14 | 61 |  | 0 |  |
| Total Planned Activity |  |  | 451 | 818 | 814 | 787 | 785 | 780 | 771 | 785 | 1488 |  |  |  |
| Backlog Forecast |  |  | 7727 | 6909 | 6095 | 5308 | 4523 | 3743 | 2972 | 2187 |  |  |  |  |
| Expected Increase of 20% Conversion from Stage 2/3 |  |  |  |  |  |  |  |  |  | 176 |  |  |  |  |
|  |  | Backlog Reduction with ROTT at 20% |  |  |  |  |  |  |  | 437 |  |  |  |  |
|  |  | Backlog Reduction with INNU at 5% |  |  |  |  |  |  |  | 109 |  |  |  |  |
| Backlog Forecast with BMI POLICY at 15% |  |  |  |  |  |  |  |  |  | 328.05 |  |  |  |  |