## Slide 1
Q4 Annual Plan 25/26 Reporting
Data pack providing progress against Plans on a Page and latest performance data (correct at 20th April 2026)

## Slide 2
UEC
Q4 Delivery

## Slide 3
2025/26
We will reduce ambulance patient handovers to <45 mins
2026-2028
Pre-hospital pathways & Front door
Community Model Review
Mental Health ED and Older People's Mental Health
Interdependent Workstreams
Regional
Digital
Improve Management of Flow
Discharge
Implement a Single Point of Access (SPOA) for UEC activity (UEC Navigation Hub)
Ensure (and where possible enhance) Acute Frailty Service provision at the front door(s) and pre-hospital via ACT & Virtual Wards
Develop a L1 & L2 Community Falls Service to avoid unnecessary conveyance
Review direct pathways to specialities (to avoid ‘front’ doors’ where appropriate and include palliative patients)
Implement High Intensity User scheme at front door(s)
Revise/ redesign SDEC/ AMU model
System Priorities
Areas to Deliver
Outputs
Mental Health ED
D2RA
We will reduce ED waits >12 hrs
We will deliver a 12-month reduction trend in the number of people who are delayed in hospital
We will reduce admissions
Reshape Virtual Wards and ACT (Hospital at Home) – to support discharge (step down) and admission avoidance (step up)
Remodel Inpatient Rehabilitation aligned to D2RA
Respiratory Service Improvement Plan
Develop Discharge Hub (aligned with front door SPOA – system specialists able to signpost all potential admission avoidance and discharge opportunities)
Review Ty Olwen Palliative Care beds
Older People's Mental Health
Stroke Improvement Plan
Develop secondary care diabetes and endocrine service
UEC Plan on Page 2025/2026
We will decrease assessments in hospital and increase assessments in a patients place of residence
Further implement Centralised Flow Model – Improve flow across NPT, Singleton and community sites
Re-invigorate the roll-out of the Optimal Hospital Flow Framework (SAFER, R2G, Avoiding deconditioning, Trusted Assessors)
Joint development of D2RA (across organisational boundaries)
Redesign and refine Silver and Gold On-call
Undertake ongoing Service Improvement activity building on Morriston site 6-week Tests of Change
Implement POCD action plan (reduction of COP)
Pre-hospital admission avoidance
Notes: APPROVED UEC PB 7/10/25

## Slide 4
Chart: 
| GMO Completed | GMO On Track | GMO Off Track Mitigation in Place | GMO Off Track | Outcome Met / Exceeded Target | Outcome Target not Met but on Trajectory | Outcome Off Track
GMO Milestone | 0 | 1 | 18 | 0
Outcomes | 0 | 0 | 4
Milestones
Measures
UEC Delivery Plan on a Page
UEC Summary Dashboard
Chart: Milestone Delivery Trend
| Q1 | Q2 | Q3 | Q4
Complete | 0 | 0 | 0 | 0
Red | 0 | 0 | 0 | 0
Amber | 11 | 13 | 14 | 17
Green | 1 | 3 | 3 | 1
Highest Risks
 | Previous | Q4
Risk that we fail to significantly reduce the number of clinically optimised patients in hospital beds | 25 | 25
Risk that patient safety concerns related to lengthy Chair and Trolley waits at our front door(s) (ED, AMU, SDEC, OPAU) are not mitigated and these negatively impact patient outcomes/ experience (and health board performance measures) | 20 | 20
Risk that we fail to improve ambulance handovers (hrs lost) and ED 4/12 hrs performance | 16 | 20
Key Outputs & Measures
Q4 Delivery Headlines
Ambulance Demand
Ambulance attendances appear lower in the most recent period, but this does not reflect reduced community demand as large numbers of vehicles have been stranded outside ED for prolonged periods, unable to offload
This has reduced the rolling stock available to respond to 999 calls, artificially suppressing the number of conveyances reaching the hospital.
The data therefore masks a front‑door capacity failure, not a demand reduction—community risk is rising while ED congestion prevents recovery.
ED new attends
Earlier in the period demand fluctuated significantly day to day - there were clear low‑demand days that naturally created breathing space for the system - peaks were isolated events, not clusters.
In the most recent period, the peaks are stacked back‑to‑back and there are no low days at all and attendance levels have remained in the upper decile band for more than a week.
Ambulance Handover <45 mins:
Recent values have dropped sharply below the long‑run average, meaning fewer ambulances are being released within 45 minutes. This is a negative trend, indicating worsening offload delays, reduced fleet circulation, and growing risk in the community due to unavailable vehicles.
ED Attendances Waiting >4 Hours: Sustained elevation above the average, with several days nearing or exceeding the 90th percentile (~133 patients), demonstrating entrenched flow block and inability to progress patients through the department.
ED Attendances Waiting >12 Hours: Persistent high numbers, frequently around or above the 90th percentile (~51 patients), signalling severe downstream bed delays, exit block, and an overwhelmed internal system unable to decompress.
Emergency bed-day consumption shows a clear upward trend, with values rising from ~4,200 in mid‑2025 to ~4,500–4,650 by early 2026.
To end of Q4 sit at the highest levels in the entire series, indicating sustained pressure with no meaningful periods of relief. Volatility persists but around a higher baseline, meaning even the “low” weeks are now materially higher than six months ago. The system is carrying a structurally larger emergency inpatient load, reflecting entrenched exit block and reduced throughput, combined with recent increases in the demand profile.
Clinically optimised bed‑days and patient numbers have risen steadily, sitting consistently above previous baselines, meaning a growing proportion of beds remain occupied by patients who no longer require acute inpatient care.
COP Patients at end of Q4 account for a higher share of total occupancy (frequently 15–18%), pushing the hospital into chronic over‑occupancy and removing the flexibility needed to respond to surges.
Q4
Measure & Target | Q1 | Q1 | Q2 | Q3 | Q4
We will reduce admissions |  |  |  |  | 
Total number of emergency admissions from Type 1 ED (MDS) |  | 5745 | 6437 | 6743 | 6159
We will reduce ambulance patient handovers to <45 mins |  |  |  |  | 
Continuous reduction of ambulance handovers over 1hr |  | 1477 | 400 | 664 | 595
We will reduce ED waits >12 hrs |  |  |  |  | 
Continuous improvement towards no more than 7% of patients waiting over 12 hours |  | 10.88% June | 9.39% Sept | 9.95% Dec | 11.26% Mar
We will deliver a 12-month reduction trend in the number of people who are delayed in hospital |  |  |  |  | 
Continuous reduction in delayed pathways of care |  | 192 June | 191 Sept | 169 Dec | 223 Mar
We will decrease assessments in hospital and increase assessments in a patients place of residence |  |  |  |  | 
Measure not confirmed / available |  |  |  |  | 

## Slide 5
                UEC Q4 DELIVERY
System Priority | Work programme | Q1 Milestone | Q2 Milestone | Q3 Milestone | Q4 Milestone
Pre-hospital pathways & Front door | Implement a Single Point of Access (SPOA) for UEC activity (UEC Navigation Hub) |  |  |  | Bed in new service and review progress to date/ further amendments required
 | Ensure (and where possible enhance) Acute Frailty Service provision at the front door(s) and pre-hospital via ACT & Virtual Wards |  |  |  | 
 | Develop a L1 & L2 Community Falls Service to avoid unnecessary conveyance |  |  |  | Continue roll-out/ review services trialled and investigate funding opportunities moving into 26/ 27 F/Y
 | Review direct pathways to specialities (to avoid ‘front’ doors’ where appropriate and include palliative patients) |  |  |  | Roll out/ embed changes/ direct pathways (where possible in line with available resource)
 | Implement High Intensity User scheme at front door(s) |  |  |  | Continue roll-out/ review delivery to date and investigate funding opportunities moving into 26/ 27 F/Y
 | Revise/ redesign SDEC/ AMU model |  |  |  | Roll out/ transfer to BAU
Improve Management of Flow | Further implement Centralised Flow Model – Improve flow across NPT, Singleton and community sites |  |  |  | Make model BAU
 | Re-invigorate the roll-out of the Optimal Hospital Flow Framework (SAFER, R2G, Avoiding deconditioning, Trusted Assessors) |  |  |  | Further roll-out of components listed in Q3 and evaluation of work to date
 | Joint development of D2RA (across organisational boundaries) |  |  |  | Roll-out
 | Redesign and refine Silver and Gold On-call |  |  |  | BAU
 | Undertake ongoing Service Improvement activity building on Morriston site 6-week Tests of Change |  |  |  | Continuous service improvement and review. Implement PDSA cycle across the system to improve ambulance handovers times
 | Implement POCD action plan (reduction of COP) |  |  |  | Remain on target until March 26 as directed by the Cabinet Secretary
ON TRACK – Action progressing as planned & agreed timelines | OFF TRACK – Action not progressing as planned / to original timelines, however, management & mitigating actions are in place | OFF TRACK – Action not progressing as planned / to original timelines, there is significant issue which require escalating

## Slide 6
              UEC Q4 DELIVERY
System Priority | Work programme | Q1 Milestone | Q2 Milestone | Q3 Milestone | Q4 Milestone
Discharge | Reshape Virtual Wards and ACT (Hospital at Home) – to support discharge (step down) and admission avoidance (step up) |  |  |  | 
 | Remodel Inpatient Rehabilitation aligned to D2RA |  |  |  | Embed/ BAU
 | Respiratory Service Improvement Plan |  |  |  | 
 | Develop Discharge Hub (aligned with front door SPOA – system specialists able to signpost all potential admission avoidance and discharge opportunities) |  |  |  | Continue implementation (subject to funding)
 | Review Ty Olwen Palliative Care beds |  |  |  | No change to bed base
ON TRACK – Action progressing as planned & agreed timelines | OFF TRACK – Action not progressing as planned / to original timelines, however, management & mitigating actions are in place | OFF TRACK – Action not progressing as planned / to original timelines, there is significant issue which require escalating

## Slide 7
UEC Q4 DELIVERY – OFF TRACK
System Priority | Work Programme | Q4 Milestone Off track | Reason | Mitigating Actions | When on track | Decision for IPPR
1. Pre-hospital pathways & Front door | Implement a Single Point of Access (SPOA) for UEC activity (UEC Navigation Hub) | Bed in new service and review progress to date/ further amendments required | No confirmed budget moving into 26/ 27 – further works required to maximise/ improve model | Budget and overall strategic direction to be confirmed – service to be rightsized in line with demand (success dependent on resource and services to be able to refer to) | TBC | 
 | Ensure (and where possible enhance) Acute Frailty Service provision at the front door(s) and pre-hospital via ACT & Virtual Wards |  | OPAU, ACT and Virtual Wards all have challenged staffing positions which limiting level of capacity and ability to improve provision | Limited mitigation at present – Improvement activity was underway with QI Matron working with OPAU to look at potential improvements by increasing scope of practice of teams. This ceased in Q4. Potential for improvements with ACT & VW post community services review | TBC | 
 | Develop a L1 & L2 Community Falls Service to avoid unnecessary conveyance | Continue roll-out/ review services trialled and investigate funding opportunities moving into 26/ 27 F/Y | L1 & L2 falls provision implemented towards end of Q3. Funding for these services ceased at end of Q4. Way forward into 26/ 27 to be confirmed and linked with available resource | Continue to discuss regional services and linkages to WAST developed national services – any service roll-out into 26/ 27 dependent on available resource | TBC | 
 | Review direct pathways to specialities (to avoid ‘front’ doors’ where appropriate and include palliative patients) | Roll out/ embed changes/ direct pathways (where possible in line with available resource) | Some direct pathways in place – lack of improvement capacity and system pressures preventing significant works in increasing direct pathways | Ambition to reallocate improvement capacity to work on direct pathways as part of tests of change at Morriston Hospital to improve front door handovers – this dependent on resource – activity may be possible in line with SBUHB centrally developed Delivery Unit/ PMO | TBC | 
 | Implement High Intensity User scheme at front door(s) | Continue roll-out/ review delivery to date and investigate funding opportunities moving into 26/ 27 F/Y | Some funding accessed – role in place to support high intensity activity until end of Q4 (no confirmation post this period) | Some activity continuing based on good will – any development of service aligned to available time of colleagues | TBC | 
 | Revise/ redesign SDEC/ AMU model | Roll out/ transfer to BAU | Limited improvement/ redesign activity able to be progressed due to system pressures. | Ambition to reallocate improvement capacity to work on the SDEC/ AMU model in 26/ 27 – then implement agreed changes/ improvements (likely subject to available improvement resource) | TBC | 

## Slide 8
UEC Q4 DELIVERY – OFF TRACK
System Priority | Work Programme | Q4 Milestone Off track | Reason | Mitigating Actions | When on track
2. Improve Management of Flow | Re-invigorate the roll-out of the Optimal Hospital Flow Framework (SAFER, R2G, Avoiding deconditioning, Trusted Assessors) | Further roll-out of components listed in Q3 and evaluation of work to date | 2x B6 Flow roles have were created until the end of the F/Y coupled with a focussed programme of works aimed at rolling out the Optimal Hospital Flow Frameworks key components. Roles have been extended for 3 months into 26/ 27 (confirmation on potential activity post this period) | 2x B6 roles continued for 3 months into 26/ 27 – requires confirmation post this period | TBC
 | Joint development of D2RA (across organisational boundaries) | Roll-out | Work begun – specifically in relation to maximising the use of existing P2 beds. However still works required to progress to a true joint D2RA model | Plan/ desire is to allocate associated improvement resource and improve D2RA (likely dependent on partners to further assist/ increase discharges) | TBC
 | Redesign and refine Silver and Gold On-call | BAU | Redesign of Silver and Gold on-call stalled. Organisation wide buy-in/ change required to implement | TBC | TBC
 | Undertake ongoing Service Improvement activity building on Morriston site 6-week Tests of Change | Continuous service improvement and review. Implement PDSA cycle across the system to improve ambulance handovers times | Successful change process within Q2 – system and resource pressures within Q3 & Q4 has limited ongoing service improvement activity across all domains | Desire to implement further tests of change in 26/ 27 – will require improvement/ project/ programme management resource to implement | TBC
 | Implement POCD action plan (reduction of COP) – | Remain on target until March 26 as directed by the Cabinet Secretary | Trend of reducing POCD (as per national census) has ceased – increase in POCD within West Glamorgan region. National census figures note increase of 158 delays (Dec 25) to 214 (Mar 26) | To sustainably reduce POCD (and associated COP) it is likely that increased assessment resource be in place and able to ‘flex’ to meet periods of high demand. Furthermore, it may involve altering bed pool to match system demands re; discharge (e.g. increase in P1 vs P2 beds) – all mitigating actions dependent on joint working across boundaries and a likely increase in resource at peak times | TBC

## Slide 9
UEC Q4 DELIVERY – OFF TRACK
System Priority | Work Programme | Q4 Milestone Off track | Reason | Mitigating Actions | When on track
3. Discharge | Reshape Virtual Wards and ACT (Hospital at Home) – to support discharge (step down) and admission avoidance (step up) |  | ACT and Virtual Wards all have challenged staffing positions which limiting level of capacity and ability to improve provision. | Community Services Review underway which includes ACT and VW. Anticipated that this review will in 26/ 27 highlight way forward and any changes to service provision | TBC
 | Remodel Inpatient Rehabilitation aligned to D2RA | Embed/ BAU | Activity aligned to maximising P2 beds – work underway but stalled in part due to system pressures – further activity needed | Plan/ desire to utilise internal improvement resource to maximise use of P2 beds – dependent on available resource | TBC
 | Respiratory Service Improvement Plan |  | Workforce review continuing with good progress made against nursing workforce especially Key personnel have been away from work for periods – now returned but recruitment freeze limiting progress Competing clinical priority of winter Resp preparedness prevented significant progress pre-set milestones | TBC – desire that resource be reallocated to this work and that key members of staff that have returned are able to drive. Recruitment/ funding freezes limiting progress – progress dependent on resource | TBC
 | Develop Discharge Hub (aligned with front door SPOA – system specialists able to signpost all potential admission avoidance and discharge opportunities) | Continue implementation (subject to funding) | Integrated Discharge Hub launched and operational but on unsustainable staffing model (team members rotate into IDH form other teams as available) | SBAR submitted for OCP to progress to sustainable staffing model – awaiting confirmation on way forward. | TBC
Issues for escalation
i.e. support required, recurring issues, blockages to delivery etc.
Notes: LE to review

## Slide 10
UEC Q4 DELIVERY
Q4 Reporting: Delivery Expectations , Targeted Intervention , NHS Wales Performance Framework metrics
DE
TI
TI
TI
DE
TI
DE
TI
Accident & Emergency | Target | Jan-26 | Feb-26 | Mar-26
4 -hour performance | 95% | 70.81% | 67.68% | 68.41%
12-hour performance | 0 | 1,272 | 1,202 | 1,356
Number of A&E Attendances | N/A | 10,910 | 10,132 | 12,030
Number of Clinically Optimised Patients (HB wide) | Continuous Reduction | 175 | 200 | 223
Number of cancelled Electives | 0 | 29 | 9 | 11
Number of ambulance patient handovers over 1 hour | 0 | 445 | 501 | 595
Ambulance (WAST measures incl in 25/26 Performance Framework) | Target | Jan-26 | Feb-26 | Mar-26
Median emergency ambulance response time to purple: arrest category calls | 6-8 minutes | 7.16 | 7.22 | Not available
Median emergency ambulance response time to red: emergency category calls | 6-8 minutes | 9.46 | 8.33 | Not available
Delivery against Targeted Intervention & Enhanced Monitoring Criteria 25/26 | Target | Jan-26 | Feb-26 | Mar-26
Continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on Q2/Q3 2023 baseline |  | 445 | 501 | 595
Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across HB |  | 11.66% | 11.86% | 11.26%
Median time from arrival at emergency department to assessment by a clinical decision maker should not exceed 60 minutes |  | 84.10% | 82.93% | 80.34%
Continuous reduction in delayed pathways of care of 5% for three consecutive months and then maintained for three months (based on Oct-Dec 23 baseline) |  | 175 | 200 | 223

## Slide 11
UEC - FORWARD LOOK
Opportunities and Focus for Q1 26/27
Focus on Ministerial Targets

## Slide 12
Planned Care & Cancer
Q4 Delivery

## Slide 13
We will maintain zero 104 week waits for treatment
2026-2028
Referral Advice & Guidance
Critical Care
Pharmacy & Medicines Management
Interdependent Workstreams
Diagnostics
Regional
/ JCC
Deliver Outpatients Transformation Programme – Health Pathways; RTT Outpatients Delivery Plan; 3Ps | Outpatients Digital Transformation – Roll out Hybrid Mail, Hospital Initiated Referrals, Digital Assessment Platform (Promptly).
Monitor CNA/DNA rates | Clinical and Admin Clerical Validation
System Priorities
Areas to Deliver
Outputs
Interventional Radiology Sustainability
Theatre Developments
We will maintain 0 patients waiting over 52 weeks for a first outpatients' appointment
We will reduce the number of patients waiting over 8 weeks for a diagnostic endoscopy
We will maintain our current position of no patients waiting over 8 weeks for all other diagnostics
Pathology Engagement in Test of Change Phase 2 to rationalise demand | Maintain 8-week diagnostic target
Implement National Diagnostic systems – LIMS and RISP | 
Regional Specialised Services Partnership Programme with CVUHB – HPB Centralisation, Establish Gynae Oncology Operational Delivery Network
JCC Cardiac Review
Regional Orthopaedics and Ophthalmology programme (with HDdUHB, delivered through Eye Care Collaborative)
Critical Care / Burns Expansion
Building Resilient Cell Pathology
Laboratory Medicine Improvement Plan
Treatment Times and Outcomes
Community By Design/ Delivering Integrated Services
Pre-hab
Theatres Improvement Programme | Theatres refurbishment programme
Increase HVLC lists linked to OR1 Theatres development | Data Intelligence and Demand and Capacity planning
Develop Robotic strategy | Hybrid Theatre & Interventional Radiology Transformation
Implement CIN Optimisation Frameworks | 
Planning for future programme and maintaining existing programme of work to include primary care services for – ring pessary, vasectomy, basal cell carcinoma, breathlessness/ spirometry, joint injections (DSS
Planned Care Plan on Page 2025/2026
We will reduce number of patients waiting over 26 weeks for a first outpatients' appointment
We will deliver 14 week waits for Therapies
Diabetes
Implement robust community diabetes model
Further expanding hybrid closed loop system for Type 1 diabetics
We will improve compliance with 8 care process for diabetes

## Slide 14
2025/26
We will reduce waiting times across Radiotherapy pathways
2026-2028
Non-Surgical Oncology including SWWCC Regional Programme
Cancer Strategy
Prehabilitation
Interdependent Workstreams
Prevention
Digital
System Priorities
Areas to Deliver
Outputs
Scope potential additional linacs in SWW
Review Swansea Uni Pilot re MRSIM
We will reduce wait times across SACT pathways
We will deliver a 12month improvement trend for patients starting first definitive treatment within 62 days building to 80% by 03.2026
Cancer Plan on a Page
Operationalise 2nd CT SIM
Develop business case for 5th Linac + spare bunker at Singleton
Reset and Redesign Acute Oncology and Haematology Unit (including developing IO Toxicity Service)
Develop sustainable Regional Oncology OPD hub and spoke model
Increase SACT capacity – Additional 4 chairs for 25/26
Develop 3-year plan for TrAMs programme
Permanent PET CT in place
Deliver tumour site action plans
Develop plan for lung cancer health checks/screening
Deliver Prehab in Cancer Programme
Develop D&C plan across Allied Health Professionals
Cancer Plan on Page 2025/2026
Compliance with National Optimal Pathways in the 5 High Impact Areas
Develop 3-year Plan for SACT including TRAMS programme

## Slide 15
Chart: 
| GMO Completed | GMO On Track | GMO Off Track Mitigation in Place | GMO Off Track | Outcome Met / Exceeded Target | Outcome Target not Met but on Trajectory | Outcome Off Track
GMO Milestone | 0 | 25 | 1 | 0
Outcomes | 6 | 1 | 0
Milestones
Measures
Planned Care and Cancer Delivery
Planned Care Summary Dashboard
Chart: Milestone Delivery Trend
| Q1 | Q2 | Q3 | Q4
Complete | 0 | 0 | 0 | 0
Red | 0 | 0 | 0 | 0
Amber | 11 | 10 | 7 | 1
Green | 1 | 2 | 19 | 25
Highest Risks
Key Outputs & Measures
Q4 Delivery Headlines
Elimination of 52 weeks wait for outpatients and culmination of national insourcing programme which processed over 20k op appointments and reduced waits below 26 weeks in a number of specialities
Diagnostics and therapies targets met or exceeded
Productivity opportunity quantified – clear baseline established to shift from non-recurrent activity to core capacity and productivity in 2026/27.
Q4
Measure and Target | Q1 | Q2 | Q3 | Q4
We will maintain 0 patients waiting over 52 weeks for a first outpatients' appointment | 0 | 0 | 0 | 0
We will reduce number of patients waiting over 26 weeks for a first outpatients' appointment | 14,200 June | 11,250 Sept | 8,530 Dec | 4,124 Mar
We will reduce the number of patients waiting over 8 weeks for a diagnostic endoscopy | 2,089 June | 2,046 Sept | 1,760 Dec | 285 Mar
We will maintain our current position of no patients waiting over 8 weeks for all other diagnostics | 2,246 June | 3,017 Sept | 6,042 Dec | 980 Mar
We will maintain zero 104 week waits for treatment | 0 | 0 | 0 | 0
We will deliver 14 week waits for Therapies | 3 June | 0 Sept | 0 Dec | 0 Mar
We will deliver a 12month improvement trend for patients starting first definitive treatment within 62 days building to 80% by 03.2026 | 51.9% June | 59.6% Sept | 52.4% Nov | 46.3% Feb
 | Q3 | Q4
Risk of insufficient diagnostics capacity to meet Tier 1 targets due to rising demand for therapies, new diagnostics, USCs and 8 weeks and surveillance backlogs. | 20 | 20
There is a risk that the additional commitments for the Health Board necessitated by Phase 3 of Cab Sec Delivery plan could impact clinical capacity and impact achievement of wider milestones and plans. | 9 | 12

## Slide 16
PLANNED CARE Q4 DELIVERY
System Priority | Work programme | Q1 Milestone | Q2 Milestone | Q3 Milestone | Q4 Milestone
Referral Advice & Guidance | Deliver Outpatients Transformation Programme – Health Pathways; RTT, Outpatients Delivery Plan, 3Ps |  |  |  | 6 National (Lead Region) Pathways implemented, published and available for SB Community HealthPathways users 15 Localised (lift & shift) Pathways implemented, published and available for SB Community HealthPathways users Continue with Primary & Secondary Care comms Project Closure
 | Monitor CNA / DNA rates |  |  |  | Achieve combined CNA / DNA target
 | Outpatients Digital Transformation – Roll out Hybrid Mail, Hospital Initiated Referrals, Digital Assessment Platform (Promptly) | Hybrid Mail HIR PROMPTLY | Hybrid Mail HIR PROMPTLY |  | Implement Hybrid Mail in line with the plan approved by Outpatients Modernisation group Continued roll out of HIR in line with plan approved by Outpatient Redesign Group. PROMPTLY - Continue to engage with NHS App build and PROMs NDR project. Further plans to be developed
 | Clinical and Admin Clerical Validation |  |  |  | Maintain targets as agreed in Q3
Diagnostics | Maintain 8 week diagnostic target – Right size endoscopy services |  |  |  | 
 | Implement National Diagnostics systems – LIMS and RISP | LIMS RISP | LIMS RISP |  | <<<<
Treatment Times and Outcomes | Theatres Improvement Programme |  |  |  | TBC
 | Theatres Refurbishment Programme |  |  |  | OR1 NPTH to complete and Morriston AHU phase to begin.
 | Increase HVLC lists linked to OR1 Theatres development |  |  |  | Finalise 26/27 delivery plans against WG targets, assess any recovery time, develop regional plans for income generation
 | Data Intelligence and Demand and Capacity planning |  |  |  | Submit D&C plan for 2026/2027
 | Develop Robotic strategy |  |  |  | Audit of Robotic surgery in Singleton to be reviewed
 | Hybrid Theatre & Interventional Radiology Transformation |  |  |  | 
 | Implement CIN Optimisation Frameworks |  |  |  | Business cases and service developments for 26/27 to be submitted
ON TRACK – Action progressing as planned & agreed timelines | OFF TRACK – Action not progressing as planned / to original timelines, however, management & mitigating actions are in place | OFF TRACK – Action not progressing as planned / to original timelines, there is significant issue which require escalating

## Slide 17
PLANNED CARE Q4 DELIVERY
System Priority | Work programme | Q1 Milestone | Q2 Milestone | Q3 Milestone | Q4 Milestone
Community By Design / Delivering Integrated Services | Planning for future programme & maintaining existing programme of work to include primary care services for – ring pessary, vasectomy, basal cell carcinoma, breathlessness/ spirometry, joint injections (DSS) |  |  |  | Ongoing monitoring and review
Diabetes | Implement robust community diabetes model |  |  |  | Work locally and nationally as part of NHS Exec network for the introduction of Hybrid Closed Loop pumps. Workforce review for Diabetes Inpatient provision as well as hospital based DSN's
 | Further expanding hybrid close loop system for Type 1 diabetes |  |  |  | 
Regional / JCC | Regional Specialised Services Partnership Programme with CVUHB – HPB Centralisation, Establish Gynae Oncology Operational Delivery Network |  |  |  | 
 | JCC Cardiac Review |  |  |  | Monitor activity and retention of staff.
 | Regional Orthopaedics and Ophthalmology programme (with HDdUHB), delivered through Eve Care Collaborative |  |  |  | 
ON TRACK – Action progressing as planned & agreed timelines | OFF TRACK – Action not progressing as planned / to original timelines, however, management & mitigating actions are in place | OFF TRACK – Action not progressing as planned / to original timelines, there is significant issue which require escalating

## Slide 18
CANCER Q4 DELIVERY
System Priority | Work programme | Q1 Milestone | Q2 Milestone | Q3 Milestone | Q4 Milestone
Non-Surgical Oncology including SWWCC Regional Programme | Operationalise 2nd CT SIM |  |  |  | 
 | Develop business cases for 5th Linac + spare bunker at Singleton |  |  |  | 
 | Reset and Redesign Acute Oncology and Haematology Unit (including developing IO Toxicity Service) |  |  |  | Begin pilot
 | Develop sustainable Regional Oncology OPD hub and spoke model |  |  |  | Consider new ways of working Alternative funding for staffing
 | Increase SACT capacity – Additional 4 chairs for 2025/26 |  |  |  | 4 chairs fully staffed with SACT competent workforce
Compliance with National Optimal Pathways in the 5 High Impact Areas | Develop a 3 year plan for TrAMs programme |  |  |  | Submit phase 2 of Business Case - additional chairs for 2026/27
 | Permanent PET CT in place |  |  |  | 
 | Deliver tumour site action plans |  |  |  | 
 | Develop plan for lung cancer health checks / screening |  |  |  | 
 | Deliver Prehab in Cancer Programme |  |  |  | 
ON TRACK – Action progressing as planned & agreed timelines | OFF TRACK – Action not progressing as planned / to original timelines, however, management & mitigating actions are in place | OFF TRACK – Action not progressing as planned / to original timelines, there is significant issue which require escalating

## Slide 19
PLANNED CARE AND CANCER Q4 DELIVERY – OFF TRACK
System Priority | Work Programme | Q4 Milestone Off track | Reason | Mitigating Actions | When on track
Compliance with National Optimal Pathways in the 5 High Impact Areas | Deliver Prehab in Cancer Programme |  | RDC only just live on Promptly therefore evaluation delayed due to lack of data availability. Webinars not live yet due to IG and IT issues; being worked through | RDC evaluation pushback but in pipeline. Video evaluation planned now live. Webinars ongoing testing until live to patient. | Q1

## Slide 20
PLANNED CARE AND CANCER Q4 DELIVERY
Q4 Reporting: Delivery Expectations , Targeted Intervention Level 3 , NHS Wales Performance Framework metrics
DE
L3
L3
L3
L3
L3
DE
L3
L3
L3
TI
L3
DE
Planned Care | Target | Jan 26 | Feb 26 | Mar 26
Percentage of patients waiting < 26 weeks for an outpatient appointment | 75% | 80.33% | 83.41% | 86.90%
Total number of patients waiting < 36 weeks | 80% | 75.08% | 76.24% | 78.53%
Number of patients waiting at Stage 1 > 52 Weeks | 0 | 0 | 0 | 0
Total number of patients waiting > 104 Weeks | 0 | 0 | 5 | 0
Diagnostics & Therapies | Target | Jan 26 | Feb 26 | Mar 26
Number of patients waiting > 8 weeks for diagnostics | 0 (National Perf Framework 25/26 and Ministerial Target) 85% wait <8 weeks (L3) | 6,059 | 2,917 | 980
Number of patients waiting < 8 weeks for an Endoscopy | 85% wait <8 weeks (L3) | 1,444 | 830 | 285
Number of patients waiting > 14 weeks for Therapies (Adults) *see CYP for Children reporting | 0 (National Perf Framework 25/26) 90% wait <14weeks (L3) | 0 | 0 | 0
Number of patients waiting > 14 weeks for Audiology (Adults) *see CYP for Children reporting | Month on month reduction | 43 | 55 | 22
Follow up Outpatients | Target | Jan 26 | Feb 26 | Mar 26
Number of patients waiting for an outpatient follow-up (booked and not booked) who are delayed past their agreed target date (All Specialties) |  | 78,567 | 75,892 | 75,944
Total number of patients waiting 100% over their target date | Reduction compared to prev. year | 47,379 | 45,996 | 46,236
Total number of patients waiting for a follow-up appointment |  | 161,799 | 158,618 | 159,543

## Slide 21
PLANNED CARE AND CANCER Q4 DELIVERY
DE
Cancer | Target | Jan 26 | Feb 26 | Mar 26
12-month improvement trend in the percentage of patients starting first definitive cancer treatment within 62 days from point of suspicion (regardless of the referral route), building toward a national target of 80% | 12 month improvement | 54.6% | 46.3% | Not available
Delivery against Targeted Intervention & Enhanced Monitoring Criteria 25/26 | Target | Jan 26 | Feb 26 | Mar 26
Cancer |  |  |  | 
60% performance maintained for 3 months against the SCP target. |  | 54.6% | 46.3% | Not available
100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 month |  | 100% | 100% | 100%
Continuous improvement towards 75% of all open outpatient pathways waiting less than 26 weeks |  | 80.33% | 83.41% | 86.90%
100% of open pathways to be waiting less than 104 weeks and maintained for 3 months |  | 100% | 99.99% | 100%
Continuous improvement towards 80% of all open pathways waiting less than 36 weeks |  | 75.08% | 76.24% | 78.53%
12% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2024 baseline.) |  | 23.26% | 19.67% | 20.29%
68% R1 ophthalmology patient pathways to be waiting within or no longer than 25% of their target date for an outpatient appointment and maintained for 3 months |  | 72.64% | 72.60% | 71.04%
85% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months |  | 66.64% | 82.17% | 93.11%
85% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 month |  | 47.68% | 63.87% | 83.14%

## Slide 22
PLANNED CARE & CANCER FORWARD LOOK
Opportunities and Focus for Q1 26/27
Planned Care – Q1 26/27 Forward Look
Theatre productivity mobilisation – implementation of timetable redesign (initial focus NPTH and first-follower specialties), targeting ≥85% utilisation and improved alignment of capacity to demand.
Outpatient transformation acceleration – scaling PIFU/SOS models, strengthening referral management (“modern front door”) and reducing follow-up waiting list reliance.
Operationalisation of productivity intelligence – rollout of specialty-level analytics (Deloitte self-serve) supported by Delivery Unit PMO to drive accountability and grip.
Performance oversight reset – establishment of Health Board Delivery Unit and revised governance architecture to strengthen weekly operational grip and trajectory management.
Diagnostics fragility to be actively managed – anticipated dip in 8-week performance (particularly endoscopy/radiology) due to system changes and capacity constraints.
Risk-managed trajectory approach – delivery framed on scenario basis, with prudent planning assumptions and clear articulation of risks, dependencies and productivity requirements.
Cancer – Q1 26/27 Forward Look
Maintain SCP performance ≥60% as a stable recovery baseline while building trajectory toward improved performance across 26/27.
Transition from stabilisation to improvement – focus on reducing backlog and variation across tumour sites through targeted pathway optimisation.
Cancer Improvement Programme mobilisation – establishment of unified programme and delivery plan following March workshop, with clear governance and ownership.
Immediate action alongside programme build (dual-track approach) – prioritisation of “known problems with known solutions” to accelerate impact in Q1.
Diagnostics and pathway flow prioritised – targeted actions across radiology, pathology and endoscopy to address key constraints impacting SCP performance.
Tumour-site focus on highest opportunity areas (e.g. urology, skin, lower GI) to drive measurable improvement in Q1.
Strengthened system working – alignment across primary care, diagnostics and treatment pathways, including regional dependencies (e.g. SWWCC).

## Slide 23
Primary Care & Community Services
Q4 Delivery

## Slide 24
2025/26
We will increase the numbers accessing Pharmacists Independent Prescribing Services
2026-2028
Improve Prevention and Wellbeing
Primary & Community Estates Strategy
PCPG Priorities
Interdependent Workstreams
Contract Reform
Strategic Programme for Primary Care
Implementation of the full primary care model at cluster level
Data and digital technology is a key enabler of transformational change
Develop sustainable plan for Hearing Aids
Delivery of Tobacco Control Priorities
Ensure GMS access and sustainability
System Priorities
Areas to Deliver
Outputs
We will maintain our delivery of NHS dental services for adults and children
We will increase weekend capacity for community nursing and specialist palliative care
We will maintain national target of 100% GP practices achieving all National Access Standards for In-hours GMS
Implementation of Electronic Prescribing
Maximise number of Pharmacies offering the Independent Prescribing Services
Continue with implementing Community Psychology Model
Review all high CHC placements
Planning for Community by Design Programme
Sustainable Diabetes Prevention Programme
Primary Care and Community Services Plan on Page 2025/2026
We will increase capacity of Enhanced Community Care
Improvement of GMS Estates
Implementation of Dental Access Portal
Implementation of Optometry Contract
Review access to Special Care Dentistry / Specialist Dentistry / Generalist Dentistry
Maintain services of Paediatric Dentistry general aesthetic
Implementation of Pan Cluster Priorities
Implement Local Cluster Plans (208 key actions)
Sustainable Weight Management Pathway
Workforce Strategy
Digital
Community by Design
Care to be delivered locally and integrated to ensure primary care is consistent on a 24/7 and geographic basis
Notes: APPROVED UEC PB 7/10/25

## Slide 25
Chart: 
| GMO Completed | GMO On Track | GMO Off Track Mitigation in Place | GMO Off Track | Outcome Met / Exceeded Target | Outcome Target not Met but on Trajectory | Outcome Off Track
GMO Milestone | 0 | 14 | 0 | 0
Outcomes | 0 | 0 | 0
Milestones
Measures
Primary Care & Community Delivery
Primary Care Summary Dashboard
Chart: Milestone Delivery Trend
| Q1 | Q2 | Q3 | Q4
Complete | 0 | 0 | 0 | 0
Red | 0 | 0 | 0 | 0
Amber | 2 | 2 | 2 | 0
Green | 11 | 12 | 12 | 14
Highest Risks (25)
Key Outputs & Measures
Measure | HB Target | Q1 | Q2 | Q3 | Q4
We will maintain national target of achieving 100% GPs achieving all National Access Standards for in hours GMS |  |  |  |  | 
 | 100% | Reported annually |  |  | 
We will increase the numbers accessing Pharmacist Independent Prescribing Services |  |  |  |  | 
 | Access Increase | 35 | 34 | 32 | Not available
We will maintain our delivery of NHS dental services for adults and children |  |  |  |  | 
 | % Increase | Data not available |  |  | 
Q4 Delivery Headlines
Q4
Maintained compliance for 14-week RTT for Therapies and Health Science
Successful recommissioning of PSALT ( circa 300 patients)
Reduction in CMAT waiting times
Weight management (level 3) partnership with Roczen delivery
Year end (draft) finance position underspend
Maintained reduced Variable pay compared to Q1&2
DSS for 0.5% Complex Frailty population – improved uptake compared to 2024/25 (impact tbc)
Success delivery across the 8 Cluster IMTPs (66% green and 22% amber)
Progress across the 3 priorities in the Pan Cluster Plan
  eg extending Community Psychology to four clusters and attracting RPB budget for a 5th post.
  Integrated T&F Falls Pathway group across Primary, Secondary and RPB.
Launch of joint injections and minor surgery DSS
Launch of revised sexual health LSS
Primary Care training and education programme for women’s health
Dental Access Portal – reduced total numbers waiting access in Q4.
Successful recommissioning of dental activity ( new dental practice)
WGOS 4&5 continued roll out
Increased Independent Prescribers in Optometry and Comm Pharmacy
Community By Design Programme initiated
 | Q4 | Previous
ID: 3638 Extended Waiting Times - Adult/Paeds Special Care Dentistry Treatments (PCT_13) | 20 | 20
ID:2461 HB Wide DN Staffing Levels (PCT_20) | 20 | 20
ID: 3071 Prison - Healthcare Nursing Staff Levels (PCT_19a, PCT_20) | 20 | 20
ID: 4139 DN SPOA | 20 | 20

## Slide 26
PRIMARY CARE AND COMMUNITY Q4 DELIVERY
System Priority |  | Work programme | Q1 Milestone | Q2 Milestone | Q3 Milestone | Q4 Milestone
Improve Prevention and Wellbeing |  | Develop sustainable plan for hearing aids |  |  |  | 
 |  | Delivery of Tobacco Control priorities |  |  |  | 
Community By Design/ Delivering Integrated Services |  | Planning for future programme and maintaining existing programme of work to include primary care services for – ring pessary, vasectomy, basal cell carcinoma, breathlessness/ spirometry, joint injections (DSS) |  |  |  | 
Implementation of the full primary care model at cluster level |  | Improve GMS Estates |  |  |  | 
 |  | Implement Dental Access Portal |  |  |  | 
 |  | Implement Optometry Contract |  |  |  | 
 |  | Maximise the number of pharmacies offering the Independent Prescribing Service |  |  |  | 
Deliver care locally and ensure primary care is consistent on a 24/7 and geographical basis |  | Review access to Special Care Dentistry/ Specialist Dentistry/ General Dentistry |  |  |  | Review of service provision and activity for 26/27 planning. Risk in POW provision remains
 |  | Maintain Paediatric Dentistry General Anaesthetic Services |  |  |  | 
 |  | Implement Pan Cluster Priorities |  |  |  | 
 |  | Implement Local Cluster Plans (208 key actions) |  |  |  | 
 |  | Continue implementing Community Psychology Model |  |  |  | 
 |  | Review all high cost CHC placements |  |  |  | 
Data and Digital |  | Implement Electronic Prescribing in GMS and Community Pharmacy – national programme to be led by DHCW |  |  |  | 
ON TRACK – Action progressing as planned & agreed timelines | OFF TRACK – Action not progressing as planned / to original timelines, however, management & mitigating actions are in place | OFF TRACK – Action not progressing as planned / to original timelines, there is significant issue which require escalating

## Slide 27
PRIMARY CARE AND COMMUNITY Q4 DELIVERY
Q4 Reporting: Delivery Expectations and Performance Framework metrics
Primary Care and Community | Target | Forecast Q4 | Actual Q4
100% of GP practices achieving all National Access Standards for Inhours GMS | 100% | Can't report on quarterly basis | Access end of year reporting currently being verified available June 2026
Increase in number of people accessing Pharmacist Independent Prescribing Service for acute minor conditions and routine contraception services where the patient reports they would have otherwise visited their GP | Access Increase | 9000 | Not currently available
Increase in % of adult population accessing NHS Dental care over a 24 (adult) month period | % Increase | 45% | Data not currently available
Increase in % of child population accessing NHS Dental care over a 12 (child) month period | % Increase | 52.9% | Data not currently available
Increase in capacity at the weekend of community nursing and specialist palliative care nursing to at least the required levels previously set for 2024/25 and greater where possible | Capacity Increase | No current plan to increase weekend capacity | No current plan to increase weekend capacity - Future changes to be based on Community Services Review
Percentage of primary care dental services (GDS) contract value delivered (for courses of treatment for new, new urgent and historic patients) | A month on month increase towards a minimum of 30% contract value delivered by 30 September 2025 and 100% by 31 March 2026 | Data not available to provide a forecast | Data not currently available. Final year end position available at the end of June
DE
DE
DE
DE
DE
DE
DE

## Slide 28
PRIMARY CARE & COMMUNITY FORWARD LOOK
Opportunities and Focus for Q1 26/27
Currently assessing 49 Annual Plan Schemes/Project areas across UEC (11) , Planned Care & Cancer (5), Women’s Health (5), Population Health (6), Diabetes (4) and Prevention and Early Years (2), Primary Care (13), Mental Health (3)
Community Services Review– develop and implement plans based on outcomes from the Review, aligned to Clusters
Reduced POCD within the UEC programme and across RPB partnership
Community By Design Programme – clarity regarding focus of areas of improvement
Maintain focus on 14 week targets and respond to new Audiology RTT.
Digital Improvement programme will support a range of these (eg OpenEyes) and be cross cutting
New Dental Contract regulations implementation
Implementation of Cluster IMTPs and Agreement and commence implementation of Pan Cluster Plan 2026/27.
Support Mental Health Transformation Plan via Clusters/ Community models

## Slide 29
Children & Young People, Women’s Health, Perinatal
Q4 Delivery

## Slide 30
2025/26
We will establish a Women's Health Pathway Finder Hub by March 2026
2026-2028
Delivery of Women's Health Priority Areas as directed by WG
Community Model Review
CHC
Interdependent Workstreams
Digital
System Priorities
Areas to Deliver
Outputs
Delivery of Women's Health Priority Areas as directed by WG
Women's Health Plan – Development of a Women's Health Hub
Agree for a sustainability model for Gynae Oncology across Wales in partnership with Cardiff & Vale UHB
Sustainable Fertility Services – Maintain de-escalated status and review JCC contracted arrangements
Deliver the recommendations of the HIW recommendations and Independent Review Recommendations
Children & Young People
Perinatal
Develop plans to redesign Morriston Paediatric footprint (no funding)
Partnership working with RPB – No Wrong Door and commissioning arrangements for children with complex needs
NDD Service improvements: Workforce/Waiting Times/Accommodation
CYP Strategic Actions aligned to new WH Peri CYP Care Board
Perinatal Workforce Plan to align with HIW & HEIW
Perinatal safety programme
Deliver the SBU Independent Reviews Recommendations
Perinatal Assessment Recommendations All Wales
Scope Perinatal Framework and align to other Perinatal strategies
Neo Natal Transport service –Overnight service at risk given no JCC funding
Maternity Electronic Patient Record
Delivery of CYP Strategy
Sustained improvement in NDD waiting times
We will deliver EPR for Maternity Services
Women's Health, Children and Young People & Maternity Neonatal Plan on a Page
Children & Young People, Women’s Health, Perinatal System Plan on Page 2025/2026

## Slide 31
CYP, WH, Perinatal Summary Dashboard
Q4
Chart: 
| GMO Completed | GMO On Track | GMO Off Track Mitigation in Place | GMO Off Track | Outcome Met / Exceeded Target | Outcome Target not Met but on Trajectory | Outcome Off Track
GMO Milestone | 0 | 11 | 2 | 0
Outcomes | 1 | 1 | 0
Milestones
Measures
CYP, WH, Perinatal
Chart: Milestone Delivery Trend
| Q1 | Q2 | Q3 | Q4
Complete | 0 | 0 | 0 | 0
Red | 0 | 1 | 0 | 0
Amber | 2 | 1 | 3 | 2
Green | 5 | 10 | 10
Key Outputs & Measures
Measure | HB Target | Q1 | Q2 | Q3 | Q4
We will establish a Women's Health Pathway Finder Hub by March 2026 |  |  |  |  | 
 |  |  |  |  | In place
Sustained improvement in NDD waiting times |  |  |  |  | 
 | 85% | 35.1% June | 31.9% Sept | 35.5% Dec | 43.6% Mar
We will deliver EPR for Maternity Services |  |  |  |  | 
 | No metric to report |  |  |  | 
Q4 Delivery Headlines
Womens Pathway Finder hub established
Wales Fertility institute workforce issues continue to be raised as concern regarding delivering of WJCC contract and also sustaining service, active recruitment plan in place and recovery plan agreed. Successful meeting held with WJCC further work to continue in 2026/27
Interim neonatal transport model maintained
Outsourcing service for ND service successful deliver nil patients waiting over 156 weeks and reduced number waiting over 104 weeks as plan
Badger successfully launched 31st March 2026
Perinatal Safety Programme Manager now in post
RPB successfully appointed 'No Wrong Door' Project manager

## Slide 32
CYP, WOMENS AND PERINATAL Q4 DELIVERY
System Priority | Work programme | Q1 Milestone | Q2 Milestone | Q3 Milestone | Q4 Milestone
Delivery of Women’s Health Priority Areas as directed by WG | Women’s Health Plan – Development of a Women’s Health Hub |  |  |  | Pathfinder Hub Live
 | Agree for a sustainability model for Gynae Oncology across Wales in partnership with Cardiff & Value UHB |  |  |  | Project Board, Operational Groups in place and agreed service spec following consultation
 | Sustainable Fertility Services – Maintain de-escalated status and review JCC contracted arrangements |  |  |  | Workforce pressures and increased gaps in staffing groups, locum cover in place whilst recruitment progresses. Recovery plan in place to delivery revised contract level.
Children & Young People | Develop plans to redesign Morriston Paediatric footprint (no funding) |  |  |  | Aim to achieve decision on suitable footprint
 | Partnership working with RPB – No Wrong Door and commissioning arrangements for children with complex needs |  |  |  | No Wrong Door Project lead commenced in post 16th march. Meetings held to discuss CYP Complex Needs Multi-agency SOP review
 | NDD Service improvements: Workforce, Waiting Times, Accommodation |  |  |  | Meeting with RPB scheduled for 30th April
 | CYP Strategic Actions aligned to new WH Peri CYP Care Board |  |  |  | First meeting scheduled for 27th April
Perinatal | Perinatal Workforce Plan to align with HIIW & HEIW |  |  |  | To be confirmed during quarter 3
 | Perinatal safety programme |  |  |  | Successful candidates uptake posts
 | Deliver the SBU Independent Reviews Recommendations |  |  |  | Final sign off pending approval from Oversight Panel; majority of actions on track.
 | Perinatal Assessment Recommendations All Wales Embed the All wales Midwifery led care guidance into practice to ensure high quality care is provided in all settings including Perinatal engagement Framework |  |  |  | Delivery of action plans
 | Neo Natal Transport service - Overnight service at risk given no JCC funding |  |  |  | Interim model to continue until WJCC confirm permanent funding arrangement
 | Maternity Electronic Patient Record |  |  |  | Project plan to remain on track
ON TRACK – Action progressing as planned & agreed timelines | OFF TRACK – Action not progressing as planned / to original timelines, however, management & mitigating actions are in place | OFF TRACK – Action not progressing as planned / to original timelines, there is significant issue which require escalating

## Slide 33
CYP, WOMENS AND PERINATAL– OFF TRACK
System Priority | Work Programme | Q4 Milestone Off track | Reason | Mitigating Actions | When on track
Children & Young People | Develop plans to redesign Morriston Paediatric footprint (no funding) | Aim to achieve decision on suitable footprint for Paediatric in-patient services at Morriston Hospital | No funding and no decision on appropriate alternative space as yet | Paediatric wards continue in current space | Quarter 3
Children & Young People | Wales Fertility Institute Service Sustainability |  | Service has experienced high sickness levels and also high number of resignations recently | Workforce pressures and increased gaps in staffing groups, locum cover in place whilst recruitment progresses. Recovery plan in place to delivery revised contract level. | Qtr 2 2026/27

## Slide 34
WOMENS HEALTH, CYP AND PERINATAL Q4 DELIVERY
Q4 Reporting: NHS Wales Performance Framework metrics (none within Delivery Expectations and TI/EM Level 3 (aside from CAMHS which is reported in MH System slides)
CYP | Target | Actual Jan 2026 | Actual Feb 2026 | Actual March 2026
Percentage of children (aged under 18 years) waiting 14 weeks or less for a specified Allied Health Professional therapy | 100% | 100% | 100% | 100%
Number of children waiting more than 6 weeks for all audiology pathways (to include new assessment and intervention pathways) | Month on Month reduction | 139 | 107 | 176
Percentage of children and young people waiting less than 26 weeks to start an ADHD or ASD neurodevelopment assessment | 80% | 33.2% | 38.3% | 43.6%

## Slide 35
CYP, WOMENS AND PERINATAL FORWARD LOOK
Opportunities and Focus for Q1
Aim to achieve decision on suitable footprint for Paediatric in-patient services at Morriston Hospital
Establish the Womens Health, CYP and Babies Programme Board and CYP steering Group – Quarter 1
Wales Fertility institute workforce issues continue to be raised as concern regarding delivering of WJCC contract and also sustaining service, active recruitment plan in place and recovery plan agreed. Successful meeting held with WJCC further work to continue in 2026/27 - Recruitment and Recovery plan to get Wales Fertility Service back on track with service sustainability
Continue to embed badger into maternity services
Maintain no CYP waiting over 156 weeks for ND assesment and diagnosis and continue with recruitment and transformation plans

## Slide 36
Mental Health & Learning Disabilities
Q4 Delivery

## Slide 37
2025/26
We will deliver Progress against the priority areas to improve the lives of people with learning disabilities
2026-2028
Adult Inpatient and Community Modernisation
UEC 6 Goals and D2RA
Mental Health ED /Older People's Mental Health
Interdependent Workstreams
CHC
Digital
System Priorities
Areas to Deliver
Outputs
Mental Health ED
LD Inpatient service model and estate
We will maintain the 80% target of mental health assessments undertaken within 28 days from receipt of referral
We will maintain 80% target of therapeutic interventions started within 28 days following assessment by LPMHSS
L2 escalation support NHS Exec/Independent Consultant
Medical workforce review/service demand
Outpatient Pathways /Single Point of Access
Develop OPMHS enhanced assessment and Therapy Hub
Review OPMHS bed model
Continue to implement Community Psychology model
Older People's Mental Health Service
CAMHS
Specialist Mental Health
Mental Health Estate
LD Modernisation
Deliver RPB CYP Plan: No wrong door / Appropriate Placements / Transition Principles
Progress implementation of JCC MH Specialist Strategy
Develop HDU Facilities
Reconfigure Dan Y Deri/submission of BC to RPB
Develop seclusion facilities LD acute assessment unit /submission of BC to RPB
Relocation of CDAT base
Refurbishment of Ward F Seclusion Facility
Progress Capital BC modernisation of Adult Inpatient
Co-locate Community OPMHS
Mental Health and Learning Disabilities Plan on Page

## Slide 38
Chart: 
| GMO Completed | GMO On Track | GMO Off Track Mitigation in Place | GMO Off Track | Outcome Met / Exceeded Target | Outcome Target not Met but on Trajectory | Outcome Off Track
GMO Milestone | 0 | 6 | 6 | 2
Outcomes | 2 | 0 | 0
Milestones
Measures
MH & LD
MH & LD Summary Dashboard
Chart: Milestone Delivery Trend
| Q1 | Q2 | Q3 | Q4
Complete | 0 | 0 | 0
Red | 4 | 2 | 2 | 2
Amber | 5 | 9 | 7 | 6
Green | 5 | 3 | 6 | 6
Key Outputs & Measures
Q4 Delivery Headlines
Temporary bed reduction in OPMHS Inpatient Ward
Continued collaborative working with RPB to delivery CYP Plan: No wrong door
Refurbishment of Ward F seclusion signed off
CDAT NPT Team relocated
Successful Go Live of Rio in Phase 1 to paper based services
Tawe Clinic works underway
Q4
Measure | HB Target | Q1 | Q2 | Q3 | Q4
We will deliver Progress against the priority areas to improve the lives of people with learning disabilities |  |  |  |  | 
 | Unable to measure |  |  |  | 
We will maintain the 80% target of mental health assessments undertaken within 28 days from receipt of referral |  |  |  |  | 
 | 80% | 98% Jun | 93% Sep | 98% Dec | 93% Mar
We will maintain 80% target of therapeutic interventions started within 28 days following assessment by LPMHSS |  |  |  |  | 
 | 80% | 76% Jun | 52% Sep | 89% Dec | 87% Mar

## Slide 39
High Risks Quarter 4
No | Ref | Title | Rating (Q3 previous) | Rating Q4
1 | Learning Disabilities | Poor Standard of LD Complex Care Unit Environments | 20 | 20
2 | Adult Mental Health | CRR 69 – Adolescents being admitted to adult mental health wards | 20 | 20
3 | Adult Mental Health | Clinical Risk - Typing Backlog for consultants and in CMHT's due to workload and lack of workforce capacity | 20 | 20
4 | Adult Mental Health | Ward F Seclusion Facility Non-Compliant with Standards | 20 | 20
5 | Adult Mental Health | Deficits in administrative cover across adult mental health services | 20 | 20
6 | Psychology | Psychological Therapies Waiting List Position | 20 | 20
7 | Service Group | MH & LD Nursing workforce/Safe Staffing levels in accordance with the Nurse Staffing Act | 20 | 20
8 | Adult Mental Health | Cefn Coed Environments of Care - Fendrod & Clyne Wards | 20 | 20
9 | MH Division | Mental Health Site Security Issues (Cefn Coed & Garngoch) | 20 | 20
10 | Forensic | Inadequate Seclusion Facilities at Caswell Clinic | 20 | 20
11 | Forensic | Implementation of an Electronic Patient Record System | 20 | 20
12 | Adult Mental Health | Increased use of adult private provision | 20 | 20
13 | Low Secure | Absence of an Electronic Patient Record System | 20 | 20
14 | Low Secure | Reduced MSU Admission Capacity following Taith Newydd Fire | 20 | 20
15 | CDAT | lack of access to Dyfodol criminal justice electronic records | 20 | 20

## Slide 40
MH & LD Q4 DELIVERY
System Priority | Work programme | Q1 Milestone | Q2 Milestone | Q3 Milestone | Q4 Milestone
Adult Inpatient and Community Modernisation | L2 escalation support NHS Exec / Independent Consultant |  |  |  | Conduct review of progress against key performance indicators as per the measures outlined and produce a highlight report to summarise next steps.
 | Medical workforce review / service demand |  |  |  | End of year review, advocate for any necessary funding and support required to enhance and sustain medical workforce model. This is now part of the workforce workstream un the MH Transformation Program
 | Outpatient Pathways / Single Point of Access |  |  |  | Centralised booking system in place. Part of the Health Boards review of all its outpatients review.
 | Develop OPMHS enhanced assessment and Therapy Hub |  |  |  | Develop plan for the reinstatement of OPMHS day support services
 | Review OPMHS bed model |  |  |  | Continue with OPMHS bed reduction on a temporary basis
 | Continue to implement Community Psychology model |  |  |  | 
CAMHS | Deliver RPB CYP Plan: No wrong door, appropriate placements, transition principles |  |  |  | Data evaluation and written benefits analysis Attend and contribute to the CYP Board ad relevant local workstreams/ subgroups LA have advertised a lead for this and will be taking forwards it implementation with CAMHs input
Specialist Mental Health | Progress implementation of JCC MH Specialist Strategy |  |  |  | Continue to progress local improvement plans until steer from JCC received regarding MH Specialist Services Strategy
 | Develop HDU facilities |  |  |  | BJC approved by HB in March – now with WG for final approval.
Mental Health Estate | Relocation of CDAT base |  |  |  | Move teams to a new base. Operationalise teams in their new base. Neath teams have moved to Cimla, Swansea teams remain in third sector buildings.
 | Refurbishment of Ward F Seclusion facility |  |  |  | Completion of refurbishment work and review outcomes against performance measures. Desings signed off and now with PFI. Building will start in 26/27
 | Progress Capital BC modernisation of Adult Inpatient |  |  |  | Awaiting decision by WG. All milestones are dependent on this decision. Once approved timeframes and milestones will be reset and project board reinstated to oversee work.
 | Co-locate Community OPMHS |  |  |  | Continue to look at relocation options with capital planning.
LD Modernisation | Reconfigure Dan Y Deri / submission to BC to RPB |  |  |  | Business Case approved by WG and implementation of the changes will commence in June 2026
 | Develop seclusion facilities LD acute assessment unit / submission of BC to RPB |  |  |  | Q4 Action was removed from 25/26 plan in Q3.
ON TRACK – Action progressing as planned & agreed timelines | OFF TRACK – Action not progressing as planned / to original timelines, however, management & mitigating actions are in place | OFF TRACK – Action not progressing as planned / to original timelines, there is significant issue which require escalating

## Slide 41
MENTAL HEALTH & LEARNING DISABILITIES – OFF TRACK
System Priority | Work Programme | Q4 Milestone Off track | Reason | Mitigating Actions | When on track
Adult Inpatient & Community Modernisation | Develop OPMHS enhanced assessment and Therapy Hub | Develop plan for the reinstatement of OPMHS day support services | Tonna day hospital vacated as well as Onnen ward at present. Options being worked up by clinical teams to look at what initiatives they want. | Services continue as they are at present with reinvestment long term being scoped | Q1 26/27
Mental Health Estate | Relocation of CDAT base | Move teams to a new base | Neath teams have moved to Cimla, Swansea teams remain in third sector buildings. | Options for Swansea bases continue to be explored in line with APB partners | Q1 26/27
Adult Inpatient & Community Modernisation | Outpatient Pathways / Single Point of Access | Centralised booking system in place | Centralised booking remains an aim for MH&LD. Deloitte are leading a piece of work around A&C use and MH&LD will be tied into this | Raised to leads for planned care. Medical secretaries continue to book. | Q2 26/27
Mental Health Estate | Progress Capital BC modernisation of Adult Inpatient | Awaiting decision by WG. All milestones are dependent on this decision. Once approved timeframes and milestones will be reset and project board reinstated to oversee work. | WG have not approved capital plans for interim model. A regional scoping is currently underway | £2.4million refurbishment of Tawe clinic and assessment of regional options is underway | Q2 26/27
Mental Health Estate | Co-locate Community OPMHS | Continue to look at relocation options with capital planning. | OPMHS remain in aging estate and were being factored into potential new build in Swansea City Centre. | Review internal options in line with potential use of Central clinic as well as options on CCH site | Q2 26/27
LD Modernisation | Reconfigure Dan Y Deri / submission to BC to RPB | Continue with Organisational change process. | Decision on capital funding by Welsh Government has not been communicated. Unlikely this will take place until after Senedd elections now. | Project board continues to meet to review risk log. | Q2 26/27
MH Specialist Services | HDU Development | Business Case awaiting approval by Welsh Government | Awaiting funding decision | Ongoing absence of these facilities will require further use of private sector placements (at cost to commissioners) | Qtr 1 26/27 (if funding is approved)
MH Specialist Services | Progress implementation of JCC MH Specialist Strategy | Modernisation strategy sits with the JCC | JCC decided not to progress with the strategy however they are indicated this will be picked back up this financial year. | Various aspects of environmental and service improvement continues in collaboration with the JCC | Qtr 3 26/27

## Slide 42
MENTAL HEALTH Q4 DELIVERY
Q4 Reporting: Delivery Expectations , Level 3 and NHS Wales Performance Framework metrics
Mental Health & Learning Disabilities | Target | Jan 26 | Feb 26 | Mar 26
Percentage of mental health assessments undertaken within (up to and including) 28 days from the date of receipt of referral | 80% | 90% | 98% | 93%
Percentage of therapeutic interventions started within (up to and including) 28 days following an assessment by LPMHSS | 80% | 80% | 84% | 87%
Percentage of patients waiting less than 26 weeks to start a psychological therapy in Specialist Adult Mental Health | 80% | 40% | 40% | 39%
DE
DE
L3
Escalation Area (Level 3) | Criteria to achieve | Target | Jan 26 | Feb 26 | Mar 26
CAMHS | 80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral | 80% | 94% | 94% | 82%
 | 70% of therapeutic interventions started within 28 days following an assessment by LPMHS | 70% | 76% | 75% | 81%
 | 85% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan | 85% | 97% | 95% | 90%

## Slide 43
c
MENTAL HEALTH & LEARNING DISABILITIES FORWARD LOOK
Opportunities and Focus for Q1
  MENTAL HEALTH
  Continue with the Mental Health Transformation Program (as set out by the board)
  Continue planned capital works on Tawe clinic to improve patient experience.
  To begin demonstrator projects around Stepped Care 2.0 model.
  To continue working towards a centralised booking system for Mental Health services.
  Continue to roll out and expand digital systems on all areas to aid in achieving digital medical records and increase digital correspondence with service users.
  Continue embedding new admission model whilst reviewing the role of Crisis and Home Treatment Teams.
  Continue work to support the reduction of private placements
  SECURE SERVICES AND REHABILIATION
  BJC scrutiny and capital funding approval required from Welsh Government.
  Commence operational planning with capital planning and contractors to undertake the work in a live ward environment.
  LEARNING DISABILITIES
  Confirm service model with 3 HBs for future redevelopment of all inpatient units. Start process to develop case for change with ultimate aim of drafting SOC according to capital processes and timelines
  Progress engagement for reduction of capacity within existing LD inpatient facilities
  DIGITAL
  Embed Rio into Phase 1 services, undertake Benefits Realisation and continue with Phase 2 preparation work, aligning with Swansea CIty Council
  Awaiting confirmation from Welsh Government for funding for Phase 3 of roll out of Rio

## Slide 44
Digital
Q4 Delivery

## Slide 45
DIGITAL - Q4 OVERVIEW
Successes and Achievements
March 2026 marked a major achievement in our digital transformation journey, with four significant systems successfully going live: BadgerNet (Digital Maternity), Radiology RIS and PACS, and the Rio Community Mental Health System.
Digital Services continue to provide a significant on-site presence, with support across all major programmes. This approach underpins safe delivery, rapid issue resolution and high-quality support to users throughout implementation. Digital staff will be supporting teams up to 15 hours a day according to service needs across a 2-week period post go-live to safely adopt and embed new systems.
Digital Maternity System – Badgernet
Key enabler for the Health Board maternity transformation programme, supporting remote advice and guidance
A revised incremental approach to delivery is underway, with rollout across two phases
Successful Phase 1 Go-Live on 31 March 2026 (for all new antenatal bookings)
Phase 2 (implementation across all maternity services) is on schedule and due to commence 18 May 2026
Local communications plan initiated and will be updated in parallel with the project plan
Radiology Information System Procurement (RISP)
The new Radiology systems (RIS and PACS) successfully went live as planned on 30th March across Morriston, Singleton and Neath Port Talbot, following coordinated cutover activity involving Radiology, Digital Services, the supplier and Digital Health and Care Wales.
Hands-on digital and radiology support continues with staff present to offer troubleshooting and guidance to ensure safe adoption and a smooth transition to the new system during this busy period for the Radiology teams.
The project team will continue to support the adoption of Phase 2 elements such as AVW, Orchestrator and Brantec Breach, along with Electronic Test Requesting, building on new capabilities such as electronic vetting.
Rio – Paper based teams in Mental Health and Learning Disabilities (MH&LD)
Successful go-live of the Rio electronic patient record on 24 March 2026 across the Mental Health and Learning Disabilities services with strong early usage of the system.
Staff have manually entered patient caseload information in readiness for the go live on 24th March. Most team caseloads were completed before the go live, where this was not possible team managers are actively validating and updating to ensure the information is a true reflection of existing caseload.
Floor walkers remain on site until 17th April, and daily virtual support continues for all teams.
Positive overall adoption of agreed workflows with only minor adjustments identified and made through early operational feedback.
Activity since the go live on 24th March includes:
  443 users logged into Rio
  5,786 referrals created
  1159 appointments created
Cellular Pathology on LIMS 2.0
Cellular Pathology successfully went live on LIMS 2.0, making Swansea Bay the first Health Board in Wales to deploy the new national system. This represents a significant milestone for the programme and demonstrates effective clinical, digital and operational collaboration in delivering a safe and controlled transition. The go‑live provides an important foundation for subsequent pathology deployments as the programme progresses.
NHS Wales App
Continues to be used as the digital front door for patients and citizens with over 90,000 patients registered across Swansea Bay during 25/26. Integration with the Swansea Bay Patient Portal has seen an increase in adoption of the portal during 25/26, with over 1,000 patients registering to use the portal on a weekly basis.

## Slide 46
DIGITAL - Q4 OVERVIEW
Successes and Achievements
Network Transformation In February NPT Hospital became the first site in SBU to implement the new secure network, part of a wider three‑year £8.68m digital infrastructure modernisation programme. The digital network doesn’t just connect computers — it connects telephones, X‑ray machines, security cameras, medical devices, and many other systems that rely on fast, reliable, and secure connectivity to function safely. The new network gives the health board a more secure, and more resilient network that improves system performance for clinicians, protects against cyber threats, and ensures that critical equipment and services can operate without interruption.
Telephone System Upgrade
The Health Board telephony system was upgraded in February. The telephone system consists of approximately 10,000 phones/extensions and is critical for the safe delivery of services. The new telephony system software will provide a supported platform and has the functionality to link with cloud-based services to improve remote working and increase resilience in the future and rollout would need to be determined by a costs/benefit exercise. More importantly the new telephone system will provide enhance cyber security protection.
Digital Infrastructure
The total capital allocation for essential digital infrastructure in 25/26 was £8.68m.This is enabling the modernisation of services provided:
•Replacement of a significant number of desktop, laptop and ipad computers
•Network equipment to replace and modernise the network at Morriston Hospital
•Fibre optic cabling for the acute Hospitals for increased resilience and speed to run modern digital systems
•Laptops and infrastructure for Mental Health to implement the new digital system (Rio)
•Additional devices and mobile carts for the new Maternity system
•Additional storage capacity for digital systems
•New hardware for the Health Board wide telephony system
•Cardiology system upgrade
•New Servers for Business Intelligence
Equipment for the new dialysis unit opening in Neath Port Talbot this month
Data Literacy
Re-development of Data Literacy courses completed with additional modules now being offered. All digital intelligence courses are now available for staff to self-book via the Electronic Staff Record system. Over 60 staff attended a Digital Intelligence Data Literacy Course during Q4.
Business Intelligence
The Neonatal dashboard has been added into the Maternity and Neonatal app allowing the service to monitor a host of different operational and quality measures such as high dependency occupancy and incidents for the previous month. The dashboard also allows the data to be further drilled into to show trends of measures over time.
Staff and patient experience quadrant of the Quality and Safety Dashboard has been released containing metrics across a range of areas including complaints, compliments, clinical negligence claims, personal injury claims, staff survey results.
Radiology waiting list pages detailing the projected eight-week breaches at the end of the current month which can be filtered by modality have been added to the Planned Care App. These pages replicate what was already available in the app for other diagnostic waiting lists and will help the service monitor, manage and report their waiting list position.
Clinical Coding App
The Clinical Coding App has been launched for Neurology Episodes. The app collates all electronic data from numerous systems relating to an episode and allows the coder to auto-code the episode via a machine learning model. The codes are then audited before the codes are confirmed. Work has now started on creating a similar model for Rheumatology episodes.

## Slide 47
DIGITAL - Q4 OVERVIEW
Risks and Challenges
LIMS
The LIMS 2.0 programme faces significant challenges and risks due to delays in implementation. Progress has been constrained by prolonged User Acceptance Testing, a sustained volume of defects, and ongoing reliance on a limited pool of specialist resources. Blood Transfusion remains the highest‑risk component, reflecting the scale, age and variable quality of legacy data (spanning over 40 years), and the complexity of cleansing, validation and regulatory assurance required prior to any safe deployment. Infrastructure and cyber risks are increasing, as several nationally hosted critical components approach end‑of‑life, heightening vulnerability to outages and security threats. Continued reliance on the current LIMS therefore presents growing operational and cyber risk, alongside diminishing supplier support. Delays continue to compress the remaining delivery window, increasing pressure on Health Board capacity and financial exposure.
Mitigation: Strengthened national oversight of User Acceptance Testing, further refinement of the Blood Transfusion delivery approach (including consideration of alternative go‑live models), improved defect prioritisation, and ongoing efforts to secure additional specialist and financial support through national governance arrangements.
Unscheduled & Emergency Care
The MIU currently use WEDS (Symphony), however the contract with the supplier expires 31st August 2026. A replacement solution is required. At the request of the national 6 goals programme for unscheduled care, DHCW have developed the UEC app (including (WECDS) as a Minimal Viable Product (MVP) to replace the functionality in WPAS ED, however there are concerns with delivery of the UEC App and that the solution will not provide the functionality to support the UEC footprint in Swansea Bay. Recent usability testing with clinicians has raised concerns due to a lack of integration with WPAS. Mitigation: The health board are working closely with DHCW to inform the development of the UEC App and are also engaging with suppliers to understand whether their systems will better meet the needs of the UEC footprint and deliver the WECDS. MIU will revert to WPAS ED as a mitigating action in September.
Maternity
Three of the four key integrations with the national architecture were not delivered in phase 1 of the Badgernet implementation (31st March), presenting several key risks (e.g. dual entry, administrative burden, delays in care delivery, transcription error). A clinical risk assessment was undertaken by digital midwives across Wales. Mitigation: This risk has been escalated nationally via the Technical Advisory group to agree workarounds to mitigate this risk. Health board requirements for future integrations have also been collated nationally. In the meantime, SBUHB will continue to work towards the second phase of rollout (18th May 2026) as per the agreed project plan.

## Slide 48
DIGITAL Q4 DELIVERY DIGITAL TO UPDATE
Delivery Action & System | Q1 Milestone | Q2 Milestone | Q3 Milestone | Q4 Milestone
Procure module 1 of an Electronic Health Record (EHR) with a focus on Urgent and Emergency Care including ePMA [DIGITAL, UEC, PLANNED CARE] |  |  |  | Amended: Engage with third party suppliers and seek funding opportunities for a third party UEC solution is being factored into the UEC re-design discussions between the Health Board and Welsh Government
Implement the new Laboratory Information Management System (LIMS 2.0) [DIGITAL, UEC, PLANNED CARE, CANCER] |  |  |  | Amended: Go-live of SBUHB Cellular Pathology on the new LIMS. Receive national plan for go-live of Blood Sciences and Blood Transfusion
Radiology digital systems replacement (RISP) [DIGITAL, UEC, PLANNCED CARE , CANCER] |  |  |  | The new Radiology Information System (RIS) and Picture Archiving and Communication System (PACS) systems are live and have reached 'stable operations'.
Work with the national programme to deliver a technical solution for the WECDS data set [DIGITAL] |  |  |  | Amended: Continued engagement with DHCW and complete UAT testing of the UEC App
Implementation of the NHS App in parallel with the Swansea Bay Patient Portal [DIGITAL, UEC, PLANNED CARE, CANCER] |  |  |  | Over 90,000 citizens now registered to use the App. New features e.g. outpatient appointment and referral notifications enabled for additional services.
Identify and procure an alternative system for WCCIS and migrate existing 750+ Health Board users who are using WCCIS on the Swansea Council contract, aligned with Swansea Council timelines Decide on the future direction of the Health Board and whether a National or Regional approach to a solution will be followed [DIGITAL, PRIMARY CARE, MH LD] |  |  |  | Continue data migration activities, configuration and testing for a go-live of Rio in September 2026
Increase the spread and scale of adoption of the Hybrid Mail [DIGITAL, PLANNED CARE] |  |  |  | Implement Hybrid Mail in line with the accelerated plan approved by Outpatients Modernisation Group/Planned Care Board
Support new ways of working through the Integrated Discharge Hub. Prepare for working with the Electronic Health Record (EHR). [DIGITAL, UEC] |  |  |  | Amended: v4 Signal development of ADTs. Development underway in readiness for go live at end of Q1 26/27
Complete the implementation of HIR (Hospital Initiated Referrals) across all specialities [DIGITAL, PLANNED CARE] |  |  |  | Amended: Complete evaluation of initial pilot roll out and agree an implementation plan for wider roll out.
Implementation of PROMPTLY [DIGITAL, PLANNED CARE] |  |  |  | Amended: Move all data into PSOM compliant templates by 06/03/26. Full Health Assessment Data from Promptly into data warehouse by end of Q4. Onboard final patient cohorts for the 3Ps Waiting Well Assessment by end of Feb 2026. Data flow to NDR due by end of Q4. Move Promptly to BAU.
ON TRACK – Action progressing as planned & agreed timelines | OFF TRACK – Action not progressing as planned / to original timelines, however, management & mitigating actions are in place | OFF TRACK – Action not progressing as planned / to original timelines, there is significant issue which require escalating

## Slide 49
DIGITAL Q4 DELIVERY
Delivery Action & System | Q1 Milestone | Q2 Milestone | Q3 Milestone | Q4 Milestone
Implementation of WNCR in Paediatrics [DIGITAL, CYP] |  |  |  | Complete system testing in readiness to roll out to Morriston
Digital Maternity Cymru - Digitisation of maternity records - in line with National Programme [DIGITAL, MAT NEO] |  |  |  | Deploy IT hardware and continue configuration and testing to support an implementation of digital maternity solution.. Go live 31st March
ePMA - Integrate HEPMA with National solutions such as the Shared Medicines Record (SMR) [DIGITAL, UEC] |  |  |  | Amended: System C review of capability to connect to the SMR. Receive quote from System C for time and cost for development.
Disaggregation of WPAS currently combined with Bridgend/Cwm Taf [DIGITAL] |  |  |  | Completed in Q2.
Implement Open Eyes aligned to the pathways as prioritised by the Ophthalmology Service including regional working with Hywel Dda UHB [DIGITAL, PLANNED CARE] |  |  |  | Continue to work with DHCW and the supplier to understand the resource requirements to implement ERS in line with the national plan.
Implement WICIS in line with national implementation plan [DIGITAL] |  |  |  | Awaiting decision from Welsh Government on whether the project will proceed.
Expand the use of Electronic Test Requesting and Reporting [DIGITAL, PLANNED CARE] |  |  |  | Amended: Go-live with new electronic test report types
Engage with the National Programme on the replacement of the Systemic Anti-Cancer Therapy SACT e-prescribing system [DIGITAL, CANCER] |  |  |  | Supporting national procurement to replace existing solution
In-Touch - Go live with 'In Touch' outcome form and write back to WPAS [DIGITAL, PLANNED CARE] |  |  |  | Roll out according to agreed plan (to be confirmed)
The Millcare System in Sexual Health is no longer supported, work is underway (led by PHW) to plan for a national solution. [DIGITAL, PRIMARY CARE] |  |  |  | 
WPAS roll out across Mental Health, Learning Disabilities and Primary Care and Therapies [DIGITAL, PRIMARY CARE, MH LD] |  |  |  | Go live with Rio to replace WPAS HCP module for MH. Agree resources required to implement WPAS for community and therapies
ON TRACK – Action progressing as planned & agreed timelines | OFF TRACK – Action not progressing as planned / to original timelines, however, management & mitigating actions are in place | OFF TRACK – Action not progressing as planned / to original timelines, there is significant issue which require escalating

## Slide 50
DIGITAL Q4 DELIVERY
Delivery Action & System | Q1 Milestone | Q2 Milestone | Q3 Milestone | Q4 Milestone
Cyber Secure Back Ups [DIGITAL] |  |  |  | Complete
NPT Wireless Equipment Replacement [DIGITAL] |  |  |  | Installation complete
Replace ageing hardware [DIGITAL] |  |  |  | <<<<
Additional server equipment including storage [DIGITAL] |  |  |  | [No milestone: Delivery Action complete]
Complete rollout of Imprivata card login system to all acute hospital wards [DIGITAL] |  |  |  | Continue roll out of Imprivata
Implement new core network at Morriston & Singleton hospitals [DIGITAL] |  |  |  | Implementation complete
Upgrade to Windows 11 operating system and remove Windows 10 as Microsoft are ceasing support by in October 2025 [DIGITAL] |  |  |  | No further upgrades to complete in Q4 due to a requirement for suppliers to upgrade client software
Undertake an options appraisal to assess a Call Manager Upgrade to Cloud Voice [DIGITAL] |  |  |  | Continue implementation of upgrade.
Delivery of a suite of Quality & Safety dashboards [DIGITAL] |  |  |  | Complaints, additional Infection control and Cardiac arrest measures to be added to Dashboard.
Re-banding of Coding Staff and development of auto-coding software to improve coding completeness in accordance with Clinical Coding Audit Action Plan. [DIGITAL] |  |  |  | Auto-coding App in use for Neurology and additional specialties identified.
Delivery of Data Literacy and Value Programme [DIGITAL] |  |  |  | Self-booking of data literacy courses available on ESR with 9 courses to take place including new Power BI training courses.
Help support the creation of the NDR across NHS Wales [DIGITAL] |  |  |  | Trust Integration Engine purchased to enable FHIR integration from WNCR to Signal. Migration of data warehouse to Google platform continues to be scoped out.
Centralisation of Health Records function to Ty Samlet [DIGITAL] |  |  |  | Completed
Digitise cellular pathology services [DIGITAL, CANCER, PLANNED CARE] |  |  |  | Amended: Publish Invitation To Tender
eTriage [DIGITAL, UEC] |  |  |  | This is now on hold as the requirements to integrate with WEDS (Symphony) did not make the investment worthwhile, due to the Symphony contract expiring August 2026.
ON TRACK – Action progressing as planned & agreed timelines | OFF TRACK – Action not progressing as planned / to original timelines, however, management & mitigating actions are in place | OFF TRACK – Action not progressing as planned / to original timelines, there is significant issue which require escalating

## Slide 51
DIGITAL OFF TRACK
Delivery Action and System | Q4 Milestone Off track | Reason | Mitigating Actions | When on track
Procure module 1 of an Electronic Health Record (EHR) with a focus on Urgent and Emergency Care including ePMA [DIGITAL, UEC, PLANNED CARE] | Amended: Engage with third party suppliers and seek funding opportunities for a third party UEC solution is being factored into the UEC re-design discussions between the Health Board and Welsh Government | The requirements of the 6 goals programme to deliver against the Welsh Emergency Care Data Set (WECDS) and the need for DHCW to develop a UEC app to address this, coupled with the contract end date of Symphony in the Minor Injuries Unit (MIU) has meant that the Health Board has had to prioritise these challenges. The Health board have conducted engagement sessions with suppliers to assess the capabilities of their solutions in meeting the health board requirements. A paper was presented and approved by Execs to agree the procurement of a third-party solution, as a strategic way forward for UEC. | The health board are engaging with third party suppliers to establish how alternative solutions could support flow and safety across the UEC footprint, including the timescales for delivery. Funding for a third party UEC solution is being factored into the UEC re-design discussions between the Health Board and Welsh Government | Q1
Implement the new Laboratory Information Management System (LIMS 2.0) [DIGITAL, UEC, PLANNED CARE, CANCER] | Amended: Go-live of SBUHB Cellular Pathology on the new LIMS. Receive national plan for go-live of Blood Sciences and Blood Transfusion | Delivery of LIMS 2.0 has been impacted by prolonged User Acceptance Testing, the volume and complexity of outstanding defects, and ongoing dependency on a limited pool of specialist pathology and digital resource. The most complex modules, particularly Blood Sciences and Blood Transfusion, require extensive data migration, validation and regulatory assurance, which has constrained the ability to confirm safe go‑live sequencing within the original timescales. | The Health Board is working closely with the national LIMS programme to prioritise critical defect resolution, complete Blood Sciences testing and progress development and assurance of the Blood Transfusion module. Enhanced national oversight, strengthened validation and continued engagement on affordability and risk support safe onward deployment. | Q1
Work with the national programme to deliver a technical solution for the WECDS data set [DIGITAL] | Amended: Continued engagement with DHCW and complete UAT testing of the UEC App | There have been delays to the development of the UEC App, clinical and digital teams continue to engage with the national programme to inform the requirements | The health board are working closely with DHCW to inform the development of the UEC App and are also engaging with suppliers to understand whether their systems will better meet the needs of the UEC footprint and deliver the WECDS. MIU will revert to WPAS ED as a mitigating action in September | Q1
Identify and procure an alternative system for WCCIS and migrate existing 750+ Health Board users who are using WCCIS on the Swansea Council contract, aligned with Swansea Council timelines Decide on the future direction of the Health Board and whether a National or Regional approach to a solution will be followed [DIGITAL, PRIMARY CARE, MH LD] | Continue data migration activities, configuration and testing for a go-live of Rio in September 2026 | SBUHB use WCCIS on the Swansea Council contract, therefore go live must be closely aligned to the Swansea Council go live date. Migration activities are ongoing, however there has been a delay to the go live date, which is currently being re-scheduled. We are awaiting confirmation of this from Swansea Council | Continue to work closely with Swansea Council to align with the agreed implementation plan | This is dependent on the plan agreed with Swansea Council
ePMA - Integrate HEPMA with National solutions such as the Shared Medicines Record (SMR) [DIGITAL, UEC] | Amended: System C review of capability to connect to the SMR. Receive quote from System C for time and cost for development | Progress is dependent on national solution readiness and supplier capability to support integration with the Shared Medicines Record. Further clarity is required on technical standards, timescales and funding for national interoperability. | Continued engagement with the national programme and System C to clarify technical requirements, delivery approach and dependency alignment. | This work is dependent on System C’s ability to meet the technical requirements. Aim is to complete development in Q4 26/27 in readiness for go live Q1 27/28 TBC

## Slide 52
DIGITAL OFF TRACK
Delivery Action and System | Q4 Milestone Off track | Reason | Mitigating Actions | When on track
Implement WICIS in line with national implementation plan [DIGITAL] | Awaiting decision from Welsh Government on whether the project will proceed. | Welsh Government have approved in principle to proceed with formal confirmation expected at the DDaT Board. SBUHB is committed to implementing the solution, and lead clinicians are actively engaged. | Clarification on the national funding is being sought. | Welsh Government have confirmed that WICIS will be a digital priority for delivery in FY 2026-27
Expand the use of Electronic Test Requesting and Reporting [DIGITAL, PLANNED CARE] | Amended: Go-live with new electronic test report types | Limited engagement from suppliers to quote for integration work for some elements e.g. cardiology reports. Rollout of radiology requesting is a priority for 26/27 building on new capabilities available via delivery of the RISP programme in 25/26. | Escalation with suppliers | Q1
NPT Wireless Equipment Replacement [DIGITAL] | Installation complete | Other work has been prioritised and there has been a delay in getting agreement from NPT senior management to progress with the replacement work | Now agreed for April 18th and 19th | April 2026
Digitise cellular pathology services [DIGITAL, CANCER, PLANNED CARE] | Amended: Publish Invitation To Tender | Progress constrained by the requirement for all Health Boards to agree business cases in advance of issuing the national digital cellular pathology ITT. | Support updated national plan to issue Invitation to Tender, carry out supplier engagement, response evaluation and contract award in 2026/27. | Q1

## Slide 53
DIGITAL Q4 DELIVERY
Performance Framework metrics
Digital | Target | Trajectory Jan 26 | Trajectory Feb 26 | Trajectory Mar 26 | Actual Jan 26 | Actual Feb 26 | Actual Mar 26
Percentage of episodes clinically coded within one reporting month post episode discharge end date | Maintain the 95% target or demonstrate a 12-month improvement trend | 80% | 63% | 63% | 80% | 68% | 68%
Percentage of all classifications’ coding errors corrected by the next monthly reporting submission following identification | 90% | 90% | 90% | 90% | 95% | 98% | 93%
Enabling Action | End of Year position
Ensure implementation of national digital priorities, specifically the implementation of the digital maternity system, and NHS Wales app. | Digital Maternity Phase 1 Go-Live of the Badgernet System was successfully completed on 31 March 2026 (for all new antenatal bookings). Phase 2 (implementation across all maternity services) is on schedule and due to commence 18 May 2026 Digital Eyecare Open Eyes/ERS Building on a successful go live of the Open Eyes solution, project readiness activities are underway across primary and secondary care to support the implementation of the National OPERAi electronic referral solution. SBUHB is part of Cohort 2, with implementation planned from mid-May 2026. The project team continues to work with DHCW and RMSL (the supplier) to complete all readiness activities as per the project plan.
Support the implementation and roll-out of the NHS Wales app for maximum impact and benefit to include the uptake of its use for repeat prescriptions. | NHS Wales App Functionality has been implemented to support referral acknowledgement notification and a notification for new stage 1 appointments. Over 90k citizens have registered for the NHS Wales App. The App acts as the digital front door to the Swansea Bay patient portal, over 55,000 patients on an outpatient pathway use portal to empower them to manage their care.
Eradicate unsupported systems and devices and ensure a clear cyber response plan for the organisation. | Upgraded systems to supported versions which included the R4 Dental System and Citrix Infrastructure, telephony system and Neath Port Talbot Hospital network. Invested £8.68m capital for tech refresh and supporting additional devices for strategic projects. £2.31m investment allowed the procurement of network equipment for Morriston Hospital which will be implemented in financial year 2026/27. The Rio implementation provided opportunities for rolling out new modern devices and replacing outdated equipment. Radiology RISP programme also provided opportunities to implement modern cloud-based services and replacement of old hardware. The new system will allow SBU to further reduce the number of Windows 10 devices which there are currently 350 devices left out of an estate of circa 11850 (<3%). Invested capital in 2025/26 to provide the capability to upgrade Windows Server infrastructure to the latest supported version (Windows Server 2025).
Enabling Actions Q4 Reporting

## Slide 54
DIGITAL FORWARD LOOK -Matt John
Opportunities and Focus for Q1 26/27
Digital Maternity - Badgernet
Following the successful implementation of Phase 1, and alongside the provision of onsite support, project readiness activities - including data migration, system configuration, and training, will continue to support the Phase 2 rollout, which is scheduled to commence on 18 May 2026 across all Maternity Services.
Digital Eyecare Open Eyes/ERS
Project readiness activities are underway across primary and secondary care to support the implementation of the National OPERAi electronic referral solution. SBUHB is part of Cohort 2, with implementation planned from mid-May 2026. The project team continues to work with DHCW and RMSL (the supplier) to complete all readiness activities as per the project plan.
Hybrid Mail
The key focus for Q1 will be to implement the next 13 services on the implementation plan. Implementation beyond this will be dependent on agreeing the finances for future services.
Rio Implementation/WCCIS Migration
Work will continue to embed the Rio solution into those teams that have gone live in March 2026. Teams will continue to be supported either via floorwalking (until April 17th) or virtually. Work will continue to develop reporting dashboards to meet service requirements.
LIMS
The focus for Q1 is on completing User Acceptance Testing and readiness activities for Blood Sciences, alongside progressing data migration and assurance of the Blood Transfusion module. This includes continued national engagement to resolve critical defects, confirm safe go‑live sequencing and manage affordability and risk as the LIMS programme moves into its most complex phase.
Welsh Intensive Care Information System (WICIS)
The implementation of WICIS is dependent on Welsh Government funding to support the work required to deliver the solution. The decision from Welsh Government to support this implementation is expected in Q1.
NHS Wales App – further rollout of new features in line with the DHCW release plan.
Electronic Prescription Service (EPS)
SBU are hosting first of type testing of EPS within GP Out of Hours and Urgent Primary Care Centres on behalf of all health boards, alongside the implementation of EPS across primary care. This testing is expected to be completed in Q1.
RISP
Following the successful go live of PACS and RIS during Q4, there will be continued support for the project during Q1 in reaching Stable Operations, full data migration and rollout of full functionality.
SIGNAL
The key focus for Q1 will be to configure and test Version 4, which delivers Admission, Discharge and Transfer functionality alongside WCP.
Network Transformation
In April, the NPT Hospital will have the wireless network replaced with new state‑of‑the‑art Cisco wireless network—an exciting and strategically important upgrade that will deliver fast, secure, reliable access to digital services for clinicians exactly where they’re needed most: at the point of care. Following this, work will commence to replace the Singleton network.
Clinical Coding App
A machine learning model will be created for Rheumatology that can auto-code day-case episodes. Once this model is created it will be tested with the clinical coding department and then implemented for the coding of these episodes.

## Slide 55
Workforce
Q4 Delivery

## Slide 56
WORKFORCE Q4 DELIVERY
Delivery Action | Q1 Milestone | Q2 Milestone | Q3 Milestone | Q4 Milestone
Support line managers with timely Occupational Health advice to support health at work/enable timely return to work after sickness absence |  |  |  | The 1st offered appointment date will be within 29 calendar days of the date referral received.
Improve Attendance at Work |  |  |  | Increased audit compliance on Managing Attendance at Work Policy across the Health Board
Best Practice Review of HR policies and processes |  |  |  | Review number of ER cases to determine impact (target: 5% reduction of formal ER cases by Q4)
Deliver Speaking Up Safely audit recommendations specific to Workforce & OD, in collaboration with key stakeholders |  |  |  | Integrate Speaking Up Safely measures into the Workforce Performance Scorecard.
Embed the retention plan across service groups |  |  |  | Ensure all service groups have had the retention plan embedded within their work areas
In collaboration with stakeholders, design, embed and evaluate a suite of management and leadership development initiatives for all levels of clinical and non-clinical leaders that supports us to embed our values, behaviours and deliver our One Bay Way 10 year vision |  |  |  | In collaboration with key stakeholders, evaluate delivery and impact of our revised management and leadership development initiatives
Build on workforce Metrics Dashboard to increase insights |  |  |  | Evaluate and define plan moving forward
Implement workforce-related programmes of work to achieve the ministerial priorities of ​reducing agency spend |  |  |  | Evaluate and define actions to improve further
ON TRACK – Action progressing as planned & agreed timelines | OFF TRACK – Action not progressing as planned / to original timelines, however, management & mitigating actions are in place | OFF TRACK – Action not progressing as planned / to original timelines, there is significant issue which require escalating

## Slide 57
WORKFORCE – Q4 Overview & Q1 26/27 Look Forward
Opportunities and Focus for Q1
Review options for increasing line-manager awareness of support/early intervention for stress, anxiety and depression (S10) using tailored adjustments, staff health passport & work-related stress assessment
Increased Service Group focus on Managing Attendance at Work compliance and hot spot areas informing specific action plans and measurable goals. Noticeable reduction in sickness absence in some hot spot areas – work to continue and best practice shared.
The pause on recruitment has vastly reduced the number of Apprentices employed in the Health Board, as has the national decision to remove the requirement for HCSW to undertake qualifications (linked to the job description review). There is a real risk that momentum around Apprenticeships will stop, leading to a substantial reduction in numbers in future years.
Risk of increasing waits for Occupational Health Medical assessments due to demand and complexity of cases
ER Cases are increasing in volume and complexity – AHRBP's have been released for a % time per week to dedicate support on case work.
Q4 Overview – Key Achievements
All of Cohort 6 of our Graduate Gateway Programme have successfully gained employment in SBUHB and completed the programme ahead of the May 2026 end date.
Continuing to recruit Apprentices and support the development of existing staff via Apprenticeships and other training routes through Welsh Government funding streams. This has included new Apprenticeship pathways e.g. Electrical Apprentices, and the enrolment of existing staff onto the Legal Services Apprenticeship pathway.
Utilising opportunities to develop our staff through Welsh Government (MEDR) funding (e.g. 41 enrolling on and completing the Level 3 Coaching and Mentoring qualification through Bridgend College). Some have chosen to further their development, joining our internal Coaching Network
Despite a significant increased in demand on the Occupational Health Service, the WG management referral KPI of 1st appt within 4 weeks of referral remains at 69% compliant
Significant increase in quality of Occupational Health reports as measured by monthly audit outcomes against national standards.
Staff turnover rates have reduced across all professions
Challenges and Risks

## Slide 58
WORKFORCE Q4 DELIVERY
Q4 Reporting: NHS Wales Performance Framework and Local Measures
Workforce | Target | Jan 26 | Feb -26 | Mar 26
Percentage of sickness absence rate of staff – 12 month rolling | 12-month reduction trend | 7.19% | 7.21% | 7.25%
Percentage of sickness absence rate of staff – in month |  | 7.76% | 7.20% | 7.04%
Agency spend as a percentage of the total pay bill | 12-month reduction trend | 1.30% | 1.34% | Not available
Percentage headcount by organisation who have had a Personal Appraisal and Development Review (PADR)/medical appraisal in the previous 12 months (excluding doctors and dentists in training) | 85% | 73.78% | 75.79% | 76.34%
Percentage of staff who have completed all statutory & mandatory training modules | 85% | 88.97% | 88.39% | 88.17%

## Slide 59
Q4 DELIVERY: OTHER AREAS NOT INCLUDED ELSEWHERE
Q4 Reporting: TI metrics and Performance Framework
TI
TI
TI
TI
TI
Quality and Safety | Target | Actual Jan 26 | Actual Feb 26 | Actual Mar 26
Number of Hospital onset C-Diff Cases | Reduce the number of hospital onset infections by 40% and maintain for 3 months | 3 | 7 | 12
Number of hospital onset Staph aureus Cases | Reduce the number of hospital onset infections by 25% and maintain for 3 months | 3 | 0 | 5
Number of hospital onset E-Coli Cases | Reduce the number of hospital onset infections by 20% and maintain for 3 months | 3 | 6 | 6
Number of hospital onset Klebsiella Cases | Reduce the number of hospital onset infections by 10% and maintain for 3 months based on 2017/18 figures | 2 | 2 | 4
Number of patient experience surveys completed and recorded on CIVICA | month on month improvement | 7,253 | 6,668 | 6,888