NHS WALES PLANNING FRAMEWORK 26-29- TEMPLATES

The Ministerial templates support the development of organisational IMTPs/ plans along with the Minimum Data Set (MDS).

A template will be required to detail milestones, actions and risks etc for the delivery expectations against each of the following strategic priorities:

- Timely Access to Care

- Population Health and Prevention

- Community by Design

- Mental Health Access

- Women’s Health

- Quality and Safety

Progress on these expectations, including specific delivery metrics, have been referenced in the planning framework.  The set of 3-year strategic priorities and year 1 delivery expectations must be delivered by all health boards, and other NHS organisations where relevant, and will be a focus of the planning process for 2026-27.

Completing the template will provide detailed delivery points including baseline, milestone and actions to demonstrate how the priority will be implemented. The detail contained in the template should align to the narrative plan. For clarity and to reduce duplication, organisations are free to include narrative in the IMTP document and to include the more detailed information on baseline, milestones and specific actions within the Ministerial Templates should they choose to do so.  However, clear delivery commitments must be made and sign posting between documents would be helpful.

All priorities need to be underpinned by a focus on quality, safety and prevention as a part of the planned activity, with good medical outcomes at the heart of NHS services.

MINISTERIAL TEMPLATE BLANK

All organisations are expected to complete the templates proportionate to their direct or supporting roles and functions.

The completed templates must be collated and submitted alongside the organisation’s plan and the completed Minimum Data Set by 31 March 2026. Please send to: HSS-planningteam@gov.wales

The blank template below needs to be replicated as required for each delivery expectation identified under each of the Cabinet Secretary’s strategic priorities. Additional rows can be expanded as necessary.

| Priority area(s) to deliver 25/26: |  |
| --- | --- |
| Key focus should be on delivering | Community by Design |

| Overarching outcome measures/ metrics: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Deliver a 12-month reduction trend in both the number of people who are delayed in hospital and the total days delayed for these patients, as measured by the Delayed Pathways of Care dashboard. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline position 25/26 Q4=175 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance Trajectories 26/27 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quarter 1 |  |  | Quarter 2 |  |  |  | Quarter 3 |  |  |  | Quarter 4 |  |  |
| Apr | May | Jun | Jul |  | Aug | Sep | Oct | Nov |  | Dec | Jan | Feb | Mar |
| 210 | 200 | 190 | 180 |  | 170 | 160 | 150 | 140 |  | 130 | 120 | 110 | 100 |
| 2. Increase in capacity at the weekend of community nursing and specialist palliative care nursing to at least the required levels previously set for 2024/25 and greater where possible. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline position 25/26 TBC as per Community Services Review in progress |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance Trajectories 26/27 TBC as per Community Services Review in progress- unable to provide until this concludes. Discussion with Execs in June 2026. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Delivery via UEC Programme. See UEC Sections of Plan. Ref; Scheme/ Project and Description; Delivery Actions 26/27; Delivery Date. UEC_C_02; Reducing Clinically Optimised Patients • To continue to develop the D2RA model in partnership with Local Authorities with a key focus on the Pathway 2 bed pool utilisation.; - Undertake baseline capacity and demand in respect of the Pathway 2 bed pool. - To analyse the findings of the Pathway 2 snapshot audit of all patients in Pathway 2 beds in hospital and community settings. - To remodel the bed pool based on the learning from the audit, benchmark LoS opportunities and scenario planning (what does an increased P1 offer do the number of P2 beds required). - To implement a COP reduction programme (cross system – health & social care); Q1-Q4. UEC_B_05; Acute and Community Hospital ‘Back Door’ flow Deliver, as a minimum, all principles set out in the six goals for urgent and emergency care programme Optimal Hospital Flow Framework. Lessons should be learnt from the 2025-26 ‘Winter Sprints’, with a focus on 7-day working with leaner acute hospital processes and more efficient discharge transport services to facilitate earlier discharges and increasing weekend discharges.; To implement (subject to sufficient resource) the Optimal Hospital Flow Framework and realise outcomes expected by Enabling Actions /UEC 6 Goals -Consistently realise 33% of discharges by midday -Achieve a minimum of 20% of total weekly discharges on weekends (Saturday and Sunday) by the end of December 2026, and exceed 25% by the end of March 2027, while maintaining mid-week discharge volumes at current levels; Q1-Q4. Regional Partnership: Develop new model of integrated community-based care across Health and Social care that is financially sustainable and focussed on the principles of Community by Design To include: •Integrated Services Review (S33 – Services and workforce) –; - Workshops planned through 2026 – first workshop 13th Feb 2026 - Further workshops scheduled for March and April 2026. - Review of finance/ workforce and recommendations. - Propose pathway and model; Q1 2026 March 2027. Internal Community Nursing Review: To include: -A review of District nursing / CRT/ Specialist Palliative Care Virtual Wards and ACT. -Cluster based model for one community pathway aligning core services and enhanced care service to provide seamless step up/ down; - Review and mapping of current services - Options paper outlining findings and recommendations - Develop agreed actions and timelines to deliver recommendations; Q1-Q4. |
| Outcomes |  |  |  | Deliver a 12-month reduction trend in the Number of people who are delayed in hospital as measured by the Delayed Pathways of Care Dashboard, reducing this to 100 patients delayed in hospital by March 2027. |  |  |  |  |  |  |  |  |  |
| Risks |  |  |  | Risks of Non-Delivery |  |  |  |  | Mitigations |  |  |  |  |
|  |  |  |  | Linked to Strategic Risk: Clinically Optimised Patients [Level 20] |  |  |  |  | UEC Programme Delivery |  |  |  |  |
|  |  |  |  | Risks to Delivery |  |  |  |  | Mitigations |  |  |  |  |
|  |  |  |  | Limitation of resources impacting on the delivery of actions |  |  |  |  | Delivery prioritisation to be determined through UEC Programme Board. Director level discussion. Regional workshops planned for March/ April |  |  |  |  |
|  |  |  |  | Reduced capacity and flow within acute services due to delay in the implementation of the Community Services Review |  |  |  |  | Senior leadership engaged with LA and RPB, Director level discussions , Deputy COO co-chairs C&OP, Regional workshops planned March/ April |  |  |  |  |
| Critical Enablers |  |  |  | Finance |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Within existing resources |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Workforce |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Within existing resources |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Digital |  |  |  |  |  |  |  |  |  |
|  |  |  |  | UEC Digital Transformation Priorities include: - UEC Electronic Patient Record: Implement a system to span the Health Board UEC footprint; supporting flow and safety whilst enabling broader service transformation (Awaiting DPIF Bid feedback submitted 29th April) - Signal: Continue to enhance Signal to support Optimal Hospital Flow ​ |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Other (Specify) |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Beds rationalisation programme and associated enablers. |  |  |  |  |  |  |  |  |  |