| Date | 24th September, 2024 |  | Agenda Item |  |  | 5.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Annual Plan 24/25 Delivery: Quarter 1 Progress Report |  |  |  |  |  |
| Report Author | Andrea Folland, Strategic Planning Manager Ruth Tovey, Head of Strategic Planning Ffion Ansari, Head of IMTP Development & Implementation |  |  |  |  |  |
| Report Sponsor | Nerissa Vaughan, Interim Executive Director of Strategy Karen Stapleton, Deputy Director of Strategy Deb Lewis, Chief Operating Officer |  |  |  |  |  |
| Presented by | Nerissa Vaughan, Interim Executive Director of Strategy |  |  |  |  |  |
| FOI | Open |  |  |  |  |  |
| Purpose of the Report | This paper provides the reported Quarter 1 status of the priorities for delivery, as set out in the Health Board Annual Plan 24/25 as Goals Methods Outcomes (GMOs). |  |  |  |  |  |
| Key Issues | - High-level summary provided of the position at the end of Q1 (1st April 2024 – 30th June 2024) in respect of delivery against Annual Plan priorities (Goals and Methods). Where Methods are reported as off-track, mitigating actions and revised delivery timescales are highlighted as recommended by the Annual Plan Oversight Group on 2nd July, 2024. - Performance against Annual Plan System Indicators (aligned to KPIs set by WG) at the end of Q1 are reported. - The Minimum Data Set (MDS) has been updated for Q1 with actual data against the required metrics, as requested by Welsh Government as part of the NHS Wales planning process. |  |  |  |  |  |
| Specific Action Required | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☒ |  |
| Recommendations | The Committee is asked to: - NOTE the areas of achievement in delivery of the Annual Plan in Q1. - NOTE mitigating actions against GMOs which are off-track. - APPROVE the revised timescales and changes to the plan where delivery is off track. - APPROVE updated MDS for Quarter 1 for submission to Welsh Government. |  |  |  |  |  |

ANNUAL PLAN 24/25 DELIVERY: QUARTER 1 PROGRESS REPORT

1. INTRODUCTION

This paper provides the reported status against the priorities for delivery in Quarter 1 24/25, as set out in the Annual Plan as Goals Methods Outcomes (GMOs). Any changes from the plan submitted to WG, including revisions to quarterly milestones, are presented for the approval of Performance and Finance Committee (the Committee). In addition, the updated Minimum Data Set (MDS) for Quarter 1 24/25 is provided.

2. BACKGROUND

The Health Board has a statutory duty to submit a financially balanced Integrated Medium Term Plan (IMTP) annually. The Health Board approved and submitted to WG its Annual Plan for 24/25 in March 2024. Subsequently the Health Board resubmitted the Annual Plan for 2024-25 to WG on 31st May 2024. Whilst the Plan remained unchanged in terms of planning assumptions, the HB advised WG that further work at speciality/divisional level had been undertaken to refine the 24/25 demand and capacity profiles, leading to revised performance trajectories for a number f the WG Key Performance Indicators (KPIs). As such the respective Ministerial Templates and Minimum Data Set (MDS) were resubmitted as revised on the basis of the updated trajectories set against new targets from WG.

The Annual Plan is structured in ‘Systems’ based programmes of work that have key deliverables (GMOs) outlined. The responsibility for GMO operational delivery and performance sits with the Service Groups.  However, the accountability in providing direction and monitoring the delivery progress of System GMOs is via Programme Boards (or equivalent group). The Exec Lead/ SROs for the System areas are set out in Table 1, below:

| System /Programme | SRO/ Exec Lead |
| --- | --- |
| Urgent & Emergency Care | Chief Operating Officer |
| Planned Care | Chief Operating Officer |
| Cancer | Executive Medical Director |
| Children and Young People | Executive Director of Nursing and Patient Experience |
| Maternity and Womens’ Health | Executive Director of Nursing and Patient Experience |
| Mental Health and Learning Disabilities | Group Service Director for Mental Health and Learning Disabilities (reporting to Chief Operating Officer) |
| Primary Care | Group Service Director for Primary, Community, and Therapies (reporting to Chief Operating Officer) |
| Workforce | Executive Director of Workforce and Organisational Development |
| Digital | Director of Digital |

The Annual Plan Oversight Group (APOG) chaired by the Chief Operating Officer received an update on Q1 position from all areas on 2nd July 2024.

2.1 Minimum Data Set

The Minimum Data Set (MDS) is a part of the IMTP and forms part of the formal submission to WG. The MDS provides a data triangulation between workforce, planned service activity and finance. The MDS is considered by WG as a tool to aid planning, providing quantification of the ambition in plans at organisational level, and not as a performance monitoring tool.3. ANNUAL PLAN 24/25 DELIVERY UPDATE

3.1 PROGRESS AGAINST PLAN – SUMMARY

SROs were asked to update on the Q1 status of the Method (Action) component of the GMOs (see Appendix 1 for full, final Quarter 1 GMO list) , assessed against delivery of Q1 milestones, using the definitions outlined in Table 2:

| METHODS STATUS | Definitions |
| --- | --- |
| Green | ON TRACK - Progressing as planned /to agreed timelines |
| Amber | OFF TRACK – Not progressing as planned/ to original timelines, however this is manageable & mitigating actions are in place |
| Red | OFF TRACK – Not progressing as planned/ to original timelines, there are significant issues which require escalating |

Q1 Highlight Reports were also provided to inform discussions at the APOG meeting.

Service Group reporting on the GMOs that they own and lead (as agreed through the GMO Mapping and Governance exercise undertaken by Strategy in May 2024) were extracted into the System Highlight Reports. The Service Group Directors provided their review and sign off on the resulting System Plan Highlight Reports related to their areas.

Table 3, below, summarises performance by reporting area, reflecting cross-cutting (Service Group and Programme Board reporting group) GMOs in the figures of each area to which they are relevant:

| Reporting Area: | Q1 status METHODS: |
| --- | --- |
| Primary Care, Community & Therapies |  |
| Neath Port Talbot Singleton |  |
| Morriston |  |
| Mental Health & Learning Disabilities |  |
| Outpatients |  |
| Urgent & Emergency Care |  |
| Digital |  |
| Workforce & Operational Development |  |
| Value Based Healthcare |  |
| Population Health |  |
| One Bay Way |  |
| Overall performance against Q1 milestones: |  |

Table 4, below, summarises performance of systems included in the figures reported by service, above:

| Reporting System: | Q1 status METHODS: |
| --- | --- |
| Cancer |  |
| Children & Young People |  |
| Maternity & Women’s Health |  |
| Planned Care |  |

3.2 QUARTER 1 ACHIEVEMENTS

Q1 achievements are outlined in Appendix 2.

3.3 OFF-TRACK METHODS

Table 5, below, details red, ‘significantly off-track,’ methods reported, including reasons for delay and the mitigating actions being undertaken. In addition, where it has been identified that GMOs which are off-track at Q1-end will have a knock-on effect on delivery by the end of the year, revisions to subsequent milestones were proposed and agreed by the Annual Plan Oversight Group (APOG), as detailed. The Committee are asked to approve these changes to the Plan.

| GMO (Reference number and Method) | Off-track Milestone for Q1 | Reason for delay and what is being done to bring activity back ‘on track’ (Mitigating actions) | Change to Plan & Proposed Next Steps |  |
| --- | --- | --- | --- | --- |
| PRIMARY CARE, COMMUNITY & THERAPIES (PCCT) Service Group Lead: Brian Owens |  |  |  |  |
| PCT_08: Ensure delivery of all actions/recommendations from HMP Swansea HIW inspection reports alongside delivery of Health, Care and Wellbeing Delivery Plan (HCWDP) 2023-25. | Explore all funding opportunities both external and internal in order to fully achieve all outstanding actions in the Healthcare and Wellbeing Delivery Plan. The successful implementation of the HCWDP is one of the outstanding recommendations from the HIW 2022 action plan. The HCWDP has 28 actions, of which 23 actions are completed. Progress against the five open actions is monitored by the Prison Partnership Board and the Service Group Patient Safety and Compliance Meeting and can only be fully achieved if funding is secured. | Reason for delay: HIW 2022: 2 actions remain open (of 35) - Closing the HCWDP - Regarding staffing levels (funding dependent). HCWDP: 5 actions remain open (of 28) All 5 of these actions require Local Authority input. Mitigation in place: Exploring other opportunities within the group to support funding additional staff. The five HCWDP actions are owned by the Head of Service for Local Authority who is part of the Prison Partnership Board. |  | Original Q2 milestone: Dependent on identification of funding, partial completion of actions in the Health Delivery Plan Proposed revised Q2 milestone approved at PCTG Operational Business Group on 23.07.2024: Establishment to be reviewed again once the new Deputy Head of Nursing is in post. Aim will be to identify any possible additional staffing from a forensic review of all nursing workforce plans in conjunction with a deep dive review of all the activities that require a RGN in HMP. Work will continue with the GMO Lead to establish re-profiled milestones for Q3 and Q4, together with a possible revised outcome. Given the complex and fragile situation surrounding this GMO, changes may be required each quarter. |
| NEATH PORT TALBOT SINGLETON (NPTS) Service Group Lead: Ceri Gimblett |  |  |  |  |
| Sitting within the NPTS Service Group, this method relates to the Children & Young People System, led by Gareth Howells. NPTS_59: Work with RPB and colleagues within Mental Health services to undertake a review of services required for children with learning disabilities, to identify gaps in service provision, unmet need and priorities for development. Implementing the multi-agency CYP Emotional Wellbeing & Mental Health Delivery Plan. | Initiate Health Board-wide Review to identify any unmet need for children with learning disabilities | Liaising with WGRPB to understand whether this piece of work falls under any WGRPB programmes/tasks to eliminate duplication of work | Revised Q2 Milestone: Identify lead within Health Board to work with WGRPB in undertaking analysis |  |
| NPTS_81: Urgent and Emergency Care settings receive a clinical pharmacy service and that appropriately trained pharmacist prescribers are incorporated into multidisciplinary teams within all Emergency Departments and Same Day Emergency Care units as a priority (RPS/WG clinical review.) | This GMO remains in planning, as per submitted plan, with further consideration of funding required to progress. No further milestones to be documented for 2024/25 unless there is a change to this position. |  |  |  |
| Sitting within the NPTSSG, this method also relates to, and is reported by, the Planned Care System, led by Deb Lewis. NPTS_82: Review of Surgical Business case. Phased funded BC- Phase 1- 1.9 8a Pharmacists, 1.5 B5 Technicians. | This GMO remains in planning, as per submitted plan, with further consideration of funding required to progress. No further milestones to be documented for 2024/25 unless there is a change to this position. |  |  |  |
| Sitting within the NPTSSG, this method also relates to, and is reported by, the Planned Care System, led by Deb Lewis. NPTS_83: Pharmacy Business Case. | Plan to increase numbers of clinics to 10 sessions per week, however currently awaiting confirmation. No funding currently allocated but would need 1.3 x 8a to provide service for 10 clinics per week. | This GMO remains in planning, as per submitted plan, with further consideration of funding required to progress. No further milestones to be documented for 2024/25 unless there is a change to this position. |  |  |
| NPTS_85: Review of current pharmacy priorities, input into Business Case/funding to support patient flow & improve discharge. | This GMO remains in planning, as per submitted plan, with further consideration of funding required to progress. No further milestones to be documented for 2024/25 unless there is a change to this position. |  |  |  |
| NPTS_87: Review of Frailty Pharmacist business case - 2WTE 8a Pharmacists. | This GMO remains in planning, as per submitted plan, with further consideration of funding required to progress. No further milestones to be documented for 2024/25 unless there is a change to this position. |  |  |  |
| MORRISTON Service Group Lead: Sue Moore |  |  |  |  |
| M_04: Create a Mental Health A and E in conjunction with mental health division. *Create a tailor-made environment to reduce risk of absconding **Align with MH&LD GMOs **Interdependent with TI work | Development of the strategy. Review demand and activity to inform the model that is needed. | Focus on progressing Frailty and SDEC. MH will be addressed within the year to formalise a strategy. | This is planning only for 24/25. Given the TI, GIRFT visit and volume of work being undertaken in the UEC space, this piece of work will be completed by the end of the financial year and feed into the 25/26 plan. Considering this, proposed revised milestones are as follows: Q2: Undertake review of current provision Q3: Develop the strategy Q4: Service model ready for governance sign-off and scrutiny process. |  |
| Sitting within the MSG, this method also relates to, and is reported by, the Planned Care System, led by Deb Lewis. M_24: Creation of a new 6-day service pathway for Acute Coronary Syndrome (ACS) within an ARCH project with Hywel Dda UHB to achieve the 72-hour treatment target which is best practice. | Agreement to proceed dependent on Hywel Dda's investment. Agree on financials. | Update awaited from finance teams, with the GMO having been through the VBHC teams of both SBUHB and Hywel Dda. Further review on how to progress to be undertaken on receipt of update. Milestones will be revised when an update is available. |  |  |
| Sitting within the MSG, this method also relates to, and is reported by, the Planned Care System, led by Deb Lewis. M_32: Increase pace of service developments and improve service efficiency by developing a robust network to support Research, Innovation and Continuous Quality Improvement opportunities. | 1) Meet with Arch to support mapping of stakeholders for networking and engagement plan 2) Develop up to date Job description for research Radiographer that is job matched and benchmarked. | 1) Due to limited service management roles and increased portfolio coverage required as a result of OCP and new IR TSU workload, this work has been delayed and re-prioritised. 2) Work ongoing with R&D and National Imaging programme to identify options to update this JD and ensure it benchmarks well across Wales. Issues to escalate regarding volume of workload and prioritisation to ensure this GMO can achieve the targets identified will be completed via 1-1 and Radiology Service Performance review. Some mitigation is in place in the form of the management paper development noted in one of the above action points which will allow the service to identify the clinical and general management roles required for sustainability and efficiency, with benchmarking. |  |  |
| M_34: Nuclear Medicine: *Achieve sustainability of the DXA Scanning Service at SBUHB by increasing efficiency, lowering costs and delivering better care in a healthier environment, developing a demand and capacity plan, optimising the use of the equipment through lunchtime and evening use. *Achieve sustainability of the DXA Reporting, developing a demand and capacity plan, appointing new reporters, increasing reporting sessions. *Recovery of the waiting lists for DXA Scanning and reporting at Hywel Dda UHB, developing a demand and capacity plan, implement a revised SLA with Hywel Dda UHB, recruit and train additional staff, extend scanning schedules. *Prevention of Vertebral Fractures, reducing morbidity and mortality rates associated with osteoporosis in SBU & HDD. *Electronic booking system to improve scheduling efficiency and the ability to send text reminders. | Extend temporary contract as part of the DXA recovery, establish evening scanning shifts to meet demand. for DXA reporting, look at recruitment options. HDda: Revise SLA and agree recovery strategy Prevention of vertebral fractures; Recruitment and training of 2 x clinical nurse specialists. | DXA Scanning SBUHB: Temporary contracts have been extended until end of March 2025, as part of DXA recovery. Evening scanning shifts have been re-established to meet demand, following resignation of the previous clinical technologists undertaking this work. The scanning waiting list for DXA are nearly within the limits of below 8 weeks. This target (which has been revised after resignation of the clinical technologists developing the extra lists) should be achieved within the next 2 months. DXA Reporting SBUHB: for DXA reporting, WLI have ceased at the end of March 2024 and recruitment options have not been considered for SBUHB. DXA Scanning HDda: recovery strategy has been agreed. Recruitment of staff has started with the aim of implementing extended weekdays and Saturday scanning lists. DXA Reporting HDda: recovery strategy has been agreed. Recruitment of staff has started with the aim of addressing reporting in 3 fronts: baseline, extended scanning lists and backlog. However, reporting WLI have ceased at the end of March 2024 and no interim capacity available until appointment and training for the new reporting posts. Prevention of vertebral fractures: Recruitment and training of 2 x clinical nurse specialists not started - no funding awarded to NM for this. | This is planning only for 24/25. Work will continue to assess capacity v demand, and given the new constraints of no further WLI, the impact that has on waiting times. Consequently, revised milestones are proposed as follows: Q2: Undertake review of current provision Q3: Develop the strategy and complete options appraisal Q4: Service model ready for governance sign-off and scrutiny process. |  |
| MENTAL HEALTH & LEARNING DISABILITIES Service Group Lead: Janet Williams |  |  |  |  |
| MHLD_02: Learning Disabilities Match inpatient capacity to demand for hospital care and meet Welsh Government objective to reduce the overall number of people with LD in hospital settings. | Agreement of acute bed reduction | Temporary closure of acute unit due to paucity of estate. This will provide further evidence of ability to cope with reduced beds. No capital identified for seclusion suite development. | Revised Q2 milestone: Review opportunities for capital for seclusion suite development. Revised Q3 milestone: Seclusion room designs submitted and to be considered for funding. Revised Q4 milestone: Tendering submitted pending funding agreement. |  |
| MHLD_11: Secure Services & Recovery To fully embed the hybrid clinical model into the assessment and treatment wards in Caswell Clinic. | Develop revised role and function documents for the wards and establish robust timetable of CTMs and Patient Reviews. | Reason for delay: Impacted by Consultant deficits. Mitigation: Reviewing workforce and recruitment options. | Revised Q2 milestone: Develop revised role and function documents for the wards and establish robust timetable of CTMs and Patient Reviews. Newly added Q3 Milestone: Implement measures described to improve integration and communication between ward and clinical teams. |  |
| MHLD_16: Adult Mental Health (Inpatient) Centralised inpatient model of service within a purposed built environment meeting the needs of the patient population for the Health Board area. Development of Adult Mental Inpatient provision business case. | Project Board remains suspended until September 2024. | Reason for delay: Awaiting decision from Welsh Government in relation to project bid submitted. Mitigation: Discussions continue with Executive Management Board in relation to the project bid. |  |  |
| MHLD_17: Adult Mental Health (Inpatient) To provide safe and effective care in Ward F when Seclusion Facility is in use. | Capital Teamto consider bid and MH&LD to provide any further information required and finalise the plans. | No agreement for capital investment at this stage | Continue discussions with Capital planning. |  |
| MHLD_26: Older Peoples Mental Health (Inpatient) Continue with the redesign of the Older People’s Mental Health Inpatient Services across the Service Group and input into the wider West Glamorgan regional work. | Continue with plans to renovate Suite 4, Tonna Hospital, to modernise our inpatient setting for Older People. | Await confirmation of funding from Welsh Government. | No further update received regarding funding from Welsh Government. Revised Q2 milestone: Await confirmation of funding from Welsh Government. Revised Q3 milestone: Finalise capital plans already drawn up and approved. Revised Q4 milestone: Begin tender process to identify contractor to undertake the renovation. |  |
| MHLD_34: Service Wide (Digital) Digital Systems and Infrastructure Programme (WCCIS) (Also reported in Digital GMOs) | Together with DHCW, HB Digital and key stakeholders, identify and agree on alternative solution to WCCIS | Health Impact Assessment for WCCIS for MH & LD services completed. Still awaiting decision and agreement on solution. | Revised Q2 milestone: DHCW to submit full business case to WG. Alternative solution to WCCIS agreed. To be taken forward by Connecting Care programme. Revised Q3 milestone: Development of implementation plan of viable alternative to WCCIS. Revised Q4 milestone: Agreed timescales for data migration, training and implementation agreed. |  |
| MHLD_41: Psychology Meeting therapeutic demand in a timely manner. | Organisational Change in psychological therapy. | Reason for delay: No additional finances available to support release capacity to cope with increased demand. Mitigation in place: Review unused vacancies that could be deployed into psychological therapies to improve access. Development of improvement plan and review of current pathways to assist with demand. | Revised Q2 milestone: Development of improvement plan and review current pathways and referrals to assist with demand. Revised Q3 milestone: Recruitment Deployment of longstanding vacancies into psychological therapy. Revised Q4 milestone: Recruitment. |  |
| OUTPATIENTS Lead: Ceri Gimblett |  |  |  |  |
| Sitting within Outpatients, this method also relates to, and is reported by, the Planned Care System, led by Deb Lewis. OP_03: Reduce the number of patients who are more than 100% delayed on their Follow Up appointment by 30% (March 2019 baseline,) Targeted Intervention: 15% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2023 baseline.) | > Digital validation with downtrend in number of patients more than 100% delayed | Delivery plan developed and approved at Outpatients Recovery & Redesign Group, 12 June. This includes the identification of the specialities that will be in the scope of work. In addition to the DHCW known WPAS "bug" preventing removals from list which is creating a false baseline figure. Further updates on this will be available in Q2, following their sighting and agreement through the Outpatients Redesign and Recovery Group governance process. |  |  |
| Sitting within Outpatients, this method also relates to, and is reported by, the Planned Care System, led by Deb Lewis. OP_10: Deliver Integrated E-Referral and E-Advice, | Reduction in rejected and redirected referrals. Reduction in time taken from referral to triage. Reduction in manual referrals. | Clinical Leads and membership for Task and Finish Group required in order to proceed with operational plan. To be agreed at Q2 Outpatients Redesign and Recovery Group. Dashboard recommendations submitted and agreed by Patient Access Management group; scoping needed with HCSE and Digital colleagues for decisions to be made in Q2 regarding further development. |  |  |
| Sitting within Outpatients, this method also relates to, and is reported by, the Planned Care System, led by Deb Lewis. OP_11: Deliver Remote Advice and Guidance, | Scoping requirements & planning compliance improvements for Consultant Connect. | Lack of resource to progress scoping and planning activities. Decision making ongoing regarding ownership to progress required activities to take place in Q2. |  |  |
| Sitting within Outpatients, this method also relates to, and is reported by, the Planned Care System, led by Deb Lewis. OP_13: Ensure efficient use of resources. | Forward look report of trajectories against ministerial targets developed and shared with services through bi-weekly targeted intervention meetings. | Priorities for Theatres and SOS / PIFU have resulted in this activity being re-prioritised for Q2. This remains on HCSE programme of work and will be revisited once the HCSE team have capacity, expected Q2/Q3. |  |  |
| OP_16: Deliver 'See on symptoms’ and patient initiated follow up – including digital approaches. | Digital media to be developed. | Person appointed and working notice period and started with SBUHB mid-June 2024. Milestone revised to Q2. |  |  |
| Sitting within Outpatients, this method also relates to, and is reported by, the Planned Care System, led by Deb Lewis. OP_18: Patient Reported Outcome Measures. | PROM & PREM record tied into national roll out of Promptly system. | Further work is needed to establish correct milestones for 2024/25. This will be taken forward by the VBHC Team in Q2. |  |  |
| Sitting within Outpatients, this method also relates to, and is reported by, the Planned Care System, led by Deb Lewis. OP_21: Effective Demand and Capacity Planning. | Write 3Ps training programme. Develop monitoring parameters for numbers of staff trained. | Training programme agreed in 2023/24 budget but money was not utilised by 31/03/2024. There is now, no additional funding for training as budget for 2024/25 has been re-worked. |  | It was proposed to, and agreed by, Outpatients Board, during its June meeting, that this GMO be removed given the update provided on it from VBHC colleagues. There is no funding for previously planned training so this cannot in 24/25. GMO requested for removal from Plan |
| DIGITAL Executive Lead: Matt John |  |  |  |  |
| D_17: Canisc Replacement | Palliative Care – complete testing and sign off MDT and Dataset– go live: Gynae, lung, skin, head & neck, haematology, lymphoma, thyroid Data and Reporting - Support Radiology and SACT testing | Reason for delay: Although the quarterly milestone can be described as Amber, overall, the project is Red, due to the lack of assurance the necessary products will be available by the Canisc 'switch off' date. Palliative care testing is complete; however, defects were identified in WCP and there are still outstanding fixes from previous rounds of testing. Continuing to work with DHCW to resolve the issues identified. Gynae and lung are live and the remaining areas are planned for Q2. Mitigation in place: Maintain contact with the service and ensure the risk around losing the system in October is documented and escalated. Continue to work with DHCW to progress, request plans for assurance and support the service in testing where possible. Ensure local dependencies are understood and escalate if the plan for implementation by October 2024 is unachievable. | Revised Q2 milestone: Complete MDT and Dataset. Go live in screening and colposcopy. Continue to work on integration for radiology and radiotherapy solutions. |  |
| D_18: Welsh Intensive Care Information System – Implementation. | Evaluate options for the future of WICIS, as presented at the National WICIS Programme Board | Although the quarterly milestone is Green as the milestone has been hit, options evaluated and a response provided to the National Programme, the project, as a whole, remains at risk while an evaluation, relating to implementation, is conducted by Welsh Government, which will inform the direction forward. | Work with DHCW and the local WICIS Project Board to establish next steps. Facilitate and review DHCW benefits work within the ICU to establish an updated benefits profile, locally, that will inform any decisions about next steps.WG is to facilitate the review, with DHCW having received early indications that this could take up to 6 weeks to complete. Further updates will become available as Q2 progresses. |  |
| D_22: WCCIS (Connecting Care) Linked to PCT and MHLD GMOs | Work with the MH & LD and PCT to agree Health Requirements to inform Connecting Care procurement exercise. In parallel, consider options for the use of WPAS as a stop gap for MH and Communities. | Although this is not funded, work has continued locally to inform the national set of requirements. There is still a lack of clarity and understanding nationally as to how the proposed solution will meet the requirements of the integrated teams currently using WCCIS. | Continue to work with the regional and national teams to inform the national requirements and procurement activities. DHCW to visit integrated teams in Swansea to understand their requirements. |  |
| D_31: Replacement of NPT wireless equipment which will no longer be supported by Cisco. | Secure funding to commence replace NPT wireless equipment which will no longer be supported by Cisco. | Funding was not made available, as hoped, at the end of Q4 last year. This item has been listed as a ‘Red’ in our capital priorities for 24/25, capital finance has been made aware of the requirement. The current infrastructure will be supported by Digital, however it needs to be noted that when Cisco stops support then critical security patches will not be issued or installed. | Escalation to capital finance. |  |

3.4  SYSTEM INDICATORS PERFORMANCE

Table 6 below details the key system indicators reported for Q1 which are aligned to the NHS Wales Key Performance Indicators and national targets, including those set by Targeted Intervention. Performance in Q1 is correct as at July 2024, encompassing the performance trajectories submitted by the Health Board to Welsh Government in June 2024, and are rated accordingly:

- Green, if the outcome measure has met or exceeded the original target/ trajectory,

- Amber, if the measure is moving away from the baseline position in the desired direction, has not yet reached the target / trajectory, but the trajectory indicated that it is likely to do so,

- Red, if the measure is not moving in the desired direction, or the trajectory indicates that it will not meet the target. Mitigating actions being undertaken for off track outcomes are routinely reported to P&F Committee and the Board and are therefore not duplicated in this report.

| System | System Indicator | Target | Baseline Position (March 2024) | April 24 FORECAST | April 24 ACTUAL | May 24 FORECAST | May 24 ACTUAL | April 24 FORECAST | April 24 ACTUAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| URGENT AND EMERGENCY CARE | Number of ambulance patient handovers >1 hr | National target: 30% reduction by December 2024 TI Target: A continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on quarter 2 and 3 2023 baseline) | 629 | 620 | 625 | 600 | 695 | 590 | 590 |
|  | Number of patients who spend 12 hrs or more in all major and minor emergency care facilities from arrival until admission | National target: 20% reduction by September 202, Further 20% reduction by March 2025 TI Target: Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across the health board | 1,132 | 1,110 | 994 | 1,100 | 1,115 | 1,050 | 980 |
| PLANNED CARE | Number of patients waiting more than 52 weeks for a new outpatient appointment | National target: 40% reduction by end of September 2024 Zero by March 2025 TI Target: 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Number of patients waiting more than 104 weeks for referral to treatment | National target: Zero end of December 2024 TI Target: 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months | 1,832 | 1,727 | 1,725 | 1,612 | 1,579 | 1,509 | 1,477 |
|  | Number of patients waiting over 8 weeks for a specified diagnostic | National target: 95% to be zero by December 2024 TI Targets: - 80% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months. - 80% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 months. - 80% of patients waiting for a NOUS and non-cardiac MRI to be waiting less than 8 weeks and maintained for 3 months | 3,687 | 3,746 | 3,746 | 3,343 | 3,576 | 3,267 | 3,493 |
| CANCER | Percentage of patients starting their first definitive treatment within 62 days from point of suspicion (regardless of the referral route) | National target: 60% performance by December 2024 70% performance by March 2025 TI Target: 60% performance maintained for 3 months against the SCP target | 56% | 51% | 56% | 54% | 57% | 57% | 58% |
| MENTAL HEALTH | Percentage of therapeutic interventions started within (up to and including) 28 days following an assessment by LPMHSS for people age under 18 years | National target: 80% by December 2024 TI Target: 65% of therapeutic interventions started within 28 days following an assessment by LPMHSS | 100% | 97% | 97% | 95% | 98% | 90% | 100% |
|  | Percentage of therapeutic interventions started within (up to and including) 28 days following an assessment by LPMHSS for adults age 18 years and over | National target: 80% by December 2024 | 98% | 100% | 100% | 98% | 100% | 90% | 98% |

3.5 MDS UPDATE FOR QUARTER 1

Welsh Government has requested formal submission of the MDS, updated for Quarter 1 24/25. A copy of the Q1 actual data as provided, to date, is included as Appendix 3 and will be submitted to WG following approval by both Performance and Finance Committee and Board.

3.6 WELLBEING OBJECTIVES: ALIGNMENT AND REPORTING

It is intended that updates in relation to the Health Board’s duty to deliver the Wellbeing of Future Generations Act (2015) be included in reporting from Q2 onwards. These will indicate position mapped against the strategic indicators.

4. FINANCIAL IMPLICATIONS

The Health Board submitted an Annual Plan on 28th March 2024 which reported a deficit of £50.1m. This has not been approved by Welsh Government (WG) with the request that as a minimum the Health Board reduces its deficit to £17m or better; work and discussions are ongoing. In order to meet the £50.1m deficit plan operational savings totalling £26.1m are required and all service areas are required to breakeven to their delegated budgets. This will require the need for a significant reduction to the Health Board’s run rate of expenditure.

A further review of the planned deficit in light of the actual position reported in Q1 was undertaken, and considered alongside the thematic work programme to reduce the deficit. The Board was advised in May 2024 that whilst the thematic review work had identified some technical changes that could be made and some variable benefits which could be realised, in light of the emerging in year delivery there were not sufficient granular plans to reduce the forecast deficit as actions would first be required to de-risk the run rate.

The expectation was that the in-month position would reflect a 12th of the £50.1m deficit, and so at Month 2 this would be £8.4m. At Month 2 the Health Board (HB) has reported Year To Date deficit of £18.3m against a £8.4m, and so is already £10m off target, driven by non-delivery of £26.1m savings target and operational pressures.  Clearly this position is unacceptable and immediate actions are being taken, which have been reported through the WG Monthly Monitoring Return submissions.5. WORKFORCE IMPLICATIONS

There have been some achievements in Q1 from a workforce planning and recruitment perspective for most service areas, with plans progressing as per the original timescale.

Where workforce issues have been raised as impacting on the delivery of Q1 milestones, these have predominantly been due to lack of workforce funding allocation, resulting in the need to update future milestones to reflect the delays.

6. RISKS TO ONGOING DELIVERY OF THE 2024/2025 ANNUAL PLAN

The need to address run-rate in order to de-risk the Health Board financial forecast poses a risk to the potential to realise the desired level of additionality in planned activity for 2024/2025. Following the direct issuing of an instruction, from the CEO, to senior leaders and budget holders to this end, it is likely that goals and methods relating to impacted areas of activity will require redress, in line with the Health Board position, as the year progresses. Specific areas of focus in managing run-rate have been outlined to include:

- Total variable pay

- Assurance on CHC controls and robust assessments

- Urgent delivery of further granular and deliverable savings to target levels

- Identification of the most cost-effective way to support surge capacity with a plan to reduce surge requirements to Nil as quickly as possible

- Enactment of all actions to reduce run rate, balanced with TI recovery requirements

| The Committee is asked to: - NOTE the areas of achievements in delivery of the Annual Plan in Q1. - NOTE mitigating actions against GMOs which are off-track. - APPROVE the changes to the plan where delivery is off track. - APPROVE the updated MDS for Quarter 1 for submission to WG. |  |  |
| --- | --- | --- |
| Governance and Assurance |  |  |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |
|  | Best Value Outcomes and High Quality Care |  | ☐ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |
| No direct implications of this report, however the Plan is predicated on improving quality, safety and patient experience. |  |  |
| Financial Implications |  |  |
| No direct financial implications of this report, see financial implication section for detail on the Finance Plan. |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |
| A Quality Impact Assessment and Equality Impact Assessment process will be part of the broader planning arrangements to ensure that service models detailed in the Plan are quality and equality/ diversity impact assessed. |  |  |
| Staffing Implications |  |  |
| No direct impact outlined in this report however there will be significant staffing implications as a result of new service models outlined in the Annual Plan – risks and implications to workforce form an integral part to planning arrangements. |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |
| The Annual Plan aims to deliver our Strategic Objectives which were aligned to our Wellbeing Objectives through the development of the Organisational Strategy. It is intended that updates in relation to the Health Board’s duty to deliver the Wellbeing of Future Generations Act (2015), mapped against the strategic indicators, be included in reporting from Q2 onwards. |  |  |
| Report History |  | First version of this report. Version to be received by Performance & Finance Committee |
| Appendices |  | Appendix 1: Updated GMO Master List for Q1 Appendix 2: Q1 Key Achievements Appendix 3: Updated MDS for Q1 |