## Slide 1
Marmot Nation Health / Equity Wales Initiative
(2026/27 & 2027/2028)
A Marmot Approach in NPT
Health Equity Wales Delivery Board
30th April 2026

## Slide 2: How the local place plan has been developed (story so far)
Who has been involved….
NPTCBC Senior Leadership Team (Chief Executive, Strategic Directors)
Cabinet
Strategic Manager – Policy, Governance & Performance
Public Services Board Co-Ordinator
Head of Data – Digital Services
Public Services Board Steering Group:
  Swansea Bay University Health Board (Strategy & Public Health
  Natural Resources Wales
  Mid & West Wales Fire & rescue Service
  South Wales Police
  NPT Community for Voluntary Service
  Codi Housing
Institute of Health Equity (Deputy Director / Senior Consultant – Marmot Places / Researcher

## Slide 3: How the local place plan has been developed (story so far)
The process….
(EOI) developed in partnership with Public Health (Swansea Bay University Health Board) on behalf of the NPT Public Services Board(PSB) and discussed and agreed at the PSB Steering Group meeting (15th January 2026).
Workshop 1 (1st April) – To establish a shared understanding of current priorities for the PSB (NPTCBC, Public Health, IHE)
Workshop 2 (20th April) – To consider more specific aims based on data provided by the IHE, input from partners and the ambitions of the PSB (NPTCBC, Public Health, IHE, Natural Resources Wales, NPT Community for Voluntary Service)

## Slide 4: What we have found… key themes and priority areas
Strong partnership working and a willingness to collaborate and make a change embedding health equity in all aspects of work:
  Shared ambitions and understanding a need to focus our efforts in areas where we can make a difference utilising a positive narrative
  Strong foundations to build on what the PSB has achieved to date for the next 5,10,15 years
  Recognition of partners ability to influence policy and change across the social determinants of health

## Slide 5: What we have found… key themes and priority areas
An ambition to optimise the opportunities the inward investment in NPT will bring to benefit everyone (a “just” transition) with a particular focus on future generations. By ……..
  Understanding the health and wellbeing impacts of the Tata Transition on people, communities and place (HIA in progress)
  Creation of new jobs to benefit local people and action to remove barriers to employment (including qualifications, skills, health), employment aspirations
  Having a Future Generations focus – impact on children and young people – opportunities - reducing child poverty (Principles 2 & 3) / access to employment (Principle 3) / environmental sustainability (Principle 8)

## Slide 6: What we have found… key themes and priority areas
Partnership approach…
  To deliver tangible action by coalescing around the following Marmot principles
    2. and 3: Enable all children, young people, and adults to maximise their capabilities and have control over their lives and ensure a healthy standard of living for all (reduce child poverty)
    3. Create fair employment and good work for all
    8. Pursue environmental sustainability and health equity together
  Learn from others…
    Make best use of available data to prioritise & equitably allocate resources
    To inform approach to reducing child poverty
    From other areas with a similar diverse geography

## Slide 7: What we have found… key themes and priority areas
IHE…
  To provide support to make progress in optimising the opportunities inward investment will bring to drive health equity
  Help understand the “so what ?” from local assessments through a health equity lens – an opportunity to build on the Wellbeing Assessment and the Population Needs Assessment with more granular data to better inform action
  Engage with children and young people to understand what we are doing well and what to do next (as part of Wellbeing Assessment)
  Build on good PSB participation to improve health equity by better understanding what it is doing well and what it can improve – initial focus here on reducing child poverty
  Raise the profile of the role of climate change in health equity

## Slide 8: What we have found… key themes and priority areas
Need to evaluate and communicate progress:
  Development of local evaluation and monitoring tool to evidence progress
  Develop mechanism for capturing learning
  Communicate progress and learning

## Slide 9: What we have found…
Identified specific opportunities that will support / contribute to embedding health equity:
  NPT PSB Well-being Assessment 2027
  NPT PSB Well-being Plan 2028-2033
  NPT Corporate Strategy 2028 – 2033
  NPT Children & Young People’s Plan
  NPT Economic & Regeneration Strategy
  Cost of Living & Poverty Prevention Partnership
  Climate Change Risk Assessment and Adaptation Strategy
  Employment & Skills Strategy
  State of the Population Health Report
  Health Impact Assessment (TATA Transition)

## Slide 10: What / How / Who – first 6 months
What / How | Who
Further develop local ownership / understanding of the initiative | NPT Council
Enable programme delivery (capacity) – confirm Programme Structure – Programme Lead, Working Group (to work with IHE) and Steering Group | NPT Council / PSB
Develop and clarify the PSB’s advisory board role | NPT Council / PSB / IHE
Develop shared goal and narrative which everyone can coalesce | NPT Council / PSB / IHE
Develop communication plan, including mechanism/s to share existing work and report on progress | NPT Council / PSB / IHE
Design and deliver PSB Workshop (July) – to further develop understanding of the programme, the inward investment opportunities, identify key stakeholders and next steps to inform Delivery Plan | NPT Council / PSB / IHE

## Slide 11: What / How / Who – first 6 months
What / How | Who
Determine wider stakeholder involvement (coalition of willing) to participate in work to appraise and prioritise proposals for tangible action | NPT Council / PSB / IHE
Develop proposals on how to initiate / launch programme | NPT Council / PSB / IHE / Stakeholders

## Slide 12: What / How / Who – first 6 months
What / How | Who
Determine wider stakeholder involvement (coalition of willing) to participate in work to appraise and prioritise proposals for tangible action | NPT Council / PSB / IHE
Develop proposals on how to initiate / launch programme | NPT Council / PSB / IHE / Stakeholders
What / How | Who
Provide full data pack & capacity to help understand the “so what” for NPT’s programme and health equity in the longer term Develop data-based local intelligence building on / into the Wellbeing Assessment and Population Needs Assessment & MSOA work To gather insight, advocate for health equity and programme participation | IHE
Map existing work on child poverty, including contribution of NPT Community Voluntary Service in readiness for deep dive | IHE
Work with PSB Subgroups, appraise existing strategies and upcoming decisions for impact and opportunities to improve health equity | IHE
Speak to relevant stakeholders to gather insight, advocate for health equity and programme participation | IHE

## Slide 13: What else would help us…asks of HEW national partners
Wales Council for Voluntary Action (WCVA) and environment and nature to be represented on Delivery Board
Example outputs from other Marmot places – learning from others
Longer term funding to enable strategic planning and sustainability of projects