| Meeting Date | 07 December 2023 |  | Agenda Item |  |  | 2.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Management Report – Population Health & Partnership |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to inform the Population Health & Partnerships Committee (PHPC) of the risks within the Health Board Risk Register (HBRR) relevant to its scope. |  |  |  |  |  |
| Key Issues | - This is the first risk report for the PHPC. - It presents for consideration two risks assigned to other committees for oversight, whose content is relevant also to the scope of this Committee. - Additional discussion is scheduled with Directors to consider any potential further areas for risks for inclusion. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the current Health Board Risk Register (HBRR) risks relevant the scope of this this Committee’s role. - DISCUSS any additional areas for inclusion and assurance requirements to support the Committee’s role. |  |  |  |  |  |

RISK MANAGEMENT REPORT

- INTRODUCTION

The purpose of this report is to inform the Population Health & Partnerships Committee of the risks from the Health Board Risk Register (HBRR) relevant to the scope of its responsibilities.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular HBRR update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

Risk Register management is supported by a Risk Management Group (RMG) which meets quarterly and is responsible for overseeing the operational management of risk, ensuring local systems and processes are in place and are operating effectively to ensure appropriate reporting and escalation. The Group last met in July 2023.

Additionally, a Risk Scrutiny Panel is responsible for ensuring there is an appropriate and robust risk management system in place and working throughout the organisation. It is responsible for moderating new risks and risks escalated to the Health Board Risk Register (HBRR) and Board Assurance Framework (BAF) and recommending and advising the Management Board on the escalation and de-escalation of risks. The Panel last met in October 2023.

2.2 Risk Appetite

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating  lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

- GOVERNANCE AND RISK

3.1 Action to Update the HBRR

Health Board risk register entries are circulated to lead Executive Directors monthly for review and updated where required. A consolidated, updated register is circulated to the Executive Team for agreement and final version issued. The report is based on risks as recorded in the October 2023 HBRR.

3.2 HBRR Population Health & Partnership Risks

The terms of reference of this Committee indicate the scope of its assurance activity to encompass the following in respect of the achievement of the Boards’ strategic aims, objectives and priorities:

- Approach, systems and processes for developing and implementing strategies and plans in partnership or collaboration with other bodies, within and outside the NHS;

- Financial decision making in partnership arrangements, both capital and revenue and including any pooled budgets;

- Partnership governance and partnership working ;

- Arrangements in place to improve population health and wellbeing.

All risks within the HBRR are assigned to other Committees of the Board for oversight. However, there are two which are also relevant to the Population Health & Partnerships Committee’s (PHPC) scope which have been included in the attached HBRR extract for consideration by this Committee:

Table 1: HBRR risks associated with PHPC scope

| HBRR Ref | Description of risk identified (Summary) | Current Score | Exec Lead & Board Committee | Notes |
| --- | --- | --- | --- | --- |
| 52 | Engagement & Impact Assessment Requirements (statutory compliance) The Health Board does not have sufficient skills & resource in place to undertake impact assessments in line with strategic service change and policy development. | 12 | Director of Insight, Communication & Engagement Performance & Finance Committee | This risk relates to a statutory requirement and is connected to the need to engagement with partners in the development and agreement of service change. This risk is assessed to be at a level within the Board’s risk appetite. Current Controls: - A Strategic Equality Group is in place to support processes. - The appointment creation of a Director of Insight, Communication & Engagement role has provided some additional capacity but alongside this there has been a significant increase in activity/demand. Further Actions: - Aim is to appoint a Head of EDI post to support equality impact assessment. Action targets have been refreshed in line with timescales for budget agreement and appointment to a Head of EDI post. |
| 96 New Risk | Failure to Develop an Approvable IMTP (statutory compliance) If we fail to have an approvable (Integrated Medium Term Plan) IMTP for 2024/5 then we will lose public confidence and breach legislation. | 20 | Director of Strategy Performance & Finance Committee | The NHS Wales Planning Framework (2022-25) expects IMTPs to be developed in conjunction with partner organisations. While there are other factors that present risk to achieving a balanced plan, this risk is included here in recognition of the above expectation within the Framework. This risk is assessed to meet the Board’s risk appetite threshold. Current Controls: - There is an integrated process in place to develop annual plan 2024/25. - IMTP Executive Steering Group in place to oversee Recovery & Sustainability plan. - Performance & Finance Committee and Workforce & Digital Committee oversee performance, finance and workforce plans. - JET meetings held with Welsh government. Further work to be undertaken to establish a timeline for financial recovery. |

Meetings have been arranged between the Risk & Assurance team and Director of Public Health and Assistant Director of Strategy to consider any additional risks impacting upon the Committee scope of work that may not be captured currently.

This report and appendix present information on risks relevant to the Committee scope. Within the report, particular attention is drawn to those risks exceeding the Board’s appetite, together with updates on action being taken to treat them by lead Directors and management.

- FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information.

- RECOMMENDATION

Members are asked to:

- NOTE the current Health Board Risk Register (HBRR) risks relevant the scope of this this Committee’s role.

- DISCUSS any additional areas for inclusion and assurance requirements to support the Committee’s role.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - This is the first report for the PHP Committee |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) Risks relevant to PHP Committee scope |  |