| Meeting Date | 03 December 2024 |  | Agenda Item |  |  | 2.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Report – Population Health & Partnership Risks |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Interim Director of Corporate Governance |  |  |  |  |  |
| Presented by | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to highlight the risks from the Health Board Risk Register (HBRR) assigned to the Population Health & Partnership Committee (PHPC) for scrutiny. |  |  |  |  |  |
| Key Issues | - The Committee last received a Risk Report in September 2024. - There are no movements in the overall profile of risks allocated to the Committee. Two risks are allocated to the Committee for oversight, one of which is currently at the Board’s risk appetite threshold. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - REVIEW the update in relation to external reviews and the health board responses to issues raised. - CONSIDER & COMMENT where appropriate on any areas requiring further assurance. |  |  |  |  |  |

RISK MANAGEMENT REPORT

Population Health & Partnership Risks

- INTRODUCTION

The purpose of this report is to highlight the risks from the Health Board Risk Register (HBRR) assigned to the Population Health & Partnership Committee for scrutiny.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular HBRR update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

Risk Register management is supported by a Risk Management Group (RMG) which meets quarterly and is responsible for overseeing the operational management of risk, ensuring local systems and processes are in place and are operating effectively to ensure appropriate reporting and escalation. The Group last met in October 2024 (special meeting to discuss review of risk management & reporting approach).

Additionally, a Risk Scrutiny Panel is responsible for ensuring there is an appropriate and robust risk management system in place and working throughout the organisation. It is responsible for moderating new risks and risks escalated to the Health Board Risk Register (HBRR) and Board Assurance Framework (BAF) and recommending and advising the Management Board on the escalation and de-escalation of risks. The Panel last met in October 2024.

2.2 Risk Appetite

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating  lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

3.	GOVERNANCE & RISK

3.1 Action to Update the HBRR

Health Board risk register entries are circulated to lead Executive Directors monthly for review and updated where required. A consolidated, updated register is circulated to Executive Team for agreement and final version issued. This report presents the risks allocated to this Committee recorded in October 2024 by their lead Executive Directors – the relevant risk extracts are attached at Appendix 1. Key changes made in the most recent update are highlighted in red font.

3.2 HBRR Population Health & Partnership Risks

There are two risks are assigned to the Quality & Safety Committee for oversight. The profile of risk scores is presented below:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 |
| --- | --- | --- | --- | --- | --- |
| Number of Risks | 1 | - | - | 1 | - |

Key risk profile movements since last report:

| New risks | Nil |
| --- | --- |
| Risks with increased scores | Nil |
| Risks with reduced scores | Nil |
| Closed risks | Nil |

In respect of current risks, the Population Health risk is assessed as exceeding the Health Board’s risk appetite threshold at which action is required to reduce risks to acceptable levels. Table 1 below highlights key aspects of this risk and actions taken in response:

Table 1 – HBRR High Risks Assigned to this Committee

| Risk Reference | Risk Description | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| 99 | Failure to implement the population health strategy approaches at the required scale. This arises from risk of a failure of the organisation to understand and act on the provisions of the strategy for building whole of system actions across the 4 pillars; and the consequent lack of systems and processes to support the delivery of population health improvements. Currently identified contributors to this risk include the absence of the tactical level planning required to design and deliver cross-cutting programmes within a federated operational delivery system; lack of systematic review and capture of population health contributions of existing services; limited behaviour change to adopt a population health focus at service and corporate level; uncertainty about the financial commitment to support Population Health Strategy Implementation as well as a lack of clear processes for accessing available funding; a limited focus on prevention; and a lack of consideration of how to act to influence the wider determinants that affect the population’s health and how the Health Board might contribute to addressing these. The outcome if the risk is not addressed is worsening health in our population with widening health inequities. | 20 | Lead: Interim Director of Public Health The risk score remains unchanged currently. Currently there is a lack of capacity and capability in the wider organisation to create the conditions to enable delivery of this transformation agenda. This is in part being driven by the financial climate and political focus on key targeted intervention areas. Controls remain in place as previously reported, supplemented by the involvement of the Public Health team in supporting development of 2025/26 with corporate partners. Actions remain: - Gateway review of progress on governance actions: - Service Group reporting changes (target 31/12/2024); - Capability and capacity review and development work (target 31/03/2025); - Population Health Strategy implementation audit to be undertaken (target 31/01/2025). - Systems working capability development programme is in development – for both Health Board colleagues and external partners (target 31/03/2025); - Development of joint work programme for improved health intelligence as part of and supporting the implementation of the Digital Strategy (target 31/12/2024). |

The level of risk associated with the Health Board’s approach to Partnership Working is not assessed to reach the Boards’ risk appetite currently. However, in line with the Board’s aspiration that thresholds could be reduced in the future, this risk is presented for information:

Table 2: HBRR risks assigned to the Committee that do not currently meet the risk appetite threshold.

| Risk Reference | Risk Description | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| 100 | A lack of a robust approach to partnerships & collaboration If the health board does not have effective structures, processes and working relationships with its external partners at the Public Services Board (PSB) and/or Regional Partnerships Board (RPB), there is a risk that areas of work dependent upon collaboration with partners may not deliver what is required in a timely way, impacting on the delivery of health board priorities. | 12 | Lead: Director of Strategy The risk score remains unchanged currently. Actions remain as follows: - Development of a robust Strategic Partnerships Group and the Collaborative Framework (Target 31/12/2024) - Alignment of Partnership priorities with the Health Board IMTP (Target 31/03/2025) - Consideration of the OD working progressed with the WGRPB Directors (Target 31/12/2024). - Consideration of Health Board position in relation to identified challenges areas including children & young people (Target 31/12/2024). |

4. FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information.

5. RECOMMENDATIONS

Members are asked to:

- REVIEW the update in relation to external reviews and the health board responses to issues raised.

- CONSIDER & COMMENT where appropriate on any areas requiring further assurance.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - This report provides an update on risks allocated to the PHPC which were last reported to the Board in Sept 2024. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) Risks Assigned to the PHPC Committee |  |