| Meeting Date | 14 March 2024 |  | Agenda Item |  |  | 4.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Internal capability & capacity development to progress delivery of our population health strategy commitments |  |  |  |  |  |
| Report Author | Jennifer Davies, Deputy Director of Public Health |  |  |  |  |  |
| Report Sponsor | Keith Reid, Executive Director of Public Health |  |  |  |  |  |
| Presented by | Keith Reid, Executive Director of Public Health |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This report updates the Committee on: - The work agreed through the Management Board and Population Health and Partnerships Sub-Committee to develop our capability and capacity to deliver our Population Health Strategy (PHS) commitments. |  |  |  |  |  |
| Key Issues | - On approval of the Population Health Strategy (PHS) by Board, there was a recognition that there are some risks identified around progressing implementation. These risks fall broadly into two areas. - Inconsistent organisation-wide understanding of the strategic, tactical and operational perspectives of strategy implementation at scale; and - Linked to the above, a lack of current capability within SBUHB to design and deliver a coherent coordinated whole of organisation response within and across our current federated structures (corporate and service delivery groups). - Considerable effort has been put in place this year to address this through:- - awareness raising activities across the organisation; - working with Strategy & Planning on the development of the R&S plan to include embedding population health considerations; - development of a new performance reporting framework for Service Delivery Groups to draw out and focus on their contributions to population health gains; - development of an organisational Strategic Objective that aims to recognise and embed the PHS alongside the Organisational 10-year vision, hence attempting to knit together the different strategic narratives; - development of an approach to identify strategic indicators to help direct and capture progress towards population health outcomes; - developing considered and purposeful intent and ways of working in our external partnerships. - capturing PHS related risks under the Health Board risk assurance framework. - Despite the progress made, capability and capacity to deliver population health remain limited and the implementation of PHS being owned by the whole of organisation / whole of system is still not well understood or appreciated. This is shown in poor overall engagement and how the strategy is talked about, which indicate that this is still seen as a ‘public health team’ agenda as opposed to a whole of organisation strategic intent with reputational and population health risks to non-delivery. - Embedding and adopting a population health approach requires different behaviours across all parts of the system. There remains a need to shift our ways of thinking and working – embedding population health principles, priorities and considerations into our business as usual processes and mindset. Instead, there remains a focus on ‘service based’ activity aimed at ‘lifestyle factors’ e.g. weight management, smoking cessation services. These have only marginal impact on population health but the paradigm is familiar (doing things to individual people) and therefore not challenging to current thinking and ways of working. - During 2023-24 the Executive Director of Public Health was asked to provide a plan to allocate the £1m population health reserves (<0.08% of the organisational budget) in support of the population health strategy implementation. Despite an outline for the use of this money being shared with the Performance and Finance Committee, this funding was never delegated to the Exec DPH and the process for agreeing/approving spend against it remained unclear. - As the developmental work programme needed to address the challenges of implementation emerged, proposals against the £1m population health reserves, were brought through the Management Board governance structure, alongside this Committee. To date, the requests have been for: - Capability and capacity to develop and utilise population health intelligence methods, tools and infrastructure. A necessary first step in being able to make intelligence informed decisions that increase allocative and technical efficiency in our financial allocations in support of population health outcomes. Given the financial constraints & disinvestment context, the ability to re-think our current resource allocation based on intelligence & insight has never been greater. The initial investment request that was approved was £90K/annum, acknowledging that this is a transformational agenda and hence allocation will be incremental. This was approved at Management Board 12th July 2023. - Development programme that supports the need for whole of organisation culture, behavioural and operational change, in order to realise SBUHB’s ambition to be population health competent. This proposal, utilising behavioural science, would allow us to develop a deep understanding of present attitudes and behaviours but also a process to understand how we could change them. The initial investment required was £60K this financial year, rising to an estimated £125K/annum for 2024-25 onwards. This would need to be reviewed in line with the adaptive, developmental nature of the programme of work and any further investment that may be needed arising from this work will need to be quantified. This was approved at both Management Board (8th November 2023) and this Committee (7th December 2023). - Correspondence from the WFGA Commissioner has urged public bodies to maintain a long-term view and ensure that the spending of public funds is aligned with the well-being goals, the five ways of working and corporate areas of change. - Work undertaken to scope the marketplace; agree specifications; identify preferred routes to securing skills, experience and capabilities means we are now in a position to proceed. However, at the time of writing, it is unclear, due to the financial pressures the Health Board is facing, whether the funding from the population health reserves, approved by Management Board, is still available to support this work. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to: - Note the update to progressing work approved by the Committee and Management Board to address the challenges to implementation of the PHS highlighted / identified - Note the current position in relation to the different work streams. |  |  |  |  |  |

Internal capability and capacity to progress our population health aspirations

- INTRODUCTION

The Population Health Strategy (PHS) was approved by the Board in March 2023 recognising that the necessary response is one of whole organisational and system collaboration to achieve our aspiration of becoming a population health competent organisation.

There has been progress made during 2023-24 to address some of the key challenges we face in implementing the Population Health Strategy. However, challenges remain and proposals emerged in line with the developmental nature of the organisational journey. These included two proposals for developing the Health Board’s capability and capacity to deliver our strategic intent at scale through consideration of the way the totality of the organisation’s resources in terms of capital, staffing, intellectual capital and revenue are allocated to maximise population health gain.

This report provides an update on these proposals and progress made in taking them forward. This is a long-term developmental programme and does not lend itself to the current annual cycles of financial decision making, necessitated by the current economic context. Hence, the progress against these commitments are at risk of stalling if the funding approved by Management Board is no longer available.

- BACKGROUND

The case has been accepted that inequalities in health arise because of inequalities in society and the conditions in which people are born, grow, live, work and age – leading to differential levels of vulnerabilities. These inequalities may be amplified by how healthcare is organised and delivered.

Our PHS describes the evidence informed actions (collated in the Marmot & WHO reports) needed to tackle health inequities.  The 4-pillar model (see figure 1 below) has been developed to enable the translation of the evidence base into our corporate functions.

Implementation of the PHS requires an ability to develop our understanding of population health and to act on this as a whole organisation and as part of a wider system. For successful delivery of population health gain these new ways of working require behaviour change at scale across all parts of our organisation.

Delivering on the Population Health Strategy requires a set of collective actions, dependent on different ways of working and bold, disruptive commitments at organisational and policy level. This goes beyond single services or initiatives. As such, it requires population health and equity considerations across all pillars of the strategy and aspects of our business. To achieve this, there is a need to re-orientate all our resources – both revenue & capital – to consider how the totality of our budget as a £1.4bn organisation should/could be used to maximise the benefit through a population health and equity lens.

Capability in relation to population health (knowledge and technical skills) is currently limited and spread unevenly through the system. A programme of work was developed to start the journey of building capability and capacity, from our existing starting point, to achieve sustainable delivery of population health approaches, within our current operational machinery.

During 2022-23, a commitment was made by the Health Board to a recurrent allocation of funding of £1m (0.08% of the £1.4bn organisational budget), to catalyse the implementation of population health approaches, capability and understanding. The Executive Director of Public Health was asked to provide proposals against this allocation in support of the implementation of the PHS. This was recognised as a transformational/developmental journey the work programme and emergent proposals were brought forward through Management Board and the Population Health & Partnerships Committee for discussion & approval.

- CHALLENGES & OPPORTUNITIES

At its simplest level there are three challenges:

| Challenge | Proposed approach |
| --- | --- |
| - Finance as key enabler towards population heath competence |  |
| Budgets, or allocation of resources, are currently an indicative representation of the spend at a point in time, i.e. 2019/20 uplifted for inflation and growth but do not link directly to: what the Health Board wants to internally commission from its provider arm, changes in demand, delivery of LTA contracted value, quality, outcomes or value to our patients. | To overhaul the current budget setting arrangements to move to a position where the allocation of internal resources supports the challenges being faced in the NHS, whilst recognising value and outcomes for our population. To achieve this radical change in approach, requires the development of the necessary technical expertise through the establishment of a team of dedicated experts, with a range of different skills & expertise who understand the Health Board, the financial / information systems and population health intelligence systems, critical to progressing the work. |
| - Maximising opportunities to work, behave and think differently |  |
| Current spending against budgets pays no regard to and is not actively used to address population health needs. It is the hostage of demand and history. Added to that the significant levels of inequities in our population and that the way we provide healthcare can (intentionally or unintentionally) lead to a widening of these inequities. With increasing pressures on finances the need to consider how we spend each £1 in terms of our population health needs as outlined in our PHS becomes even more apparent. This involves looking not only at health care provision but purposeful action across all 4-pillars of health board activity. | This complex and challenging programme of work will require an adaptive and responsive approach with good collaboration across different aspects of the business and partners (internally & externally). This will require changes in ways of working and development of relationships that support the whole organisation cultural, behavioural and operational change. |
| - Developing the tactical competence to enable transformation |  |
| How the system responds to strategic imperatives by considering and then creating a tactical response is a critical part of the transformation approach. This tactical response requires the organisation to develop the concepts and products and environment, systems, processes, tools, to translate strategic aims (which are often aspirational) into tangible work packages that allow expert operational input and implementation and the development of value for patients. The contribution at the tactical perspective is key to enabling transformation to occur at the operational level through adoption of different behaviours and working practices. | Senior level capability and expertise to lead the programme development, creating an expert informed common understanding or agreement of what is needed. Current expertise across the organisation is limited and inadequate to meet our aspirations in terms of both population health intelligence and ways of working, thinking and planning/designing services. A programme is needed that will secure senior leadership buy in and build an integrated, adaptive programme that seeks to understand and adapt to our issues and external environment and landscape. It will utilise established behavioural science techniques that work; developing our wider capability and capacity; and demonstrate impact & value. |

In response to these challenges, the following work programmes were proposed, funded through the £1m population health reserves:

| Proposal | Investment sought | Approval process |
| --- | --- | --- |
| - Capability and capacity to develop and utilise population health intelligence methods, tools and infrastructure. Agreed as a necessary first step in being able to make intelligence informed decisions that increase allocative and technical efficiency in our financial allocations in support of population health outcomes. | Initial investment request of £90K/annum. Acknowledgement that this is a transformational agenda and hence allocation will be incremental. | Management Board 12th July 2023. |
| - Developmental programme that supports the need for whole of organisation culture, behavioural and operational change, to realise SBUHB’s ambition to be population health competent. This proposal, utilising behavioural science, would allow us to develop a deep understanding of present attitudes and behaviours but also a process to understand how we could change them. | Initial investment request of £60K for 2023-24, rising to an estimated £125K/annum for 2024-25 onwards. This would need to be reviewed in line with the adaptive, developmental nature of the programme of work. Any further investment that may be needed arising from this work will need to be quantified. | Management Board (8th November 2023) Population Health & Partnerships Committee (7th December 2023). |
| - Development of a baseline position as an anchor institution which would be the start point in a journey towards becoming a purposeful and impactful anchor system. Need to seek external support to progress this work. | Estimated financial requirement to progress this work of £160K for 2024-25 | Agreement to explore external support at Population Health & Partnerships Committee (7th December, 2023)* |

* No agreement to date on funding for the proposal. It is due to be considered at the Population Health & Partnerships Committee on 14th March 2024.

- PROGRESS TO DATE

| Proposal | Update/progress | Next steps |
| --- | --- | --- |
| - Capability and capacity to develop and utilise population health intelligence methods, tools and infrastructure. | - Discussions with procurement leads on engaging with the market for external support to progress work - Exploratory/scoping conversations with potential sources of expertise/support - Development of initial set of strategic population health indicators in support of organisational strategic objectives - Development of job description/profile for fixed term (12-18 month) role as organisational health intelligence lead to develop and drive forward this work - Job Description ready to be taken through Job Evaluation panel (estimated 6 weeks) | Confirmation awaited that funding from the population health reserves, previously approved by Management Board, is still available into 2024-25, to support this work. |
| - Developmental programme that supports the need for whole of organisation culture, behavioural and operational change. | - Exploratory / scoping conversations with potential external sources of expertise/support. - Dialogue with procurement leads on routes to commission/contract with identified partner. - Clarity sought on appropriate route - Procurement brief issued & proposal submitted - Ready to award contract for up to 6 month activity – total cost £30K. | Require confirmation of funding accessible from population health reserves into 2024-25 for £20K as work will not complete 2023-24. |
| - Development of a baseline position as an anchor institution | - Scoping of potential sources of external support - Confirmation / approval of approach and estimated costs | To be discussed at Committee 14.03.24 |

- GOVERNANCE AND RISK ISSUES

A proposed governance structure has been established to take forward and provide assurance for the delivery against the Population Health Strategy aims and aspirations. Initiatives, approaches and actions in service of the PHS naturally sit across all service groups and in partnership spaces. As has previously been commented, the structures are designed for a mature system.  They are not appropriate to guide a developmental / transformational phase of establishing and embedding the PHS.  Identifying and creating appropriate supporting structures to facilitate the required cultural and behavioural change forms a necessary part of the underpinning work to implementation of the strategy.

A proposal based on the current structures, is that the development work would report into the Population Health Development Board (PHDB) during its design phase/stage. The PHDB was established in October 2022 and upon review was stood down in November 2023 due to lack of senior attendees inhibiting effective decision making with regards to population health. A change in the role and membership of the PHDB making it a key tactical forum for cross functional development of initiatives, is required:  mandating attendance by senior management from all Service Delivery Groups and linking with Corporate functions.  As the work becomes systematised and operationalised, the intention would be to embed the reporting on progress and performance through the appropriate existing performance & governance structures, where these exist.

- FINANCIAL IMPLICATIONS

The initial financial commitment to progress this work is outlined above and is in addition to the investment of staff time (which is uncosted here). The intention is to draw on the population health reserved funds to meet these initial costs of the development of the work leading to the creation of a programme to support behaviour change and skills development. The extent of this programme emerging from the insights work is not possible to predict or quantify currently. The insights & proposal arising from this work will be aimed at enhancing our ability to consider & re-orientate SBUHB’s activity better to achieve population health gains.

The funding secured for these work areas represent an important and necessary step in helping us reshape / rethink how we consider how our total resource allocation as an organisation, is maximised in pursuit of population health & wellbeing outcomes.

The WFGA Commissioner has recently written to all Chief Executives of public bodies urging a focus on direction set by the WFGA, a focus on prevention, long-term thinking and effective corporate functioning in line with the statutory guidance.

As with all other Health Boards, we are facing a challenging economic position. As such, at the time of writing, we are awaiting formal confirmation of whether the funding approved can be made available into 2024-25 to support these pieces of work and as such, it is not possible to progress this work further.

- RECOMMENDATION

Members are asked to:

- Note the update to progressing work approved by the Committee and Management Board to address the challenges to implementation of the PHS highlighted / identified.

- Note the current position in relation to the different work streams.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| The paper outlines what is needed to progress the population health strategy implementation and adoption. Implementation of an effective population health approach will lead to a more consistent approach to prevention. |  |  |  |
| Financial Implications |  |  |  |
| The paper notes the investment required in order to progress these workstreams. The intention is to draw on the population health reserves to support this work. These costs are initially for developmental work. Any further investment that may be needed arising from this work is not yet quantified. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| No legal implications identified. The incorporation of population health approaches will allow for the identification of equality and diversity issues and development of appropriate responses. |  |  |  |
| Staffing Implications |  |  |  |
| The proposed programmes will offer an opportunity to significantly increase the organisation’s capacity and capability to adopt different / new ways of working and thinking in order to implement the PHS aspirations. The Public Health Team remains small. Additional roles are being created and recruitments underway but progress remains slow. This is likely to impact on the speed & scale of delivery of the org programme. It may also require a different skills mix. Development of the implementation plan will identify the skills and workforce requirements. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Population health approaches incorporate a prevention ethos and delivery is contingent on collaboration among partners to deliver better outcomes for our population. A coproduction approach is integral to public health practice and seeks to involve communities and staff in designing services and programmes. |  |  |  |
| Report History |  | No previous reports |  |
| Appendices |  |  |  |