## PCT IPC Improvement Plan 23-24
Outcome | Metric Name /Narrative | Baseline for 22/23 | Welsh Government Infection Reduction Expectation | PCTG Infection Reduction Target for 2023/2024 | PCT Service Level Cumulative Cases Target for 2023/2024 | Global Actions to Achieve Targets (Q1-Q4) | Directed Actions to Achieve Targets | Directed Action Target Date | PCT Tier 1 Service Level Case Trajectories (Accumulative) |  |  |  | Metric Type (Qualitative / Quantitative?) | SRO/Key Contact
[9 empty] | Q1 | Q2 | Q3 | Q4
Population Health Target | N/A | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | 390000 | N/A | N/A
Reduce incidences of the following Tier 1 target for Community associated/ acquired infection; Clostridioides difficile | Infection Prevention & Control - Tier 1 Target | Total Cumulative cases (Apr 22 – Mar 23) = 64 | < by 54% CAI cases for 2023/2024 = Overall reduction of 34 cases | < by 15% CAI cases for 2023/2024 | < 55 CAI cases | Bi-monthly PCTG Meeting Of Healthcare Acquired Infections & Antimicrobial Stewardship (HCAI/AMS) to provide scrutiny and momentum around the IPC agenda and to support a platform for innovation and change. Clinical Lead Role. 0.2wte Clinical Lead for HCAIs to provide strong clinical leadership, drive innovation & identify and disseminate best practice. IPC Clinical Nurse Specialist Role. Appointment of a 1.0 wte IPC Senior Clinical Nurse Specialist for HCAIs to provide education & disseminate/embed best practice across the care home sector (jointly funded with LA). Create Webinars/ Key Presentations/Newsletters with aim to build suite of educational resources for primary care & care homes (UTI & C.Diff completed). Antimicrobial Stewardship - expand here with Bethan Increase IPC Staff Training compliance for: IPC Level 2 (all clinical staff) ANTT (all staff using ANTT procedures) Hand Hygiene (all staff) Organise Focus Group to identify what IPC resources practices / community clinic would like to support best practice. Increase Profile of IPC & PCTG IPC Targets at planned staff engagement/training events such as Team Brief, PLTS, Professional Forums etc Collaboration and Co-production with SBUHB Delivery Groups to ensure oversight of Improvement Plans , maximising all opportunities to streamline processes and care pathways. | 1. C.difficile Scrutiny Panel to identify key themes, lessons learned and provide feedback to practices and care homes. Establish, avoidable or non-avoidable status to shape actions and highlight responsibility. Outcomes of each case discussion fed back to patients registered GP with action points and more general feedback on the case. Themes from the case discussions are fed into the regular emails / newsletters to practices 2. C.difficile SEA reporting. Bespoke MS Forms questionnaire being utilised for digital SEA reporting process for General Practice and Care Homes to trace, chase, audit and analyse data associated with each toxin positive community case. 3. C.difficile prescribing guidance by antimicrobial team to support General Practice in implementing the prescribing updates associated with the c.difficile prescribing guidance. Microguide app is promoted across SBUHB General Practice and Health Board services to ensure correct prescribing practice 4. PPI Prescribing - Encouraging practice passed prescribing reviews for patients on long term PPIs | 1. Target Complete - Ongoing Q1 through to Q4 2. Target Complete - Ongoing Q1 through to Q4 3. Target Complete - Ongoing Q1 through to Q4 4. Target Ongoing Q1 through to Q4 | < 12 CAI cases | < 26 CAI cases | < 40 CAI cases | < 55 CAI cases | Qualitative | TBC
Reduce incidences of the following Tier 1 target for Community associated/ acquired infection; Staph Aureus bacteraemia | Infection Prevention & Control - Tier 1 Target | Total Cumulative cases (Apr 22 – Mar 23) = 65 | < by 63% CAI cases for 2023/2024 = Overall reduction of 41 cases | < by 20% CAI cases for 2023/2024 | < 52 CAI cases |  | 1. Undertake Clinical Audit - Snapshot of 3-5 cases to identify RCA, Avoidable/Unavoidable status, lessons learnt, shape actions and highlight responsibility. 2. Wound Swabbing - Collaboration between Public Health Microbiology & Community Wound Care Clinic to disseminate best practice regarding correct procedures in Wound Swabbing, use of Healthy IO APP to promote antimicrobial stewardship. 3. Wound Cleansing Audit - In collaboration with Public Health & Community Wound Care Clinic, undertake Wound Cleansing Audit to identify best practice. Findings to be disseminated widely. | 1. Q4 (recruitment of Deputy Head of Nursing for Primary Care key dependency) 2. Target - Ongoing Q1 through to Q4 3. Q3 | < 17 CAI cases | < 28 CAI cases | < 40 CAI cases | < 52 CAI cases | Qualitative | TBC
Reduce incidences of the following Tier 1 target for Community associated/ acquired infection; E.coli bacteraemia | Infection Prevention & Control - Tier 1 Target | Total Cumulative cases (Apr 22 – Mar 23) =136 | < by 10% CAI cases for 2023/2024 = Overall reduction of 13 cases | < by 10% CAI cases for 2023/2024 | < 123 CAI cases |  | 1. UTI task and finish group focussing on hydration, sampling, prescribing and general training and education across General Practice, Care Homes and wider Health Board services 2. Improving appropriateness of diagnostics and prescribing via Care Home Education Package - ongoing work 3. Coding - Ongoing work with practices to standardise coding of UTI / prescribing decisions / diagnostics used to enable audit of same 4. Standardisation - Developing a standardised template for Vision and EMIS IT systems used across General Practice 4. OOH - Work with Out of Hours Provider to share learning points and also agree and review audit outcomes of prescribing of antibiotics. | All 4 targets Complete - Ongoing Q1 through to Q4 | < 34 CAI cases | < 63 CAI cases | < 93 CAI cases | < 122 CAI cases | Qualitative | TBC
Reduce incidences of the following Tier 1 target for Community associated/ acquired infection; Klebsiella bacteraemia | Infection Prevention & Control - Tier 1 Target | Total Cumulative cases (Apr 22 – Mar 23) = 43 | < by 30% CAI cases for 2023/2024 = Overall reduction of 13 cases | < by 10% CAI cases for 2023/2024 | < 41 CAI cases |  | 1.0 Limited ability within PCTG to reduce cases as largely linked to hepatobiliary infections, Clinical Lead for IPC will take forward developing a task and finish group with hepatobiliary surgeons / teams. | 1. Q4 | < 9 CAI cases | < 19 CAI cases | < 30 CAI cases | < 41 CAI cases | Qualitative | TBC
Reduce incidences of the following Tier 1 target for Community associated/ acquired infection; P. aeruginosa bacteraemia | Infection Prevention & Control - Tier 1 Target | Total Cumulative cases (Apr 22 – Mar 23) = 12 | < by 42% CAI cases for 2023/2024 = Overall reduction of 5 cases | < by 10% CAI cases for 2023/2024 | < 11 CAI cases |  | See Global Actions | N/A | < 3 CAI cases | < 5 CAI cases | < 8 CAI cases | < 11 CAI cases | Qualitative | TBC
Reduce Primary Care antibiotic prescribing for Urinary Tract Infections in the following 4 medications: 1. Trimethoprim 2. Nitrofurantoin 3. Fosphomycin 4. Pivmecillinam Reduce repeat antibiotic prescribing in Primary Care Continuation of the 4C prescribing reduction campaign with the main focus on the top 3 highest prescribing practices within SBUHB. | Antimicrobial Stewardship | Significant improvement seen in prescribing of 4C broad spectrum antibiotics within SBUHB Primary Care. SBUHB has moved from the highest 4C prescribers in 2020 to the lowest 4C prescribers in Wales as per most recent Data (National Prescribing Indicators 2022-2025). Reduction of 37.6%. | N/A | N/A | N/A | To implement more effective, safe prescribing habits aligned to national prescribing indicators, SBHB Antimicrobial Team will: Work collaboratively with PCTG Medical Director and Clinical Lead for IPC providing strong professional leadership to collectively embed best practice across all Clusters and Practices. Perform ongoing audits of national, regional and cluster based prescribing data to identify key areas of directed workplans. Individual prescribers within outlier practices will be identified and prescribing practice questioned as part of the ongoing effort to reduce prescribing. Produce and disseminate updated prescribing guidelines to all practices. Provide antimicrobial stewardship education to Primary Care Practices. This includes GP Trainees and Locums. Provide targeted education to whole practice teams and individual prescribers. Support annual Prescribing Leads Meetings to all eight Clusters. | Targeted education with care homes regarding UTI prescribing and correct sampling processes. Work collaboratively with new IPC Senior Clinical Nurse Specialist for HCAIs in Care Homes. Engagement with all 3 top prescribing practices for 4C antibiotics. Agreed collaboration between the identified practices, PCTSG and antimicrobial Pharmacy team. | Ongoing Q1 through to Q4 with regular internal audit of prescribing data. The 2022–2023 NPI report for quarter ending March 2023 will be available on July 21st 2023 | N/A | N/A | N/A | N/A | Qualitative | TBC
Achieve compliance with national training target for infection prevention for all available PCT staff. Increase staff compliance in training: IPC Level 1 ≥85% (all staff) | Infection Prevention & Control Training | IPC LEVEL 1 = 90% Compliance for PCTG | N/A | N/A | N/A | Above target - no actions required | Above target - no actions required | N/A | N/A | N/A | N/A | N/A | Qualitative | TBC
Develop robust reporting mechanisms to collate compliance data. Achieve compliance with national training target for infection prevention for all available PCT staff. Increase staff compliance in training: IPC Level 2 ≥85% (all clinical staff) | Infection Prevention & Control Training | Data unavailable due to lack of reporting mechanisms | N/A | N/A | N/A | Develop PCTG IPC Training Digital Intelligence Platform via SharePoint to record and collate training compliance. Use an "economy of scale" approach to provide training across staff platforms, i.e.: Professional Forums Professional/Service Specific Study Days Engagement Events On-Site Service Specific Continued Collaboration between Corporate IPC and PCTSG to support the education and training agenda. PADR Requirement - Embed requirement to undertake role specific IPC training into PADR for all staff. | 1. Secure Lead Nurse Link Role for Level 2 IPC Training. 2. Increase number of service based Level 2 IPC trainers 3. Increase compliance with IPC level 2 training for all clinical staff | 1. Q2 2. Q3 3. Q4 | N/A | N/A | N/A | N/A | Qualitative | TBC
Develop robust reporting mechanisms to collate compliance data. Increased ANTT training and assessment compliance for clinicians performing aseptic non-touch procedures as part of their core role ≥85% (all staff using ANTT) | Infection Prevention & Control Training | Data unavailable due to lack of reporting mechanisms | N/A | N/A | N/A |  | 1. Lead Nurse Link Role for ANTT to represent PCTG at ANTT Steering Group. 2. Increase number of service based ANTT nominated assessors 3. Increase compliance with ANTT training for all staff using ANTT. | 1. Complete - Ongoing Q1 through to Q4 2. Q3 3. Q4 | N/A | N/A | N/A | N/A | Qualitative | TBC
Develop robust reporting mechanisms to collate compliance data. Increased Hand Hygiene training for all PCTG staff ≥85% (all staff) | Infection Prevention & Control Training | Data unavailable due to lack of reporting mechanisms, ESR does not consider Hand Hygiene Training as mandatory. | N/A | N/A | N/A |  | 1. Secure Lead Nurse Link Role for Hand Hygiene. 2. Increased number of Hand Hygiene Trainers 3. Increase compliance with Hand Hygiene training for all staff. | 1. Q2 2. Q3 3. Q4 | N/A | N/A | N/A | N/A | Qualitative | TBC