Tier 1 Target Health Care Associate Infection Reduction Improvement Plan, 2022/23

Service Group:  Mental Health & Learning disabilities

Date: 24.04.2022

Outcome Objective

Welsh Government Targets - To reduce Health Care Associate Infections by 10-15%

| Green | On target for completion by deadline date or completed. |
| --- | --- |
| Amber | Delay or risk of delay but some progress is being made. Escalation may be required to Directorate/Locality, Site and/or Executive Lead. |
| Red | Progress not being made, or very significant delay in progress. Escalation to Executive Lead required. |

|  | OBJECTIVE | ACTION | BY WHOM | Q1 | Q2 | Q3 | Q4 | PROGRESS; ASSOCIATED RISKS | STATUS (RAG) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |  |
| 1.1 | 1 A Delivery Group IP&C structure and management system for Infection reductions will be in place | The service group will identify a clinical lead for IPC and HCAI across sites to align with expectations from corporate structures. | MH/LD Unit Nurse Director | IPC and HCAI Lead will be identified. MHLD SG to review interface between IPC and physical health group to inform reporting assurance pathways. | Ongoing monthly monitoring through Divisional performance scorecards, HCMS, DATIX, Quality assurance reporting structures |  |  | MHLD SG have confirmed new governance (March 2022) IPC Lead identified – Paula Hopes HoN. IPC and HCAI’s will be managed in the same Service Group meetings due to volume of crossover. |  |
| 1.2 |  | The Service Group will identify, assess and manage risks in relation to HCAIs, antimicrobial stewardship, decontamination and immunisation through the governance structure. | Unit Nurse Director | Establish a multi professional IPC group as part of MHLD SG Governance structure. This will be led by identified IPC Lead Nurse. Communicate expectations to all clinical staff in their role in the Tier 1 HACI through sharing of action plan. | Ongoing monthly monitoring through Divisional performance scorecards, HCMS, DATIX, Quality assurance reporting structures. |  |  | Achieving via IPC lead and service group IPC approach. |  |
| 1.3 |  | Scope All Wales IPC tier 1 policies to inform localised Service Group IPC policies where this is appropriate. | Quality Governance HoN, MHLD SG Policy Group, MHLD SG IPC Group, Heads of Departments | Undertake scoping of All Wales IPC Policies to inform localised need. | Identify leads for localised policy development taking a multi professional approach | Communicate and disseminate policies across the MHLD SG promoting IPC as everyone’s business. | Through quality assurance framework and MHLD SG Governance structures, Monitor application of IPC policies for assurance purposes | Laundry policies and standard operating procedures in development |  |
| 2 | Objective; ACTION; BY WHOM; Q1; Q2; Q3; Q4; PROGRESS; ASSOCIATED RISKS; STATUS (RAG). |
| 2.1 | 2 Health Care staff will receive regular training in practical infection prevention and control techniques, including staff actions to prevent and manage patients with HCAI | To maintain a minimum 90% compliance with mandatory training. | Heads of Department |  | Ongoing monthly monitoring through Divisional performance scorecards, HCMS, DATIX, Quality assurance processes |  |  | Service Group have achieved over 90% each month from April 2021-March 2022. Monthly Lead Nurse Quality Assurance audits in place. Areas of concern or hotspot areas will undergo specific focus in collaboration with IPC Colleagues. |  |
| 2.2 |  | 85% Aseptic Non Touch Technique (ANTT) compliance for clinical staff. All trained clinical staff will be assessed as competent in ANNT. | H0Ns, Learning and Development Ward/Team Manager | Confirm current compliance for baseline to inform roll out of training programme Identify staff to attend training the trainer programme | Train the trainers will complete ANNT training programme Develop and begin roll out of ANNT training programme | Ongoing monthly monitoring through Divisional performance scorecards, Divisional Quality assurance processes Quality Governance Structures |  | Specific sessions continue for MH and LD staff, attendance has been challenging, escalated through individual managers in partnership with L&D team. L&D lead has been designated to reach out to trainers to assist the up-take of cascaded training. To report numbers trained in April 2024 |  |
|  |  | 85% compliance for all clinical staff in Level 2 IPC training. | Heads of Department | Disseminate How To Guide from IPC to correct access of IPC on ESR. Establish an accurate baseline for MHLD SG compliance with L2 IPC training on ESR. Include L2 IPC training on divisional scorecards | Ongoing monthly monitoring through Divisional performance scorecards, Divisional Quality assurance processes Quality Governance Structures |  |  | Divisional performance scorecard currently reports on Level 1 IPC training not L2 MH/LD service group to complete a scope of level 2 compliance via quality team review Nov 2023. Lead for IPC – to link with Informatics RE up-date to divisional scorecard to reflect scoping results (Nov 2023). To disseminate to all HONs baseline from scoping and link to Level 2 training for prompt to complete for all clinical staff (Dec 2023) |  |
| 2.3 |  | Scope a collaboration with IPC for training in the prevention and management of UTIs specific to the patient population of MHLD SG. | Designated IPC HON lead and IPC Service Group Leads. | Establish the specific clinical needs of patients in MHLD SG to inform skills requirements its clinical (multi professional) workforce | In collaboration with IPC and clinical colleagues, develop a multi- professional bespoke training programme based on the clinical needs analysis under taken in Q1. | Ongoing monthly monitoring through Divisional performance scorecards, Divisional Quality assurance processes Quality Governance Structures |  | Task and finish group remains to be set up – HON IPC lead and L&D link to action by Jan 2024 |  |
|  |  | Each ward area will have access to local hand hygiene trainers to achieve and sustain 100% hand hygiene training within a rolling training programme. July 2023 Hand Hygiene 92.1% | Lead Nurses/Heads of Nursing | Scope availability of hand hygiene trainers across MHLD SG to identify areas for focus of trainers. Source availability of HB hand hygiene training to meet MHLD SG need | Ongoing monthly monitoring through Divisional performance scorecards, HCMS, Divisional Quality assurance processes Quality Governance Structures |  |  | Review of Hand hygiene trainer numbers still required – to complete by Oct 2023 |  |
| 3 | OObjective; ACTION; BY WHOM; Q1; Q2; Q3; Q4; PROGRESS; ASSOCIATED RISKS; STATUS (RAG). |
| 3.1 | 3 Prompt detection of Tier 1 HCAI cases, appropriate sampling, prompt isolation, diagnosis and treatment of positive cases. | Each case of a Tier 1 HCAI will receive a rapid multi-disciplinary review to inform learning opportunities and inform the ongoing management and prevention of HCAI Medical and Service Group directors to undertake scrutiny of the rapid MDT review for assurance. | Lead Nurses/HoN/ Medical and Nurse Director | To communicate to clinical areas expectations of the rapid MDT review process for all Tier 1 HCAI. Ongoing monitoring through Divisional performance scorecards, HCMS, Divisional Quality assurance processes Quality Governance Structures | Ongoing monthly monitoring through Divisional performance scorecards, HCMS, Divisional Quality assurance processes Quality Governance Structures |  |  | Process for rapid review disseminated joint work via IPC leads (service group and Health board to embed process) |  |
| 3.2 |  | Unexplained diarrhoea poster and SIGHT mneumonic poster will displayed in every clinical area. | HONs | Relevant posters to be disseminated a displayed. Review compliance through Quality assurance and quality governance processes for assurance. | Ongoing monthly monitoring through Divisional performance scorecards, HCMS, Divisional Quality assurance processes Quality Governance Structures |  |  | Baseline audit of compliance across all clinical areas conducted. (see document in 1.3) |  |
| 3.3 |  | To collaborate with the IPC team to increase awareness of timely and good quality samples and how to obtain those. | HON’s/ IPC MHLD SG Link | To undertake a baseline needs analysis to inform training programme. | In collaboration with IPC to develop a training package based in work in Q1 and plan roll out of same. | Ongoing monthly monitoring through Divisional performance scorecards, HCMS, Divisional Quality assurance processes Quality Governance Structures Ongoing monthly monitoring through |  | Task and finish group not yet established – requires to action by Jan 2024 |  |

|  | Objective | ACTION | BY WHOM | Q1 | Q2 | Q3 |  | Q4 | PROGRESS; ASSOCIATED RISKS | STATUS (RAG) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 | Environmental cleanliness and mitigation of risk to others | Hand hygiene compliance and adhering to the rules on ‘bare below the elbow’ audited monthly. | Ward Managers/Lead Nurses. | Ongoing monthly monitoring through Quality assurance processes, senior nurse leadership walkabouts, MHLD SG Quality Governance Structures |  |  |  |  | Monitored in monthly HCM’s reporting. March 2022 Hand Hygiene Audits achieved over 90% in inpatient services. |  |
| 4.2 |  | Cleanliness & maintenance of the ward environment and equipment to be monitored by domestic supervisors and ward manager. | Hotel Services and Ward Managers | Establish with Hotel Services a Standardised approach implementing and auditing to be considered in Service Group IPC meeting. | Ongoing monthly monitoring through Quality assurance processes, hotel services cleanliness audit structures, senior nurse leadership and IPC walkabouts, MHLD SG Quality Governance Structures |  |  |  | Action in Q1 commenced through service group IPC governance group |  |
| 4.3 |  | To review the use of washing machines in clinical areas that support patient rehabilitation and implement appropriate actions to prevent risk of cross contamination. | IPC and Service Group IPC Leads. | Collate a baseline of clinical areas where patient washing machines are in use and current practice measured against IPC Standards | MHLD SG and IPC to review baseline data collated in Q1 to inform a collaborative risk management plan for clinical areas to prevent risk of decontamination. | Ongoing monthly monitoring through Quality assurance processes senior nurse leadership and IPC walkabouts, MHLD SG Quality Governance Structures |  |  | Q1 Directorate managers have reviewed and introduced Standard Operating processes for all wards and units utilising patient accessed washing machines – to provide up- date of review/ audits in April 2024 |  |
| 5 | Objective | ACTION | BY WHOM | Q1 | Q2 | Q3 | Q4 |  | PROGRESS; ASSOCIATED RISKS | STATUS (RAG) |
| 5.1 | Preventing Infections | Identify infection indications across the MHLD SG. Improve compliance with 'Start Smart Then Focus' (SSTF) antimicrobial stewardship programme, with timely feedback of results to Service Groups | Pharmacy and Medical staffing | Gather data from antimicrobial audits to identify and better understand the indications of infections within MHLD SG. Continue quarterly audits by Pharmacy, with feedback to Service Group Quality Governce Structures. | Utilise data gathered in Q1 to inform workforce training requirements in relation to Tier 1 HCAI. Work with pharmacy and IPC colleagues to develop training programme as indicated specific to the MHLD SG indication data | Ongoing monthly monitoring through Divisional performance scorecards, HCMS, Divisional Quality assurance processes Quality Governance Structures |  |  | Being managed via drugs and therapeutics |  |
| 5.2 |  | With low numbers of Tier 1 HCAI MHLD SG will explore with IPC how to present data in terms of numbers of days free from infection. All wards will display days free performance against HCAI | Service Group IPC Leads/MHLD SG IPC Link | Work with IPC link nurse and agree time parameters for a baseline measurement for clinical areas to display days free data. Engage with clinical staff for them to have ownership of reporting data at ward level | Develop ongoing systems for measurement of compliance of displaying data on days free from infection. | Ongoing monthly monitoring through Divisional performance scorecards, HCMS, Divisional Quality assurance processes Quality Governance Structures |  |  | Information disseminated via MH and LD ICC group to provide resources to display free from infection rates. |  |
| 5.3 |  | Promote handwashing before meals and after toilet use for our patients and service users. | IPC and Service Group IPC Leads. | Baseline observations on handwashing to be conducted. Assess environments and consider equipment/resource needs. | Develop health promotion activities on hand washing and supporting materials | Ongoing monthly monitoring through Quality assurance processes senior nurse leadership and IPC walkabouts, MHLD SG Quality Governance Structures |  |  | Examples of work to be collated through service group IPC governance group. Agreement that this is ward level initiatives, to be considered within the quality assurance framework/health promotion work. |  |