| Meeting Date | 29 August 2023 |  | Agenda Item |  |  | 4.3 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | External Inspections Report |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to highlight matters arising in respect of Healthcare Inspectorate Wales (HIW) inspections and reviews, and to provide assurance regarding action to address issues raised. The report has been expanded to capture other external reviews. |  |  |  |  |  |
| Key Issues | - Two final HIW inspection reports have been published. One area of immediate assurance was highlighted within one of the reports. An update has subsequently been provided to HIW in respect of that inspection and is attached to this report. A third report has been finalised but awaits publication in August 2023 – no immediate improvements were required. - An update on improvement actions previously agreed in relation to HMP Swansea was submitted to HIW in June 2023 (this has previously been received by the QSC, so not attached with this report). The update has been accepted by HIW as providing assurance that recommendations are being addressed. - An up to date status position has been submitted to HIW in relation the recommendations made following HIW’s National Review of Maternity Services. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the update in relation to external reviews and the health board responses to issues raised. - CONSIDER any areas requiring further assurance. |  |  |  |  |  |

EXTERNAL INSPECTIONS REPORT

- INTRODUCTION

The purpose of this report is to highlight matters arising in respect of Healthcare Inspectorate Wales (HIW) inspections and reviews, and to provide assurance regarding action to address issues raised. The report has been expanded to capture information on other external reviews.

- BACKGROUND

The Healthcare Inspectorate Wales (HIW) looks at the quality, safety and effectiveness of the services that are being provided to people and communities, drawing attention to good practice where it is found and highlighting practices that could cause harm to those who are receiving it and areas for improvement. It inspects NHS services in Wales, and regulates and inspects the independent healthcare sector. HIW also works with other review and inspectorate bodies to consider the quality of healthcare delivered in non-healthcare settings such as prisons. In addition to inspections, HIW undertakes a programme of reviews to look in depth at national or more localised issues.  As part of its work it makes recommendations to make improvements, immediate and longer term, where appropriate.

This report presents information in respect of reviews/inspections approaching or in progress, and those recently concluded and reported.

Where reviews/inspections identify areas for improvement, HIW presents recommendations against which improvement plans may be developed by the health board and shared. Progress against these actions is communicated periodically by service leads to the corporate Risk & Assurance team and the position summarised and reported to support corporate oversight and the provision of assurance to the Quality & Safety Committee.

This report presents the status of actions agreed following HIW reviews/inspections within the health board as informed by updates received to date from service areas.

Health board services are reviewed and inspected by other external bodies, in accordance with statutory arrangements, quality management accreditation systems, and commissioning arrangements. Steps are being taken to coordinate information on these so that it is clear how risks and assurances arising from these are captured and reported.

- NEW REPORTS RECEIVED – HIW

3.1 Health Board Services – Final Reports & Agreed Improvement Plans

3.1.1 Final Report & Update – IR(ME)R Inspection, Diagnostic Imaging Services

An unannounced inspection was undertaken within Diagnostic Imaging service within Morriston Service Group in February 2023. HIW required immediate assurance of action being taken to improve mandatory staff training compliance in respect of both resuscitation training and safe moving and handling training, and to promote patient safety in the interim. An Immediate Improvement Plan was submitted on 2 March and accepted by HIW.

A wider improvement plan was submitted on 18 April 2023 in response to HIW’s formal draft report following the inspection, accepted by HIW and the final report published on 25 May 2023. Findings are summarised below:

Quality of Patient Experience: There were suitable arrangements in place to promote the privacy and dignity of patients, and staff treated patients with respect and kindness. Patients provided positive feedback about their experiences of attending the Diagnostic Imaging Department at the hospital. Relevant information was made available to patients about their examination and the associated benefits and risks. Whilst the use of the Welsh language was promoted within the department, appointment letters sent to patients were in English only and the size of the text could make it difficult for some patients to read. This is what HIW recommended the service can improve: • Ensuring appointment letters are bilingual, in both Welsh and English, and consideration should be given to revising the size of text used • Promoting the availability for patients to speak to staff in Welsh. This is what the service did well: • There was good provision of information for patients displayed within the department • Patients provided positive feedback about the service they had received and the respect shown by staff.

Delivery of Safe and Effective Care: Generally, there was good compliance with IR(ME)R 2017. Written employer’s procedures were clear and comprehensive. There was clear evidence that medical physics experts (MPEs) were available for consultation on all areas and staff were complimentary about their support. However, some routine quality assurance performance equipment testing and X-ray dose audits which are performed by the medical physics service, had not been completed in line with the recommended time frames as documented in professional guidance (IPEM 91) due to a lack of medical physics resources. HIW was told the lack of resources had been escalated to the Chief Executive. HIW also found suitable arrangements were in place to provide patients attending the department with safe and effective care. The environment was clean and appropriate arrangements were in place to promote effective infection prevention and decontamination within the department. This is what HIW recommended the service can improve: • Mitigating the risk of MPEs not completing the relevant equipment QA performance testing and dose audits • Ensuring there is sufficient MPE cover for the hospital and the health board in general. This is what the service did well: • Written employer’s procedures were clear and comprehensive • Patient referral documents were completed comprehensively.

Quality of Management and Leadership: The Chief Executive of the health board was the designated employer under IR(ME)R and clear lines of delegation and responsibilities were described and demonstrated. Staff HIW spoke with demonstrated they had the knowledge, skills and training required to undertake their respective roles and scope of practice within the department. Staff training records, competencies, entitlement and scope of practice were clearly documented and linked to the appropriate equipment training records provided. The radiologist’s equipment training and entitlement records were noted to be of the same standard as the radiographers. Whilst feedback from staff was generally positive, there were negative responses and comments from staff. These were mainly in relation to staffing, the rota/shift pattern, management and staff relations and management not acting on staff concerns reported to them. The department’s compliance with the health board’s face to face mandatory training requirements needed to be improved. Immediate assurances: The health board was required to provide HIW with details of the action taken to improve staff compliance with resuscitation training and moving and handling training. This is what HIW recommended the service can improve: • Addressing the issues raised by staff in their comments and questionnaire replies, particularly regarding discrimination. This is what the service did well: • Documenting staff training records, competencies, entitlement and scope of practice. • Ensuring compliance with online training.

Since publication the Health Board has also provided a formal update on progress against the improvements agreed to HIW. The full report and an updated improvement plans reflecting progress to date are attached at Annexes 2a, b & c.

3.1.2	Final Report – Assessment and Treatment Unit, Learning Disabilities

An unannounced inspection of the above services (managed by the Mental Health & Learning Disabilities Service Group) was undertaken on 17-19 April 2023. No immediate assurances were required following the inspection. The final report was published on 20 July 2023. Findings are summarised below:

Quality of Patient Experience:

HIW found patients were provided with a positive experience. HIW observed staff interacting with patients in a proactive and engaging manner, and staff HIW spoke with demonstrated a genuine patient focus. Patients were also happy to engage with the inspection team and the views expressed to the inspectors were overall supportive of the care they receive.

HIW identified an area for improvement in relation to the physical environment and resources available for patients who are in receipt of rehabilitative care under the new service model. This is what HIW recommended the service can improve: • The health board must reflect on and ensure that the physical environment meets the needs of patients in receipt of rehabilitative care. This is what the service did well: • Physical health needs of patients were assessed, reviewed and monitored in a full and individualised manner • Staff communicated with patients in a kind, proactive and engaging manner throughout the course of the inspection • There were appropriate patient feedback mechanisms which enabled patients to voice their views and opinions on a range of topics.

Delivery of Safe and Effective Care: HIW found that patients received safe care based on a review of patients care records, discussions held with staff, and a review of the quality and safety governance mechanisms. There were particularly positive findings in areas of infection prevention and control, medicines management, and care planning. HIW identified a small number of areas for improvement to fully strengthen aspects of behaviour management, record keeping, and the physical environment. This is what HIW recommended the service can improve: • Aspects of record keeping must be strengthened in relation to seclusion documentation and mental health act administration. • The ability of staff to access training to complement the Positive Behaviour Support model must be reviewed. This is what the service did well: • There were good care planning arrangements, which had been regularly reviewed and were appropriate to the individual • Infection prevention and control practices were robust, and the unit was visibly clean throughout • There was good knowledge, implementation and oversight of safeguarding matters.

Quality of Management and Leadership: HIW found a number of positives in relation to service level management and leadership. Management was visible and all staff told inspectors that their line manager could be counted on to help with a difficult task. Staff all confirmed that they had received training appropriate to their role and HIW found good use of external learning and development opportunities. There were however less favourable findings in relation to the service change affecting the unit, and some staff told HIW that this affected their wellbeing and recommendation of the service as a place to work. This is what HIW recommended the service can improve: • The health board must continue to engage with staff and ensure that staff are supported in any changes to their roles aligned with the service change from assessment and treatment to that of rehabilitation • The health board must reflect upon these issues when considering the training needs of staff and how supported staff feel in their role. This is what the service did well: • Staff told HIW that there was visible management and that their line manager could be counted on to help with a difficult task • Staff were clear on their responsibilities and demonstrated a good knowledge of patients and their care needs • There were appropriate quality and safety oversight processes in place.

The full report, incorporating the Health Board’s improvement plan, is attached at Annex 3.

3.1.3	Final Report (pending publication) – Ward F, Neath Port Talbot Hospital

An unannounced inspection on the above ward (managed by the Mental Health & Learning Disabilities Service Group) was undertaken on 22-24 May 2023. No immediate assurances were required following the inspection. An improvement plan has been submitted and accepted by HIW. The proposed final report has been received by the Health Board and is due for publication on 24 August 2023. The report will be included in the next update.

3.2 Health Board Services – Recent Inspections & Draft Reports

3.2.1	New Requests, Unannounced & Planned Inspections

There are no new matters to raise under this heading that have not already been covered earlier in the report.

3.3 Primary Care Contractors – HIW Reports issued

Responsibility for addressing concerns raised by HIW inspections within independent contractors rests with the independent contractors. Reviews & inspections of the health board’s primary care contractors have been identified by review of publications on the HIW website and are provided below for information – reports are received by the Primary Community & Therapies Service Group. The following activity is noted since the last QSC meeting:

- SA1 Medical Centre(Activity Date: 29 June 2023)

An Immediate Improvement Plan was required, submitted by the practice, and accepted by HIW on 11 July.

- Pontardawe Health Centre (Activity Date: 4 July 2023)

An Immediate Improvement Plan was required, submitted by the practice, and accepted by HIW on 13 July 2023.

- Riverside Surgery (Activity Date: 1 August 2023)

An Immediate Improvement Plan was required, submitted by the practice, and accepted by HIW on 11 August.

- PROGRESS AGAINST ACTION PREVIOUSLY AGREED

4.1 Health Board Directly Managed Services

The below table summarised the overall status of actions agreed for those services with actions remaining open (more detail is provided at Annex 1):

| Number of Recommendations | Number of Actions Agreed | Number of Actions Completed | Number of Actions Ongoing | Number of Actions Overdue |
| --- | --- | --- | --- | --- |
| 100 | 216 | 160 | 55 | 30 |

Actions agreed following the Ward F inspection will be included following publication of the final report.

- OTHER HIW REVIEWS INCLUDING NATIONAL/JOINT REVIEWS

National reviews and those requiring a joint response with partners are not included in sections above, but set out below:

5.1.1	Local Review of Governance Arrangements at Swansea Bay UHB for the Provision of Healthcare services to Her Majesty’s Prison [HMP] Swansea

The Primary Community & Therapies Service Group presented a report to the QSC in June 2023 on progress against the above improvement plan. The update was also submitted to HIW that month and the Health Board has subsequently received confirmation in August 2023 that the update was accepted by HIW as providing assurance that the recommendations are being addressed.

5.1.2	National Review of Patient Flow (Stroke Pathway)

As part of the HIW national review of Patient Flow, focusing on the stroke pathway, HIW conducted an onsite visit at Morriston Hospital on 26-28th April 2022. As previously reported, no issues were raised at the time of the on-site inspection with the service lead.

An embargoed copy of the proposed report was shared with the Health Board in July 2023 for review and comments were returned the same month. Publication is scheduled for September 2023. A further update will be brought to the Committee following publication.

5.1.3	National Review of Mental Health Crisis Prevention in the Community (March 2022)

The above report made 19 recommendations. The Service Group has indicated that most actions agreed in response to recommendations have been completed with only one remaining ongoing (the review of the role and function of the Community Mental Health Teams by the MH Service Development and Transformational Manager).

5.1.4	National Review of Maternity Services (Nov 2020) – Progress

In June 2023, HIW requested an update from the Health Board on progress against the recommendations made in the National Review of Maternity Services report published in 2020. An updated progress table was submitted in July 2023 – it reflects afresh on the current position in respect of the recommendations made. A copy is included at Annex 4.

5.1.5	Patient Safety, Privacy, Dignity and Experience whilst Waiting in Ambulances during Delayed Handover (Oct 2021)

The progress updates against the above are coordinated by EASC. The last progress updates submitted to HIW by EASC was reported to the last meeting. There is no further update currently. Future updates on this will be reported to the Committee when further updates are provide by EASC.

- LEARNING FROM INSPECTION

6.1 Thematic Review of HIW Inspections 2022/23

A thematic review of recommendations raised across HIW inspections conducted during 2022/23 was discussed by the Patient Safety & Compliance Group. The analysis was based on the alignment of recommendations to Health Care Standards (HCS) for those reviews undertaken in 2022/23 – there were five service reviews undertaken & reported by HIW during that period:

- Dan Danino Ward

- Learning Disabilities	 Unit

- Morriston ED

- Morriston Oakwood & Ward M

- Morriston Radiology IRMER

Detailed findings were presented to the group. In summary, the review highlighted 4 HCS areas with issues across several services, the nature of the issues was varied:

Standard 2.1 Managing Risk And Promoting Health & Safety

Security: This was raised across four of the areas visited. The need to secure access to utility rooms, medication rooms, and storage areas (oxygen cylinders) was highlighted. Additionally, consideration was recommended to security arrangements where there was access to vulnerable patients / DoLS considerations.

Environment/Maintenance: In two areas, staff feedback highlighted environmental/maintenance matters needing resolution, including: the absence of clean facility; delays to fix equipment; the environment not being suitable for care provision/child friendly; buzzer system needs replacement; leaks

Alarms: Three areas had matters in this respect: In one the ability to call 999 was an issue at the time (since resolved); HIW recommended consideration to providing staff with personal alarms (LD area); And in a third (as above), the need to replace the buzzer system was highlighted by staff.

Standard 2.4 Infection Prevention & Control (IPC) And Decontamination

Issues varied across the services reviewed with few common issues across all or several. While environmental issues appeared for two, they were different in nature: one point recommended refresh of shower facility (which had become stained since the last, recent refresh); and another related to action required to storage & room usage issues that impacted in ability to clean effectively (which had been identified in a local audit).

Standard 2.6 Medicines Management

Medication Records: Five recommendations (across three reports) were aimed at improvements to record-keeping. These included: - Patient identification (on each page) - Reasons for non-administration - Recording checks (oxygen & fluid balance, including fluid output) - Double signatures where required to evidence checks

Standard 7.1 Workforce

Mandatory Training: Four of the recommendations made (across 2 reports) relate to the need to demonstrate mandatory training compliance. These referred to core skills and higher level skills pertinent to the clinical area (eg safeguarding, IPC and ALS).

Staffing: Two recommendations (across two reports) relate to aspects of staffing level management: one relating to the need to demonstrate sustained safe staffing levels; the other to the need to ensure adequate rest day provision.

Following review of this summary, and the supporting detail, the Risk & Assurance team has been requested to develop the a mechanism by which assurance can be provided by service groups to the corporate Patient Safety & Compliance Group on the position across wider services in relation to areas highlighted.

- UPCOMING & RECENT REVIEWS BY OTHER EXTERNAL BODIES

The table of other external reviews & inspections is presented at Annex 5.

- OTHER MATTERS

8.1.2 Other Correspondence since QSC May 2023:

- April/May 2023: An anonymous letter was forwarded by HIW highlighting concerns relating to patient safety and care & support for staff. This was considered by the Executive Team and a letter of assurance provided to HIW on 19th May 2023 setting out a list of actions taken to address issues raised.

- June 2023: The Health Board reported to HIW an IR(ME)R incident occurring within Singleton Hospital on 19th June 2023. Arrangements are being made to investigate and provide the outcome to HIW by 12th September 2023.

- June 2023: HIW highlighted information received through its concerns process relating to the potential safety of the environment and staff professionalism on Oakwood Ward, and some other areas to note. The matters raised were investigated and a letter of assurance setting out findings together with an improvement plan returned on 7th July 2023.

- GOVERNANCE AND RISK

This report aims to provide assurance regarding action taken to address issues & risks highlighted by HIW inspections and to inform Committee members and the Board of approaching and ongoing inspection activity.

- FINANCIAL IMPLICATIONS

It is possible that actions to address some issues raised in external reviews and inspections may require resources. However, this report does not make any recommendations with financial implications.

- RECOMMENDATIONS

Members are asked to:

- NOTE the update in relation to external reviews and the health board responses to issues raised.

- CONSIDER any areas requiring further assurance.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| HIW inspections may identify issues impacting upon the quality or safety of services, or the experiences of those affected by them. This reports aims to provide assurance on actions taken to address issues. |  |  |  |
| Financial Implications |  |  |  |
| It is possible that actions to address some issues raised in HIW inspections may require resources. However, this report does not make any recommendations with financial implications. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| HIW inspections may identify areas of non-compliance with legislation. This reports aims to provide assurance on actions taken to address issues. |  |  |  |
| Staffing Implications |  |  |  |
| HIW inspections may identify issues related to the staffing of services eg staffing numbers, or staff training/competency, or the solutions to other issues raised may have implications in terms of staff resources. This reports aims to provide assurance on actions taken to address issues. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The work of HIW provides an independent view of issues and risks within services. In addressing matters arising from reviews and inspections, the health aims to understand the causes of issues in order to prevent them from re-occurring. |  |  |  |
| Report History |  | This is report has been prepared directly for the Committee |  |
| RESOURCES |  | Annex 1: Progress Against Action Previously Agreed Annex 2a: HIW Report: IRMER Diagnostic imaging Annex 2b: IRMER DI – General Improvement Progress Annex 2c: IRMER DI – Immediate Improvement Progress Annex 3: HIW Report: LD Assessment & Treatment Unit Annex 4: NIW National Maternity Review – SBU Update Annex 5: Other External Inspections |  |