Strategic Risk Register

June 2026 Summary

Quality & Safety Committee

| SRR Ref | Strategic Risk | Lead Director | Risk Score |  |  | Overall Assurance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Previously | Currently | Target | Previously | Currently |
| Objective 2: Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  |  |  |  |  |  |
| 2.4 | Quality, Safety & Patient Outcomes | EDON | 16 | 16 | 12 | Good | Good |
| 2.6 | Perinatal Service | EDON | 16 | 16 | 9 | Good | Good |
| 2.7 | Mental Health | COO | 16 | 16 | 8 | Good | Good |

Strategic Risk Register

June 2026 Detail

| Risk ID Number SRR 2.4 | Risk Label – Quality, Safety & Patient Outcomes Risk Description – If we do not have robust quality governance systems and processes, use our data intelligently, and develop a strong safety culture that supports learning and improvement then this may result in increases in avoidable harm and mortality and poorer clinical outcomes. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 4 | 5 | 20 |  | Lead Director / Risk Owner | Executive Director of Nursing |
| Current Score | 4 | 4 | 16 |  | Monitoring Committee | Quality & Safety Committee |
| Target Score | 4 | 3 | 12 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 2025 | Dec 2025 | Feb 2026 | Apr 2026 | Jun 2026 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 16 | 16 | 16 | 16 | 16 |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |
| 4 | Healthcare Acquired Infection Risk of patients acquiring infection as a result of contact with the health care system, resulting in avoidable harm, impact on service capacity, and failure to achieve national infection reduction goals. | 20 |
| 111 | Listening to People If we do not listen to and act upon the issues raised by people there is a risk that matters of concern to them will continue unaddressed, resulting in dissatisfaction, the potential for poor outcomes, greater regulatory intervention and loss of public trust and confidence. | 16 |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Quality and Safety Process Framework |
| 2 | Annual Strategy Quality Plan |
| 3 | Quality Assurance Framework |
| 4 | Quality Impact Assessment Process |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | Service group quality and safety group scrutiny. Weekly executive Quality Huddle | Service group reporting into QSG sub-groups (PSEG, PSCG, COEG, Safeguarding, IPC, QPPB). Service group performance reviews. Quality dashboard reporting to QSG (monthly), reporting to QSC (bi-monthly) and Management Board (monthly) Service group presentation at QSG (quarterly) | A&A Review – Quality Management System SBUHB-2324-003 (June 2024) – Reasonable Assurance Audit Wales Structured Assessment. | Reasonable |
| 2 | Reporting from action owners within annual strategic quality plan | Quarterly reporting to QSG Quarterly reporting to QSC and Management Board |  | Reasonable |
| 3 | Quality assurance visits within service groups. Service group AMaT scrutiny. | Service group bi-monthly updates to PSCG. PSCG bi-monthly reporting to QSG Corporate Quality Assurance audit programme and reporting into PSCG. Service group Quality Assurance Audit programmes and reporting to PSCG | HIW reviews Llais reviews A&A Review – Quality Assurance SBUHB-2425-009 (March 2025) – Limited Assurance Independent Members’ visiting programme | Limited |
| 4 | QIA scrutiny within service groups’ management boards for service groups decisions QIA scrutiny in Management Board for HB wide decisions | Board scrutiny of QIAs |  | Limited |
|  | Current Overall Assurance Rating |  |  | Good |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Individual, team and service level understanding of the Quality Assurance Process Framework requires embedding. | Action refreshed: QMS self-assessment undertaken and approved in QSG in April. Wider work to be undertaken as part of developing our organisational QMS to identify areas requiring strengthening across the organisation Date changed to reflect this work and the associated impact of Organising for Success | Head of Q & S | 31/3/2027 | On track |
| 2 | Service groups need to ensure that quality assurance audits are completed regularly. AMaT completeness at service group level requires improvement. | Bi-monthly reporting from service groups to PSCG, as part of internal audit management actions. Service groups have developed forward plans for assurance activities and these are beginning to be reported through to PSCG. Service group quarterly reporting to QSC has been replaced with monthly reporting to QSG on key quality and safety metrics. Assurance activities are reported into PSCG. | Service Group Medical and Nurse Directors | 31/12/2025 Now expected 31/07/2026 | Off Track |
| 3 | The Quality Impact Assessment process is not fully embedded across organisation | Action Refreshed: Board reporting template being revised to reflect the key domains of the QIA. | Head of Corporate Governance | 28/02/2026 Now expected 31/8/2026 | Off track |

Additional Comments

13/05/2026: Actions reviewed & refreshed. Update: Controls effectiveness: • Key controls are operating effectively, with strengthened senior clinical leadership, established perinatal governance structures, a Board reported Perinatal Committee, an agreed Independent Review action plan, and ongoing external oversight through the Oversight Panel, providing clear accountability, scrutiny and assurance of progress against recommendations. Residual risks: • Residual risk remains in relation to digital maternity record implementation, specifically limited national system integrations and reliance on external dependencies, which continue to create operational, safety and workforce pressures; these risks are actively managed through escalation to national digital programmes, local mitigation planning, and continued executive and Board oversight.

| Risk ID Number SRR-2.6 | Risk Label – Perinatal Service Risk Description – If we do not respond in a timely and effective way to the recommendations of the External Review of Maternity & Neonatal services, there is a risk that matters of concern identified within the report will not be addressed, resulting in a lack of demonstrable improvement to quality, low morale and wellbeing amongst staff (with associated implications for recruitment and retention) and a potential loss of wider public confidence in these services. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 4 | 5 | 20 |  | Lead Director / Risk Owner | Executive Director of Nursing & Patient Experience |
| Current Score | 4 | 4 | 16 |  | Monitoring Committee | Quality & Safety Committee |
| Target Score | 3 | 3 | 9 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 2025 | Dec 2025 | Feb 2026 | Apr 2026 | Jun 2026 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 16 | 16 | 16 | 16 | 16 |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Appointment of new leadership roles (e.g., Clinical Director of Midwifery, Clinical Director of Womens Health, Associated Service Group Director, Associate Service Group Medical Director, Service Group Medical Director) |
| 2 | Establishment of a Perinatal Committee and enhanced governance structures. |
| 3 | Implementation of a maternity and neonatal dashboard for real-time monitoring |
| 4 | All-Wales MEWS tool has been implemented to identify and escalate deteriorating condition of pregnant women. |
| 5 | All Clinical Maternity staff attend Infant Fetal Surveillance training annually |
| 6 | Engagement with families through Maternity and Neonates Voices Partnership and community outreach. |
| 7 | Womens Experience Specialist Midwife role is in place to support wider engagement with women, families and the community. |
| 8 | Forward Audit Plan in place (this will be revised in view of the Independent Review report recommendations to ensure the ongoing assessment of implementation and impact continues throughout the year.) |
| 9 | Publication of a clear, time-bound action plan addressing all review recommendations (due Nov 2025 – see Actions) with regular progress updates reported to the Perinatal Committee. |
| 10 | Recruitment of a Project Manager to support and oversee the action plan and evidence base to demonstrate implementation and delivery of the report recommendations. |
| 11 | Ongoing support from the Chair and Oversight Panel members of the external review for 18 months to provide assurance and scrutiny in relation to actions and recommendations |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 4,5,6,7 | Perinatal dashboard for real time data monitoring by the Division and Service Group of key performance metrics along with exceptions from the perinatal assurance group. | Board oversight of service improvement using agreed outcome, process and experience measures via the Perinatal Committee – Chairs report presented at Board level meetings. | Chair and Oversight Panel members of the external review for 18 months to provide assurance and scrutiny in relation to progress in addressing actions and recommendations. | Reasonable |
| 8 | Elements of Forward Audit Plan are reviewed at Perinatal Assurance Group. | Elements of Forward Audit Plan is reviewed at Perinatal Committee and overview is maintained at COEG (and monitored by WG). | Chair and Oversight Panel members of the external review for 18 months to provide assurance and scrutiny in relation to progress in addressing actions and recommendations. | Limited |
| 5 | Reporting of compliance rate for completion of annual Infant Fetal Surveillance training by clinical Maternity staff at Perinatal Committee. | Board oversight of service improvement using agreed outcome, process and experience measures via the Perinatal Committee – Chairs report presented at Board level meetings. | Chair and Oversight Panel members of the external review for 18 months to provide assurance and scrutiny in relation to progress in addressing actions and recommendations. | Reasonable |
|  | Current Overall Assurance Rating |  |  | Good |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Consolidation of actions for oversight. | Development and approval of an action plan to deliver recommended improvements required by the Independent Review. | Executive Director of Nursing & Patient Experience | 30/11/2025 | In Progress Expected completion date 30/07/2026 |
| 2 | Improvements to record-keeping arrangements. | Launch of Digital Maternity Electronic Record. | Clinical Director of Midwifery | 31/03/2026 | Complete |

Additional Comments

13/05/2026: Actions reviewed and progress updated. 02/07/2026: Badgernet live across Maternity services (May)

| Risk ID Number SRR 2.7 | Risk Label – Mental Health Risk Description – If we do not organise ourselves effectively, and secure and direct sufficient resource and effort to priority areas set out within our mental health and learning disability transformation plan, then there is a risk that we will not transform our environments and the delivery of care sufficiently and in a timely way in line with the recommendations of the mental health transformation plan and in line with the All-Wales Strategy for Mental Health & Wellbeing. This may result in poor patient experience, outcomes and at worst incidents of avoidable harm. |
| --- | --- |

| Risk Score |  | Consequence |  | Likelihood |  | Overall Score |  | Trend |  | Strategic Objective |  |  |  |  | Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inherent Score |  | 4 |  | 5 |  | 20 |  |  |  | Lead Director / Risk Owner |  |  |  |  | Chief Operating Officer |  |  |  |  |  |  |  |  |  |  |
| Current Score |  | 4 |  | 4 |  | 16 |  |  |  | Monitoring Committee |  |  |  |  | Quality & Safety Committee and MH and LD Transformation Program Board |  |  |  |  |  |  |  |  |  |  |
| Target Score |  | 4 |  | 2 |  | 8 |  | N/A |  | Risk Appetite |  |  |  |  | T.B.C. |  |  |  |  |  |  |  |  |  |  |
| Risk Score Over Time | Nov 2025 |  | Dec 2025 |  | Feb 2026 |  | Apr 2026 |  | Jun 2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 16 |  | 16 |  | 16 |  | 16 |  | 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |
| 114 | Mental Health & Learning Disabilities Staffing If workforce shortages and fragility persist across Mental Health and Learning Disabilities services (vacancies, sickness, turnover, reliance on temporary staff and insufficient skill mix), then services will be unable to deliver safe staffing and consistent therapeutic input across community, crisis and inpatient pathways. This may lead to avoidable harm (including self-harm/suicide risk), increased restrictive practice, delayed access and extended length of stay, deteriorating staff wellbeing and retention, failure to meet national quality expectations and performance standards, and increased regulatory, financial and reputational impact. | 20 |
| 115 | Mental Health & Learning Disabilities Estate If the condition, configuration and security of the mental health inpatient, crisis and community estate (including ligature risks, blind spots, backlog maintenance, ageing infrastructure, water/heating/ventilation vulnerabilities and inadequate seclusion and Section 136 facilities) cannot be stabilised and improved at pace, then the Health Board may be unable to provide safe, therapeutic and dignified care. This may result in serious harm or death (including self-harm/suicide risk), increased violence/aggression and restrictive practice, service disruption or temporary closure/decant due to infrastructure failure, failure to meet statutory health & safety requirements, national standards and HIW expectations, and significant regulatory, financial and reputational impact. | 20 |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Programme in place, with Chief Operating Officer (COO) as nominated Senior Responsible Officer (SRO), with formally agreed Project Initiation Documentation. |
| 2 | Programme Board with formal terms of reference (TOR), chaired by COO, reports periodically to Board / Quality & Safety Committee |
| 3 | Programme structure incorporates workstream groups to address; information; quality & safety; service redesign; workforce; estates. Each has TOR and reports to the Driver Group (see below). |
| 4 | External expert engaged to challenge & support the Service Group |
| 5 | There is a Driver Group, chaired by the independent expert, to oversee the workstream groups, provide challenge, and report into the Programme Board. |
| 6 | Key quality indicators have been identified aligned to improvements required |
| 7 | Engagement & partnership involvement has been strengthened, particularly in respect of modernisation & redesign workstreams. |
| 8 | Communication & activities relating to transformation feed into weekly MHLD management team and divisional meetings, and MHLD management board meeting (which includes partner agencies and service users). |
| 9 | Regular engagement sessions with staff. |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | Highlight reports are submitted to the monthly Programme Board meeting from each of the workstreams to maintain oversight of progress against delivery plans | Regular updates are provided to Executive Team meetings via the SRO | All workstreams are chaired by a Health Board Executive or a nominated deputy | Substantial |
| 2 | Updates from each workstream provided to the monthly Driver Group meetings, which are chaired by the Independent Expert and facilitate discussion for a collaborative approach | The details of these discussions and agreements form part of the presentation to the MH Transformation Board |  | Reasonable |
| 3 | Quality and Safety workstream overseeing work to ensure recommendations from HIW and external inspection reports are embedded into improvement plans |  |  | Substantial |
| 4 | Dedicated workstream established for Engagement and Communications to ensure coproduction and collaboration |  |  | Reasonable |
|  | Current Overall Assurance Rating |  |  | Good |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Leadership | Leadership is identified as influencing engagement, motivation and decision making in developing a strategy and implementation plan from the work within the Transformation Program. This needs to be at all levels of the organisation to influence such significant change across a service. | All Executives & Service Group Directors | 09/06/2026 | Presentation on MH Transformation Program took place with the full Board to increase oversight and understanding or programs details |
| 2 | Review of actions for oversight as the Transformation Program continues to progress. | Development and approval of an implementation plan to deliver recommended improvements required by the MH Transformation Program which incorporates the NHS PI Adult MH Review. | All Executives & Service Group Directors | 09/06/2026 | Presentation on MH Transformation Program took place with the full Board to increase oversight and understanding or programs details |
| 3 | Workforce | Business Case developed and presented to RFAG with the aim to improve some aspects of the adult mental health inpatient nursing workforce in line with the NSA Principles | Executive Nurse Director and Service Group Nurse Director | 30/06/2026 | Case presented and awaiting a decision from the Executive Board on progress |

Additional Comments

30/03/2026: Risk reviewed by Exec Team on 30/03/2026. Risk retained on SRR and score confirmed. Risk CRR69 flagged for de-escalation in CRR following Exec team discussion. Reference removed from this SRR entry. 26/06/2026: Assurance & Actions sections reviewed and updated.

Key / Convention / Glossary

| Strength of Control |  | Level of Overall Assurance |
| --- | --- | --- |
| Substantial – The identified control(s) provide a strong mechanism for controlling the risk. Few matters require attention, which are advisory or compliance in nature. |  | Significant – Key governance, risk management and control processes in place provide significant assurance that the risk(s) is/are being managed effectively. Evidence demonstrates that systems and processes are being consistently applied and implemented. Outcomes are consistently achieved across all relevant areas. |
| Reasonable – The identified control(s) provide a reasonable mechanism for controlling the risk, albeit there is scope to strengthen this further. Some matters require management attention in control design or compliance. |  | Good - Key governance, risk management and control processes in place provide a good level of assurance that the risk(s) is/are being managed effectively. Evidence is available to demonstrate that systems and processes are generally being applied and implemented, but no across all relevant areas. Outcomes are generally achieved, but with inconsistences in some areas. |
| Limited – The identified control(s) provide only limited/partial mechanisms for controlling the risk. There are notable weaknesses which require management attention. |  | Moderate – Key governance, risk management and control processes in place provide moderate assurance that the risk(s) is/are being managed effectively. Evidence is available to demonstrate that systems and processes are being applied, but is insufficient to demonstrate implementation across all relevant areas. There is some evidence that outcomes are being achieved, but this is inconsistent and/or there are risks to current performance. |
| Unsatisfactory – The identified control(s) is/are not effective in providing a mechanism for controlling the risk. Action is required to address the whole control framework in this area. |  | Weak – Key governance, risk management and control processes in place provide only weak assurance that the risk(s) is/are being managed effectively. There is only limited evidence available that systems and processes are being applied or implemented. |

Lines of Assurance

First - This is the internal control environment put in place by Managers. It will typically include reports which detail their plans, performance monitoring data, and the results of local checks and reviews of controls within departments performing relevant day-to-day operational activities. Examples would include: - Results of compliance reviews undertaken within Departments/Functions, and reported to senior management - Progress and/or performance reports received by SDG Boards / Committee Sub-Groups

Second – This level of assurance is often referred to as organisational oversight. It is typically provided by Health Board corporate departments and functions which do not directly manage or deliver specific services, but which oversee and report on how controls are operating, thus providing a greater separation from day-to-day management. Typically, this level of assurance is typically provided to the Board or one of its committees (which allows Independent Members to bring an additional level of challenge and scrutiny), as well as to senior management groups (e.g., Management Board). Examples would include: - Reports on the results of Infection Control Audits undertaken by the IP&C Team - Reports on Fire Safety Audits - Progress and/or performance reports received by the Board or one of its committees

Third – This is independent assurance, which typically comes from outside the organisation. Examples would include reports received from: - NWSSP Audit & Assurance - Audit Wales - Healthcare Inspectorate Wales - Llais - Royal colleges

| Glossary of Register Fields & Their Use |  |
| --- | --- |
| Table / Field | Considerations for completion |
| Key Controls | What key controls/systems/processes/governance mechanisms do we already have in place to manage this risk? |
| Assurance on Control | What information do we have about the adequacy, effectiveness and application of each of our controls, where is it coming from, and what is it telling us? |
| Current Overall Assurance Rating | The Lead Director and/or nominated representative should state the overall level of assurance that can be taken and given regarding the effective management of this risk, having considered all of the information available regarding the adequacy, effectiveness and application of each of the controls in place, and any gaps identified. A convention is provided. |
| Gaps in Control and/or Assurance | Do we require further assurance that the key controls / systems / processes / governance mechanisms we have in place are working effectively? What more do we need to do to control this risk, that we are not already doing? |
| Actions to Address Gaps in Control and/or Assurance | What are we going to do, by when, to further manage and mitigate this risk? |