## 12 month HCAI Improvement Plan
Infection Prevention Improvement Plan 2023/24
Goal | Method | Baseline position | 3 month | 6 month | 9 month | 12 month | Outcome | Responsibility | Q1 Progress | Q2 Progress | Q3 Progress | Q4 Progress
Infection Prevention & Control Infection Prevention and Control(IPC) and reduction of HCAIs as per the Health Board refreshed IPC Improvement plan 2023/24 | Achieve reduction in 5 key healthcare associated infections through application of evidence-based practice and best practice guidance | Baseline for 22/23: C. difficile: 202 cases | Cumulative total to Q1: C. difficile: 29 cases | Cumulative total to Q2: C. difficile: 76 cases | Cumulative total to Q3: C. difficile: 95 cases | Cumulative annual total: C. difficile: 95 cases | Cumulative annual total: C. difficile: 95 cases | All Service Groups, reporting via Infection Prevention & Control Groups | Cumulative total to Q1: C. difficile: 52 cases (12 > baseline) | Cumulative total to Q2: C. difficile: 202 cases (exceeding annual maximum)
|  | Baseline for 22/23: Staph. aureus bacteraemia: 147 cases | Cumulative total to Q1: Staph. aureus bacteraemia: 20 cases | Cumulative total to Q2: Staph. aureus bacteraemia: 57cases | Cumulative total to Q3: Staph. aureus bacteraemia: 60 cases | Cumulative annual total: Staph. aureus bacteraemia: 71 cases | Cumulative annual total: Staph. aureus bacteraemia: 71 cases |  | Cumulative total to Q1: Staph. aureus bacteraemia: 39 cases (= baseline) | Cumulative total to Q2: Staph. aureus bacteraemia: 73 cases (exceeding annual maximum)
|  | Baseline for 22/23: E. coli bacteraemia: 260 cases | Cumulative total to Q1: E. coli bacteraemia: 65 cases | Cumulative total to Q2: E. coli bacteraemia: 123 cases | Cumulative total to Q3: E. coli bacteraemia: 178 cases | Cumulative annual total: E. coli bacteraemia: 234 cases | Cumulative annual total: E. coli bacteraemia: 234 cases |  | Cumulative total to Q1: E. coli bacteraemia: 73 cases (4 > baseline) | Cumulative total to Q2: E. coli bacteraemia: 148 cases (11 > baseline)
|  | Baseline for 22/23: Klebsiella bacteraemia: 107 cases | Cumulative total to Q1: Klebsiella bacteraemia: 23 cases | Cumulative total to Q2: Klebsiella bacteraemia: 43 cases | Cumulative total to Q3: Klebsiella bacteraemia: 57 cases | Cumulative annual total: Klebsiella bacteraemia: 71 cases | Cumulative annual total: Klebsiella bacteraemia: 71 cases |  | Cumulative total to Q1: Klebsiella bacteraemia: 24 cases (2 > baseline) | Cumulative total to Q2: Klebsiella bacteraemia: 49 cases (2< baseline)
|  | Baseline for 22/23: Pseudomonas aeruginosa bacteraemia: 44 cases | Cumulative total to Q1: Pseudomonas aeruginosa bacteraemia: 7 cases | Cumulative total to Q2: Pseudomonas aeruginosa bacteraemia: 13 cases | Cumulative total to Q3: Pseudomonas aeruginosa bacteraemia: 19 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 24 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 24 cases |  | Cumulative total to Q1: Pseudomonas aeruginosa bacteraemia: 7 cases (1 < baseline) | Cumulative total to Q2: Pseudomonas aeruginosa bacteraemia: 12 cases (8< baseline)
| Develop a proactive schedule of antimicrobial-related audit, using the Audit Management and Tracking (AMaT) clinical audit assurance software | N/A | Programme established and launched | Review of progress in priority areas | Evaluations of audits, identify potential interventions and implement | Re-audit | Improved compliance with Start Smart Then Focus antimicrobial stewardship key indicators. | All Service Groups, reporting via Antimicrobial Advisory Group and Infection Prevention & Control Groups | Programme established and launched | 141 audits have been undertaken by the IPC team across Morriston, Singleton, Neath Port Talbot, Cefn Coed and Gorseinon hospitals.
| Achieve compliance with national training target for infection prevention & control-related mandatory training (all available staff). Working toward IP&C Training, Level 1 and Level 2 – ≥85% (available staff) | Baseline @ February 2023 Level 1: 87%; Level 2: 21% | Draft of Management Board Paper to propose Level 2 IPC training as mandatory for all Health Board staff, to be presented to Management Board in July. | ESR Team updated mandatory training requirements dashboard in ESR. Evidence of improved compliance against Q1. | Improved compliance against Q2 | ≥85% compliance | Improved compliance with Level 1 and Level 2 IPC and other IPC-related training, progressing to national target level | All Service Groups, reporting via Infection Prevention & Control Groups | Management Board Paper proposing Level 2 IPC training as mandatory for all Health Board staff, presented to Management Board in July and supported. ESR lead making necessary changes. | Compliance against IPC Level 1 has increased from 86.30% in Q1 to 88.23% in Q2. Compliance against IPC Level 2 has increased from 22.74% in Q1 to 26.28% in Q2. Contact made with ESR to update dashboard to show Level 2 as a requirement for all staff. Communications supporting with bulletins for staff to cascade the change.
| Develop a proactive schedule of IPC-related audit for Service Groups, and IPC team, using the Audit Management and Tracking (AMaT) clinical audit assurance software | Reactive IPC audit system in existence, but this does not have an effective system for tracking results, actions and improvement | Development of the audit programme outline, and minimum data sets. | Pilot tools and system in 20 trial areas; amend as necessary | Roll-out to other Wards across Health Board | Improvement in audit compliance, monitoring and tracking and establishment of a baseline for future improvement | Improvement in audit compliance, monitoring and tracking and establishment of a baseline for future improvement | All Service Groups, reporting via Infection Prevention & Control Groups | Development of the audit programme outline, and minimum data sets. | An audit tool has been developed in the AMaT system and is being piloted by Junior Doctors.
| Environment – Cleaning Compliance scoring matrix >95% | Baseline February 2023: 97.94% | >95% | >95% | >95% | >95% | Maintain compliance with National Standards of Cleanliness | Support Services and Service Groups reported via Infection Prevention & Control Group | HB MyAudit compliance = 98.2% | HB MyAudit compliance = 97.7%
| Develop a Quality Improvement programme to work towards compliance with the National Decontamination Agenda and relevant Welsh Health Technical Memorandum documents. | Partial compliance | Key Decontamination Quality Priorities agreed at Decontamination Quality Priority Group and Infection Control Committee. | Evidence that Service Groups report on progress against the relevant key decontamination Quality Priorities | Evidence that Service Groups report on progress against the relevant key decontamination Quality Priorities | Evidence that Service Groups report on progress against the relevant key decontamination Quality Priorities | Evidence that Service Groups report on progress against the relevant key decontamination Quality Priorities | Support Services and Service Groups reported via Decontamination Quality Priorities Group and Infection Prevention & Control Group | Key Decontamination Quality Priorities agreed at Decontamination Quality Priority Group and Infection Control Committee. | Progress with updates is variable across service groups.