| SERVICE DELIVERY GROUP: | Corporate Nursing | REPORTING PERIOD: | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- | --- | --- |
| SENIOR RESPONSIBLE OFFICER: | Angharad Higgins | APPROVED BY: |  |  |  |  |
| REPORT AUTHOR: | Sheena Morgan | DATE: | October 2023 |  |  |  |

DELIVERY ANALYSIS

Link to live document shared with action assignees. Quality Strategy Implementation Plan April 23 (003).xlsx - Assignees to update their actions. - Meetings held to discuss any queries/issues. - Quarterly reviews and updates scheduled.

ACHIEVEMENTS IN QUARTER

Quality Ambition; Actions Completed; Actions Not Started; Actions On-Track; Actions Off-Track; Comments. Safe & Reliable Care; 0; 4; 21; 1; All 'not started' for 2023 have been chased. An Organisation Our Patients & Communities Can Be Proud Of; 2; 10; 14; 0; All 'not started' for 2023 have been chased. Empowered Staff; 3; 4; 5; 0; All 'not started' for 2023 have been chased. High Quality Services Now & in the Future; 0; 3; 5; 0; All 'not started' for 2023 have been chased. Actions Commenced and On Track:

| ID | Goal | Method | Action | I | Name | Start date | Due date | Last updated | Status | Desired outcome | Enablers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Learning from patient safety incidents | We will review and strengthen our arrangements for learning from serious incidents. | Review of process and paper to PSC | Assistant Head of Concerns | Nicola Anthony | 01/04/2023 | 31/03/2025 |  | On-track | Improved organisational learning and patient safety | WRP national programme on LFER |
|  | Learning from patient safety incidents | We will adopt an open ‘no blame’ approach to incident investigation and learning in order to achieve a more restorative approach to improvement | Review of process and paper to PSC | Assistant Head of Concerns | Nicola Anthony | 01/04/2023 | 31/03/2025 |  | On-track | improved organisational learning, patient safety and staff experience | WRP national programme on LFER |
|  | Understanding, measuring and reducing patient mortality | Thematic review of deaths within mental health services | Review of deaths presented within service group | Medical director- MH and LD | Richard Maggs/Marie Williams/Shelley Horwood | 01/04/2023 | 31/03/2024 | 12/10/2023 | On-track | Improved patient outcomes |  |
|  | Understanding, measuring and reducing patient mortality | Thematic review of deaths within learning disability services | Review of deaths presented within service group | Medical director- MH and LD | Richard Maggs/Marie Williams/Shelley Horwood | 01/04/2023 | 19/04/2024 | 12/10/2023 | On-track | Improved patient outcomes |  |
| SRC101 | Learning from patient safety incidents | We will review our processes for working with patients and their families when things go wrong, i.e. ensure that incidents involving the safety of our patients, complaints, mortality and morbidity reviews are joined up from the patient/family perspective and they have a key and clear point of contact. | Implementation of Duty of Candour | Assistant Head of Concerns | Sue Ford | 01/04/2023 | 31/03/2024 |  | On-track | Improved patient experience | Delivery of Duty of Candour |
|  | Learning from patient safety incidents | We will contribute to national work to ensure that there are effective incident reporting systems in place for independent contractors | Contribution to and roll out of national system | Assistant Head of Risk and Assurance, CD Primary Care |  | 01/04/2023 | 03/04/2024 | 29/08/2023 | On-track |  | Agreed process to dedicate services in datix for capture of Independent Contractor incidents. Ongoing work to clear legacy incidents starting. |
| SRC102 | Preventing Peri-operative Never Events | We will sustain 95 per cent compliance in the use of the WHO surgical safety checklist | Monitoring of WHO compliance through audit and incident review | Service group medical directors (Morriston, NPTSSG) | Mark Ramsey, Dougie Russel | 01/04/2023 | 31/03/2024 | 11/10/2023 | Off -track | Improved patient outcomes |  |
| SRC103 | Medicines safety including at the point transfer of care (medicines optimisation) | We will set a target for the number of patients with complex medicines referred for a post discharge community pharmacy review | Target developped, method of measurement agreed, communication with Community Pharmacies | Head of Primary Care | Sam Page | 01/04/2023 | 31/03/2024 | 27/07/2023 | On-track | Improved patient outcomes |  |
|  | Medicines safety including at the point transfer of care (medicines optimisation) | “Get it on time”- develop an approach to ensure patients receive their Parkinson’s medicines within 30 minutes of the prescribed time | Programme developped | Medicine | Dave West | 01/04/2023 | 31/03/2024 | 27/07/2023 | On-track | Improved patient outcomes |  |
|  | Medicines safety including at the point transfer of care (medicines optimisation) | Utilisation of the electronic prescribing and medicines administration system to audit and improve the quality of medicines management across the Health Board. | Reporting into Medicines Management Board | Digital | Dee Roberts/Tracey Bell | 01/04/2023 | 31/03/2025 | 31/07/2023 | On-track | Improved patient outcomes |  |
| SRC104 | Understanding, measuring and reducing patient mortality | We will identify the top ten causes of adult mortality; from this we will develop learning to support and enhance our patients safety and quality improvement programmes | Development of mortality action plan based on top 10 themes. Feedback from learning into Patient Safety Congress programme | Deputy Executive Medical Director | Raj Krishnan | 01/04/2023 | 14/04/2024 |  | On-track | Improved patient outcomes |  |
|  | Understanding, measuring and reducing patient mortality | Review our maternal and neo-natal mortality data and use this to develop a safety and quality improvement programme | Development of local processes for gaining assurance within service groups | Deputy Executive Medical Director | Sue Jose | 01/04/2023 | 15/04/2024 |  | On-track | Improved patient outcomes |  |
| SRC105 | Improving outcomes and learning from National audits, registries, confidential enquiries . | 95 per cent of relevant published NICE guidance will be formally reviewed by the Health Board within 90 days of publication. | Process for review and dissemination in place | Deputy Executive Medical Director | Raj Krishnan | 01/04/2023 | 31/03/2024 |  | On-track | Improved patient outcomes |  |
|  | Improving outcomes and learning from National audits, registries, confidential enquiries. | All clinical services (at sub-specialty level) will participate regularly in clinical audit (measured by registered clinical audit activity during each year of this strategy) | Audits completed and learning shared | Deputy Executive Medical Director | Mark Ramsey, Dougie Russell, Ceri Todd, Richard Mags | 01/04/2023 | 31/03/2025 |  | On-track | Increased assurance and learning |  |
| SRC106 | Using data and benchmarking intelligence to understand variation in outcomes | To develop a quality dashboard for the organisation and service groups that give people live access to the quality information they need | Development and launch of dashboard | Business Intelligence Partner | Dai Williams | 01/04/2023 | 31/03/2024 | 06/09/2023 | On-track | increased use of data to support patient safety and outcomes | Beta version launched July 2023 |
|  | Using data and benchmarking intelligence to understand variation in outcomes | Review the current arrangements for the generation and reporting of quality, experience, outcome and effectiveness in order to provide reliable, accurate and timely information on the quality of our care | Review of quality measures across HB to support Duty of Quality | Head of Quality Safety and Improvement | Angharad Higgins | 01/04/2023 | 31/03/2025 |  | On-track | Improved data quality to inform decision making | National dashboard revised and being launched 23.10.23 |
|  | Understanding, measuring and reducing patient mortality | Development of safety and improvement programme based on outcome of the review M/H | Development and delivery of improvement programme | Medical director- MH and LD | Richard Maggs/Marie Williams/Shelley Horwood | 01/10/2023 | 31/03/2025 | 12/10/2023 | On-track | Improved patient outcomes |  |
|  | Understanding, measuring and reducing patient mortality | Development of safety and improvement programme based on outcome of the review L/Dis | Development and delivery of improvement programme | Medical director- MH and LD | Richard Maggs/Marie Williams/Shelley Horwood | 01/10/2023 | 31/03/2025 |  | On-track | Improved patient outcomes |  |

DELIVERABLES / ACTIONS IN NEXT QUARTER

- Learning from Patient Safety Incidents- Learning from Serious Incidents: SBUHB scoping review to be presented to PSC in December 2023: Lead Charis Jones - Understanding, measuring and reducing patient mortality review of MH and LD deaths: Review findings from MH and LD to be presented to QSG in January 2024 - Learning from Patient Safety Incidents- Implementation of Duty of Candour: Annual report on Duty of Candour to be reported to QSG in April 2024 - Learning from Patient Safety Incidents- Independent Contractors: status report to be presented to PSC Group in January 2024 - Preventing Peri-operative Never Events: AMAT users within theatres to be established an using system by January 2024, NatSSIPs2 to be launched in within HB by January 2024, Never events to be reported to QSG on a monthly basis – December 2023 - Medicines safety including at the point transfer of care (medicines optimisation)- post-discharge community pharmacy review: report to be presented to PCCT QSI Group by March 2024 - Medicines safety including at the point transfer of care (medicines optimisation)- Get it on time medication and Electronic Prescribing: Update to be included in IMM report to QSG December 2023 - Understanding, measuring and reducing patient mortality Mortality review findings: To be reported to QSG March 2024 - Understanding, measuring and reducing patient mortality: Neonatal quality improvement: report to QSG March 2024 - Understanding, measuring and reducing patient mortality- Completion of audits: COEG annual report to include this in March 2024 - Using data and benchmarking intelligence to understand variation in outcomes: Bi monthly dashboard updates to report to QSG form December 2023

RISKS AND MITIGATIONS

- Peri-operative never events, PSC deep dives undertaken and all never events will now be reported to QSG on a monthly basis from November 2023.

ISSUES FOR ESCALATION

- Never events