2020 National Maternity Services HIW Improvement Plan

(November 2025 update)

Appendix C – Health board recommendations

As a result of the findings from this review, we have identified the following recommendations in the table below. Where applicable, the health boards should:

| 1. |  | Recommendation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ensure that women are aware of how they can request information or support in their language of choice. |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  | Action progress update |  |  | Responsible Officer | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Develop a directory for staff of all available maternity related leaflets in different languages to provide to women or signpost to an on-line service |  |  | On the labour ward forum workplan. Priority for the digital midwife |  |  | Digital Midwife | March 2024 | August 2024 update Work progressing - also commenced work on updating the maternity website 25.11.2025 Update Completed – the website now has the functionality of translating all pages into 29 different languages that are audible to the listener. |
| Identify 10 women whose first language is not English and undertake an audit of their All-Wales Maternity Record for evidence of access to interpreter services and other forms of information provision that have been offered. |  |  | This was tasked to community Matron pre Covid - however, there has been significant staff change since. This action will be revisited, and the Deputy HOM will progress urgently |  |  | Deputy Head of Midwifery (DHOM) | Original: April 2021 Revised: January 2024 | Completed 16th January 2024 |
| 2. | Recommendation |  |  |  |  |  |  |  |
| Ensure that wherever possible, women are able to communicate in their language of choice. |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  |  | Action progress update | Responsible Officer |  | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Identify 10 women whose first language is not English and undertake an audit of their All Wales Maternity Record for evidence of access to interpreter services, sign language (face to face or language line) and this has been available at each visit. |  |  |  | As above | DHOM |  | Original: May 2021 Revised: January 2024 | Completed 16th January 2024 |
| Maintain the Health Board interpreter services information is directly accessible from Maternity guidelines page (Wisdom) |  |  |  | Ongoing work in progress regarding information. | Matron Community and AN OPD |  | Completed | Completed |
| 3. | Recommendation |  |  |  |  |  |  |  |
| Consider how water birth options can be made available across all units. |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  |  | Action progress update | Responsible Officer |  | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Maintain the option for water birth in each Intrapartum Area within Swansea Bay UHB, |  |  |  | Two birthing pools available in the alongside midwifery led unit. One birthing pool available on labour ward. Neath Port Talbot Birthing Centre currently closed. | Consultant Midwife / Head of Midwifery |  | Completed | Completed |
| Secure capital funding for replacement of pool in NPT for upgrade as service degraded and porous |  |  |  | The initial bid for funding was not supported when considered alongside other health board service bids. A further Risk Assessment supported by IPC review will be undertaken. | Consultant Midwife / Service Manager |  | Original: March 2022 Revised: October 2023 | Completed Dec 2023 - Funding approved and pool ordered. |
| 4. | Recommendation |  |  |  |  |  |  |  |
| Take steps to ensure that women have contact with a consistent group of healthcare professionals, to improve continuity of care. |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  |  | Action progress update | Responsible Officer |  | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Collate baseline information for current continuity of care provision by community midwives |  |  |  | Completed at time of original response. | Consultant midwife |  | Originally Completed | Completed |
| Community service working group set up to review of working patterns to ensure community midwives caseloads and working practices support antenatal and postnatal continuity of care model |  |  |  | Nurse Group Director immersion into maternity services - paper presented at Management Board with recommendations. Workforce Transformation midwife employed and project board developed. Community Organisational Change Process (OCP) has been written and awaiting approval by Senior Management Team (SMT). Development of Band 3 Maternity Care Assistant role to support midwives in practice. | Head of Midwifery (HOM)/DHOM/Community Midwife (CM)/ Matron Community and Ante Natal (A/N) OPD. |  | Original: Sep 2021 Revised: March 2024 | Completed – new teams commence in March 2024 roster |
| Review of Obstetric antenatal clinic provision commenced in July 2020- delayed due to Covid pandemic. Group reconvened February 2021. Continuity of obstetric team to be included within the parameter of the review. |  |  |  | Once Obstetric and Community OCP complete this work will be reconvened. | Head of Midwifery / Clinical Lead / Service Group manager |  | Original: Sep 2021 Revised: March 2024 | In progress TOR being developed 25.11.2025 Update Completed – The ANC review completed an action plan which is being progressed and monitored via the Task and Finish Group; midwifery and medical staffing have been reviewed with job plans in progress in support of the ANC flow and functionality. Work ongoing to align midwives to consultant clinics. Midwifery sonography services are well established and supporting compliance with guidance and increasing capacity within the department. Current training opportunity open with HEIW to train another 1 wte midwife sonographer. Smoking cessation advisors are available in the ANC and across our services via our referral mechanism. |
| 5. | Recommendation |  |  |  |  |  |  |  |
| Consider the introduction of smoking cessation leads. |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  |  | Action progress update | Responsible Officer |  | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Maintain Public Health Midwife role to lead on smoking cessation. |  |  |  | A collaborative business case was completed between maternity / HMQ and Public Health Team and submitted to WAG, which was initially declined. A further business has been completed and submitted WAG. Currently awaiting funding decision. | Head of Midwifery |  | October 2023 | Funding approved from PHW – posts being advertised. Completed |
| Multi professional action plan developed for all staff to support smoking cessation activity in the Health board |  |  |  | Public Health midwife member of multidisciplinary of new Tobacco Control working group, chaired by Public Team to support smoking cessation across HB and WAG national ‘smoke free Wales – 2030 strategy’ | Public Health Midwife |  | Completed | Completed |
| Reintroduce CO monitoring in line with all Wales guidance (currently not in place due to Covid pandemic) |  |  |  | CO monitoring at routine antenatal appointments reinstated since July 2022. Recent snap shot survey identifies compliance low. Training opportunities for midwives made available. Training session delivered to all new MCA’s to support Midwives with screening and increase uptake of monitoring. | Public Health Midwife |  | Revised date: January 2023 Revised date: January 2024 | Recommenced Jan 2024 currently monitoring compliance Completed |
| Swansea Bay UHB to develop a strategy for informing women of the new legislation related to smoking on hospital grounds. To include; - Maternity helpline to advise women at first point of contact of the new legislation banning smoking on hospital grounds - Communication for service users and their families in relation to all Wales smoking ban in hospital. Posters for public information to be placed in public areas - Provide information on Health Board Facebook page for women and families in relation to the new law |  |  |  | Strategy was developed pre Covid pandemic | Head of Midwifery / Clinical lead / Service Group Manager |  | Completed | Completed |
| 6. | Recommendation |  |  |  |  |  |  |  |
| Consider working with Public Health Wales to further promote healthier living and lifestyles. |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  |  | Action progress update | Responsible Officer |  | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Swansea Bay UHB employ a Public Health Midwife to link with Public Health Wales. Public Health midwife will continue to collaborate with Public Health Wales on the Stop Smoking initiative for health gains among pregnant women |  |  |  | Public Health Midwife collaboration with Public Health Wales continues. | Public Health Midwife |  | Completed | Completed |
| Continue representation of Swansea Bay maternity service health professionals at national working groups who have core membership from Public Health Wales (e.g. Maternity and Neonatal network, 1st 1000 days). |  |  |  | Primary Care Weight Management Working group, including the development of a systems approach postnatal care pathway. Representation on the Early Years Pathfinder Steering group. Representation on Maternity and Neonatal Network workstreams and steering group. | HoM/ Clinical lead |  | Completed | Completed |
| To ensure specialist midwifery team who have a Public Health aspect to their role, work in collaboration with Public Health Wales to identify Quality Improvement Initiatives. |  |  |  | Public Health midwife participates in HB’s Weight Management Workshop. The workshop is chaired by Public Health Team with aim of development of adult weight management service in SBUHB. This aligns with healthy Weight Healthy Wales Strategy. Public Health Midwife leads on development / QI initiates with a focus on first 1000’s days | Deputy Head of Midwifery |  | Original: May 2021 Revised: May 2023 | Completed |

| 7. | Recommendation |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Ensure the appropriate level of breastfeeding advice, guidance, and support is provided at all times. |  |  |  |  |  |
| Initial action submitted |  | Action progress update | Responsible Officer | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Swansea Bay UHB will complete the BFI action plan as provided as an outcome of the assessment and reaccreditation review February 2021. |  | Review undertaken and accreditation achieved. | HoM/IFC | July 2021 | Completed |
| To develop a business case to increase the current provision for Infant feeding Coordinator (IFC) hours to full time in line with the Welsh Government infant feeding strategy and the BFI action plan (Currently have 0.5 WTE in post) |  | Employed for 18.5 hours now Increased 22.5 hours. Risk assessment been complete and SBAR to be submitted to Senior Management Team to increase to full time. | HoM/Service Group manager | Original: July 2021 Revised: September 2023 | Completed |
| Devise a development programme for midwife champions to support women with feeding choices in all clinical areas |  | Development of band 3 MCA role delegated to support infant feeding. 4 champions in community and 4 in the obstetric unit | Infant Feeding Coordinator | Completed | Completed |
| Maintain locality based infant feeding support clinics across Swansea Bay UHB |  | Support clinics continue across both Swansea and Neath. | Infant Feeding Coordinator | Completed | Completed |
| 8. | Recommendation |  |  |  |  |
| Review the adequacy and availability of perinatal and postnatal mental health support for women. |  |  |  |  |  |
| Initial action submitted |  | Action progress update | Responsible Officer | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Recruit to a new post for perinatal mental health midwife for Swansea Bay University Health Board. |  | Perinatal Mental Health Midwife recruited. | Head of Midwifery | April 2021 | Completed |
| Make the following improvement to the current perinatal mental health clinics: - A dedicated multi-professional team of obstetrician, midwife and mental health professional - Continuity of carers - Links with the Swansea Bay UHB mental health teams and primary care - Links with third sector services for referral and support e.g.(NSPCC/MIND) |  | Meetings in diaries to take this work forward Transformation work in line with Antenatal Clinic review National pathway for perinatal mental health implemented in HB – inc. screening tools. Referral process for provides support/upskilling sessions for midwives to discuss individual women with named perinatal mental health midwife, which includes opportunities to use the services of the 3rd sector Further work to develop a more dedicated multi-professional team is required – SBAR completed and options appraisal developed. | Clinical lead / Head of Midwifery / PRAMS / Perinatal mental health midwife | Original: December 2021 Revised: April 2024 | In progress to form part of the antenatal clinic service review 25.11.2025 Update – The service has a named Obstetric Consultant, Perinatal Mental Health Midwife and Mental Health professionals providing perinatal mental health support in Swansea Bay. There are established links within the HB with primary care and mental health teams. Further work and resource are required to fully implement the Perinatal Mental Health Pathway including the upskilling of our Maternity team and a business case is in progress for submission. The Maternity team have the access and pathway in place to support individual case discussions with the Perinatal Mental Health Midwife and wider team where cases are discussed at High-Risk Meetings as an MDT. |
| Complete a random sample of records for assurance all women with significant perinatal mental health issues have individualised care plan |  | A pre training notes audit was completed, but this was not around the inclusion of a mental health care plan as such, it was focussing on the inclusion of mental health enquiry and quality of documentation in the handheld records. | Deputy Head of Midwifery / Perinatal Mental Health Midwife | completed | Completed |
| Complete a Training needs analysis to assess midwife skills & confidence to provide care for women with PNMH issues |  | A training needs questionnaire went out during the scoping exercise before the introduction of the Perinatal Mental Health (PNMH) Role. The recommendations from the Perinatal network is that midwives are offered the opportunity to attend the multi professional Institute of Health Visiting Perinatal and Infant Mental health training delivered by the local champion group within Swansea Bay. Given the staffing challenges which prevents uptake, an approach has been taken to offer individual midwives and obstetricians consultation spaces with the PNMH midwife to case discuss, which offers an opportunity for individualised upskilling of the maternity workforce, whilst offering supervision. | Deputy Head of Midwifery / Perinatal Mental Health Midwife | completed | Completed |
| 9. | Recommendation |  |  |  |  |
| Consider the introduction of PRAMS across its services. |  |  |  |  |  |
| Initial action submitted |  | Action progress update | Responsible Officer | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Swansea Bay University Health Board has a well-established PRAMS service. Maintain Senior maternity representation at the PRAMs steering group toward Future perinatal mental health service development. |  | PRAMs Service continues to operate. Following changes within service, current HOM not on steering group. Awaiting re-establishment of a steering group – need to confirm midwifery representation on that group with PRAMS lead. | Head of Midwifery | Originally Completed Revised date: March 2024 | Completed |
| 10. | Recommendation |  |  |  |  |
| Ensure that staff are able to access bereavement training in a timely manner. |  |  |  |  |  |
| Initial action submitted |  | Action progress update | Responsible Officer | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Training for post mortem consent maintained during the pandemic using TEAMS for initial and update training |  | Training continues to be in place. | Bereavement midwife | Completed | Completed |
| Develop and maintain a central database of health professional who have completed the training in PM consent |  | Database of trained staff in place. | Bereavement midwife | Completed | Completed |
| Develop bereavement Champions in all clinical areas of the service. |  | Champions now in place in clinical areas. | Bereavement midwife | Completed | Completed |
| Bereavement Midwife to present at all health professional induction programme into the health board |  | Bereavement presents on induction training programme. | Bereavement midwife | completed | Completed |

| 11. |  | Recommendation |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Consider what steps can be taken to ensure that learning from women’s experiences can be improved, with a particular focus on sharing what has changed in response to feedback. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  | Action progress update |  |  | Responsible Officer | Timescale |  |  | Action Status (Complete/In Progress/Not Actioned) |
| Engagement Strategy “Maternity Voices partnership ” action plan developed for introduction in 2021 |  |  | Appointed Chair and Vice chair Launch event Attending Maternity Forums and meetings. Annual action plans. Established the SBMVP Board meetings underway. Annual report 2023 Recruitment underway for maternity service user representatives. |  |  | Consultant midwife | September 2021 |  |  | Completed |
| All clinical areas to have a lead midwife for Womens feedback who must maintain the “YOU SAID WE DID” poster board in all public areas |  |  | Feedback boards in clinical areas Ipads and QR codes given to women and their families to feedback regarding services. Feedback boards in clinical areas. Governance process includes asking women for feedback and comments to include in reviews. |  |  | Deputy HoM/ Maternity Matrons | Completed |  |  | Complete |
| Continue to monitor the Swansea bay UHB Maternity service Facebook page for feedback and follow up- |  |  | A team of administrators who review and respond to comments and direct messages, signposting as required. |  |  | Consultant Midwife | Completed |  |  | Completed |
| 12. | Recommendation |  |  |  |  |  |  |  |  |  |
| Consider strengthening arrangements for sharing patient stories at board and quality and safety committees. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  |  | Action progress update | Responsible Officer |  |  | Timescale | Action Status (Complete/In Progress/Not Actioned) |  |
| Identify staff to develop and train to undertake patient stories within maternity services. |  |  |  | 2 members of staff have been trained with others to be identified. | Deputy HoM |  |  | July 2021 | Completed |  |
| Maintain a repository of patient stories available to the corporate team for use in relevant multi-professional forums |  |  |  | Due to staffing escalation difficulty in release trained midwives to take patient stories. Plan going forward to have one a quarter. | Consultant Midwife/Strategy team |  |  | Original: July 2021 Revised: April 2024 | Completed |  |
| Appoint to the “Maternity Voices partnership ” following approval |  |  |  | As discussed above, chair and vice chair appointed. In the process of service user representatives recruitment. | Consultant midwife |  |  | September 2021 | Completed |  |
| 13. | Recommendation |  |  |  |  |  |  |  |  |  |
| Ensure the ongoing monitoring in line with health board policy of neonatal resuscitaires and emergency medical equipment. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  |  | Action progress update | Responsible Officer |  |  | Timescale | Action Status (Complete/In Progress/Not Actioned) |  |
| The operational leads will monitor the daily check and is reviewed as part of the matron monthly assurance audit. Increase monitoring frequency where compliance is not at required standard |  |  |  | Monthly assurance/ audits are saved as evidence and assurance. | Midwifery Matron |  |  | Completed | Completed |  |
| Purchase a new resuscitaire funded from capital for Neath Port Talbot Birth Centre |  |  |  | New Resuscitative purchased for Neath Port Talbot Birth Centre, to replace old so that all resuscitaires are same throughout Maternity services. | Midwifery Matron |  |  | Completed | Completed |  |

| 14. | Recommendation |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ensure staff awareness of procedures and responsibilities to follow in the event of a medical emergency. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  | Action progress update |  | Responsible Officer |  |  | Timescale |  | Action Status (Complete/In Progress/Not Actioned) |
| Prepare annual plan for Skills and drills to be undertaken in the clinical areas |  |  | Intrapartum Lead taking the lead on annual training plan. |  | Training and education lead / fetal surveillance leads / PROMPT leads |  |  | Completed |  | Completed |
| All health professionals in maternity to undergo annual PROMPT training and report 100% compliance of mandated available staff to Welsh Risk Pool |  |  | Revised Action: Service to ensure improved uptake of PROMPT training by relevant health professionals in order to achieve the national 95% target. |  | SBUHB PROMPT |  |  | Original: August 2021 Revised: September 2024 |  | Completed |
| All maternity service health professionals undergo annual BLS and ALS training |  |  | BLS annual training continues. |  | CPD/Education leads |  |  | Completed |  | Completed |
| All staff undergo managing medical/obstetric emergencies during their induction period |  |  | All new staff receive PROMPT training during their first 6 months as part of induction. |  | CPD/Education leads |  |  | Completed |  | Completed |
| Train 4 additional midwives to become NLS trainers at earliest opportunity to develop a sustainable training service for all midwives and doctors undergo NLS training |  |  | We have sent 15 midwives on the NLS course so far this year filling all available spaces, with 4 midwives identified to complete the Generic Instructors Course to teach on our NLS updates on the upcoming M & S days. We are waiting on dates for the next available Generic Instructors Course (GIC) courses for them to attend to become trainers. We have 2 further dates this year for NALS training which 10 midwives have already been allocated. Neonatal team supporting training midwives. |  | HoM/Service manager |  |  | March 2022 |  | Completed |
| 15. | Recommendation |  |  |  |  |  |  |  |  |  |
| Ensure staff awareness of procedures and responsibilities to maintain the safety of the women using water birthing facilities. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  | Action progress update |  | Responsible Officer |  |  | Timescale |  | Action Status (Complete/In Progress/Not Actioned) |
| Guideline developed on use of water for birth |  |  | Guideline available on WISDOM |  | Consultant midwife |  |  | Completed |  | Completed |
| Evidence pool evacuation training and maintain training log for required staff attendance |  |  | Training video available to staff on Z drive |  | Consultant midwife |  |  | Completed |  | Completed |
| Produce a video for training purposes of pool evacuation for all staff to access |  |  | Training video available to staff on Z drive. |  | Consultant midwife |  |  | completed |  | Completed |
| 16. | Recommendation |  |  |  |  |  |  |  |  |  |
| Ensure that a clutter free and safe environment is maintained across units. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  | Action progress update |  | Responsible Officer |  |  | Timescale |  | Action Status (Complete/In Progress/Not Actioned) |
| Maintain Monthly environmental assurance audit |  |  | Monthly audits undertaken and results maintained on file. |  | Operational lead midwives/matrons |  |  | Completed |  | Complete |
| Plan environmental area inspections with the Fire safety officer for clinical areas as standard |  |  | Completed on CDS, ward 19 and ward 20, Antenatal Clinic Neath Port Talbot and Singleton. |  | Matrons |  |  | March 2022 |  | Completed |
| Ensure a 100% of available staff are compliant in the following mandatory training: - Fire safety - Manual handling |  |  | Staff would have had access to virtual fire safety training via ESR at time of initial action. Revised action: Service to ensure improved uptake of fire safety training by all Health Care Professionals in order to achieve national target. |  | CPD lead midwife |  |  | April 2021 Revised: March 2024 |  | Completed |
| 17. | Recommendation |  |  |  |  |  |  |  |  |  |
| Ensure adequate infection control measures are in place, and adhered to. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  | Action progress update |  | Responsible Officer |  |  | Timescale |  | Action Status (Complete/In Progress/Not Actioned) |
| Maternity services will introduce an IP&C monitoring and improvement group |  |  | IP&C Maternity meetings introduced. Due to Covid and staffing unavailability these meetings have been postponed on occasions. Revised action: For Maternity meetings planned bi monthly. |  | Deputy Head of Midwifery |  |  | April 2021 (Completed originally) Date for Revised Action: July 2023 |  | Complete – new IPC meetings booked for 2024 |
| All clinical areas will complete monthly environmental audits |  |  | Monthly environmental audits in clinical areas completed by ward managers and feedback to matrons. |  | Deputy Head of Midwifery |  |  | completed |  | Completed |
| Each clinical area to have a minimum of two handwashing assessors |  |  | Handwashing assessors trained at time of action. Further staff identified to undergo training to enable assessment in all clinical areas. |  | Operational lead midwives/matrons |  |  | May 2021 (Completed at time of action) Date for Revised Action: March 2024 |  | Completed |
| Letter sent to all staff to inform them to complete the required e-learning by March 31st 2021 |  |  | Letter was sent to all staff at time of original action. Revised action: Matrons developed action plan to ensure that all staff have completed required E-Learning |  | Head of Midwifery Matrons |  |  | Completed at time of original action Date for Revised Action: March 2024 |  | Completed |
| Datix reporting of hospital acquired infections and completion of required RCA’s |  |  | Staff continue to report and investigate hospital acquired infections. |  | Midwifery Matron |  |  | Completed |  | Completed |
| Ensure a 100% of available staff are compliant in the following mandatory training: Level 2 Infection prevention and Control |  |  | Compliance low in staffing groups- action plan developed by Matron and area leads, to improve compliance. |  | Matrons / Area Leads / PDM |  |  | April 2021 Revised dates: March 2024 |  | In progress July 2024 update Level 1 Completed / Level 2 at 77.4% 25.11.2025 Update Completed – Compliance figures of all available staff improved and maintained. Level 1 97.12%, Level 2 93.93% both well above the 85% compliance required. |
| 18. | Recommendation |  |  |  |  |  |  |  |  |  |
| Ensure the safe storage of COSHH substances at all times. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  | Action progress update |  | Responsible Officer |  |  | Timescale |  | Action Status (Complete/In Progress/Not Actioned) |
| Maternity services will introduce an IP&C monitoring and improvement group |  |  | Bi monthly meetings commenced at time of the action. Due to Covid and staffing unavailability due to clinical requirements, meetings postponed. Revised action: Recommencement of Bi monthly meetings. |  | Deputy Head of Midwifery |  |  | April 2021 (Completed at time of action) Revised date: July 2023 |  | Completed |
| 19. | Recommendation |  |  |  |  |  |  |  |  |  |
| Ensure that staff are aware of their responsibilities in relation to the safe storage of medication. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  | Action progress update |  | Responsible Officer |  |  | Timescale |  | Action Status (Complete/In Progress/Not Actioned) |
| Maintain monthly Controlled drug audits are undertaken in relevant clinical areas |  |  | Monthly CD audits completed, evidence saved on file |  | Operational lead midwives/matrons |  |  | Completed |  | Completed |
| Maintain monthly assurance checks in all clinical areas to ensure: - All medicines are locked in a secure cupboard in a secure clinical room - All medicines trolleys are locked and secure - Lockable cupboards available in bedside lockers if self-administration of medicines used |  |  | Part of monthly assurance checks and reviews of storage continues. |  | Operational Lead midwives/matrons |  |  | Completed |  | Completed |
| All midwives who are employed by Swansea bay UHB will undergo medicines management training on their induction programme to comply with medicines policy for safe storage of medication |  |  | Medicine management training continues for new staff. |  | CPD lead |  |  | Completed |  | Completed |
| Ensure Health Board Policy available to all staff |  |  | Medicine management policy available to all staff on COIN. |  | Operational lead midwives/matrons |  |  | Completed |  | Completed |
| 20. | Recommendation |  |  |  |  |  |  |  |  |  |
| Ensure that the prescription and administration of medication for the induction of labour is done in line with health board policy. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  | Action progress update |  | Responsible Officer |  |  | Timescale |  | Action Status (Complete/In Progress/Not Actioned) |
| To update the Induction of Labour Policy |  |  | Induction in labour policy updated – available on WISDOM Further action: Due for update June 2023 |  | Clinical Director |  |  | Completed |  | Completed |
| Update the information leaflet for women |  |  | Information leaflet updated –Available on WISDOM and shared with women. Further action: Currently updating working with MVP. |  | Clinical Director |  |  | Completed |  | Completed |
| Obstetrician to review all women undergoing IOL on a daily ward round |  |  | Daily ward consultant ward rounds continue on the antenatal ward. |  | Clinical Director |  |  | Completed |  | Completed |
| Maintain delays in Induction of labour on the risk register- update three monthly |  |  | All delays in induction of labour are reported through Datix and attached to risk register, which is reviewed. |  | HoM/Clinical lead/Service manager |  |  | Completed |  | Completed |
| Ensure Datix reports are completed for all women who experience delays in transfer to labour ward in a timely manner |  |  | As above |  | Operational leads |  |  | Completed |  | Completed |
| Undertake a service evaluation using 20 sets of records to ensure compliance with the administration of medication for IOL is in line with health board policy |  |  | Audit not fully carried out due to staffing unavailability and requirement to work clinically. Revised action: audit to be undertaken. |  | Governance lead |  |  | Original: April 2021 Revised: January 2024 |  | Completed |
| 21. |  | Recommendation |  |  |  |  |  |  |  |  |
| Ensure women have access to Female Genital Mutilation clinics. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  | Action progress update |  |  |  | Responsible Officer | Timescale |  | Action Status (Complete/In Progress/Not Actioned) |
| Maintain dedicated clinic for women with FGM |  |  | Identified Obstetric consultant to care for women with FGM, women assigned to their clinic for review and management of care. |  |  |  | Lead Obstetrician FGM clinic/antenatal clinic lead midwives | Completed |  | Completed |
| Undertake a service evaluation of FGM clinic management to include: - Appropriate referrals to the dedicated clinic - Health professional knowledge and management of safeguarding issues including handover to health visitor when female child |  |  | SBUHB do not currently hold an FGM clinic but have an allocated Obstetric Lead to see women. Referral process in place and assessment tool. |  |  |  | Lead Obstetrician FGM clinic/antenatal clinic lead midwives | June 2021 |  | Completed |
| Provide a training update for all midwives for issues related to FGM for 2021/22 year |  |  | Training provided for all available midwives 2021/2022. |  |  |  | Safeguarding lead midwife | March 2022 |  | Completed |
| 22. | Recommendation |  |  |  |  |  |  |  |  |  |
| Ensure learning and service improvement actions are implemented following incidents, concerns of audit, is effectively shared with staff across all sites. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  |  | Action progress update |  | Responsible Officer |  |  | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Develop a Quality Improvement Notice Board in every clinical area. Ward leads and community leads to ensure a staff board is prepared and maintained. |  |  |  | The following boards are being implemented in clinical areas, Communication Board Theme of the month Guideline update board Periprem boards Training and Education board |  | Matron / operational lead / governance midwife / intrapartum lead |  |  | Revised Date: January 2024 | Completed |
| Notice Boards to be reviewed monthly during the matrons assurance audit |  |  |  | This will be added to assurance audits from September 2023 |  | Matrons |  |  | Original: June 2021 Revised Date: January 2024 | Completed |
| 5 midwives to be asked each month if they have received communication related to learning which can include: - Wellbeing service access - Safety briefs - Newsletter - Use of email - Learning events - Themes and trends |  |  |  | Added assurance audits: 5 midwives asked regarding seeing newsletters, themes and trends and learning from safety briefs that have been released. Wellbeing service access shared via emails and asked during any sickness episodes and in PADRs. |  | Matrons |  |  | Completed | Completed |
| Register of attendance at monthly audit meetings to be maintained |  |  |  | Meetings are on teams which are recorded. |  | Audit leads |  |  | Completed | Complete |
| 23. | Recommendation |  |  |  |  |  |  |  |  |  |
| Ensure that steps are taken to encourage staff to speak up and report incidents without fear of reprisal or repercussion. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  |  | Action progress update |  | Responsible Officer |  |  | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| All staff to receive introduction to Datix reporting during their preceptorship period in the health board |  |  |  | All staff receive introduction to Datix on induction from governance team. |  | CPD lead midwife/ Governance team |  |  | Completed | Completed |
| Midwives are appointed a Clinical Supervisor for Midwives and line manager in each of the clinical areas. |  |  |  | Action in place as described |  | Matron/CSfM Operational Leads |  |  | Completed | Completed |
| Maintain an excellent reporting culture to include; - CSfM’s prepare quarterly report of themes and trends to HoM - Maintain positive relationships through established forum with workplace representatives - Ensure all staff are aware of the health board Guardian service - Maintain Manager on call rota’s for maternity services - Ensure all clinical leaders maintain “open door” practice - Maintain Consultant on call rotas to support medical staffing in relation to escalation/jump call reporting - Maintain feedback to staff when an incident is being closed of actions taken. |  |  |  | Action in place as described |  | HoM/Clinical Lead |  |  | Completed | Completed |
| 24. | Recommendation |  |  |  |  |  |  |  |  |  |
| Ensure the timely implementation of a single maternity dashboard across Wales. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  |  | Action progress update |  | Responsible Officer |  |  | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Maintain multi-professional representation within the clinical maternity and neonatal network toward dashboard development |  |  |  | Workstream currently paused due to development of Digital Maternity Cymru. Members are on distribution lists for engagement as this work progresses. |  | HoM/Clinical Lead/Consultant midwife |  |  | completed | Completed |
| 25. | Recommendation |  |  |  |  |  |  |  |  |  |
| Ensure that policies and procedures are updated, ensuring staff are aware of updates to maintain the delivery of safe and effective care. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  |  | Action progress update |  | Responsible Officer |  |  | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Maintain oversight of policy and guidance at all clinical forums pertaining to their sphere of practice. |  |  |  | Guidelines and policy oversight are on agenda in relevant forums. Revised action: Future plan will to be to develop a guideline and policy forum to have more robust oversight. |  | Forum leads Consultant Midwife |  |  | Completed Revised date: October 2023 | Completed |
| Ensure all new and revised guidelines (once ratified) are reported via the maternity MDT Quality and Safety group |  |  |  | All new and revised policies and guidelines are taken to Maternity Quality and Safety Forum and shared with staff groups. |  | Forum Chairs, Clinical Lead, HoM, Service Manager |  |  | Completed | Completed |
| Forum Chair to ensure all ratified guidance is available to all staff via WISDOM |  |  |  | Forum chairs are responsible to ensure uploaded to Wisdom, so staff can access easily. |  | Forum Chair |  |  | June 2021 | Completed |
| Develop a notice board to advertise all updated policies in each clinical area for all staff |  |  |  | Guidelines are shared in clinical areas and put up on communication boards. Guideline Boards to be implemented in all clinical areas. |  | CSfM/ Intrapartum Lead/Governance Lead. Ward Managers |  |  | October 2023 | Completed |
| Any new or amended guidelines are communicated to staff via email and the quarterly newsletter |  |  |  | All amended guidelines shared via emails, discussed on daily safety briefs at handovers in all clinical areas. |  | Governance team/CSfM |  |  | completed | Completed |
| 26. | Recommendation |  |  |  |  |  |  |  |  |  |
| Ensure all midwives complete appropriate training before being required to assist in theatre. |  |  |  |  |  |  |  |  |  |  |
| Initial action submitted |  |  |  | Action progress update |  | Responsible Officer |  |  | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Multi-professional working group convened to review obstetric theatre staffing requirements and present option appraisal presented to service directors |  |  |  | Option appraisal was completed. Now part of the Midwifery Transformation Board. |  | D/HoM Senior Matron Theatres |  |  | Completed | Completed |

| 27. | Recommendation |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Consider the implementation of champion midwives to support further innovation and research. |  |  |  |  |  |
| Initial action submitted |  | Action progress update | Responsible Officer | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Maintain funded post for Research team in partnership with Swansea University to deliver and maintain an active research programme |  | Research team consists of band 7 lead and two band 6 midwives, funded by Research and Development. | Consultant Midwife Research and Development Lead. | Completed | Completed |
| Maintain Consultant Midwife and Obstetric Consultant lead for research |  | Consultant midwife and Lead Obstetrician for research in place. | Clinical lead/HoM | Completed | Completed |
| Develop champion midwives in various aspects of the midwifery service to support midwife specialists |  | Bereavement, Infant feeding coordinator and diabetes champions in place. | Specialist midwives | Completed Further Action Date: April 2024 | Completed – new roles being identified and developed |
| 28. | Recommendation |  |  |  |  |
| Consider the introduction of live stream CTG monitoring in all units. |  |  |  |  |  |
| Initial action submitted |  | Action progress update | Responsible Officer | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Gain confirmation for Capital funding for central monitoring system to be introduced in 2021 |  | Funding was confirmed, a system procured and Implemented in June 2023. | Clinical lead/Head of Midwifery/Service Group manager | Completed | Completed |
| Complete evaluation of introduction of Fetal surveillance midwife (evaluation of year 1) |  | Fetal Surveillance role evaluated after a year and is now permeant. | Clinical lead/Head of Midwifery/Service Group manager | May 2021 | Completed |
| 29. | Recommendation |  |  |  |  |
| Ensure that staff have timely access to the training that is required for them to carry out their roles effectively. |  |  |  |  |  |
| Initial action submitted |  | Action progress update | Responsible Officer | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Maintain the Multi-professional Training and education Group established to lead on maternity service training availability. Their role is to - Devise the training programmes - monitor compliance with mandatory training - monitor when staff are called off training for clinical need - identify themes and trends for preparation and delivery of updates where issues arise - review feedback from training for continual evaluation and improvement |  | Training and education is a multidisciplinary forum and training programmes are developed around clinical need and identified themes and trends from incidents. | Clinical Lead/Head of Midwifery/Service Group manager CPD and Obstetric lead PROMPT Leads Fetal Surveillance leads | Completed | Completed |
| 30. | Recommendation |  |  |  |  |
| Review their workforce plans to ensure appropriate actions are being taken to address the impact of staff working excessive hours, and any shortfall across staff groups. |  |  |  |  |  |
| Initial action submitted |  | Action progress update | Responsible Officer | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Monitor and rearrange the teams in line with the Birthrate plus conducted in Swansea Bay October to December 2020 |  | Initially completed Further Birthrate plus assessment in 2022- Workforce Transformation programme commenced to monitor and develop appropriate staffing and skill mix in all areas in Maternity Services. | HoM | September 2021 (completed previously) Further Action Date: December 2023 | Completed – new teams established and commence in March roster |
| Establish a baseline of current working practices and measure against EWTD and service requirements |  | Established baseline of current working practices. Continued work reviewing service through Midwifery Transformation Board. | HoM/Matrons | Completed | Completed |
| Complete baseline assessment to review current practice and consider alternative models of service delivery where needed |  | Delayed due to covid and staffing unavailability. However an assessment has been undertaken and the Workforce Transformation Programme is Underway. | HoM/Matrons | Sept 2021 originally Revised Date: May 2023 | Completed |
| Maintain RCOG obstetric staffing standards at consultant level. Middle grade and junior gaps- covering with locums where available |  | Compliant with RCOG obstetric staffing levels. | Clinical lead/Service manager | completed | Completed |
| Ensure anaesthetic staffing within OOA standards |  | Anaesthetic staffing levels in line with OOA standards but are partially met for the split of Elective and Emergency Caesarean Sections. | Anaesthetic lead | completed | Completed |

| 31. | Recommendation |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Consider implementation of positive initiatives to recognise the good work carried out by staff within the midwifery and medical teams. |  |  |  |  |  |
| Initial action submitted |  | Action progress update | Responsible Officer | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Ensure Feedback given to staff when compliments received |  | Feedback given to staff with regards to complaints through line managers, senior leads and CSfM. | HoM/D HoM/Matrons/Clinical lead | Completed | Completed |
| Work with the local Royal College of Midwives workplace representatives to support the “random acts of kindness” initiative, |  | Stopped due to Covid and shortly due to resume due to efforts to reignite local RCM Branch. Caring for you REP x2 recruited awaiting affiliation, will undertake Employee of the Month and also monthly act of kindness staff wellbeing. | HoM/DHoM/Matrons RCM workplace representatives | Completed at time of original action. Revised date: January 2024 | completed |
| Ensure Feedback positive good practice messages to groups and individuals from learning events |  | Positive feedback is shared with groups and individuals verbally and through emails. | Governance lead midwife | Completed | Completed |

| 32. | Recommendation |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Ensure that a high standard of documentation is maintained, in particular ensuring that the standard of patient records is improved. |  |  |  |  |  |
| Initial action submitted |  | Action progress update | Responsible Officer | Timescale | Action Status (Complete/In Progress/Not Actioned) |
| Clinical Supervisors for midwives (CSfM) to complete annual record audit |  | CSfM team provide annual report and audits. Not completed for 2021/2022 due to internal audit process. | CSfM | March 2021 Revised date: April 2024 | Completed |
| Action plan from audit findings to be developed toward improvement |  | Record keeping Audit analysis for 2020/2021 undertaken by CSfM. Learning presented to staff. | CSfM | May 2021 | Completed |
| Ensure monthly assurance audit for notes and bundles completed |  | Area leads complete monthly audits of notes and bundles. | Matrons | Completed | Completed |
| Development of bundle booklet to replace loose sheets |  | Awaiting booklet to be printed | Operational Lead Labour Ward | Original: June 2021 Revised: January 2024 | completed |
| Maintain Safeguarding files in electronic format and centrally held – complete annual audit of compliance with safeguarding records |  | Safeguarding files are now electronic and held centrally. Audits of the Sharing information. (SIP 1,2 and 3) | Safeguarding lead midwife | Completed | Completed |

Updated November 2025