Report Recommendations - Action Plan

| # | Recommendations |  |  |
| --- | --- | --- | --- |
| 1 | Health boards must support people to develop an individual crisis plan to aid them in seeking further support when required. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: Crisis plans are integral to CTP for known service users. An audit cycle to monitor the quality of CTPs and crisis plans has been implemented. Each caller to the 111 press 2 service will have an action plan on how to access services if a crisis develops again. | Directorate Manager/Lead Nurse | August 2022 July 2022 |
| 2 | Health boards must take steps to improve the timeliness of assessment or intervention following referral to mental health statutory service (such as LMPHSS and CMHT) whilst also considering how people are supported in the community whilst awaiting assessment or intervention. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: SBUHB LPMHSS service continues to meet the Part 1 waiting target of 28 days. Each CMHT operates a Duty System allowing urgent appointments to be expedited according to risk or need. Via the 111press 2 service OT are delivering a structured programme of intervention whilst service users are awaiting intervention or assessment from CMHT or LMPHSS. | Directorate Manager/Lead Nurse/Lead OT | May 2022 July 2022 |
| 3 | Health boards must ensure that clear processes are in place to ensure that physical health assessments and monitoring is undertaken for relevant patients under the Mental Health (Wales) Measure 2010. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: The CMHTs run physical health care clinics supported by pharmacy colleagues. MHSIF (22/23) was used to appoint 3 HCSWs to support the clinics. Oversight is held at a local level (CMHT) and via the monthly community operational managers group. | Lead Nurse MH, service development and Transformational Manager | Originally: Aug 2022 (Funding) Aug 2022 (Review of clinics) Completed: March 2023 |
| 4 | Health boards and GP services must consider how communication between different teams in primary care can be improved and strengthened, to ensure prompt mental health advice and efficient and timely referral processes. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: There are mental health link workers allocated to each GP clusters and working within GP practices who will identify and offer appropriate intervention and referral into MH services. Each cluster has an identified senior manager link from the MH Division’s senior team. Regular meetings are held between the Mental Division and Primary Care leads to identify issues or concerns to improve access and pathways. SBUHB uses Consultant Connect allowing rapid advice from a range of hospital consultants. | Associate Director and MH, service development and Transformational Manager | May 2022 |
| 5 | Health boards must consider how arrangements can be strengthened to ensure primary care professionals are able to access timely specialist advice on mental health conditions, appropriate treatments and medication. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Single Point of Access (SPOA) offers a professional line where primary care professionals are able to seek advice or refer into services. This phone is manned by a registered mental health practitioner who will triage the need and make an onward referral. The triage is processed by the use of an evidenced-based triage tool (UK Mental Health Triage tool). | Associate Director and MH, service development and Transformational Manager | May 2022 |
| 6 | Health boards need to consider how they can strengthen linkages between services to improve access and provision for individuals needing support for their mental health and well-being. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | The West Glamorgan Regional Partnership group is leading on establishing priorities for all partners in order to deliver a joined-up service for individuals who need emotional and well-being support. | Associate Director and MH, service development and Transformational Manager | July 2022 |
| 7 | Health boards and GP services must ensure that there are clear and robust follow up processes in place to ensure timely and appropriate follow up for people who have received crisis intervention, and are not subsequently admitted in to hospital. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | If a person has received a period of crisis intervention delivered by the Crisis Resolution &Home Treatment Team they would receive advice on discharge on how they can re-access services in light of a relapse. Following discharge, the person’s GP would receive a notification of discharge and summary of intervention. Adastra is also used to record information about an episode of care and send further information/details to the service users GP ensuring continuity of care. Updated: Standard operational policy has been developed by directorate manager for individual who are not Care Co-ordinated to feed directly back to GP’s | Associate Director and MH, service development and Transformational Manager Directorate manager | May 2022 July 2022 |
| 8 | Health boards need to consider how they can strengthen the role and involvement of the third sector to improve the range of provision for individuals needing support for their mental health and well-being. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: MH, service development and Transformational Manager linked with the third sector to map out current provision available to eliminate duplication of services. Health Board is working in partnership with West Glamorgan Regional Partnership to develop a strategic Framework for Adults. | MH, service development and Transformational Manager | September 2022 |
| 9 | To prevent the requirement for multiple referrals, health boards must ensure that referral processes are clear to all services, and when appropriate, a single point of access to the range of health board mental health services is implemented to support referral and patient options. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: SPOA is operational and receives referrals from a range of health care professionals. 111 press 2 now provides an open access platform for people and their carers to speak directly to a registered mental health practitioner who will be able to offer support, advice and make an onward referral for the intervention if required. | Associate Director and MH, service development and Transformational Manager | July 2022 |
| 10 | Health boards should review the community mental health services available in their localities, to ensure that services focus on individualised needs of people to prevent a deterioration in mental health, and to provide timely care and support in all community services when required. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: SPOA is operational and receives referrals from a range of health care professionals. 111 press 2 now provides an open access platform for people and their carers to speak directly to a registered mental health practitioner who will be able to offer support, advice and make an onward referral for the intervention if required. In addition, the performance scorecard within the directorate captures the performance of all community mental health teams and outpatient services. As part of a MH & LD Service Group modernisation board the Associate Service Director for MH and LD is leading the Community Mental Health Services modernisation work-stream, which will commence in January 2025. Updated: The Nurse Director for MH&LD Service Group chairs the Scheduled Care Modernisation Work Stream. This work stream is responsible for providing oversight and assurance to the Adult Mental Health Modernisation Service Board in respect of all matters relating to current service provision, demands on the services and what modernisation is required to make the services sustainable and fit for purpose. | Associate Service Director for MH & LD. | Originally: Aug 2022 Revised: June 2025 Revised: November 2025 |
| 11 | Health boards and Welsh Government should consider benchmarking mental health services across Wales to identify good practice and positive initiatives and to share learning. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: Links have been made with Cardiff and Vale and visits taken place to identify best practice particularly around in-patient services. The Mental Health Service Development and Transformational Manager leads the MH benchmarking group for SBUHB. The HB engages in the annual benchmarking programme. | MH, service development and Transformational Manager & Directorate Manager | August 2022 |
| 12 | All health boards should consider how mental health crisis teams can be more accessible to emergency services, to help provide advice and/or timely care and support to people with urgent mental health needs. |  |  |
|  | Action Plan | Responsible person: | Date for completion: |
|  | Updated: SBUH has a professional’s line in place offering direct access to the Single Point of Access Mental Health practitioner. This ensures that the professional can obtain timely advice on a person in their care and tailor intervention accordingly. This might be a police officer, social worker, GP, paramedic or any other professional. SBUHB commissions a sanctuary for those individuals requiring out of hours practical and therapeutic support whilst experiencing a mental health crisis. There is now a sanctuary service in the Swansea and NPT localities commissioned from Adferiad. There are established pathways between CRHT & WAST & SWP | Associate Director and MH, service development and Transformational Manager | May 2022 |
| 13 | Health boards, emergency services and primary care services should consider how mental health staff can be incorporated within emergency call handling teams across Wales, to enable early advice and support to people who need urgent care or support for their mental health. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: Pathways are currently in place between CRHT, SWP and WAST (Reviewed as part of the Crisis Care Concordant) | Associate Director and MH, service development and Transformational Manager | May 2022 |
| 14 | Health boards should ensure clear advice and information is available and promoted to people with mental health needs, to help maximise their knowledge about additional support services available within the community including the third sector. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: SBUHB has developed the Sorted and Supported website in conjunction with the third sector. This is an online tool for service users exploring mental health and wellbeing issues and offers advice and information about how and where support can be accessed. It is also a useful resource for professional to navigate a range of services. | MH, service development and Transformational Manager | July 2022 |
| 15 | Health boards should consider how they can strengthen collaboration with third sector organisations to enable appropriate direct referrals in to NHS mental health services when required. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: 111 press 2 enables third sector organisations to refer directly into mental health services and allow an onward referral made to the most appropriate services. | Associate Director MH, service development and Transformational Manager | August 2022 |
| 16 | Health boards should ensure that single point of access services are implemented across Wales and is accessible to all professionals and public to help facilitate prompt support and care for people with mental health needs. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: SBUHB went live with 111#2 in August 2022. This service is accessible to anybody requiring mental health support, ensuring that they are put on the most appropriate pathway. SBUHB operates a Single Point of Access to health professionals via the use of a professional line, offering support and advice to professionals wishing to seek information from a mental health practitioner. | Associate Director and MH, service development and Transformational Manager | July 2022 |
| 17 | Health boards must consider how to support and embed the mental health practitioner roles further and ensure that they can link directly into a seamless mental health pathway. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: SBUHB have GP cluster workers and well-being link workers who are able to link directly with the SPOA professional line. | Associate Director and MH, service development and Transformational Manager | May 2022 |
| 18 | Health boards should consider how adults with urgent mental health needs, and who are experiencing mental distress, can easily access safe places in the community, which can provide a calm and safe space in a less clinical setting as an alternative to hospital admission or contacting emergency services. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: SBUHB currently provides a sanctuary. The sanctuary is based in Swansea and offers advice and intervention out of hours to residents of Swansea Bay. As part of MHSIF (22/23) SBUHB is expanding this service and identifying suitable accommodation in Neath/Port Talbot to offer a second sanctuary. The NPT Sanctuary opened in April 2024 | Directorate Manager, MH, service development and Transformational Manager | May 2022 August 2022 |
| 19 | Health boards, and Public Health Wales, should consider what additional steps can be taken to raise mental health support awareness in men, to support their mental well-being and signposting to support services. |  |  |
|  | Action Plan: | Responsible person: | Date for completion: |
|  | Updated: MH, service development and Transformational Manager reviewed current services available to men to support mental health wellbeing. Review and ensure that the Sorted and Supported website also offers support to the male population. The Sorted and Supported website launched in October 2024 The local 111press 2 campaign will ensure it targets the male population through local football and rugby clubs along with barbers and GP surgeries via the Local Cluster Collaborative forums. The 111 Press 2 Service is also sharing information regularly with the above stakeholders. | MH, service development and Transformational Manager | Completed: October 2024 |

| Action Plan Completed by: | Dermot Nolan (progress update) |
| --- | --- |
| Designation: | Service Group Director (Mental Health & Learning Disabilities) |
| Date of completion: | Original 10/11/2022. Reviewed & updated on 11/02/2025 |
| Date of submission to HIW: |  |