Integrated Discharge Strategy UEC TI Strategic Action Group: Project highlight report

| Project: Integrated Discharge Strategy Leads: Helen St John/Emily Warren |  |  |  |  | Previous RAG Rating: | Overall RAG Rating: |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Submission Date: 25/01/2025 |  |  | Period covered: December 2024/January 2025 |  |  |  |  |
| Work-streams |  |  |  |  |  |  |  |
| Work-stream | Current RAG | Work-stream progress | Key activities & achievements | Next period priorities |  |  | Performance Trend |
| IDH - Phase 3- Implementation of Discharge Planning Function & Escalation Framework |  | - Full roll out took place on 1st December 2024 - Live Triage for NPT & SGH referrals has now been implemented. - Collaborative workshops and engagement took place across NPT & SGH – 13th Nov to 20th Nov. - IDH Performance Dashboard now ‘live’ - Temporary funding from the RPB slippage awarded to fund staff to provide consistent MATT and to operate Escalation Framework secured until 31st March 2025 - Flow team identified within Singelton and NPT to operate within IDH - Escalation Framework prepared for implementation from 1st Feb | Impact Data - Total Referrals received up to and including December 2024- 1483 - 25 referrals closed as inappropriate or declined by community support - Average time between referral to IDH and screening onwards is 39.12 hours IDH target is 48 hours. - 100% of individuals are being placed on the correct D2RA Pathway – Improvement of 30% - Average time on hold is 73.7 hours. Worsening picture due to IPC delays, Housing delays and Social Work delays, due to high sickness. - IDH referral to discharge rate is 83.29% - Length of time between referral accepted by IDH and discharge is 3.33 days (80 hours) (8.06 days improvement – 193.5 hours per patient) - An average of 460 Bed days saved per week due to IDH activity (based off an average number of weekly referrals of 57). This equates to an approximate cost saving of £115,920 per week or £6 million per year. | - Recruit staff to IDH utilising temporary funding – essential for the delivery of the escalation framework and coordinating discharge. - Launch Escalation Framework - Communications plan to be executed to ensure awareness and understanding of the escalation framework. - Find suitable accommodation. - Transition of Staff, Home First Matron to take up post as IDH operational/clinical lead. - Daisy Pascale to take up temp post as Business Improvement Manager |  |  |  |
| IDH - Phase 3- Proposed Rollout Plan |  | - Phase 3 – Implementation of Discharge Planning Function - Live Triage for NPT & SGH referrals has now been implemented. - Collaborative workshops and engagement took place across NPT & SGH – 13th Nov to 20th Nov. - Full roll out took place on 1st December 2024 - IDH Performance Dashboard now ‘live’ - Implementation Plan for phase 3 agreed at IDH Implementation Group 14th November - Confirm plan implementation 1st Dec. - Collaborative workshops and engagement across NPT & SGH – 13th Nov to 20th Nov. |  |  |  |  |  |
| Pathways of Care Delays (POCD) action plan implementation - Delay themes to drive activity (in partnership with LA/ Third sector/ RPB). |  | POCD Action Plan refreshed following November’s census data. Continued activity updates and owner identification provided to programme support - Leads have committed to a reduction of Total Delays by 43 - Routine review of patients by severity of delay established - Enhanced scrutiny at ROAG - POCD site Audits undertaken 01/25 | - Increase in Total Days Delayed (13,405 to 14,192 Δ 501) and 2,758 days behind the target trajectory - Increase in Total POCD Delays (240 to 242 Δ 2) and 42 delays behind target trajectory. - Assessment Delays stayed constant at 140 delays, remaining 58 delays behind the trajectory | - NPT have successfully trialled the use of AI software Magic Notes to reduce the admin burden on staff. Full roll out in Jan '25 - Awaiting Start of New Care Package: review of sporadic coverage in Swansea following increase in agencies - Awaiting Social Worker Allocation: 2x filled for hospital social team and community wellbeing team to support with NPT discharge arrangements by right sizing care packages: team going through induction with process to be live in Jan '25 - New internal POCD Escalation Framework has been developed and will be managed by the Integrated Discharge Hub from February 10th, 2025, pending staffing resource. This sets specific timeframes completion of key activity, i.e., allocation of social worker, completion of assessment. This will be monitored weekly by IDH and a report provided to senior leaders. - Additional Social Worker post released and advertised in January for Swansea local Authority - Awaiting Nursing Home availability: We are actively seeking to expand the use of the Trusted Assessment Model with Nursing Homes, using the Hengoed Court model as an exemplar to roll out. Next meeting to take place in February through the local Care Home Forum Providers group in (Hengoed Court: 23.6 days COP to discharge compared to 50.2 days for other care homes). - Dedicated staff in IDH through secured funding until March 31st. This will include Therapists, Social work and admin. The expectation is quicker throughput with dedicated staff and more admin capacity to provide performance reporting on delays. - Workshop with SIGNAL to be held on 27/01 to implement changes to POCD list to mirror Welsh govt |  |  |  |
| Home First – Workforce |  | - Updated Home First Improvement Programme against all themes - Coproduced Escalation Framework developed across IDH/POCD and Home First workstreams. - SIGNAL system audited against POCD reason in bed descriptor. Initial findings presented at ROAG. - Care Home App Review in place with revised questioning to reflect actual Care Home bed capacity, feeding into the RIEF (Regional Integrated Escalation Framework) supported by the West Glamorgan Regional Partnership. | - All documentation developed to support the implementation of the Escalation Framework. - SIGNAL POCD Audit to support learning and identification of opportunities across all stakeholders. | - Finalise and implement a Communications grid to provided structured updates across relevant platforms - Continue to develop a digital resolution for the POCD Escalation Framework Reporting Template. - Work across key stakeholders to review data requirements in line with POCD census data. - Enhance performance reporting mechanisms and refine weekly performance reporting. - Identify workforce deficits to highlight and request Workforce & OD support. - Implement Workforce monitoring and planning tools. |  |  |  |
| Home First – Digital Solutions |  |  |  |  |  |  |  |
| Home First – Communications & Engagement |  |  |  |  |  |  |  |
| Home First – Quality/Operational Improvement |  |  |  |  |  |  |  |

| Performance, Measures & Metrics (In place, or to be defined) |  |  |  |  | Additional Comments |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - IDH Performance against KPI’s within following presentation slides: |  |  |  |  | N/A |  |  |  |
|  | Risks & Issues |  |  |  | Document Management |  |  |  |
| Work Programme | Description | Outcome / Impact | Escalation / Support / Mitigation | Flag to Board (Y/N) | Lead(s) | Purpose/Aim | Date Submitted | Decision |
| IDH | Risk of lack of workforce to support phase 3 as project is resource neutral | Programme outcomes not achieved | Collaboration with stakeholders and scoping of current workforce within both community and acute services that could potentially be repurposed. | N | N/A | Sufficient workforce with appropriate skills and knowledge essential to the implementation of phase 3 | N/A | N/A |
| IDH | Risk that increases in workforce may not be accommodated in current location at MGH | Fragmented workforce across site inhibiting collaborative working | Once required resource identified if required, alternative accommodation at MGH to be scoped | N | N/A | N/A | N/A | N/A |
| IDH | Risk of lack of buy-in/ push back from teams/ wards across the site | Programme outcomes not achieved | Planned engagement with key staff (nurses, therapists, ward managers, service managers etc.) as Champions to drive forward the roll-out across the Morriston site | N | N/A | N/A | N/A | N/A |
| IDH | Risk to capacity due to high staffing deficits (clinical and administrative) | Programme outcomes not achieved | Relocation of support staff from other areas to ensure resilience of IDH | N | N/A | N/A | N/A | N/A |