| Meeting Date | 15 May 2025 |  | Agenda Item |  |  | 3.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Meeting Title | Quality and Safety Committee |  |  |  |  |  |
| Report Title | Gold Command for Maternity and Neonatal Services Progress Report |  |  |  |  |  |
| Report Author | Liz Wonnacott, Head of Service – Medical Director |  |  |  |  |  |
| Report Sponsor | Dr Richard Evans, Executive Medical Director Liz Rix, Director of Nursing and Patient Experience |  |  |  |  |  |
| Presented by | Dr Raj Krishnan, Deputy Executive Medical Director |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of the report is to set out the progress discussed as part of the gold command arrangements established for scrutiny and assurance of improvement within maternity and neonatal services. |  |  |  |  |  |
| Key Issues | - In December 2023, the health board’s maternity and neonatal services were placed by Welsh Government into enhanced monitoring; - The escalation status followed an unannounced inspection by Healthcare Inspectorate Wales (HIW) in September 2023 during which seven areas of immediate action were identified; - An action plan was shared with HIW, with a follow-up unannounced visit in April 2024 to review progress; - Alongside this are other external reports and inspections which require action, as well as open incidents to be closed; - To scrutinise and seek assurance that the work required is being undertaken, a gold command structure has been established; - The report sets out the latest reported position against all areas of focus. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - ACKNOWLEDGE the work to close additional actions raised during enhanced monitoring meetings; - BE ASSURED that the maternity and neonatal dashboard is now live and providing oversight of key indicators to support reporting into relevant fora; - BE ASSURED the 2019, 2023 and 2024 HIW improvement plans are all closed and are subject to an internal governance check prior to sign-off and ACKNOWLEDGE a separate report providing assurance as to the closure of all actions was received by the Quality and Safety Committee in May 2025; - BE ASSURED that no significant or immediate concerns were raised in the HIW unannounced inspection of the free-standing midwifery unit at Neath Port Talbot Hospital and ACKNOWLEDGE an improvement plan has been submitted to HIW; - BE ASSURED by the reduction in the risk score by HEIW for the obstetrics and gynaecology service from 12 to eight and ACKNOWLEDGE the improvement plan will be progressed following receipt of the formal report; - BE ASSURED the group has included within its remit the need to ‘horizon scan’ to look ahead to potential visits and/or reports which may require action. |  |  |  |  |  |

GOLD COMMAND FOR MATERNITY AND NEONATAL SERVICES PROGRESS REPORT

- INTRODUCTION

The purpose of the report is to set out the progress discussed as part of the gold command arrangements established for scrutiny and assurance of improvement within maternity and neonatal services.

- BACKGROUND

In December 2023, the health board’s maternity and neonatal services were placed into enhanced monitoring by Welsh Government. This was because of concerns as to the quality and safety of the care provided raised by members of the Senedd and families who have accessed the services.

The escalation status followed an unannounced inspection by Healthcare Inspectorate Wales (HIW) in September 2023 during which seven areas of immediate action were identified. In addition, the formal report for the visit set out a number of recommendations for improvement, and an action plan was shared with HIW. HIW undertook a follow-up unannounced visit in undertaken in April 2024 to review progress and while some of work had been completed, there were still improvements required.

Alongside this are two Health Education and Improvement Wales (HEIW) targeted inspections of obstetrics and gynaecology in February and July 2024 as part of HEIW’s quality framework to identify areas working well or in need of improvement, as well as national reports which identify areas of improvement for maternity and neonatal services across the UK.

To scrutinise and seek assurance that the work required is being undertaken, a gold command structure has been established, led by the Deputy Medical Director as the senior responsible officer, supported by the Chief Operating Officer and Interim Director of Nursing and Patient Experience. Meetings are attended by members of the Singleton/Neath Port Talbot Service Group’s senior team under which sit maternity and neonatal services.

- GOVERNANCE AND RISK ISSUES

The main areas of focus for the group are enhanced monitoring, inspection action plans, open incidents, national reports and horizon scanning. Progress includes:

- Enhanced Monitoring

Senior members of the service group along with key members of the executive team meet with Welsh Government on a monthly basis to share progress to achieve de-escalation. During these meetings, actions additional to the criteria already set by Welsh Government can be allocated and these are reviewed within the gold command meetings to ensure completion.

For the last few reports, there has been one outstanding action from the enhanced monitoring meetings, the establishment of a maternity dashboard. Work has been ongoing in this regard, with plans shared with the Management Board and Quality and Safety Committee in January 2025 setting out the proposed performance indicators.

The dashboard went live on 1st April 2025 as planned, with a demonstration provided to the gold command meeting. This will now be used for regular reporting in the service group’s Quality, Safety and Risk Group meetings, and form the basis of assurance reports to the Quality and Safety Committee and Board going forward. Members of the gold command were assured by the detail being covered within the system and the oversight this would provide the service group.

At the March 2025 enhanced monitoring meeting, three additional actions were set for the health board to deliver by the May 2025 meeting:

- Themes for neonatal incidents be presented including timeframes;

- Unfilled shifts to be included in future slides;

- Health board to provide written assurance to the Welsh Government on gap and grow serial scanning given that the current data indicates that only 50% of babies born under the 10th percentile are identified.

The slides for the April 2025 meeting were updated to include the detail required in the first two points enabling these two actions to be closed by the gold command. Assurance around gap and grow serial scanning was provided during the enhanced monitoring meeting and Welsh Government were satisfied with the information provided. This will now be followed up with a formal letter as requested in the written summary of the meeting setting out the numbers of babies born under the 10th centile who had been identified due to high risk pregnancies receiving serial ultrasound screening and those which were unknown as the pregnancies had been low risk and suitable for fundal height measurements (using measuring tape from the top of the uterus to the pubic bone) rather than ultrasounds.

In addition to the criteria set by Welsh Government for the enhanced monitoring presentation, each month the health board incorporates a different element of the de-escalation framework:

This has been well received so far, and the current position was to be reviewed in the service group’s Quality, Safety and Risk Group in April 2025, after which a comprehensive update will be provided to the gold command meeting.

- Inspection Action Plans

- HIW Inspections

The improvement plans for the 2019, 2023 and 2024 HIW inspections have now been completed in full. A sample check of the actions undertaken in response to the recommendations is now underway by the corporate assurance team to test if the work completed is robust enough to close the recommendations. A meeting has also been arranged with HIW to talk through the progress made. Feedback from both of these processes would be provided to the next gold command meeting for any concerns to be addressed.

One of the actions on the 2024 general improvement plan had been the establishment of a women’s experience midwife. This was closed once the recruitment process commenced. Following interviews in April 2025, an offer of appointment will be made.

It is anticipated HIW will return to review the services, but no formal arrangements have been made to date. However, an unannounced visit was made by HIW to the free-standing midwife unit at Neath Port Talbot Hospital in February 2025. This in general was a positive report but did identify areas for improvement, none of which related to patient care or safety. The majority were process, document or policy-based, while some were in relation to support available to the workforce. A draft improvement plan has been shared with the HIW and once agreed, will be monitored for progress and closure through the gold command meetings.

- Health Education and Improvement Wales (HEIW)

HEIW undertook a follow-up visit to obstetrics and gynaecology in April 2025. It was a positive visit which saw the risk score reduce from 12 to eight following the actions undertaken in response to two visits in 2024. Eight is classed as a moderate risk, and a further visit will be scheduled in six months.

While the formal report and recommendations are awaited, one area to be focused upon based on the trainees’ feedback is ensuring handovers are robust and comprehensive, so resident doctors are aware of which patients they will be covering. SIGNAL, the patient information system, is to be made accessible to the more senior trainee doctors but also a handover book is to be completed at the end of each shift. If any handovers take place over the telephone, these also need to be documented.

HEIW also recommended that any concerns regarding inappropriate behaviour are managed correctly. Assurance was provided to the gold command that the service group has a Professional Advisory Group in place at which any concerns around a clinician’s conduct or capacity are discussed. Where necessary, the concerns are escalated to the Responsible Officer Advisory Group, which is the executive level group for the management of doctors’ performance, appraisal and revalidation.

Once the final report has been received by HEIW, an action plan, including timescales, will be agreed through the silver group and monitored by gold command.

- Open Incidents

The service is now in a position where it is closing more incidents each month than are opened and the table below sets out the current position.

|  | Maternity |  | Neonatal |  |
| --- | --- | --- | --- | --- |
|  | Open | Overdue | Open | Overdue |
| Incidents | 88 | 50 | 9 | 5 |
| Duty of Candour | 7 |  | 0 |  |
| Concerns | 9 | 8 | 0 | 0 |
| Redress | 33 |  | 2 |  |
| Claims | 63 |  | 8 |  |

There has a been a significant improvement in the number of open incidents as there were 230 reported when the gold command group was first established in August 2024 and the majority of those which are overdue are from this period onwards. However, seven remain from 2023. A target was set in the gold command meeting for these to be closed by the end of May 2025 as for most of them, a response is now in the final stages and requires senior sign-off.

35 of the incidents are as a result of an unexpected admission to the Neonatal Intensive Care Unit (NICU). As many of these were babies born at full term, they will be reviewed as part of the ATAIN programme (Avoiding Term Admissions into the Neonatal unit) to reduce avoidable causes of harm that can lead to infants born at term (more than 37weeks gestation) being admitted to a neonatal unit.

The majority of incidents reported remain under the category of maternity adverse outcomes. These could include stillbirths, cord prolapse or birth trauma, the numbers for these are small. The most common low or no harm incidents such as post-partum haemorrhage, born under 10th centile (meaning the baby is smaller than expected for its gestational age) and unexpected admissions to the neonatal intensive care unit. In order to better understand and learn from each incident, the option of ‘other’ under this category has been removed so a specific description now has to be given.

Finally, a review has been completed of HIE (Hypoxic-Ischemic Encephalopathy – where baby’s brain has potentially been impacted by lack of oxygen during birth) cases since 2023. Work is now underway on a thematic analysis to identify any learning required, and this would form part of the paper to be presented to the Quality and Safety Committee and Board in May 2025.

- National Reports

- MBRRACE-UK (Mothers and Babies: Reducing Risk through Audits and Confidential Enquiries across the UK) 2023

The national MBRRACE-UK report for 2023, published in March 2025, identified the health board as an outlier for stabilised and adjusted extended perinatal mortality (the number of stillbirths and neonatal deaths which meet the MBRRACE criteria as opposed to all stillbirths and neonatal deaths in that period). Thematic analysis and learning have been identified from the cases, and include improvements around CTG (cardiotocography), which is the monitoring of a baby or (babies) heartrate before and during labour, as well earlier identification of very sick babies. A number of actions were agreed to address the issues highlighted in the report, all of which have been completed ahead of the gold command deadline of September 2025.

- Horizon Scanning

As part of the gold command’s role, it looks ahead to any potential reviews or reports relating to maternity or neonatal services. These could be regular national reports which are issued as standard or external reviews being undertaken either of the health board itself or other maternity and neonatal services from which there could be learning.

There is one report expected, the recently concluded report from Llais, an independent statutory body set up by Welsh Government for people to have their say in relation to health and social services. Llais undertook an assurance visit to the maternity services towards the end of 2024 and a report on its findings is expected. Any actions required will be discussed through the gold meetings.

In addition, the service will be undertaking a six-month review following the reopening of the free-standing midwifery unit in September 2024 to identify successes and lessons learned. This will be received by the health board in July 2025.

Discussions are now commencing around the direction of travel to support the governance and assurance of the improvements for maternity and neonatal services and the plans to step-down the gold command structure in due course. This will be supported by the establishment of a Maternity and Neonatal Committee, chaired by the Executive Director of Nursing, with an initial meeting planned for June 2025.

- FINANCIAL IMPLICATIONS

There are no financial implications associated with this report.

- RECOMMENDATION

Members are asked to:

- ACKNOWLEDGE the work to close additional actions raised during enhanced monitoring meetings;

- BE ASSURED that the maternity and neonatal dashboard is now live and providing oversight of key indicators to support reporting into relevant fora;

- BE ASSURED the 2019, 2023 and 2024 HIW improvement plans are all closed and are subject to an internal governance check prior to sign-off and ACKNOWLEDGE a separate report providing assurance as to the closure of all actions was received by the Quality and Safety Committee in May 2025;

- BE ASSURED that no significant or immediate concerns were raised in the HIW unannounced inspection of the free-standing midwifery unit at Neath Port Talbot Hospital and ACKNOWLEDGE an improvement plan has been submitted to HIW;

- BE ASSURED by the reduction in the risk score by HEIW for the obstetrics and gynaecology service from 12 to eight and ACKNOWLEDGE the improvement plan will be progressed following receipt of the formal report;

- BE ASSURED the group has included within its remit the need to ‘horizon scan’ to look ahead to potential visits and/or reports which may require action.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| The health board is dedicated to ensuring that pregnancy and childbirth is a safe and positive experience for all service users in order to support healthy life choices and to give children the best start in life. This requires safe and effective maternity and neonatal services. The actions identified by the reviews and external bodies will support the improvements needed to achieve this. |  |  |  |
| Financial Implications |  |  |  |
| There are no financial implications associated with the report. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| There are no legal implications associated with the report. |  |  |  |
| Staffing Implications |  |  |  |
| There are no staffing implications associated with the report. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The health board has a 10-year vision to be a high-quality organisation. Work being undertaken to address the concerns raised and to de-escalate from enhanced monitoring will not only support that vision but develop maternity and neonatal services which are safe and sustainable in the longer-term. |  |  |  |
| Report History |  | Standing agenda item |  |
| Appendices |  | No appendices. |  |