| Meeting Date | 15 May 2025 |  | Agenda Item |  |  | 3.4 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Quality and Safety Committee |  |  |  |  |  |
| Report Title | Update on Stroke Performance |  |  |  |  |  |
| Report Author | Abi Landeg – Directorate Manager Medicine Specialties Peter Slade – Stroke Clinical Lead |  |  |  |  |  |
| Report Sponsor | Neil Cooper – Assistant Director of Operations Deb Lewis – Chief Operating Officer |  |  |  |  |  |
| Presented by | Peter Slade – Stroke Clinical Lead |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This report includes an updated performance position and includes plans and timescales for improvement. Also included is a comparison of data against major stroke sites across Wales. Finally, this report includes an update on a number of service developments taking place and the establishment of a Comprehensive Regional Stroke Centre (CRSC) |  |  |  |  |  |
| Key Issues | - Compliance against the 4-hour access target and the ring-fencing of beds for admission to the Acute Stroke Unit remains challenging due to system wide pressures. - Lack of funding received to implement a 24/7 stroke consultant rota. - A number of changes to KPI metrics introduced have resulted in lower compliance levels in the below areas: - 14-hour consultant assessment (previously 24hr) - CT within 20 minutes (previously 1 hour) - Thrombolysis door to needle time <30 minutes (previously 45 minutes) - Continued high compliance of thrombolysis rate, swallow assessments and therapeutic assessments. - Reducing door to needle time for Thrombolysis is an area for improvement, more so since the introduction of the new KPI - Increase of Mechanical Thrombectomy a priority. - Embedding of CT Perfusion and MRI Perfusion. - Stroke improvement plan revised. - Pre-Hospital triage pilot commenced. - Therapy intensity compliance reduced. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☒ |  |
| Recommendations | Members are asked to: Accept the content of the report and endorse actions to improve performance |  |  |  |  |  |

UPDATE ON STROKE PERFORMANCE

- INTRODUCTION

This report aims to provide the committee with an update on performance against the stroke pathway in SBUHB.  Continued year-round pressures on acute hospitals such as Morriston mean that performance against access targets has been challenging to improve. This report will illustrate Morriston’s performance against other Welsh centres who are also experiencing the same challenges.  Stroke rehabilitation for Neath Port Talbot Hospital (NPTH) and the current performance for that site is also highlighted in the body of this report.

Whilst investment into the Stroke service was received in 2023/2024 the service is yet to receive the remaining agreed funding to allow recruitment into numerous consultant and therapy posts which will improve performance, and the overall service provided.

A Stroke services action plan for performance recovery and improvement has been developed and enhanced to include updated performance measures taking effect in 2025.

- BACKGROUND

  - Stroke Performance

Due to changes to the Sentinel Stroke National Audit Programme (SSNAP) data repository in October 2024, there have been significant challenges in extracting data from the national system. However, access has now been restored with updated indicators and reporting options.  Despite this progress, the NHS Executives’ Quality Improvement Measures (QIM) portal will not be operational until June 2025 therefore this data will not be included in this report.

In the interim, the service has implemented local arrangements to extract and report relevant data which is included within this report. Additionally, the digital team is actively developing a BI dashboard to provide comprehensive reporting on both national indicators and local performance metrics. This initiative aims to identify constraints and bottlenecks, ensuring targeted improvements in patient care and service delivery.

This section will outline the progress of each Stroke Key Performance Indictor (KPI) at Swansea Bay UHB and will identify any immediate actions being put in place in order to improve compliance.

    - Key Performance Indicator 1: 4 Hour Admission to Acute Stroke Unit (National Target 95%)

Performance was 15.4% in March 2025 against a national target of 95%.  Performance against this Key Performance Indictor has dropped considerably since December 2024 due to the following reasons:

- Lack of available beds due to continued movement of non-stroke patients into the Acute Stroke Unit

- Constant use of additional potential pre-empt space (therapies) to accommodation additional patients onto the Acute Stroke Unit

- Increase in airborne infections on the Acute Stroke Unit leading to an inability to move patients in or off the unit due to infection control procedures

- Increased pressure on the Morriston hospital site and over occupancy in the emergency department which is making it difficult to promptly identify and transfer patients to the Acute Stroke Unit from the Emergency Department.

Access to dedicated Stroke beds continues to impact on performance. Compliance remains low around the 4-hour target compared to pre-pandemic levels, but future service developments should further improve access for patients.

Performance is discussed weekly in the Stroke performance meeting held at Morriston alongside clinicians, Emergency Department staff and bed site managers. NHS executive colleagues have also attended monthly for assurance.  As of 10th July 2023, Morriston was asked to ringfence 18 Stroke beds for Stroke to improve 4 hours compliance further. To date this has rarely been achieved with medical outliers regularly exceeding the limit of 6 that should be in place.

The below graph shows comparative data for the admission into the Acute Stroke Units against 3 major stroke sites of a similar size across Wales.

The below actions, held within the services stroke action plan outline the immediate steps being taken to address compliance against the Ambulatory Stroke Unit 4-hour target:

4-hour access issues are also affecting the other major admitting sites in Wales, such as Princess of Wales Hospital and The Grange hospitals. SBUHB 4-hour performance is in line with other sites of similar size. Sites dealing with smaller volumes of Stroke patients such as Bronglais and Bangor have much higher access rates as demonstrated below. Cardiff and Vale UHB do enforce strict ringfencing of Stroke beds and their compliance far exceeds other sites in Wales on this measure despite seeing more Strokes than any other site.

2.1.2 Key Performance Indicator 2: Thrombolysis rates – (National Target 20%)

Thrombolysis rates as of March 2025 was 17.5% against a national target of 20%. This is historically an area where Swansea Bay generally performs well and whilst performance is low this still remains average against other centres.  The drop in compliance is due to natural fluctuation in the type of patients we are seeing.  Weekly performance review meetings will pick up any patients who may have been missed.

In order to address Thrombolysis compliance, we have expanded the CT perfusion service to run Monday – Friday 09:00 - 17:00 by training 17+ radiographers and this has been successful.  However, in order to further improve this, we will need to extend this provision out of hours by implementing an out of hour consultant stroke rota.  We are unable to progress this further given the health boards financial situation and the pull back of the consultant recruitment monies.

The below graph shows comparative data for Thrombolysis rates against 3 major stroke sites of a similar size across Wales.

2.1.3 Key Performance Indicator 3: Thrombolysis door to needle time <30 minutes (National Target 95% of eligible patients)

A new Key Performance Indicator was introduced in September 2024 and requires all eligible patients to be Thrombolysed within <30 minutes and this will be reported on moving forward.  0% of patients eligible for Thrombolysis received this within 30 minutes in March 2025 however the overall number of patients identified for thrombolysis was high (11.3%).

A comparatively high volume of patients suffering a Stroke receive thrombolysis at Morriston, but these patients require observation when given this treatment. Clinical Nurse Specialists and doctors are not always able to leave a patient who has received thrombolytic therapy to attend any other call or alert that goes off.

Developing an Advanced Nurse Practitioner workforce as per the Comprehensive Regional Stroke Centre (CRSC) plan will allow these members of staff to attend to other patients suffering a Stroke and reduce door to needle time.  6 Trainee Advanced Nurse Practitioners are now in post ahead of regional service plans for 2026 by which time all should be qualified.

The below graph shows comparative data for Thrombolysis door to needle time against 3 major stroke sites of a similar size across Wales.

2.1.4 Key Performance Indicator 4: CT head within 1 hour (National Target - 95%)

Performance for CT head within 1 hour for March 2025 is 62.5% against a national target of 95% and remains average for us as a health board.

A new Key Performance Indicator was introduced in September 2024 that requires all eligible patients to be receive a CT head within 20 minutes and this will be reported on moving forward Performance for CT head within 20 minutes for March 2025 was 15 %

Overall median clock time to CT is reducing which should aid in increasing compliance against this target. One measure put in place is a Direct to CT pilot in conjunction with WAST.  A successful direct to CT pilot took place back in 2024 and was very successful however this pilot relies upon the ability to ring-fence beds on Ward F.  Although we are unable to progress this further, we are working with the site team to look at how we can ring-fence beds on Ward F.

The below graph shows comparative data for a CT Scan within 1 hour against 3 major stroke sites of a similar size across Wales.

2.1.5 Key Performance Indicator 4: Mechanical Thrombectomy – (National Target 10%)

Thrombectomy is offered to SBUHB patients by an agreement in place with North Bristol NHS Trust. Suitable patients with acute ischaemic stroke with an intracranial anterior large vessel occlusion presenting within 24 hours of onset of symptoms or with an intracranial vertebral or basilar occlusion presenting within 12 hours of onset and an National Institute of Health Stroke Scale (NIHSS) of 10 or more should be considered for mechanical thrombectomy.

2.1.6 Key Performance Indicator 5: Swallow Test within 4 hours – (National Target 95%)

80% of patients received a swallow test within 4 hours in March 2025 against a national target of 95%. We generally perform well against this KPI.

The below graph shows comparative data for a formal swallow within 4 hours against 3 major stroke sites of a similar size across Wales.

2.1.7 Key Performance Indicator 6: Consultant assessment within 24 hours – (National Target 95%)

Performance for a consultant assessment within 24 hours in March 2025 was 65% against a national target of 95% and this is an area we generally perform well in.

A new Key Performance Indicator was introduced in September 2024 that requires all eligible patients to be reviewed by a consultant within 14 hours of arrival and this will be reported on moving forward.  However, against the new Key Performance Indicator in March 2025 we reviewed 47.5% of patients within 14 hours.  The below graph shows comparative data for a Stroke Consultant Review within 24 hours against 3 major stroke sites of a similar size across Wales.

2.1.8 Key Performance Indicator 7: Therapeutic Assessment - (National Target 95%).

Data highlights the current performance of therapy services for stroke patients against the national target:

- Physiotherapy (PT): 62.5% of patients were assessed within 24 hours.

- Occupational Therapy (OT): 80.6% of patients were assessed within 24 hours.

- Speech and Language Therapy (SLT): 100% of patients were assessed within 72 hours.

  - Current Service Developments

2.2.1 Pre-Hospital Triage Screening Pilot

A pilot commenced on 10th March 2025 which allows WAST crew members to contact the consultant stroke physician on call via teams to help confirm whether the patient being reviewed is having a suspected stroke. This means that the stroke team will be available and waiting at the front door when the patient arrives via ambulance. This is an All-Wales pilot, being initiated by NHS Executive teams.  An update will be provided at the next stroke board.

2.2.2 Artificial Intelligence CT analysis

Brainomix e-Stroke suite is an artificial intelligence clinical decision-making support tool which allows for rapid diagnosis of ischaemic stroke by appropriate trained individuals.  This implementation should assist long term with timely decision making in patients who are being considered for thrombectomy. This system went live in SBUHB 27th November 2023 and will remain in place.  As this is business as usual this will no longer feature in future reports.

2.2.3 CT Perfusion

2.2 Service Developments

2.2.1 Pre-Hospital Triage Screening Pilot

A pilot commenced on 10th March 2025 which allows Welsh Ambulance Services Trust (WAST) crew members to contact the consultant stroke physician on call via teams to help confirm whether the patient being reviewed is having a suspected stroke. This means that the stroke team will be available and waiting at the front door when the patient arrives via ambulance. This is an All-Wales pilot, being initiated by NHS Executive teams.  An update will be provided at the next stroke board.

2.2.2 Artificial Intelligence CT analysis

Brainomix e-Stroke suite is an artificial intelligence clinical decision-making support tool which allows for rapid diagnosis of ischaemic stroke by appropriate trained individuals.  This implementation should assist long term with timely decision making in patients who are being considered for thrombectomy. This system went live in SBUHB 27th November 2023 and will remain in place.  This is now business as usual.

2.2.3 CT Perfusion

To maximise the potential benefit from revascularisation treatments and the acute management of intracerebral haemorrhage, a corresponding increase in the availability of advanced imaging techniques is required, and all hyperacute stroke services should have timely access to brain imaging including CT or MR angiography and perfusion. This is featured in the 2023 national Stroke Guidelines.

In SBUHB to comply with this recommendation Radiology began offering this service routinely from 25th March 2024 with a Monday -Friday 9am-5pm service in place. The first case being undertaken on 2nd April 2024.  There are 17 CT radiographers on the on-call rota that will all be trained to expand the hours that CT perfusion can be performed but as CT perfusion is beneficial in a small subset of strokes there are a limited number of scans for them to be trained on.  Conversations are taking place between Radiology and our Clinical Lead to look at improving access to this provision.

2.2.4 Stroke Pre-Triage Screening Pilot

There have been delays to several patients having a CT scan and subsequent thrombolysis and thrombectomy treatments due to delayed triage and stroke calls being put out for the Stroke team to attend.  To address this issue a Pre-triage Screening pilot based in ED was developed and implemented resulting in the Stroke team directly screening patients in the Emergency Department waiting room following booking in to assess if they are a likely Stroke or not and to trigger the pathway earlier.  This is now business as usual.

2.3 Recruitment into Acute Stroke Services.

Recruitment into 2 consultants posts and a number of therapy posts were due to go to advert are currently on hold due to finances.  Integrated Community Stroke Service development is in Health Board GMO’s for 2025/26 and this will result in a host of additional community posts If the business case being developed is agreed.

- GOVERNANCE AND RISK ISSUES

In relation to Stroke services, four main areas of risk are highlighted below.  These include the inability to admit patients in a timely manner into the Acute Stroke Unit, inappropriate use of therapies space on Ward F, lack of equipment and lack of a dedicated consultant rota which affects KPI as highlighted in the paper.

These risks are being reviewed on weekly basis by the Directorate Manager and Clinical Lead.  Updates are provided at monthly Quality and Safety meetings and Stroke Board to ensure progress.  Current risks are:

| Risk ID | Title | Risk Level | Risk Handler |
| --- | --- | --- | --- |
| 2901 | Inability to admit patients in a timely manner to the ASU | High Risk – 20 | Abi Landeg |
| 3751 | Risk to patient safety due to inadequate number of oxygen and suction ports for the number of beds in the nursing bays Ward F | High Risk – 16 | Abi Landeg |
| 3340 | Lack Of Therapies space on Ward F and B2 in NPT | High Risk – 16 | Abi Landeg |
| 2147 | Potential significant harm due to lack of senior stroke medicine on-call rota | High Risk – 12 | Abi Landeg |

- FINANCIAL IMPLICATIONS

£1.5m expenditure plan over the next few years approved at management board in 2023.  Funding previously agreed to and minuted in management board has not been forthcoming in 2024/25 which has hindered progress in this speciality.

- RECOMMENDATION

There are currently no financial implications for consideration in relation to the content of this report

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| In relation to Stroke services, four main areas of risk are highlighted in detail in section 3 of this report. These include the inability to admit patients in a timely manner into the Acute Stroke Unit, inappropriate use of therapies space on Ward F, lack of equipment and lack of a dedicated consultant rota which affects Key Performance Indicator as highlighted in the paper. These risks are being reviewed on weekly basis by the Directorate Manager and in partnership with the clinical lead where appropriate. Updates are provided at monthly Quality and Safety meetings to ensure progress. Current risks are: |  |  |  |
| Financial Implications |  |  |  |
| £1.5m expenditure plan over the next few years approved at management board in 2023. Funding previously agreed to and minuted in management board has not been forthcoming in 2024/25 therefore the two further consultant posts that need to be recruited to may not be able to proceed. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Not applicable |  |  |  |
| Staffing Implications |  |  |  |
| The inability to introduce a core service requirement (stroke consultant on call rota) |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Briefly identify how the paper will have an impact of the “The Well-being of Future Generations (Wales) Act 2015, 5 ways of working. - Long Term – Providing enhanced Stroke Services for the SBUHB region. - Prevention – Enabling timely intervention in patient’s pathways resulting in better outcomes for Stroke survivors. - Integration – Integrating with other hospital sites to ensure rehabilitation pathways are utilised. - Collaboration - Acting in collaboration with any other areas such as other hospital sites and tertiary organisations such as the Stroke Association. - Involvement – Stroke performance is monitored weekly by a range of staff from different backgrounds as well as being scrutinised before a regular executive board. |  |  |  |
| Report History |  | V1 |  |