| Date of Inspection | Inspection | SG | HIW Ref | Nbr Report Rec’ns | Nbr Actions Agreed | Nbr Actions Complete | Nbr Actions Ongoing | Nbr Actions Overdue | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 16-18 Mar 2022 | Cefn Coed Hospital (Tawe) | MHLD | 21193 | 21 | 36 | 29 | 7 | 6 | Updated last in December 2022. |
| 25 May - 1 Jun 2022 | Dan Danino | MORR | 22034 | 12 | 12 | 11 | 1 | 1 | Updated last in July 2023. |
| 5-7 September 2022 | Morriston Emergency Dept (Immediate & General Improvement Plans) | MORR | 03129 | 26 | 88 | 75 | 13 | 13 | Updated last in Aug 2023. |
| 24&25 Jan 2023 | Bryn Afon LD Hospital | MHLD | 03202 | 15 | 19 | 16 | 3 | 3 | Final report was published 27 April 2023. Internal update was received in September 2023. |
| 17&18 Jan 2023 | Paediatric Services: Ward M & Oakwood Ward, Morriston | NPTS | 03294 | 10 | 12 | 0 | 12 | 6 | Final report was published 20 April 2023. Update was submitted to HIW in August 2023. |
| 21&22 Feb 2023 | IR(ME)R Inspection: Morriston Diagnostic imaging | MORR | 03297 | 16 | 49 | 36 | 13 | 3 | Final report published on 25 May. Update was submitted to HIW in July 2023. |
| 17-19 April 2023 | Assessment & Treatment Unit, MHLD | MHLD | 03633 | 12 | 20 | 15 | 5 | 5 | Update was submitted to HIW in September 2023 Action has been taken/commenced in each of the 5 remaining areas - confirmation of completion awaited. |
| 22-24 May 2023 | Ward F, NPTH | MHLD | 03367 | 33 | 66 | 0 | 66 | 63 | Final report was published in August 2023 incorporating Improvement Plan. An internal progress update is pending. |

Future Inspections for Addition when reports are finalised:

5-7 Sept 2023 – Maternity Unit, Singleton, Ref 03513

Following inspection an Immediate Improvement Plan was requested, submitted by SBU & accepted by HIW on 16 Oct - 7 areas listed for immediate improvement. Draft report has been received 03/11/2023. HIW deadline for response 16 Nov  Internal target 14 Nov.

11-13 Sept 2023 – Caswell Clinic, MHLD, Ref 03642

Draft report received and SBU improvement submitted in return. HIW response and Final report awaited.

10-11 Oct 2023	- IR(ME)R Inspection: Nuclear Medicine, Singleton, Ref 03429

This was an announced inspection. No Immediate Assurances required. Draft report awaited.