| Meeting Date | 26 November 2024 |  | Agenda Item |  |  | 4.4 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Quality Priority - Falls Prevention Update |  |  |  |  |  |
| Report Author | Eleri D’Arcy, Falls Quality Priority Lead |  |  |  |  |  |
| Report Sponsor | Hazel Powell, Acting Director of Nursing & Patient Experience Nursing |  |  |  |  |  |
| Presented by | Eleri D’Arcy, Falls Quality Priority Lead |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | To provide an update on the Falls Prevention quality priority including the progression of mainstreaming elements of this work for sustainability. |  |  |  |  |  |
| Key Issues | - Continued improvement noted but further progress on embedding sustained improvement required - Falls Prevention now a workstream on Regional Partnership Board |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to receive the report. In order to progress Falls Prevention Quality Priority work and embed it as business as usual, Service Groups (SG) must take a lead and ensure: - Embed improvement plans as part of SG objectives and establish robust SG level governance structures with identified lead, reporting via their quality and safety groups - Consistently share learning at HB wide Overarching Falls Steering Group via the SG representative - Adopt the Falls Documentation Audit as part of the wider quality Assurance Programme and report compliance via QA mechanisms - Regularly report Falls Brief Intervention training (via ESR) compliance to the overarching Falls Prevention Service Group and agree training schedule across all SGs - Overarching Falls Steering Group to monitor SGs action and improvement plans - Exploration of resource availability to support specific falls prevention offers within the HB - Recognise the need to change the culture of physical activity by supporting reconditioning approaches |  |  |  |  |  |

Quality Priority – Falls Prevention

- INTRODUCTION

Falls Prevention was identified as a Quality Priority by the Health Board (HB) in 2021.  Board received and approved a similar paper to this one, in March 2023 (appendix 1).  To summarise briefly, the first year of Falls Prevention as a Quality Priority saw the target of 10% reduction of injurious inpatient falls exceeded.  Much work was focussed on improving governance structures, bringing with it stability and engaging partner agencies such as the Welsh Ambulance Services Trust (WAST), Local Authority (LA) and third sector organisations such as Age Cymru and Care & Repair.

Falls remain however, one of the highest cause of incidents within the HB, and nationally it is the second leading cause for accidents in the home.  It is estimated approximately 130,000 older people will fall at least once in Wales this year.  There are high individual/personal and socio-economic cost to falls, with a cost to the NHS as a whole of £2.3 billion annually.

This paper provides an update as to the progress of the Falls Prevention Quality Priority since March 2023 and describes the progress on the actions generated through discussion on the previous paper; scoping of community services and relaunching action against deconditioning.

- BACKGROUND

As we know, falls occur at all ages across the lifespan and are an inevitable part of a bipedal gait and physical activity.  However, the risk increases as we age with an estimated 30% of adults aged over 65 years falling each year and for whom the consequences are more serious, despite concerted efforts of researchers and clinicians to understand, assess and manage their risks and causes.

In addition to personal distress, falls and fall related injuries are a serious healthcare problem because of their association with subsequent morbidity, disability, hospitalisation, institutionalisation and mortality.  The number of falls and related injuries will likely further increase, partly due to an ageing population, but also because of increasing prevalence of multi-morbidity, polypharmacy and frailty among them.

In Swansea Bay UHB, like other HBs in the UK, a sustained trend continues, particularly following the pandemic; patients are frailer on admission to hospital and often-frailer still on discharge.  Community teams face increased complexity on caseloads as patients with as many as 4-5 co-morbidities becomes the norm.

As stated, the primary GMO, to reduce inpatient injurious falls by 10% was achieved in 2022/2023.  2023/2024 has seen a further 7% reduction from the new baseline.

Key objectives for this year are:

- Improve compliance and quality of multi factorial risk assessment

- Agree and embed data metrics in the community

- 10% reduction in inpatient falls

- Embed falls prevention to progress improvements as Business as usual.

Health Board Falls Prevention performance overview

Falls incidents (inpatients):

Falls incidents included in this data set is reflective of inpatients only but across all sites. This is due to inconsistent, complex, and non-digital reporting mechanisms in community settings.  Incidents not reported through Datix Cymru remain unavailable.

Throughout this report, all falls incidents with or without harm caused have been used for completeness.  Accuracy of harm reporting varies, all falls can provide valuable learning despite the severity of the incident.

Graph 1: Comparison data for inpatient falls incidents over the previous 4 years (2020 – Feb 2024)

Staffing rates have been reviewed for August in 2022 and 2023; the common theme is a high percentage on unavailability of staff due to sickness and annual leave. For both rosters, the wards were using a high percentage of bank and agency staff who may lack in-depth knowledge of the patients who are a high risk of falls as well as understanding of the falls policy and protocols in place.  Some work has been identified to provide additional education for temporary and agency staff.

Falls Rates:

Using the Nationally recognised falls rate per 1000 bed days unit more accurately reflects current performance; taking into account increases in number of patients within the system.

Graph 2: HB Inpatient Falls Rate April 2022 – Feb 2024

Since Falls prevention has been a quality priority the HB falls rate has remained below the national average of 6.6/1000 bed days and has sustained a downward trajectory.

Serious Harm from Falls:

Graph 3: Falls Serious Incidents

There has been a significant reduction in falls related Serious Injuries (SIs) over the last year.  Falls where serious harm has occurred in hospitals, are referred to the Serious Incident team where a decision as to if the incident is reportable to Welsh Government is made.  A health board decision was made in 2020 to report all falls resulting in a hip fracture, to Welsh Government; this is not the case in other Health Boards.   Since 2022 there has been a 60% reduction in falls related Serious Incidents.  By improving knowledge/awareness and applying to all falls, preventative measures can be started earlier, therefore reducing the risk of SIs occurring.

National Audit of Inpatient Falls 2023

The NAIF audit 2023 has identified 5 recommendations:

- Trusts and health boards (HBs) should use their own data to inform the focus of local improvement activities.

- Focused initiatives to improve the quality of MFRA should be implemented across trusts and HBs. We specifically recommend reviewing data on lying and standing blood pressure measurement and implementing targeted improvement projects where indicated.

- As delirium is common in people who sustain inpatient femoral fractures the admission assessment processes should be reviewed to ensure effective delirium assessment and ongoing monitoring.

- Review training and competency requirements to ensure that post-fall checks for injury are effective.

- Ensure that processes are in place to hasten time to administration of analgesia after an injurious fall

These recommendations have been discussed at the Overarching Falls Prevention Steering Group (OFPSG) where action plans to address recommendations are being developed by service groups currently.  Reporting of progress of these actions will be through OFPSG and risks / issues raised through the Quality Priority Board in the first instance.

A number of audits have been completed across service groups and show significant lack of appropriate assessment in the use of bed rails.  MH&LD are yet to transfer to the digitalised Welsh Nursing Care record (WNCR) and review of paperwork across these areas show better compliance with the bed rail assessment.  Concerns that WNCR did not include this element of the assessment have been raised with system administrators.  30% of all HB falls occur from bed or transferring to bed. With poor compliance with bed rail assessment, assurance cannot be given regarding whether these falls were avoidable or not.

The National Hip Fracture Database:

The National Hip Fracture database (NHFD) is inputted into via the Health Boards Fracture Liaison Service (FLS).  Nationally, work is ongoing to ensure all HBs have a fracture liaison team; Swansea Bay UHB is ahead of many HBs in Wales as the FLS is well established. Successful recruitment to further expand this team has been achieved.

Prompt surgery and prompt admission to specialist wards where SBUHB performance is lower than the national averages continues to be an area for improvement.  The clinical team delivering our hip fracture service are making continuous improvement and this is reported both locally and through the National Fracture Discharge Group.

Additionally, the Fracture Discharge Service is now operational and supporting patients’ home from hospital, reducing length of stay.  The reporting of this service will be via the PCC&T service group and will report on number of patients discharged via the service, effect on length of stay in hospital and patient outcomes.

Bone Health:

There are currently 619 patients waiting over 8 weeks for a DXA scan in SBUHB. This has reduced from 2,578 patients waiting over 8 weeks in November 2022.  Additional funding was received in November 2022 with a target to reduce wait lists to zero by August 2023.  The team are anticipating zero waiting list to be achieved by September 2024. The reporting for all scans are currently up-to-date.

For comparison, Hywel Dda currently have 2,578 patients waiting over 8 weeks for a DXA scan with 2,759 scans pending reporting.

Community Falls Incidents

The WAST data has stayed consistent over the last three to four years.  We have however seen an increase in presentations to front door services of falls in the over 65 year’s population.  Anecdotally, emergency departments are reporting more patients are presenting who have made their own way to hospital (possibly due to response rates worsening for WAST) therefore further increasing the risks held in the front door services.

20% of all ED/MIU attendances are by people over the age of 65 yrs with falls representing 30% of reason for attendance in the over 65 age group. The number of people over 65 attending ED/MIU following a fall is increasing (Graph 4). The severity of harm experienced in these falls is increasing (Graph 5) demonstrating the impact falls have on unscheduled care.  This measure has now been added to service group reporting through the Overarching Falls Prevention Steering group (OFPSG).

Graph 4: Number of patients over 65 presenting to front door service with a fall

Graph 5: Number of patients over 65 presenting to front door service with a fracture from a fall

Scoping

A community scoping exercise has been completed together with gap analysis identifying the need for closer review of existing services and recommending a HB Falls Framework in line with the HBs Frailty Strategy to ensure consistency and clarity for all services.

Dance to Health remains one of the HBs only offer for falls prevention that meets the necessary NICE guidelines and National standards of best practice.  The service remains reliant on charitable funds although did receive funding from the Regional Partnership Board this financial year.  Further exploration of a business plan to ensure groups can become self-sufficient is required but however further funds are required to ensure more groups can be set up, reaching more isolated areas of the HB.

Two ongoing projects continue to demonstrate value.

The iStumble project with domiciliary care and care homes – this is now moving to phase 3 which will see the project supporting over 1000 service users. An 80% reduction in WAST call outs recorded. Progress is reported to Improvement Cymru due to funding received for the lifting equipment.

The Delta Wellbeing Falls response project is now provided over 2 clusters in NPT and remains in project phase.   75% reduction in WAST call outs reported.

The Community and Older Persons Board has identified Falls Prevention as one of four workstreams.  Objectives and direction of this group are to create a falls directory and clear pathways and embed the National Stay Steady Stay Safe  campaign to ensure  consistency across the region.  Additional work is required to develop falls prevention, response and aftercare

Scoping of data collection, processes and reporting has been completed for all services within PCT.          Findings suggest no consistency in reporting  or data collection.   Understanding the risk profile of services is therefore difficult to ascertain.  A working group within PCT service group is working to improve this and introduce consistent assessment  processes.

NPT and Singleton Service Group

Service Group Performance in Falls Prevention

Morriston Service Group

Morriston Service Group

Graph 8: NPTSSG Falls Rates

Graph 7: Morriston Falls rates

NPTSSG key messages

Significant improvement in falls rates – this is evident in NPTH and not solely reliant on the reduction of beds in SGH

Memory Impairment Assessment team were supporting many falls prevention interventions however that service has now been lost. Many of the falls incidents being reported would have benefitted from input from the MIAT team

Volunteer Programme Quality Improvement project underway

Recommendations:

Engage with HB Reconditioning programme of works

Data and learning to be shared at OFPSG - report structure agreed

Targeted Quality Improvement work in Ward C NPTH

Request impact report for loss of MIAT

Morriston SG Key messages

Moriston’s footprint has changed significantly since the last paper written in March 2023

Falls rate in AMU and ED remains consistently above national average

Baywatch initiative unable to be consistently applied due to staffing pressures

Stable falls rate

Recommendations:

Engage with HB Reconditioning programme of works

Hot debrief to be implemented across site

Data and learning to be shared at OFPSG – report structure agreed

Targeted Quality Improvement work in AMU

Trialled patient focussed review led by falls lead for high risk repeat faller

Primary Care, Community & Therapies Service Group

Mental Health and Learning Disabilities Service Group

Graph 10: PCC&TSG Falls rate (Gorseinon Hospital only)

MH&LD SG Key messages

Falls Documentation audit completed across all Older Persons Mental Health inpatient sites. Learning included; threshold of risk high therefore preventative measures not initialised, need for increased medical input pre and post fall

Planned engagement with NAIF audit 2024

Increasing trend – possible attribution to increased

Recommendations:

Engage with HB Reconditioning programme of works

Hot debrief to be implemented across site

Data and learning to be shared at OFPSG – reporting structure agreed

Focussed Quality Improvement projects in CCH – require medical engagement (not yet received)

Consider focussed patient review facilitated by a falls expert

Graph 9: MH&LDSG Falls Rate

PCC&T SG Key messages

Falls lead identified - scoping exercise being built on providing detail and current data collection available

Identification of falls assessment tool agreed by peers across PCT – awaiting approval by service leads.

Delta falls response project now across 2 clusters in NPT – 75% reduction in WAST Callouts.

iStumble project ongoing now being developed increasing support to over 1000 people – 80% reduction in WAST call outs

Increasing trend – correlates with increase of surge beds (45) impact on environment

Recommendations:

Engage with HB Reconditioning programme of works

Data and learning to be shared at OFPSG – reporting structure agreed

Embed falls assessment and data metrics

HB wide roll out of Stay steady stay safe campaign

Reconditioning:

An action from the previous deep dive report (submitted and discussed at Management Board March 2023) was to re prioritise reconditioning across the HB.  Deconditioning occurs due to prolonged periods of inactivity and causes muscle wastage, skin breakdown, cardiovascular and respiratory failure as well as compromising the body’s immune system.  As a result, patients require more support on discharge due to reduced function and independence, many becoming incontinent and unable to care for themselves.  Normally attributed to prolonged hospital stays, the pandemic resulted in many older people, who are particularly susceptible, in deconditioning in the community, increasing the frailty levels then entering secondary care.  Patients arriving at the front door, particularly if following an injurious fall and experiencing long waits for emergency response are already deconditioned.

Avoiding deconditioning is becoming increasingly important. The NHS Executive is driving a cohesive approach through Six Goals workstreams.

The next phase of the Safe Care Collaborative work with Improvement Cymru will likely have a focus on avoiding deconditioning.

As a HB work on avoiding deconditioning continues.  The second Active August campaign has been concluded with many events across the HB raising the awareness of deconditioning.

A successful communication campaign is ongoing reaching over 127,000 views.

The role of Reconditioning Ambassadors is currently being recruited to and is supported by Christine Morrell.  This role will be instrumental in changing culture.  Services are asked to support this role and encourage take up of the volunteer role across sites.

It is recognised that work on avoiding deconditioning will positively impact falls prevention work as well as pressure ulcer prevention and improving nutrition and hydration across the HB.

Conclusions:

Progress of the falls prevention QP has continued and the profile of falls prevention being raised has ensured reduction in falls has continued to decrease and remains on target for another 10% reduction this financial year.

Progress to Business as usual continues.  It is anticipated inpatient falls prevention will be able to progress to business as usual within the next three months, however is reliant on the digital quality dashboard currently under construction.  Falls Prevention within the community has more work to do before it can be stood down as a priority, with a target of April 2025.

- GOVERNANCE AND RISK ISSUES

There is now a robust governance structure in place and service groups are asked to ensure Falls prevention is an agenda item on quality and safety and or operational groups at SG level.

HB wide reporting has been agreed.  Service groups have action plans in place to reduce the number of open incidents to improve governance and learning.

The following risks have been identified:

- Digital Informatics – Dashboard is in development but not yet in place effecting Service Groups ability to have access to real time falls data and therefore take accountability and influence change in a more timely way.

- Backlog of open incidents related to falls impacting ability to analyse and learn from incidents

- FINANCIAL IMPLICATIONS

Through the Quality Improvement programme, there are a number of projects that may require additional funding; details for this will follow through individual project groups.

Dance to Health remains one of the HBs only offers in a preventative programme.  Start-up costs (approx. £100k/yr. for 3 yrs.) are required to ensure the service develops and expands reaching the most isolated and vulnerable.  A business model will need to be explored to ensure sustainability of these classes.

Work has commenced on the development of a national falls response framework.  It is anticipated this will be operationalised with no additional resource.

- RECOMMENDATION

Members are asked to receive the report.

- Embed improvement plans as part of SG objectives and establish robust SG level governance structures with identified lead, reporting via their quality and safety groups

- Consistently share learning at HB wide Overarching Falls Steering Group via the SG representative

- Adopt the Falls Documentation Audit as part of the wider quality Assurance Programme and report compliance via QA mechanisms

- Regularly report Falls Brief Intervention training (via ESR) compliance to the overarching Falls Prevention Service Group and agree training schedule across all SGs

- Overarching Falls Steering Group to monitor SGs action and improvement plans.

- Agree where the OFPSG will report to once no longer a quality priority.

- Recognise the need to change the culture of physical activity by supporting reconditioning approaches in order to improve a range of quality measures including falls prevention

- Encourage Service groups to include avoiding deconditioning as a theme in IMTPs.

- National Institute for Health and Care Excellence (NICE).2019 Surveillance of falls in Older People: Assessing Risk and Prevention (NICE Guideline CG161). London: National Institute for Health and Care Excellence, 2019

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| Falls prevention Quality Priority reports directly to Q&S group and Patient safety Group. The overall aim is to reduce falls incidence and reduce the harm patients are caused through falls. |  |  |  |
| Financial Implications |  |  |  |
| No financial implications noted in this report. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Each service group have Falls Prevention Meetings/Forums and these feed into a HB wide Overarching falls Prevention Steering Group. This report to both the Quality Priority Programme Board and Q&S governance structures. As project is open for FOI, we should be able to provide robust data. |  |  |  |
| Staffing Implications |  |  |  |
| Falls prevention champions have been identified across all HB areas; role to be developed through QI programme. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The focus of the Falls QP work is prevention. The Quality Improvement programme ensures integration with partner agencies including social services and third sector services. There is collaboration with both partner agencies and Improvement Cymru to progress QI work streams. |  |  |  |
| Report History |  | None |  |
| Appendices |  | Appendix 1 |  |