| Meeting Date | 26/11/2024 |  | Agenda Item |  |  | 5.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Management Report - Quality & Safety Risks |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Interim Director of Corporate Governance |  |  |  |  |  |
| Presented by | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to inform the Quality & Safety Committee (QSC) of the risks from the Health Board Risk Register (HBRR) assigned to the Quality & Safety Committee. |  |  |  |  |  |
| Key Issues | - The Q&S Committee received the August HBRR at its September 2024 meeting. This report presents the position as recorded within the October 2024 HBRR. - Twelve risks are assigned to the Quality & Safety Committee for oversight. - Recent changes of note: - One risk has increased in score (HBR66 Access to Cancer Services: SACT); - One risk has reduced in score (HBR91 Screening of Fetal Growth in accordance with Gap-Grow). - Nine of the risks are assessed to meet or exceed the Board’s risk appetite threshold. - Additional risks overseen by other committees are included for information. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - RECEIVE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Q&S Committee. - REVIEW & COMMENT on the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any. |  |  |  |  |  |

RISK MANAGEMENT REPORT – Quality & SAfety Risks

- INTRODUCTION

The purpose of this report is to inform the Quality & Safety Committee (QSC) of the risks from the Health Board Risk Register (HBRR) assigned to the Quality & Safety Committee.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular HBRR update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

Risk Register management is supported by a Risk Management Group (RMG) which meets quarterly and is responsible for overseeing the operational management of risk, ensuring local systems and processes are in place and are operating effectively to ensure appropriate reporting and escalation. The Group last met in October 2024 (special meeting to discuss review of risk management & reporting approach).

Additionally, a Risk Scrutiny Panel is responsible for ensuring there is an appropriate and robust risk management system in place and working throughout the organisation. It is responsible for moderating new risks and risks escalated to the Health Board Risk Register (HBRR) and Board Assurance Framework (BAF) and recommending and advising the Management Board on the escalation and de-escalation of risks. The Panel last met in October 2024.

2.2 Risk Appetite

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating  lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

- GOVERNANCE & RISK

3.1 Action to Update the HBRR

Health Board risk register entries are circulated to lead Executive Directors monthly for review and updated where required. A consolidated, updated register is circulated to the Executive Team for agreement and final version issued. This report presents the position as recorded within the October 2024 HBRR. Key changes made in the most recent update are highlighted in red font.

3.2 HBRR Quality & Safety Risks

Twelve risks are assigned to the Quality & Safety Committee for oversight. The profile of risk scores is presented below:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 |
| --- | --- | --- | --- | --- | --- |
| Number of Risks | - | 1 | 5 | 6 | - |

Key movements are:

- New risks:

There are no new risks

- Risks with increased scores

There is one risk with increased score:

  - HBR66 Access to Cancer Services: SACT (1520)

- Risks with reduced scores

There is one risk with reduced score:

  - HBR91 Screening of Fetal Growth in accordance with Gap-Grow (2012)

- Risks closed/de-escalated

No risks have been closed or de-escalated.

There are 9 risks meeting or exceeding the Health Board’s risk appetite thresholds in the August HBRR, for which action is required so that they may be reduced to acceptable levels. Table 1 below highlights recent changes / actions of note for those risks that are currently meeting or exceeding the thresholds.

Table 1: HBRR risks assigned to the QSC which meet or exceed the risk appetite threshold

| Risk Ref | Description of Risk (Summary) | Current Score | Exec Lead | Key Updates |
| --- | --- | --- | --- | --- |
| 4 (739) | Infection Control Risk of patients acquiring infection as a result of contact with the health care system, resulting in avoidable harm, impact on service capacity, and failure to achieve Tier 1 national infection reduction goals. | 20 | Executive Director of Nursing | The risk score currently remains unchanged. Update Sep 2024: - Executive HCAI Scrutiny Group are taking place regularly with Service Group Directors. - C. difficile cases increased further in August and this was escalated by the establishment of the Gold C. difficile High Incidence Management Group which met on 5th September, with involvement of all Service Groups and expert advisors from PHW. - Level 2 IPC training compliance continues to improve 81.47%; Level 1 training compliance 91.71% as of 31/08/24. Tier 1 infection progress to Targeted Intervention de-escalation criteria in August 2024: - C. difficile - 18 hospital onset cases (target 6). Combined (hospital onset and community onset) cumulative total – 110 cases. - Staph. aureus - 8 hospital onset cases (target 3). Combined cumulative total - 53 cases. - E. coli - 8 hospital onset cases (target 4). Combined cumulative total - 96 cases. - Klebsiella spp. - 6 hospital onset cases (target 4). Combined cumulative total - 54 cases. - Pseudomonas aeruginosa - (Not included within targeted interventions). Combined cumulative total - 6 cases. |
| 43 (1514) | Deprivation of Liberty Safeguards (DoLS) Due to a lack of Best Interest Assessor resource, there is a risk of failure to complete and authorise the assessments associated with Deprivation of Liberty/Liberty Protection Safeguards within the legally required timescales, exposing the health board to potential legal challenge and reputational damage. | 16 | Executive Director of Nursing | The risk score currently remains unchanged. Update Sep 2024: Assurances and controls remain in place. Breaches remain a risk due to increased demand on service, limited capacity and dependency on external Best Interest Assessors. |
| 61 (1587) | Paediatric Dental GA Service – Parkway Medical Safety risk as general anaesthetics are performed on children outside of an acute hospital setting. Repatriation of service to acute site delayed due to theatre capacity which means the health board continues to commission services for delivery outside of national guidance (WHC 2018-09). There is also an associated risk in that the diagnosing clinician does not deliver the care to the patient. | 16 | Chief Operating Officer | The risk score currently remains unchanged and there is no further update currently. |
| 64 (2159) | Health and Safety Infrastructure Insufficient resource and capacity of the health, safety and fire function to maintain legislative and regulatory compliance for the workforce & sites across the Health Board. | 16 | Director of Finance & Performance | The risk score currently remains unchanged. Update Oct 2024: There has been a senior structure review, with some portfolio changes. The next stage is to review the portfolio structure and provide a structure that will be recommended to the Health Board for implementation, this will likely be on a phased approach. |
| 66 (1834) | Access to Cancer Services Delays in access to SACT (Systemic Anti-Cancer Therapy) treatment in Chemotherapy Day Unit | 20 (was 15) | Executive Medical Director | The risk score has increased from 15 to 20 due to staff sickness across the Multi-Disciplinary Team with the demands outstripping capacity. Welsh SACT performance metrics expect: P2 to start within 14 days. P3 to start within 21 days Actual performance in Sep 2024: 94% patients breached P2 (average number of days over was 13) 92% patients breached P3 (average number of days over was 8) Action taken Sep 2024 includes: - Weekly SACT meetings with MDT to ensure staffing levels and deferral processes are being adhered to ensuring service is safe whilst staffing numbers are low in PTS. Workforce modelling is being mapped to increase capacity by 10% as part of draft business case. - Datix incidents are being submitted for deferrals due to late confirmation and not adhering to SACT scheduling booking rules - Where patients have breached SACT target Datix incident reports are being submitted. - Paperless drug administration is now complete and in use on CDU. - Improvements made to nurse training arrangements to improve competency in relation to SACT provision. Further Action: A demand and capacity options paper is being prepared within the service (target 30/11/2024). |
| 69 (1418) | Safeguarding Adolescents being admitted to adult MH wards resulting in potential safeguarding issues | 20 | Chief Operating Officer / Executive Director of Nursing | The risk score currently remains unchanged. Update Oct 2024: There is no change to the current arrangements and controls. The Health Board is still awaiting the outcome of its capital prioritisation requests to Welsh Government of which the Adult Inpatient new build case is a part. |
| 80 (1832) | Discharge of Clinically Optimised Patients If the health board is unable to discharge clinically optimised patients there is a risk of harm to those patients as they will decompensate, and to those patients waiting for admission. | 20 | Chief Operating Officer | The risk score currently remains unchanged. Update Oct 2024: This remains a current risk. It will be the main focus of the Winter Plan currently being developed and is also a key focus of the Care Action Committee. Action refreshed: The Care Action Committee (CAC) is focussing on reducing the impact of COPs within acute hospitals. The Health Board is actively engaging with the work from the CAC and currently developing the Winter Plan for 24/25, of which reducing COPs will be a key focus. This work is being taken forward by the Interim Head of Integrated Services in PCT to ensure cross-boundary support (target 30/11/2024). |
| 85 (2561) | Non-Compliance with ALNET (Additional Learning Needs & Education Tribunal) Act There are risks to the Health Board’s ability to meet its statutory duties and establish the effective collaborative arrangements required by the ALNET Act, which is being implemented through a phased approach. | 20 | Director of Therapies & Health Sciences | The risk score currently remains unchanged. Update Oct 2024: Activity remains on track though absence of project support continues to impact on the pace of work. It is expected that with data available in the new year, it will be possible to meaningfully review risk by 31/03/2025 as per current risk target date. |
| 89 (3071) | HMP Swansea There is a risk that the men in HMP Swansea will not receive the appropriate standard of care. This is due to the fact that the nursing establishment within the prison no longer fully meets the changed demographics and numbers of men being detained. The maximum operational capacity of the Prison can reach circa 480 men. The Health Board investment into the Prison is based on delivering services to 250 men. This was also highlighted as a risk in the recent HIW governance review. In addition there is no headroom built into the Prison nursing establishment so periods of sickness, leave and study renders the roster short. | 20 | Executive Director of Nursing | The risk score currently remains unchanged. Update Oct 2024: The base line assessment was completed and PCT have received a draft report and are in the process of responding to it. A Deputy Head of Nursing (DHoN) has been appointed and is to support review of staffing within the prison – expected completion December 2024. The findings of the baseline assessment will support the staffing review that the DHoN is undertaking. A service specification for health protection works has been submitted to Public Health. It is expected there will be investment from public protection team to support with vaccination and health protection screening work. It is expected that circa £75k recurrent funding will be available for health protection works within the prison. Once funding has been confirmed and allocated there is an expectation of improved health protection health outcomes. |

Table 2 below lists additional risks assigned to the Quality & Safety Committee whose risk levels do not meet the threshold currently set within the Health Board’s risk appetite. However, in line with the Board’s aspiration that thresholds could be reduced in the future, these risks are presented for information:

Table 2: HBRR risks assigned to the QSC that do not currently meet the risk appetite threshold

| Risk Reference | Description of risk identified (Summary) | Current Score | Exec Lead | Key Update |
| --- | --- | --- | --- | --- |
| 63 (1605) | Screening for Fetal Growth Assessment in line with Gap-Grow There is not enough Ultrasound scanning & clinic capacity within Swansea Bay UHB to offer all women serial ultrasound scan screening in the third trimester in line with the UK perinatal Institute Growth Assessment Programme (GAP). Welsh Government mandate fetal growth screening in line with the GAP programme. There is significant evidence of the increased risk for stillbirth or neonatal mortality/morbidity (hypoxic ischaemic encephalopathy (HIE)), where a fetus is growth restricted (IUGR) and/or small for gestational age fetus (SGA). Identification and appropriate management for IUGR/SGA in pregnancy will lead to improved outcomes for babies. | 12 (was 20) | Executive Director of Nursing / Director of Therapies & Health Sciences | The risk score has been reduced from 20. Update Oct 2024: GAP/GROW target training compliance was reached in September 2024 (actual compliance level was 96% Midwives, 100% Obstetric Team) The service is going live with three weekly scanning appointments for all women undergoing serial scans in pregnancy from the 28/10/24. All new bookings have been booked for three weekly scans. Midwifery sonography service to provide clinic in NPT site. |
| 102 | Inability to maintain Birthrate Plus ® complaint rosters Birthrate Plus® enables health boards to calculate their midwifery staffing requirements based on their specific activity, case mix, demographics and skill mix. There is a risk non-compliance with roster templates due to increased acuity, unplanned staff absence and vacancies. The potential impact of this may be reduced staffing levels against the agreed Birthrate Plus ®, staffing template resulting in poor patient outcomes and experience, and potential suspension of services. | 16 | Executive Director of Nursing | The risk score currently remains unchanged. Update Oct 2024: Implementation of BSOT (Birmingham Symptom Specific Obstetric Triage System) commencing in October 2024 following completion of a complex implementation framework which includes Job Planning for Obstetric cover and the arrangement of appropriate safe waiting areas for women on the three escalation pathways for review. |
| 103 | High Quality Choices in Place of Birth The Community Intrapartum services remain suspended There is a risk of not being able to provide high quality choices in place of birth (via appropriately staffed and resourced community midwifery teams, the freestanding midwifery unit at Neath Port Talbot Hospital, the alongside midwifery unit and obstetric unit at Singleton Hospital). The potential impact of this is poor patient experience and birth outcomes, poor staff morale and increased attrition of community midwives, increased acuity within obstetric services at Singleton Hospital, and the reduction of services could impact on organisational reputation. | 16 | Executive Director of Nursing | The risk score currently remains unchanged. Update Oct 2024: Birth Centre re-opened on 16th September 2024. Update Nov 2024: Community home births have also recommenced. The service are allowing these reinstated services a period of operation before re-assessment and reduction of the risk level. |

3.3 Risks Assigned to Other Committees

There are some risks assigned to other Committees in terms of overseeing actions to mitigate the risks, as outlined in table 2 below, noted here for information. As noted earlier, the detailed HBRR entries are also included in Appendix 1 for information. In view of the consequence to patients if the risks materialise, the Committees have requested that the Quality & Safety Committee be made aware of these risks.

Table 3: Risks Assigned to Other Committees with Referral to Q&S Committee for Information

| Ref | Description of Risk Identified (Summarised) | Current Score | Exec Lead | Committee |
| --- | --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care Service If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. (This risk includes ED, AMU and impact in community from ability to release ambulances at both front doors.) | 25 | Chief Operating Officer | Performance & Finance Committee |
| 16 (840) | Access to Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 20 | Chief Operating Officer | Performance & Finance Committee |
| 36 (1043) | Paper Record Storage Lack of a single electronic record means there is greater reliance on the provision of the paper record. If we fail to provide adequate storage facilities for paper records, then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. There is an increased fire risk where medical records are stored outside of the medical record libraries. | 16 | Director of Digital | Digital, Data, Research & Innovation Committee |
| 50 (1761) | Access to Cancer Services A backlog of patients now presenting with suspected cancer has accumulated during the pandemic, creating an increase in referrals into the health board which is greater than the current capacity for prompt diagnosis and treatment. Because of this there is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | 25 | Chief Operating Officer | Performance & Finance Committee |
| 94 (3516) | CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. This is further hindered by poor data quality which presents a risk to reporting until validation is complete. | 12 | Chief Operating Officer | Performance & Finance Committee |

3.4 Operational Quality & Safety Risks

Each Service Group and Directorate hold their own risk registers, which outline the operational risks facing each Service Group/directorate.

Operational risks relating to quality and safety that may need to be escalated for inclusion on the HBRR are brought to the attention of the Risk Management Group and/or Risk Scrutiny Panel for review and where appropriate added to, or linked to existing risks in, the Health Board Risk Register.

- FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information.

- RECOMMENDATION

Members are asked to:

- RECEIVE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Q&S Committee.

- REVIEW & COMMENT on the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - This report provides an update on the risk profile last reported to QSC in September 2024. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) Risks Assigned to the Quality & Safety Committee |  |