| Meeting Date | 6 November 2025 |  | Agenda Item |  |  | 4.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Quality & Safety Committee |  |  |  |  |  |
| Report Title | Risk Management Report - Quality & Safety Risks |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to inform the Quality & Safety Committee (QSC) of the risks from the Health Board Risk Register (HBRR) assigned to the Committee. |  |  |  |  |  |
| Key Issues | - The Committee last received the July HBRR at its September 2025 meeting. This report presents the position as recorded within the September 2025 HBRR, which includes some updates received in October. - Ten risks are assigned to the Committee for oversight. - One risk has reduced in score (HBR66 Access to Systemic Anti-Cancer Therapy). Nine are at the Board’s appetite threshold. - Additional risks overseen by other committees are included for information. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - RECEIVE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee. - REVIEW the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified and consider whether further action / assurance is required in respect of any. |  |  |  |  |  |

RISK MANAGEMENT REPORT – Quality & SAfety Risks

- INTRODUCTION

The purpose of this report is to inform the Quality & Safety Committee (QSC) of the risks from the Health Board Risk Register (HBRR) assigned to the Quality & Safety Committee.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular risk update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

As part of the resetting of health board risk management arrangements a new Risk Management Group had its inaugural meeting in April 2025. The Group is chaired by the Deputy Chief Executive and reports to the Management Board. It meets monthly and its role includes oversight of the risks within risk registers, and of the escalation and de-escalation of risks between them. The last meeting of the group was in August 2025. In September, Service Groups were asked by Executive Directors to review risks within their operational registers scoring 15 and above. The November meeting of the RMG will be a gateway review meeting at which these risks will be reviewed with Service Group Directors, to inform improved reporting of operational service risks to Committees and Board level, and links to the board-level strategic and corporate risk registers.

2.2 Risk Appetite

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high-quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

- GOVERNANCE & RISK

3.1 Action to Update the HBRR

Health Board risk register entries are circulated to lead Executive Directors monthly for review and updated where required. A consolidated, updated register is circulated to the Executive Team for agreement and final version issued. This report presents the position as recorded within the September 2025 HBRR, supplemented with some additional updates received in October. Key changes made in the most recent HBRR update are highlighted in red font.

3.2 HBRR Quality & Safety Risks

Ten risks are assigned to the Quality & Safety Committee for oversight (See Appendix 1 for full detail). The profile of risk scores is presented below:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Number of Risks Last Report | 0 | 0 | 3 | 6 | 1 | 10 |
| Number of Risks This Report | 0 | 0 | 3 | 7 | 0 | 10 |

Key movements are:

| New Risks | Nil |
| --- | --- |
| Scores Increased | Nil |
| Scores Reduced | HBR66 Access to Systemic Anti-Cancer Therapy (SACT) 2520 |
| Risks De-escalated | Nil |

There are 9 risks meeting or exceeding the Health Board’s risk appetite thresholds, for which action is required so that they may be reduced to acceptable levels. Table 1 below highlights recent changes / actions of note for those risks that are currently meeting or exceeding the thresholds.

Table 1: HBRR risks assigned to the QSC which meet or exceed the risk appetite threshold

| Risk Ref | Description of Risk (Summary) | Current Score | Exec Lead | Key Updates |
| --- | --- | --- | --- | --- |
| 4 (739) | Infection Control Risk of patients acquiring infection as a result of contact with the health care system, resulting in avoidable harm, impact on service capacity, and failure to achieve Tier 1 national infection reduction goals. | 20 | Reassigned: Executive Medical Director | The risk score currently remains unchanged. Update: No updates to the AMR (Anti-Microbial Resistance)/HCAI (Healthcare Acquired Infection) reduction goals have been received from Welsh Government (WG) to date. Health Board Q2 position to 30/09/2025 for HCAI Tier one infections: - C. difficile = 19 hospital onset cases (target 6). Combined (hospital onset and community onset) cumulative total = 122 cases. - Staph. aureus = 5 hospital onset cases (target 3). Combined cumulative total = 63 cases. - E. coli = 6 hospital onset cases (target 4). Combined cumulative total = 138 cases. - Klebsiella spp. = 2 hospital onset cases (target 4). Combined cumulative total = 60 cases. - Pseudomonas aeruginosa (Not included within targeted interventions). Combined cumulative total = 15 cases. IPC training compliance target has been achieved during Q2 2025/26. Compliance levels as of 30/09/2025 are: Level 1 = 91.03%, Level 2 = 85.32%. |
| 43 (1514) | Deprivation of Liberty Safeguards (DoLS) Due to a lack of Best Interest Assessor resource, there is a risk of failure to complete and authorise the assessments associated with Deprivation of Liberty/Liberty Protection Safeguards within the legally required timescales, exposing the health board to potential legal challenge and reputational damage. | 16 | Executive Director of Nursing & Patient Experience | The risk score currently remains unchanged. Update: The service is reporting one vacancy – a Band 7 Specialist Practitioner. This post is currently out to advert. The last risk report to this committee indicated numbers of breaches as 2 in June 2025 and 1 in July 2025. Since then, breaches for August increased to 7 though this this number reduced to 1 in September. Due to the increase in breaches for August the service has decided to maintain the risk score at its current level, and to continue to monitor and review monthly, to ensure the reduction in breaches is sustained, noting that the vacancy within the service may lead to an increase in October. |
| 61 (1587) | Paediatric Dental GA Service – Parkway Medical Safety risk as general anaesthetics are performed on children outside of an acute hospital setting. Repatriation of service to acute site delayed due to theatre capacity which means the health board continues to commission services for delivery outside of national guidance (WHC 2018-09). There is also an associated risk in that the diagnosing clinician does not deliver the care to the patient. | 16 | Chief Operating Officer | The risk score currently remains as previously reported. As previously noted, SBU Management Board has agreed that the contract with the current provider will be extended for 2+1 years while the Health Board explores a capital bid for a regional service as part of wider Paediatric Day Case Unit. There is no further update currently. |
| 64 (2159) | Health and Safety Infrastructure Insufficient resource and capacity of the health, safety and fire function to maintain legislative and regulatory compliance for the workforce & sites across the Health Board. | 20 | Director of Finance & Performance | The risk score currently remains unchanged. Ongoing action: - Having completed staffing structure review, next action is to work through Health Board governance processes to ensure affordability and to agree a risk-based, phased approach to implement any agreed structure going forward. (Target 31/03/2026). As noted last time, there was a successful conclusion to interviews for Head of Health & Safety post, with an agreed commencement date 01/11/2025. A further update will be provided following commencement. |
| 66 (1834) | Access to Cancer Services Delays in access to SACT (Systemic Anti-Cancer Therapy) treatment in Chemotherapy Day Unit | 20 (was 25) | Executive Medical Director | The risk score has been reduced from 25. This reflects the improvement in waiting time performance from Q4 24/25 to Q1 25/26. More recently the trend has shown a reduction in performance. The Quality Improvement Practitioner is currently investigating the reasons behind the performance dip over the summer with report expected by the end of October 2025. An action plan has been created to ensure all efficiencies are in place, including mitigating actions to address any potential challenges during the Christmas period. Ongoing actions: - Currently recruiting to posts (refreshed 31/10/2025) - Training of new staff to full competency (28/02/2026) |
| 69 (1418) | Safeguarding Adolescents being admitted to adult MH wards resulting in potential safeguarding issues | 20 | Chief Operating Officer / Executive Director of Nursing & Patient Experience | The risk score currently remains unchanged currently. Update: Controls have been reviewed by the Divisional Manager and confirmed no change. The Service Group will review again in six months. |
| 80 (1832) | Discharge of Clinically Optimised Patients If the health board is unable to discharge clinically optimised patients (COP) there is a risk of harm to those patients as they will decompensate, and to those patients waiting for admission. Lack of access to same day domiciliary care/emergency placements in the community hinders ability to avoid admission and associated harms. | 20 | Chief Operating Officer | The risk score currently remains unchanged. Update: Discharge-to-Reassess (D2RA) Principles have been reintroduced across the Health Board with external consultancy support. Actions: - Work programme and governance structure agreed by local partnership (health board & local authorities) to work up sustainable D2RA model (target 31/03/2025). - Formal agreement through Communities and Older Persons Board to proceed to OCP (Organisation Change Process) for health employees to deliver the D2RA hub and recruitment into Swansea Local Authority, with a limited offer from Neath Port Talbot Local Authority (31/01/2025). This risk will also be treated via actions taken in response to board-level risk HBR1 Access to Unscheduled Care including: - ‘Test of Change’ and advanced D2RA work. - Discharge improvement sprint (focusing on COP wards) to free up bed capacity/ improve flow across Morriston site. - Refresh of the Optimal Hospital Flow Framework at Board Rounds via sustainable ward-level discharge coaching and support). Lastly, services are exploring a revised model of COP management health board wide. |
| 85 (2561) | Non-Compliance with ALN (Additional Learning Needs) Act There is a risk of the Health Board not fulfilling the statutory requirements of the Additional Learning Needs and Education Tribunal (Wales) Act 2018 (the ALN Act) within the timescales that are required under the ALN Act, resulting in non-compliance with these duties. | 20 | Director of Allied Health Professions & Health Sciences | The risk score currently remains unchanged currently. Update: A structure of regular meetings between the DECLO and leads for ALN-impacted operational services is now in place. Ongoing actions: - Securing longer-term administrative and project management support needed to mitigate risks (target 30/11/2025). - Activity to be progressed to revise and refresh the Health Board’s ALN operational workplan for the 2025 / 26 school year, with a focus on actions required to mitigate the compliance risk (target 30/10/2025). - Revise processes through which the Health Board fulfils its duty under Section 64 of the ALN Act and ensure that accurate and reliable data is available (30/10/2025). |
| 89 (3071) | HMP Swansea There is a risk that the men in HMP Swansea will not receive the appropriate standard of care. This is due to the fact that the nursing establishment within the prison no longer fully meets the changed demographics and numbers of men being detained. The maximum operational capacity of the Prison can reach circa 480 men. The Health Board investment into the Prison is based on delivering services to 250 men. This was also highlighted as a risk in the recent HIW governance review. In addition, there is no headroom built into the Prison nursing establishment, so periods of sickness, leave and study renders the roster short. | 20 | Executive Director of Nursing & Patient Experience | The risk score currently remains unchanged. Update: An HMP and Mental Health service group workshop to develop and improve care pathway and provision was held 08/10/25. An SBAR (Situation Background Assessment Recommendation) report, risk assessment and Quality Impact Assessment has been submitted to PCT Head of Nursing for review – it covers development and enhancement of the substance misuse service in HMP in line with recommendations of RSP (Royal Society of Psychiatry) report 2024, and development of recommended actions and delivery plan for Healthcare Needs Assessment (PHW 2024) and mental health and substance misuse report (2024). A roster review meeting with Finance colleagues originally scheduled for 10/10/25 is being re-arranged to accommodate clinical pressures. Interviews for two band 6 posts are scheduled for 03/11/25 and another for administration support on 23/10/25. An additional pharmacy technician started 13/10/25 bringing the pharmacy team up to its full complement. Action (target refreshed): Review of staffing in prison. Royal College of Psychiatrists Substance Misuse and Mental Health Baseline assessment completed – analysis of outcome and agreement of further action next (30/11/2025) |

Table 2 below lists additional risks assigned to the Committee whose risk levels do not meet the threshold currently set within the Health Board’s risk appetite. However, these risks are presented for information also:

Table 2: HBRR risks assigned to the Committee that do not currently meet the risk appetite threshold.

| Risk Ref | Description of Risk (Summary) | Current Score | Exec Lead | Key Updates |
| --- | --- | --- | --- | --- |
| 105 | Significant increased cost for the replacement Pathology System (LIMS) If the new Laboratory Information Management (LIMS) system is not live before 15th December 2025 then there will be significantly more cost across NHS Wales which could impact the Health Board’s financial plans in 2025/26 and 2026/27. Costs would have to be covered to avoid pathology losing access to the current LIMS system resulting in the inability of pathology to deliver diagnostic results and blood transfusion services across all Health Board services including emergency, acute, primary and community services. | 16 | Reassigned: Director of Digital | The risk score currently remains unchanged. Update: The LIMS risk is no longer framed as a “loss of system” but as a financial risk – specifically, the cost implications of ensuring continued provision of a functioning pathology system. The programme is experiencing significant delays and defect volumes, impacting deployment timelines and operational readiness. Deployment Plan & Tranche 1 delay: The programme is structured into five tranches, with go-live dates staggered from July 2025 to March 2026. A sixth tranche (PHW / Microbiology / Cervical Screening) remains unscheduled due to unresolved middleware dependencies. Originally scheduled for mid-July, the technical go-live for Tranche 1 was deferred due to unresolved defects, including the critical trickle feed interface needed for dual running of LIMS 1.0 and 2.0. A revised dry-run is planned for late August, with go-live in early September. Defects: Approximately 160 new severity 1 and 2 defects are raised monthly. While a third have been fixed, they require retesting. Completion of UAT is contingent on resolving these defects. Dependencies and Risks: Blood Sciences must complete testing by end of August to meet the October deployment target. Significant sign-off activity is pending both locally and nationally. Actions (revised): - Determine what additional local costs may be attracted due to extending the project from 31st December 2025 until 31st March 2026 and how these could be funded (31/12/2025). - Continue to work in collaboration with other NHS Wales organisations to challenge supplier delivery and secure go-live dates before 31st March 2026 (31/02/2026). |

3.3 Risks Assigned to Other Committees

There are some risks assigned to other Committees in terms of overseeing actions to mitigate the risks, as outlined in table 3 below, noted here for information. As noted earlier, the detailed HBRR entries are also included in Appendix 1 for information. In view of the consequence to patients if the risks materialise, the Committees have requested that the Quality & Safety Committee be made aware of these risks.

Table 3: Risks Assigned to Other Committees with Referral to Q&S Committee for Information

| Ref | Description of Risk Identified (Summarised) | Current Score | Exec Lead | Committee |
| --- | --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care Service If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. (This risk includes ED, AMU and impact in community from ability to release ambulances at both front doors.) | 16 | Chief Operating Officer | Performance & Finance Committee |
| 16 (840) | Access to Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. (NB: Whilst cancer care is an element of Planned Care this risk does not include the Cancer Waiting Times target, which is covered in HBR Ref 50.) | 12 | Chief Operating Officer | Performance & Finance Committee |
| 36 (1043) | Paper Record Storage Lack of a single electronic record means there is greater reliance on the provision of the paper record. If we fail to provide adequate storage facilities for paper records, then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. There is an increased fire risk where medical records are stored outside of the medical record libraries. | 16 | Director of Digital | Digital, Data, Research & Innovation Committee |
| 50 (1761) | Access to Cancer Services There is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. The health Board remains unable to deliver on the target of 75% of patients being treated within 62 days and is currently under targeted intervention by Welsh Government to improve performance. | 20 | Chief Operating Officer | Performance & Finance Committee |
| 94 (3516) | CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. | 12 | Chief Operating Officer | Performance & Finance Committee |
| 104 | Failure to meet Tier 1 Targets in Clinical Coding Completeness There is a risk that clinical notes for inpatient episodes will not be coded in a timely way. (See HBRR for full description) | 20 | Director of Digital | Digital, Data, Research & Innovations |

3.4 Operational Quality & Safety Risks

Each Service Group and Directorate hold their own risk registers, which outline the operational risks facing each Service Group/directorate.

Operational risks relating to quality and safety that may need to be escalated for inclusion on the HBRR will now be reported to the Risk Management Group for review and where appropriate added to, or linked to existing risks in, the board-level risk register(s).

- FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information.

- RECOMMENDATION

Members are asked to:

- RECEIVE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Q&S Committee.

- REVIEW the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified and consider whether further action / assurance is required in respect of any.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - This report provides an update on the risk profile last reported to QSC in September 2025. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) Risks Assigned to the Quality & Safety Committee |  |