| Meeting Date | 24 October 2023 |  | Agenda Item |  |  | 6.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Management Report – Quality & Safety Risks |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Interim Director of Corporate Governance Gareth Howells, Executive Director of Nursing |  |  |  |  |  |
| Presented by | Hazel Lloyd, Interim Director of Corporate Governance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to inform the Quality & Safety Committee (QSC) of the risks from the Health Board Risk Register (HBRR) assigned to the Quality & Safety Committee. |  |  |  |  |  |
| Key Issues | - The QSC received the July 2023 HBRR extract at its August 2023 meeting. This report presents the updated September 2023 HBRR extract. - Twenty risks are assigned to the Quality & Safety Committee for oversight. - Seventeen of these are assessed to meet or exceed the Board’s risk appetite threshold. - Seven further risks are included in the register extract for information, but are overseen by other committees. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee. - CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any. |  |  |  |  |  |

RISK MANAGEMENT REPORT – Quality & SAfety Risks

- INTRODUCTION

The purpose of this report is to inform the Quality & Safety Committee of the risks from the Health Board Risk Register (HBRR) assigned to the Quality & Safety Committee for scrutiny.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular HBRR update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

Risk Register management is supported by a Risk Management Group (RMG) which meets quarterly and is responsible for overseeing the operational management of risk, ensuring local systems and processes are in place and are operating effectively to ensure appropriate reporting and escalation. The Group last met in July 2023.

Additionally, a Risk Scrutiny Panel is responsible for ensuring there is an appropriate and robust risk management system in place and working throughout the organisation. It is responsible for moderating new risks and risks escalated to the Health Board Risk Register (HBRR) and Board Assurance Framework (BAF) and recommending and advising the Management Board on the escalation and de-escalation of risks. The Panel last met in September 2023.

2.2 Risk Appetite

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating  lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

- MANAGEMENT OF QUALITY & SAFETY RISKS

3.1 Action to Update the HBRR

Health Board risk register entries are circulated to lead Executive Directors monthly for review and updated where required. A consolidated, updated register is circulated to the Executive Team for agreement and final version issued. The report presents the risks as recorded in the September 2023 HBRR – the relevant risk extracts are attached at Appendix 1. Key changes made in the most recent monthly update are highlighted in red font.

3.2 HBRR Quality & Safety Risks

Twenty risks are assigned to the Quality & Safety Committee for oversight (an increase from the 19 previously reported). The profile of risk scores is presented below:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 |
| --- | --- | --- | --- | --- | --- |
| Number of Risks | 1 | 2 | 7 | 9 | 1 |

Key movements are:

- One new risk

- HBR91: There is a risk that assessments under the Mental Capacity Act (MCA) are not undertaken and recorded as required.

- One risk score has been decreased

  - HBR67: Risk target breaches – Radiotherapy (from 25 to 20)

- No risks have been increased

- No risks have been closed

The new risk HBR91 has been assessed to meet the Health Board’s risk appetite threshold. Risk HBR84 has decreased but is still within the appetite threshold. All risks above are detailed with updates within the tables below.

There are 17 risks currently meeting or exceeding the Health Board’s risk appetite thresholds, for which action is required so that they may be reduced to acceptable levels. Table 1 below highlights recent changes / actions of note since the last meeting of the Committee for those risks that are currently meeting or exceeding the thresholds:

Table 1: HBRR risks assigned to the QSC which meet or exceed the risk appetite threshold

| Risk Reference | Description of risk identified (Summary) | Current Score | Exec Lead | Key Updates |
| --- | --- | --- | --- | --- |
| 4 (739) | Infection Control Risk of patients acquiring infection as a result of contact with the health care system, resulting in avoidable harm, impact on service capacity, and failure to achieve Tier 1 national infection reduction goals. | 20 | Executive Director of Nursing | The risk score currently remains unchanged. 15/08/2023 Progress update re Tier 1 reduction goals 01 Apr- 31 Jul 2023: Below trajectory for: • Klebsiella spp. bacteraemia - 27 (cumulative profile – 30 maximum) • Pseudomonas aeruginosa bacteraemia – 8 (cumulative profile - 9 maximum). Over trajectory for: • C. difficile - 70 (cumulative profile - 37 maximum) • Staph. aureus bacteraemia - 53 (cumulative profile – 26 maximum) • E. coli bacteraemia - 98 (cumulative profile - 84 maximum). |
| 13 (841) | H&S Compliance: Environment of Premises Risk of failure to meet statutory health and safety requirements. | 16 | Director of Finance | The risk score currently remains unchanged. Update 10/08/23: Site meeting in respect of PCT estate was rescheduled to 09/08/23. Some actions agreed and responsible owners identified with further review planned for end August 2023 due to some structural changes planned in PC&TSG to cover H&S/Fire/Estates for PC&TSG. Review of site wide cooperation / coordination meeting governance structure being reviewed to capture key actions i.e. fire risk assessment actions and other compliance areas. Estates Strategy and Discretionary Capital Plans approved and adopted. Actions: A review is currently taking place of current PCT structures and governance arrangements for estates and health & safety to cover key compliances and escalation processes (Target refreshed to 30/03/24). |
| 41 (1567) | Fire Safety Compliance Uncertain position in regard to the appropriateness of the cladding applied to Singleton Hospital in particular (as a high rise block) in respect of its compliance with fire safety regulations. | 16 | Director of Finance | The risk score currently remains unchanged. Actions remain: - Change in fire evacuation plans and alarm and detection cause and effect (Target 01/11/23). - Replacing the existing cladding and insulation with alternative specifications and inserting 30 minute fire cavity barriers where appropriate (Target 28/02/24). No further updates. |
| 43 (1514) | Deprivation of Liberty Safeguards (DoLS) Due to a lack of Best Interest Assessor resource, there is a risk of failure to complete and authorise the assessments associated with Deprivation of Liberty/Liberty Protection Safeguards within the legally required timescales, exposing the health board to potential legal challenge and reputational damage. | 20 | Executive Director of Nursing | The risk score currently remains unchanged. Update 16/08/2023: The breach time is approximately 8 weeks. Breaches have reduced from 41 (Jan 2023) to 17 (end June 2023). Job Description for a band 8a MCA/DoLS Lead is currently with Job Evaluation. The resources available are limited and there is still an imbalance between the workload for DoLS applications and the resources available. Agreement made 19/09/2023 that MCA/DoLS to sit within PCTSG; Training and Court of Protection to remain at present with Corporate Nursing. Formal response to be made shortly. Bespoke face-to-face training sessions for ward and medical staff is underway to help support the MCA/DoLS training need. This is in conjunction with statutory MCA/DoLS training. Regular updates on progress are provided to the Health Board Safeguarding Committee, and the Mental Health Legislative Committee. The risk score will continue to be reviewed as this work progresses. Ongoing Action: Overtime/additional hours agreed to fund. Sign off from nurse assessor team to process the backlog assessments. |
| 57 (1799) | Non-compliance with Home Office (HO) Controlled Drug (CD) Licensing requirements. The Health Board (HB) currently has limited assurance regarding compliance with HO CD Licensing requirements, nor does it have processes in place in respect of future service change compliance | 16 | Director of Corporate Governance | The risk score currently remains unchanged. Update 26/07/23: Several Home Office licence compliance visits undertaken – currently awaiting outcome from the Home Office regarding whether licences will be granted. A number of other Home Office licence compliance visits have been confirmed for the coming months. Corporate Governance team exploring options that could provide a control system to ensure ongoing compliance with Home Office CD licence requirements. Potential additional licensing requirements around care provided by external providers on SBU Health Board sites and private healthcare provision continue to be explored. Following discussion, it was agreed that the risk likelihood level should revert to the previous level (4) and therefore the overall risk score returned to 16. Update 14/08/23: No change since the previous update. |
| 58 (146) | Ophthalmology - Excellent Patient Outcomes Risk of failure to provide adequate clinic capacity for follow-up patients in Ophthalmology results in a delay in treatment and potential risk of sight loss. | 16 | Chief Operating Officer | The risk score currently remains unchanged. Update 18/08/2023: There has been a further reduction in the number of patients on the follow up not booked – down by 29% from the July 22 baseline figure. The backlog for glaucoma follow up appointments has reduced over the same period from 4639 to 3341 (ahead of trajectory for improvement). Action: An overall Regional Sustainability Plan to be delivered (Target 31/10/23) |
| 61 (1587) | Paediatric Dental GA Service – Parkway Identify alternative arrangements to Parkway Clinic for the delivery of dental paediatric GA services on the Morriston Hospital SDU site consistent with the needs of the population and existing WG and Health Board policies. | 16 | Chief Operating Officer | The risk score currently remains unchanged. Update 18/08/2023: Agreement with the Medical Director to maintain status with utilisation of Parkway. Suggested that Chief Dental Officer (CDO) be invited to visit Parkway for assurance. |
| 63 (1605) | Screening for Fetal Growth Assessment in line with Gap-Grow There is not enough Ultrasound capacity within Swansea Bay UHB to offer all women serial ultrasound scan screening in the third trimester in line with the UK perinatal Institute Growth Assessment Programme (GAP). Welsh Government mandate fetal growth screening in line with the GAP programme. There is significant evidence of the increased risk for stillbirth or neonatal mortality/morbidity (hypoxic ischaemic encephalopathy (HIE)), where a fetus is growth restricted (IUGR) and/or small for gestational age fetus (SGA). Identification and appropriate management for IUGR/SGA in pregnancy will lead to improved outcomes for babies. | 20 | Executive Director of Nursing / Director of Therapies & Health Sciences | The risk score currently remains unchanged. Actions: - Midwives provided until 30/09/2023 to complete training. CPD Midwives to escalate those non-compliant with training to Deputy Head of Midwifery for emails/meetings with staff members. (Target refreshed to 30/12/23) - Business case to be completed to include administrative support for midwife sonographer clinics to be secured to ensure streamlined service. (Target 31/08/23) Update 11/08/23: Service manager completing business case for radiology. Lead Midwife Sonographer asked to provide data to assess need for administration support as part of radiology business case. Critical staffing levels remain in Maternity and therefore no improvement in compliance. Practice Development Midwife to incorporate GAP Grow as part of mandatory training. Lead Midwife for Quality, Safety & Risk to meet with team for action plan. Mandatory training for new training year starting October 2023. Therefore action date changed. Midwifery sonography team have introduced scanning all low PAPP-A (Pregnancy Associated Plasma Protein-A) from 1/8/23. |
| 64 (2159) | Health and Safety Infrastructure Insufficient resource and capacity of the health, safety and fire function to maintain legislative and regulatory compliance. | 16 | Director of Finance | The risk score currently remains unchanged. Ongoing Action: It has been agreed to identify posts to progress recruitment on a phased approach over the next 12/24 months. This will be dependent upon availability of funding (Target 31/03/24). No further updates |
| 65 (329) | CTG Monitoring on Labour Wards Misinterpretation of cardiotocograph and failure to take appropriate action is a leading cause for poor outcomes in obstetric care leading to high value claims. The requirement to retain maternity records and CTG traces for 25 years leads to the fading/degradation of the paper trace and in some instances traces have been lost from records which makes defence of claims difficult. | 20 | Executive Director of Nursing | The risk score currently remains unchanged. Update 11/08/2023: Five incidents reported regarding K2 implementation. Maternity team identify risk should remain open until assurance provided of embedded practices with K2 implementation. All incidents logged on to K2 log and Maternity team have developed SOP to identify how to review, report and follow up incidents with K2. SOP created for ensuring access for agency and bank midwives. |
| 67 (89) | Risk target breaches – Radiotherapy Clinical risk – target breeches in the provision of radical radiotherapy treatment. Due to capacity and demand issues the department is experiencing target breaches in the provision of radical radiotherapy treatment to patients. | 20 | Executive Medical Director | Risk score decreased from 25 to 20 in August. Update 14/08/23: Current risk reduced to 20 as CT is back in clinical use and backlog reduced, but remains a single point of failure. CT1 recommissioning Business Case taken to Senior Management Team and approved at Business Case Assurance Group to go to Management Board in October. Action completed: New Linac required – Linac case agreed with WG. Actions: - Business Case to Business Case Assurance Group to recommission CT1 as resilience (Target refreshed to 31/10/23 for Management Board approval) - Business case for 2nd CT case (capital and revenue). (Target End Qtr 3 23/24) |
| 69 (1418) | Safeguarding Adolescents being admitted to adult MH wards resulting in potential safeguarding issues | 20 | Chief Operating Officer / Executive Director of Nursing | The risk score currently remains unchanged. Update 31/08/23: No CAMHS admissions to the unit for past 12 months, however this is not as a consequence to any changes to the patient pathway or service provision. After discussion at MH Legislation Committee it was agreed that this risk is scored correctly. Action: Next service group review of effectiveness of current controls. (01/12/23). |
| 80 (1832) | Discharge of Clinically Optimised Patients If the health board is unable to discharge clinically optimised patients there is a risk of harm to those patients as they will decompensate, and to those patients waiting for admission. | 20 | Chief Operating Officer | The risk score currently remains unchanged. Update 11/08/23: Actions refreshed by new COO. IDT to be set up on Morriston site to provide single point of access and support for complex dischargers prior to IDH being implemented. Action: Develop an Integrated Discharge Hub (target refreshed to 31/09/23). |
| 81 (2788) | Critical staffing levels – Midwifery: Midwifery absence rates are outside of 26.9% uplift leading to difficulty in maintaining midwifery rotas in the hospital and community setting. | 25 | Executive Director of Nursing | The risk score currently remains unchanged. Action: Development and dissemination of the organisational change to practice (OCP). Phase 1 of dissemination commencing July 2023 (Target 30/10/23 completion). Update 11/08/23: OCP consultation continues and staff offered drop in sessions and one to one with senior team. Recruitment of 7 midwives Band 5 and Band 6 (variable hours) and 15 newly qualified midwives commencing employment in October 2023. Induction for newly qualified midwives commenced 11/8/23. The Maternity Escalation guideline has been reviewed to ensure robust processes in place if acuity is high or critical staffing. Guideline is receiving comments following discussion in Maternity Quality and Safety. |
| 85 (2561) | Non-Compliance with ALNET (Additional Learning Needs & Education Tribunal) Act There are risks to the Health Board’s ability to meet its statutory duties and establish the effective collaborative arrangements required by the ALNET Act, which is being implemented through a phased approach. | 20 | Director of Therapies & Health Sciences | The risk score currently remains unchanged. Update 10/09/2023: Work to implement revisions to operational processes is close to completion. A Standard Operating Procedure and supporting documentation has been developed and training plans are in place. Lack of robustness in operational processes has been a significant challenge and the changes should address this. There is currently a gap in the ALN Project Manager post which will impact on the scale and pace of progress until a replacement is in place. Recruitment work is ongoing. Progress on addressing the backlog in compliance data has been slower than anticipated and a gap in historic data may need to be tolerated in order to focus on ensuring reliable data moving forward. DECLOs nationally have been asked by WG to develop a national assurance for Health Boards regarding their compliance with the requirements of the ALN Act. Having reliable prospective data, grounded in robust operational processes, will be essential. With limited capacity over the summer and the gap in Project Management capacity, work to establish collaborative working priorities for the next school year has been temporarily deferred. Actions added/refreshed: - Implement revisions to operational processes for statutory requests and responses, to ensure robust, clearly-understood processes and reliable prospective data capture. (Target 30/09/23) - Work with Informatics colleagues to ensure robust data regarding compliance, for which it is anticipated that national reporting will required. Activity is ongoing nationally to establish the national dataset. (Target 31/12/2023) - Address current backlog in compliance data. (Target 30/09/23) |
| 89 (3071) | HMP Swansea There is a risk that the men in HMP Swansea will not receive the appropriate standard of care. This is due to the fact that the nursing establishment within the prison no longer fully meets the changed demographics and numbers of men being detained. The maximum operational capacity of the Prison can reach circa 480 men. The Health Board investment into the Prison is based on delivering services to 250 men. This was also highlighted as a risk in the recent HIW governance review. | 20 | Executive Director of Nursing | The risk score currently remains unchanged. Actions: - Business case developed and included in IMTP, and representation made to WG and HB for additional funding. (Target 03/09/2023) - Through Prison Partnership Board exploring opportunities to implement the recommendations of HIW and Health Delivery Plan. (Target 31/09/2023) Update 01/08/23: The Group received £39k recurrent funding to support a proportion of the headroom. This has funded a band 5 pharmacy technician who can also administer medicines to the men to support the nursing deficit. There still remains a head room deficit for the nursing establishment as a total and all the risks described remain. In September the Mental Health In-Reach team are moving out of Parc Prison to work exclusively in Swansea HMP and there has been an additional successful bid for additional staff secured by the MHLD Group. Discussions are underway with the MHLD Group to consider how the nursing deficit gap can be filled utilising an integrated approach under a Trauma informed Approach. This is not yet concluded. |
| 91 (3432) NEW | There is a risk that assessments under the Mental Capacity Act (MCA) are not undertaken and recorded as required. | 16 | Executive Director of Nursing | New risk with current risk score 16. Update 19/09/2023: PCTSG Management Board meeting has formally agreed to host an expanded MCA DoLS team with an MCA Lead to oversee the application of MCA practice. Work will now begin to manage the service change. Actions: - Agree a required structure with senior accountability for MCA and the DoLS service (31/10/23). - Agreement of accountabilities and structure, an assessment to be undertaken of resource needs and funding options explored (17/10/2023) - A review of training has been placed on the agenda for the MCA / DoLS / Subgroup of the West Glamorgan Safeguarding Board – Agreed to a regional approach to reviewing and planning MCA DoLS training. (31/10/23) |

Table 2 below lists additional risks assigned to the Quality & Safety Committee whose risk levels do not meet the threshold currently set within the Health Board’s risk appetite. However, when the current appetite was agreed in November 2022, it was the Board’s aspiration that thresholds could be reduced in the future. In view of this, these risks are presented for information:

Table 2: HBRR risks assigned to the QSC that do not currently meet the risk appetite threshold

| Risk Reference | Description of risk identified (Summary) | Current Score | Exec Lead | Key Update |
| --- | --- | --- | --- | --- |
| 66 (1834) | Access to Cancer Services Delays in access to SACT (Systemic Anti-Cancer Therapy) treatment in Chemotherapy Day Unit | 15 | Executive Medical Director | The risk score currently remains unchanged. Update 14/08/23: Waiting times and breaches are scrutinised daily to ensure progress is monitored and data is captured. The self-administration of denosumab workstream is almost ready to be implemented. SACT CNS is awaiting comments, prior to going live with this. There is still inconsistency with number of breaches in CDU, therefore, it is not at a point where the risk can reduce from 15 to 12. Actions: - Relocation of SACT linked to AMSR programme and phase 2 of home care expansion case brought forward. (Target refreshed to 31/09/2023) - CDU planned to move into the main hospital Nov/Dec 2023. (Target 31/12/2023) |
| 74 (2595) | Delay in Induction of Labour (IOL) Delays in IOL can introduce avoidable risk and unnecessary intervention which can lead to poor clinical outcome for mother and/or baby. Delays in IOL lead to increased complaints and decreased patient satisfaction. | 15 | Executive Director of Nursing | The risk score currently remains unchanged. This risk should be read in conjunction with risk HBR81 on Critical Midwifery Staffing levels for further detail on controls & actions, including work on workforce paper. Updates 11/08/23: Working group continue to review induction of labour with reference to benchmarking other HB’s and induction agents. Actions: - Manage Critical midwifery Staffing (HBRR ref 81) to minimise disruption in IOL delay. (Target 30/09/2023) - Working group to be developed for the review of Induction of labour (Target 01/09/2023) |
| 84 (3036) | Cardiac Surgery – A Getting It Right First Time (GIRFT) The GIRFT review identified concerns in respect of cardiac surgery (including patient pathway/process issues) that present risks to ensuring optimal outcomes for all patients. Potential consequences include the outlier status of the health board in respect of quality metrics, including mortality following mitral valve surgery and aortovascular surgery. This has resulted in escalation of the service by WHSSC. | 8 | Executive Medical Director | The risk score currently remains unchanged. Update 12/08/23: No change. Await nursing workforce plans from Service Group. One action complete: Development of actions for improvement as advised by the Royal College of Surgeons. |

3.3 Risks Assigned to Other Committees

There are seven risks which are assigned to other Committees in terms of overseeing actions to mitigate the risks, as outlined in table 2 below, noted here for information. As noted earlier, the detailed HBRR entries are also included in Appendix 1 for information. In view of the consequence to patients if the risks materialise, the Committees have requested that the Quality & Safety Committee be made aware of these risks as well.

Table 3: Risks Assigned to Other Committees with Referral to Q&S Committee for Information

| Ref | Description of Risk Identified (Summarised) | Exec Lead | Committee | Current Score |
| --- | --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care Service If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. | Chief Operating Officer | P&F Committee | 25 |
| 16 (840) | Access to Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | Chief Operating Officer | P&F Committee | 20 |
| 36 (1043) | Paper Record Storage Lack of a single electronic record means there is greater reliance on the provision of the paper record. If we fail to provide adequate storage facilities for paper records, then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. There is an increased fire risk where medical records are stored outside of the medical record libraries. | Director of Digital | Workforce & OD Committee | 16 |
| 48 (1563) | CAMHS Failure to sustain Child and Adolescent Mental Health Services (CAHMS). | Director of Strategy | P&F Committee | 12 |
| 50 (1761) | Access to Cancer Services A backlog of patients now presenting with suspected cancer has accumulated during the pandemic, creating an increase in referrals into the health board which is greater than the current capacity for prompt diagnosis and treatment. Because of this there is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | Chief Operating Officer | P&F Committee | 25 |
| 82 (2554) | Risk of Closure of Burns Service There is a risk that adequate Burns Consultant Anaesthetist cover will not be sustained, potentially resulting in closure to this regional service and the associated reputational damage. | Executive Medical Director | P&F Committee | 16 |
| 88 (3100) | Non-delivery of AMSR programme benefits There is a risk that the Acute Medical Service Re-Design (AMSR) programme may not deliver the expected performance & financial benefits in a timely way. The principal potential causes of this risk are: workforce (OCP and recruitment requirements), capacity constraints linked to significant number of clinically optimised patients (COP), financial affordability linked to 90 beds in Singleton hospital that are due to close in Q3 2023. | Chief Operating Officer | P&F Committee | 20 |

3.4 Operational Quality & Safety Risks

Each Service Group and Directorate hold their own risk registers, which outline the operational risks facing each Service Group/directorate.

Operational risks relating to quality and safety that may need to be escalated for inclusion on the HBRR are brought to the attention of the Risk Management Group and/or Risk Scrutiny Panel for review and where appropriate added to, or linked to existing risks in, the Health Board Risk Register.

- GOVERNANCE AND RISK

This report and appendix present information on each of the risks assigned to the Committee for oversight. Within the report, particular attention is drawn to those risks exceeding the Board’s appetite, together with updates on action being taken to treat them by lead Directors and management.

- FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information.

- RECOMMENDATION

Members are asked to:

- NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee.

- CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - This report provides an update on the risk profile last reported to QSC in August 2023. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) Risks Assigned to the Quality & Safety Committee |  |