| Meeting Date | 29 October 2024 |  | Agenda Item |  |  | 3.3 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Gold Command for Maternity and Neonatal Services Progress Report |  |  |  |  |  |
| Report Author | Liz Wonnacott, Head of Service – Medical Director Kathryn Greaves, Clinical Director for Midwifery |  |  |  |  |  |
| Report Sponsor | Dr Raj Krishnan, Acting Executive Medical Director Hazel Powell, Interim Director of Nursing and Patient Experience |  |  |  |  |  |
| Presented by | Dr Raj Krishnan, Acting Executive Medical Director |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of the report is to set out the gold command arrangements established for scrutiny and assurance of improvement within maternity and neonatal services and the progress to date. |  |  |  |  |  |
| Key Issues | - In December 2023, the health board’s maternity and neonatal services were placed by Welsh Government into enhanced monitoring; - The escalation status followed an unannounced inspection by Healthcare Inspectorate Wales (HIW) in September 2023 during which seven areas of immediate action were identified; - An action plan was shared with HIW, with a follow-up unannounced visit in April 2024 to review progress; - Alongside this are other external reports and inspections which require action, as well as open incidents to be closed; - To scrutinise and seek assurance that the work required is being undertaken, a gold command structure has been established; - The report sets out the latest reported position against all areas of focus. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - ACKNOWLEDGE the work being undertaken to close the three outstanding enhanced monitoring actions; - BE ASSURED progress against the HIW action plan is on track and will be independently reviewed by the health board’s quality assurance team by the end of October 2024; - BE ASSURED the actions to address the Health Education and Improvement Wales (HEIW) maternity and neonatal specific actions are being taken forward; - ACKNOWLEDGE the successful reopening of the freestanding midwifery unit at Neath Port Talbot Hospital and the progress to recommence home births from 21st October 2024. - BE ASSURED the group has included within its remit the need to ‘horizon scan’ to look ahead to potential visits and/or reports which may require action. |  |  |  |  |  |

GOLD COMMAND FOR MATERNITY AND NEONATAL SERVICES PROGRESS REPORT

- INTRODUCTION

The purpose of the report is to set out the gold command arrangements established for scrutiny and assurance of improvement within maternity and neonatal services and the progress to date.

- BACKGROUND

In December 2023, the health board’s maternity and neonatal services were placed into enhanced monitoring by Welsh Government. This was because of concerns as to the quality and safety of the care provided raised by members of the Senedd and families who have accessed the services.

The escalation status followed an unannounced inspection by Healthcare Inspectorate Wales (HIW) in September 2023 during which seven areas of immediate action were identified. In addition, the formal report for the visit set out a number of recommendations for improvement, and an action plan was shared with HIW. HIW undertook a follow-up unannounced visit in undertaken in April 2024 to review progress and while some of work had been completed, there were still improvements required.

Alongside this are two Health Education and Improvement Wales (HEIW) targeted inspections of obstetrics and gynaecology in February and July 2024 as part of HEIW’s quality framework to identify areas working well or in need of improvement, as well as national reports which identify areas of improvement for maternity and neonatal services across the UK.

To scrutinise and seek assurance that the work required is being undertaken, a gold command structure has been established, led by the Acting Executive Medical Director as the senior responsible officer, supported by the Chief Operating Officer and Interim Director of Nursing and Patient Experience. Meetings are attended by members of the Singleton/Neath Port Talbot Service Group’s senior team under which sit maternity and neonatal services.

- GOVERNANCE AND RISK ISSUES

The main areas of focus for the group are enhanced monitoring, inspection action plans, open incidents, national reports and horizon scanning. Some of the key highlights reported in October 2024 include:

- Enhanced Monitoring

Senior members of the service group along with key members of the executive team meet with Welsh Government on a monthly basis to share progress against the actions required to achieve de-escalation and to take forward any new actions. There are three currently outstanding from previous meetings:

- Booking data – the data presented in August 2024 had shown a downward trend in the number of bookings but an interrogation of the systems highlighted not all the data from the community teams and auto-booking had been feeding into the reporting information. This has been resolved and the correct data will be shared at the October 2024 enhanced monitoring meeting;

- NHS Executive assurance visit – arranged for 31st October 2024 and an initial review of the three lines of defence assurance report has been completed to provide a baseline for the review. After the visit, an action plan can be developed of the areas on which to focus;

- Maternity dashboard – meetings are taking place between digital and maternity colleagues to commence populating the dashboard using the maternity e-reporting system BadgerNet, after which work will progress to ESR (electronic staff record) for training data.

The escalation criteria was considered by the gold command group and will now be reviewed by the maternity team to identify which are complete and which require more work in order to be de-escalated from enhanced monitoring. Any additional actions from the October 2024 enhanced monitoring meeting will be reviewed in the gold command meetings in November 2024.

- Inspection Action Plans

- HIW Inspections

As part of the work to address the recommendations made by HIW, the action plans for the 2019 HIW improvement plan and 2019 Birth Centre Improvement Plan were revisited, and all actions now closed. Also, the recommendations for the 2023 immediate improvement plan have been implemented, with the action plan closure in the process of being approved by the service group’s governance structure. In relation to the other reports:

| Report | Total Recommendations | Open Actions |
| --- | --- | --- |
| 2023 Singleton Hospital General Improvement Plan | 118 | 2 |
| 2024 Singleton Hospital Immediate Improvement Plan | 6 | 1 |
| 2024 Singleton Hospital General Improvement Plan | 27 | 12 |

The two outstanding actions for the 2023 general improvement plan are:

- 95% compliance with Breast Feeding Initiative (BFI) training – staff have been rostered to undertake the training and this will be completed in January 2025. BFI’s target of 80% has already been achieved;

- Standard operating procedure (SOP) to transfer patients to the intensive care unit (ICU) at Morriston Hospital - working draft has been agreed with ICU consultants and is in use until formal approval through the service groups governance structures is given on 21st October 2024.

In addition, two actions have been marked as closed on the 2023 general improvement plan as the planning is complete and work to implement is covered elsewhere:

- Implementation of BSOTS (Birmingham Symptom-specific Obstetric Triage System (BSOTS)  – system live but time to be included in job plans for clinicians to be available outside of labour ward to triage within 15 minutes, which will be progressed through the 2024 general improvement plan actions;

- Theatre and Bay Birthing Unit Environment – project group in place and progress will be monitored through the health board risk register.

Of the outstanding 2024 recommendations, six are to be completed in October 2024:

- Continue with plans to implement a single phone number for the whole service to direct patients to the correct phone line first time;

- Establish patient feedback forum;

- Explore issues relating to performance management and take required actions;

- Review the occupancy of the transitional care unit to ensure right staffing levels and skill mix;

- Develop system to support easy and up-to-date training compliance access;

- Review and update policies and guidelines.

Work is on course for all bar two of the recommendations to be completed by the December 2024 deadline. In addition to the BFI training referenced above is the recruitment of a women’s experience midwife, which will be completed by April 2025. Funding has been identified and recruitment is anticipated to start before the end of 2024, with the successful applicant likely take up post in 2025.

The health board’s quality assurance team will now review the work to date to provide independent assurance that the HIW actions are being completed comprehensively and in-line with the ask. This will take place before the end of October 2024.

One of milestone achievements for these action plans has been the reinstatement of community maternity services. Stage one was the reopening of the free-standing midwifery unit at Neath Port Talbot Hospital on16th September 2024. A £750,000 investment in maternity services, including the recruitment of 35 extra staff, saw the reopening of the free-standing midwifery unit and the upcoming reinstatement of home births in Swansea Bay. This comes two years after the free-standing midwifery unit was closed and the home birthing service suspended, both due to staffing shortages and pressures. All available resources were focused on Singleton Hospital to ensure safe care could continue to be provided, in line with professional guidance from the royal colleges. The health board reluctantly entered into this arrangement and recognised that it limited birth choice. It has been working hard behind the scenes to find a sustainable solution, which has now been achieved.

Board members heard in September 2024 that Swansea Bay was investing £750,000 in hospital-based and community midwifery over two years. This, coupled with changes to the way services are staffed, meant the free-standing midwifery unit at Neath Port Talbot Hospital and the home birth service could be reinstated. Previous attempts to recruit additional midwives were unsuccessful because of a national shortage. Now, Swansea Bay has succeeded in recruiting 21 midwives, a mix of newly qualified and experienced. The investment and new workforce model support effective, safe maternity services.

To date,13 babies have been born at the free-standing midwifery unit at Neath Port Talbot Hospital, with other women being able to start their labour there before being transferred elsewhere for alternative pain relief, all of whom have been happy to have the experience of the unit. In addition, parent craft classes have restarted.

The second stage is the restarting of homebirths and plans are progressing well, with women to have the option to deliver at home from 21st October 2024.

Another achievement has been an improvement in sickness absence, with a decrease from 11.99% to 6.5% in the qualified workforce, which was a recommendation by HIW and enhanced monitoring to improve staff availability.

- Health Education and Improvement Wales (HEIW)

Following two visits earlier in 2024, an action plan is place, the majority of which has already been delivered. There is one outstanding area relevant to maternity and neonates, which is job planning, and this will be completed in October 2024.

Since the two visits, a new cohort of trainees have rotated to the service and no concerns have been raised. An escalation framework is in place and a midwife attends the training forum to listen to any concerns. In addition, fortnightly catch-ups for the trainees are taking place.

- Open Incidents

|  | Maternity |  | Neonatal |  |
| --- | --- | --- | --- | --- |
|  | Open | Overdue | Open | Overdue |
| Incidents | 143 | 93 | 20 | 10 |
| Duty of Candour | 14 | - | 1 | - |
| Concerns | 16 | 14 | 0 | 0 |
| Redress | 33 | - | 3 | - |
| Claims | 58 | - | 5 | - |

Sprint sessions are taking place to close incidents as soon as possible where no harm has occurred, while the more serious are investigated by the midwifery team. The clinical leads for maternity and neonatal continue to prioritise the responses to concerns, redress and claims to sign-off the responses, but a number of the ones open are complex and part of legal proceedings.

At the most gold recent meeting, it was noted that more incidents are reported per month than can be closed. Assurance was given that this was reflective across Wales due to national triggers and the NHS Executive was looking to amend the list to make it more relevant. If this goes ahead, the health board will need to ensure it has appropriate governance structures in place to maintain good quality of care if fewer incidents are recorded. The high numbers are not necessarily a cause for concern as they show that people are not afraid to speak up. Only those which resulted in harm required investigating. The implementation of the Digital Maternal Cymru system nationally would also support with more relevant trigger reporting.

On average, the service is closing 85% of its incidents each month. However, there was a small dip to 75% for maternity and 69% in neonatal for September 2024 due to high clinical activity over the summer alongside staff annual leave, so fewer resources were available.

- National Reports

- MBRRACE-UK (Mothers and Babies: Reducing Risk through Audits and Confidential Enquiries across the UK)

The ‘State of the Nation Report Saving Lives, Improving Mothers’ Care October 2024 Surveillance findings and lessons learned to inform maternity care from the UK and Ireland Confidential Enquiries into Maternal Deaths from thrombosis and thromboembolism, malignancy and ectopic pregnancy 2020-2022, and morbidity findings for recent migrants with language difficulties’ has been published and work commenced on a benchmarking exercise and action plan, which will also take into account the findings of the Care Quality Commission review in NHS England.

- Maternity and Neonatal Safety Support Programme MatNeo SSP

The action plan for the MatNeo SSP report is being updated to ensure that any outstanding actions for Swansea Bay are being progressed and monitored.

Audit Wales Review of Operational Governance

The service had considered the recommendations made within the report around governance and leadership. The service group has recently undergone an organisational change process, resulting in a new leadership and governance structure, which address the findings of the report. The structure will be shared at the next gold meeting as there is a section specific to women and child health.

- Horizon Scanning

As part of the gold command’s role, it looks ahead to any potential reviews or reports relating to maternity or neonatal services. These could be regular national reports which are issued as standard or external reviews being undertaken either of the health board itself or other maternity and neonatal services from which there could be learning. The following two were identified for the near future:

- VON (International Vermont Oxford Network)

The VON report, which is a neonatal quality improvement review, is expected in the next few months.

- MBRRACE-UK

The national MBRRACE-UK report setting out how many stillbirths and neonatal deaths had occurred in 2023 was yet to be published. However, the maternity and neonatal services have worked through health board data to ascertain how many cases there have been. So far, there is nothing to suggest the health board is an outlier and all cases had been reviewed for learning and closure using the perinatal mortality review tool (PRMT).

- FINANCIAL IMPLICATIONS

There are no financial implications associated with this report.

- RECOMMENDATION

Members are asked to:

- ACKNOWLEDGE the work being undertaken to close the three outstanding enhanced monitoring actions;

- BE ASSURED progress against the HIW action plan is on track and will be independently reviewed by the health board’s quality assurance team by the end of October 2024;

- BE ASSURED the actions to address the Health Education and Improvement Wales (HEIW) maternity and neonatal specific actions are being taken forward;

- ACKNOWLEDGE the successful reopening of the freestanding midwifery unit at Neath Port Talbot Hospital and the progress to recommence home births from 21st October 2024.

- BE ASSURED the group has included within its remit the need to ‘horizon scan’ to look ahead to potential visits and/or reports which may require action.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| The health board is dedicated to ensuring that pregnancy and childbirth is a safe and positive experience for all service users in order to support healthy life choices and to give children the best start in life. This requires safe and effective maternity and neonatal services. The actions identified by the reviews and external bodies will support the improvements needed to achieve this. |  |  |  |
| Financial Implications |  |  |  |
| There are no financial implications associated with the report. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| There are no legal implications associated with the report. |  |  |  |
| Staffing Implications |  |  |  |
| There are no staffing implications associated with the report. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The health board has a 10-year vision to be a high-quality organisation. Work being undertaken to address the concerns raised and to de-escalate from enhanced monitoring will not only support that vision but develop maternity and neonatal services which are safe and sustainable in the longer-term. |  |  |  |
| Report History |  | Regular report |  |
| Appendices |  | No appendices |  |