| Ref | Date of Inspection | Inspection | HIW Ref | Report Rec’ns | Actions Agreed | Actions Complete | Actions Ongoing | Actions Overdue |  | Expected Completion Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MHLD |  |  |  |  |  |  |  |  |  |
| 1 | May 2023 | Ward F, NPTH | 03367 | 33 | 66 | 61 | 5 | 5 |  | TBC |
| 2 | Sep 2023 | Caswell Clinic, MHLD | 03642 | 15 | 15 | 12 | 3 | 3 |  | TBC |
| 3 | Oct 2024 | Tonna Hospital Suite 2 | 03690 | 17 | 37 | 27 | 10 | 9 |  | 30/04/2026 |
| 4 | Apr 2025 | Laurels & Briary | 04072 | 16 | 24 | 24 | 0 | 0 |  | Completed |
| 5 | Jul 2025 | Community MH Team (Swansea North) | 03871 | 32 | 79 | 23 | 56 | 56 |  | TBC |
| New | Oct 2025 | Tawe Clinic, Cefn Coed Hospital | 03641 | 39 | 89* | - | - | - |  | 30/11/2026 |
|  | NPTS |  |  |  |  |  |  |  |  |  |
| 6 | Jan 2023 | Paediatrics: Ward M & Oakwood Ward, Morriston | 03294 | 10 | 12 | 9 | 3 | 3 |  | TBC |
| 7 | Feb 2025 | Birth Centre, NPTH | 03750 | 8 | 12 | 12 | 0 | 0 |  | Completed |
|  | Morriston |  |  |  |  |  |  |  |  |  |
| 8 | Feb 2023 | IR(ME)R: DI Dept, Morriston | 03297 | 16 | 49 | 43 | 6 |  | 6 | 30/04/2026 |
| 9 | Jun 2024 | IR(ME)R: Nuclear Medicine, Morriston | 03707 | 13 | 23 | 12 | 11 |  | 11 | 30/04/2026 |
| 10 | Nov 2024 | ED Morriston | 03716 | 15 | 44 | 20 | 24 |  | 24 | TBC |
| 11 | Feb 2025 | Diagnostic Imaging, Singleton | 03653 | 21 | 23 | 22 | 1 |  | 1 | 30/04/2026 |
| 12 | May 2025 | Minor Injury Unit, NPTH | 03903 | 16 | 25 | 22 | 3 |  | 3 | TBC |
|  | PCT |  |  |  |  |  |  |  |  |  |
| 13 | Aug 2021 | HMP Swansea | N/a | 29 | 38 | 37 | 1 |  | 1 | TBC |

SUPPORTING NOTES

MENTAL HEALTH & LEARNING DISABILITIES SERVICE GROUP

1) Ward F NPTH (ref 03367): The 5 outstanding actions relate to smoking cessation/policy, nurse call alarms (estates), fire extinguishers relating to Section 136 suites and estates work, and two actions relating to the model of care (linked to transformation work). The Service Group indicates it is updating their improvement plan for approval locally at director level and then sharing with the corporate Risk & Assurance team.

2) Caswell Clinic (ref 03642): There are 3 outstanding actions relating to policy, environment and alarm system. The service has been inspected more recently by HIW. The position will be reviewed against improvements required following the more recent inspection when HIW’s report is received.

3) Tonna (ref 03690): Most actions remaining relate to capital and environmental factors, workforce, and training compliance of staff.

4) Laurels & Briary (ref 04072): All actions within the improvement plan have now been confirmed complete by the MHLD Service Group. CLOSED (pending sign off at Quality & Safety Group)

5) CMHT (ref 03871): Further review is required to update actions remaining for these inspections in the service

Also: Tawe Clinic (ref 03641): The 3-month progress against the improvement plan is being prepared for submission to HIW in April. Figures will be added above afterwards. *Figures are not included in the summary total of the main report yet.

NEATH PORT TALBOT & SINGLETON SERVICE GROUP

6) Paeds (ref 03294): Two actions are subject to review currently with a view to closure. The final action relates to the refurbishment of the environment, for which progress made and action remaining (and associated timescales) are subject to further internal discussion.

7) Birth Centre, NPTH (ref 3750): The service has confirmed the last action complete. CLOSED (pending sign off at Quality & Safety Group)

MORRISTON SERVICE GROUP

8) Diagnostic imaging Dept Morriston (ref 03297): Further review is required to update actions remaining for these inspections in the service

9) Nuclear Medicine Morriston (ref 03707): Progress towards completion has been indicated on a substantial number of actions remaining but require further review & sign off within the Service Group before confirmed complete.

10) ED Morriston (ref 03716): Further review is required to update actions remaining for these inspections in the service

11) Diagnostic Imaging Singleton (ref 03653): All but one action complete. The last matter has been discussed at All Wales Quality Imaging Forum and has been queried with HIW (response awaited).

12) MIU NPTH (ref 03903): Progress has been indicated on 2 of the 3 remaining actions but they require sign off within the Service Group before confirmed complete.

PRIMARY COMMUNITY & THERAPY SERVICE GROUP

13) HMP Swansea: One action remains: It is dependent upon allocation of further funding, which is not identified currently. The risk is on the Corporate Risk Register.