Appendix 1: SBUHB Implementation Plan Listening to People: NHS Complaints, Incidents and Redress Process

1. Programme Aim

Implementation of an integrated Listening to People (LTP) Process for Complaints, Incidents and Redress within Swansea Bay University Health Board (SBUHB).

2. Scope

This programme focuses on improving how we listen, respond and learn from people who raise concerns.

Table 1 confirms workstreams within and outside of the scope of this implementation plan.

Table 1.

| Within Scope | Outside of Scope |
| --- | --- |
| NHS Concerns managed under LTP, including early resolution | Primary care contractor concerns (unless escalated) |
| Listening discussions | Employment matters |
| Patient safety incident interface | Safeguarding (except interface) |
| Redress | Legal claims (except Redress interface) |
| Duty of Candour | General enquiries outside of the scope of LTP |
| Single point of access |  |
| Advocacy and accessibility pathways |  |
| Organisational implementation |  |
| Workforce skills and training |  |
| Performance reporting |  |

3. Roles and Responsibilities

- Executive sponsor- Executive Director of Nursing and Patient Experience

- Senior Responsible Officer- Deputy Director of Nursing and Patient Experience

- Programme Leads- Associate Director of Nursing and Patient Experience, Corporate Head of Quality and Safety

- Service Group Delivery Leads- Service Group Directors

- Operational Delivery Leads- Corporate Head of Concerns Assurance, Corporate Head of Quality and Safety, Service Group Quality and Safety Leads.

4. Implementation Approach

SBUHB will implement Listening to People through a five-phase programme aligned to the national roadmap

### Phase 1 — Initiate & Assess (Q4 2025/26)

- Board approval and executive leadership confirmed

- Corporate, Service Group and stakeholder engagement

- Accessibility, advocacy and early resolution review

- Gap analysis against the seven LTP standards

- Baseline data and reporting established

### Phase 2 — Design & Plan (Q4 2025/26)

- Co-design operating model with Service Groups

- Develop implementation, change and communications plans

- Finalise policy, Standard Operating Procedures, templates and advocacy pathways

- Design central First Contact triage hub

### Phase 3 — Embed (Late Q4 2025/26)

- Workforce training and communications rollout

- Pilot operating model and central hub

- Embed early resolution and listening discussions

- Establish communities of practice and refine processes

### Phase 4 — Operate & Assure (Q1–Q2 2026/27)

- Single point of access fully live

- Performance dashboard operational

- Independent advice pathways in place

- Quarterly board assurance reporting established

### Phase 5 — Review & Improve (Q3–Q4 2026/27)

- Audit and independent scrutiny

- Review of serious harm and death cases

- Benefits realisation (3 and 6 month reviews)

- Annual Concerns and Learning Report published

- 2027 improvement plan agreed

### 5. Outcomes and Benefits

### For People Using Our Services

By Q4 2026/27, people will experience:

- Timely, compassionate responses — at least 75% of LTP responses within timescales

- Clear, open communication — ≥90% Duty of Candour compliance

- Faster resolution of concerns — ≥50% reduction in overdue complaints

- Easier access and advocacy — a single point of access and clear independent advice pathways

- A consistent and equitable experience across all Service Groups

- Feeling heard and respected, with responses that are meaningful and personalised

### For Staff

Staff will be supported to listen, respond and learn effectively through:

- Clear, standardised processes that reduce ambiguity and re-work

- Reduced backlog pressure and more manageable workloads

- Improved confidence and competence — ≥90% training compliance

- Clear escalation and advice routes, including independent advice pathways

- A supportive listening culture, improving morale and professional resilience

### For the Organisation

The organisation will benefit from:

- Stronger Board assurance and improved governance

- Reduced organisational risk through timely responses and Duty of Candour compliance

- Improved performance visibility, including backlog management and trend analysis

- Build trust from our patients, communities and staff by showing that we listen, respond promptly and learn from what people tell us

- Greater consistency across Service Groups, reducing unwarranted variation

- Better learning and intelligence triangulation through a single access model

- Improved external assurance and trust in how concerns and incidents are handled

  - Individual Workstreams

| Workstream | Key Actions | Responsibility | Timescale |
| --- | --- | --- | --- |
| Training & Education | Training plan and needs analysis; deliver training | NHS Performance and improvement and Associate Director of Nursing and Patient Experience | Months 1–12 |
| Process | Policy, standard operating procedures, templates | Associate Director of Nursing and Patient Experience and Corporate Head of Concerns Assurance | Months 1–3 |
| Digital/Data | Dashboard; single access tracking | Digital Intelligence | Months 3–6 |
| Governance | Assurance framework; Board reporting | Corporate Head of Quality and Safety | Months 2–5 |
| Accessibility & Advocacy | Independent advice pathways | Corporate Head of Concerns Assurance | Months 2–5 |
| Workforce | Workforce plan, workforce engagement and workforce delivery | Corporate Head of Quality and Safety and Service Group Directors and Director of Workforce and teams | Plan –1-2 month. Engagement & delivery tbc |

  - Risks and Dependencies

This table highlights priority risks, current controls and mitigation actions for the Listening to People programme, with clear ownership for assurance.

| Risk Area | Risk Rating (Impact × Likelihood) | Current Controls | Further Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Systems & data reliability | Very High (4 × 5) | Manual workarounds and national templates | Datix updates, digital reporting plan and targeted training | Corporate Head of Concerns Assurance; Digital Intelligence Business Partner |
| Backlog pressures | Very High (4 × 5) | Service Group improvement plans | Targeted corporate support and oversight | Service Group Directors |
| Workforce capacity | High (4 × 4) | Workforce plan in place | Phased delivery and Service Group workforce planning | Corporate Head of Quality & Safety; Service Group Directors; Director of Workforce |
| Engagement with Primary Care Providers & Independent Sector | Moderate–High (4 × 3) | Early engagement activity | Formal engagement and mitigation plan | Associate Director of Nursing & Patient Experience; Corporate Head of Quality & Safety |
| Training & education delivery | Moderate (3 × 3) | Training implementation plan | Service Group and corporate delivery support | Associate Director of Nursing & Patient Experience; Service Group Directors |
| Internal & external comms | Moderate (2 × 4) | Implementation comms plan | Ongoing structured communications | Executive Director for Insight, Communication & Engagement (DICE) |

Dependencies

- Digital reporting capability

- National digital work

- Operational capacity

- National LTP guidance and supporting materials

- Successful staff engagement

- Duty of Candour processes

- Advocacy capacity and provision

- DICE capacity

Stakeholder Engagement and Communication

An organisational-wide communications plan will be delivered by DICE. This will be supported by corporate and service group-led communication within specific services and arenas.

Patients and the public will continue to shape improvement through the national survey and engagement with Llais, undertaken quarterly, with participation monitored against agreed targets

9. Monitoring, Evaluation & Assurance

| Category | Items |
| --- | --- |
| Progress monitoring | Monthly programme dashboard Exception reporting Milestone tracking |
| Reporting route | Listening to People Board Quality & Safety Committee Health Board (by exception) |
| Measures of success | Early resolution of concerns for ≥40% LTP ≥90% Duty of Candour ≥95% Reduction in overdue cases Improved patient feedback Single access utilisation Staff experience measures Learning data measures |
| Post-implementation | 3-month review 6-month benefits realisation Annual learning report |

10. Equality Commitment

An Equality Impact Assessment has been completed and informs the programme’s design. Welsh language standards, accessibility requirements and inclusive design principles are embedded throughout the model. Engagement with vulnerable groups has shaped development, with ongoing monitoring of experience and equality data to identify disparities and drive continuous improvement.