Appendix 2 - SBUHB Listening to People Programme — Red/ Amber/ Green (RAG) Delivery Dashboard

1. Overall Programme Status

| Area | RAG | Commentary | Trend | Owner |
| --- | --- | --- | --- | --- |
| Overall Programme | 🟡 | On track but dependent on Service Group (SG) readiness | → | SRO |
| Gap Assessment | 🟢 | Baseline underway | ↑ | Associate Director of Nursing and Patient Experience (ADON) and SG Directors |
| SOP & Policy Development | 🟡 | Draft completed. Engagement to be commenced. | → | ADON and Head of Concerns (HOC) |
| Workforce Training | 🟡 | Plan developed. Materials drafted. Dates to be advertised. National training commenced. | → | Head of Quality and Safety (HQS), Organisational Development/Quality Safety and Improvement Team |
| Digital & Dashboard | 🟡 | Requirements defined | → | Digital, HQS |
| Single Access Model | 🟢 | Planned for Q1 2026 | → | Head of Q&S and ADON |
| Board Assurance | 🟢 | Reporting framework agreed | → | SRO and HQS |

RAG Definitions

- 🔴 Red = Off track / significant risk, 🟡 Amber = Some risk / mitigation in place🟢 Green = On track

- ⚪ Not started

2. Milestone Tracker

| Milestone | Due Date | RAG | Commentary | Owner |
| --- | --- | --- | --- | --- |
| Board approval of strategic objective | Q4 2025/26 | 🟢 | Submitted to LTP Board | Exec Sponsor |
| Gap analysis complete | Q4 2025/26 | 🟡 | Drafted, to be reviewed at LTPPB. | ADON and SG Directors |
| SOPs finalised | Month 3 | 🟡 | Drafted, to be reviewed at LTPPB ed | ADON HQS HOC |
| Training package ready | Month 3 | 🟡 | Plan developed. Materials drafted. Dates to be advertised. National training commenced. | ADON, HQS, OD/QSI |
| Pilot launched | Late Q4 2025/26 | 🟢 | First contact change complete. Evaluation is dynamic. | SG Directors, HQS HOC |
| Single access live | Q1 2026 | 🟢 | Single access point live | Digital & HOC |
| Dashboards live | Month 6 | 🟡 | Build not started | Digital & Programme team |
| Quarterly Board reporting | Q1 2026 | 🟢 | Template agreed | HOFC |
| Full rollout | Month 9 | 🟡 | Being led by service groups and corporate inbox. | SRO |

3. Key Risks (Top 5)

| Risk | Current RAG | Mitigation | Owner |
| --- | --- | --- | --- |
| Workforce capacity | 🟡 | Phased rollout; prioritisation | SRO |
| HB engagement variability | 🟡 | Exec sponsorship; co-design | ADON and HQS |
| Digital delivery risk | 🟡 | Early Digital involvement | Digital |
| Training uptake | 🟢 | Mandatory programme planned | SG Directors |
| Change fatigue | 🟡 | Strong comms plan | Comms |

4. Performance Indicators (once live)

| Metric | Target | Current | RAG |
| --- | --- | --- | --- |
| LTP responses in time | ≥90% | TBC | ⚪ |
| % of concerns in Early Resolution | ≥40% | TBC | ⚪ |
| Duty of Candour compliance | ≥95% | TBC | ⚪ |
| Overdue complaints | ↓50% | TBC | ⚪ |
| Staff training compliance | ≥90% | TBC | ⚪ |
| Overdue incidents | decreasing | TBC | ⚪ |