| Meeting Date | 08 October 2026 | Agenda Item | 3.3 |
| --- | --- | --- | --- |
| Name of Meeting | Quality & Safety Committee |  |  |
| Report Title | Update report on clinically optimised patients |  |  |
| Report Author | Alison Gallagher: Interim Assistant Director of Operations: UEC |  |  |
| Report Sponsor | Chief Operating Officer |  |  |
| Presented by | Jon Scott, Chief Operating Officer |  |  |
| Freedom of Information | Open |  |  |
| FoI Closed detail | If closed, choose detail |  |  |
| Impact Assessment Summary Outcome |  | IA Completion date |  |
| Purpose of the Report | For Discussion |  |  |
| Report Summary; detailing any action required |  |  |  |
| This paper is submitted at the request of the Quality & Safety Committee to gain an update on the clinically optimised patient position. The report sets out the following: - Performance against trajectory and risks to delivery - Overview of the current position - The impact of the clinically optimised patient cohort from a patient and organisational perspective - Update on the work programme aligned to Discharge to Recover & Assess, (D2RA). |  |  |  |
| Key Issues |  |  |  |
| - There has been evidence of delivery against trajectory however there has been a growth in the number of clinically optimised patients during Sept 26. - The Health Boards ability to provide timely urgent and emergency care is compromised by the clinically optimised patient cohort occupying acute and non-acute hospital beds thus preventing flow from the Emergency Department (ED) and assessment areas. - The financial burden of accommodating the clinically optimised patient cohort is estimated at circa £18 m based on 25/26 calculations – this includes the bed day utilisation and the use of surge capacity and associated variable pay costs to staff the areas. - There is patient impact resulting from prolonged hospital stay in terms of deconditioning, loss of independence and longer-term reliance on ongoing care in the community. - The Health Board are providing an alternative to timely social care provision at the cost of delivering timely access to urgent and emergency care. |  |  |  |
| Decision / Action required | No |  |  |
| Recommendations |  |  |  |
| The Quality & Safety Committee are asked to; Take cognisance of: - The content of the report. - The growing clinically optimised patient position and the impact on individual patients. - The impact of the clinically optimised position on urgent and emergency care access and flow. - The cost of the clinically optimised patient cohort plus the surge costs associated with front door overcrowding. |  |  |  |

Update report on clinically optimised patients

- INTRODUCTION

This report provided at the request of the Quality & Safety Committee provides an overview of the Clinically Optimised patient (COP) position in respect of:

- Current performance against trajectory and risks to delivery;

- The impact of the clinically optimised patient cohort on the Urgent Emergency Care (UEC) pathway, system capacity and the delivery of urgent and emergency care services;

- An overview of the ongoing work programme in relation to reducing the number of clinically optimised patients occupying hospital beds.

- BACKGROUND

The Health Board have experienced significant challenge in respect of expediting the flow of the clinically optimised patient cohort in partnership with Local Authority colleagues.

There is evidence of genuine operational improvement. We are seeing better performance in a number of the leading indicators that we know are important for flow. Discharge before midday at Morriston is above target, there is a greater focus on weekend discharge, clinically optimised patients and discharge lounges, and there is much stronger organisational ownership of urgent and emergency care than there was previously. Welsh Government has also recognised the focus and actions we are taking are the right ones.

The reason long waits for ambulances and patients awaiting beds remain challenging is twofold:

- improvements in flow processes have not yet translated into actual delivery of sufficient bed availability and system capacity.

- the number of patients who no longer require hospital services occupying beds on the acute and non-acute hospital sites has increased outside of the trajectory to reduce the total numbers to below 100 by 31 March 2027

Actions to benefit from the improvements in flow are underway and are managed through the Operational Delivery Group and Operational Programme Board.  Actions to resolve the number of patients waiting for social care support are managed through the weekly Health and Social Care interface meeting and the Older Person’s Board.

The Welsh Government Hospital Discharge Policy indicates that Health and Social Care partners should adopt a ‘Discharge to Recover & Assess’, (D2RA) model enabling discharge of this patient group within 48 hours of being deemed clinically optimised. The aim of the D2RA pathways is to enable assessment of care needs in an appropriate environment outside of the hospital setting.

The D2RA model describes discharge to assess in four pathways as follows:

Pathway 0: is for those individuals who do not require any further community care support to leave hospital than when they arrived, whether at an emergency department, assessment areas or as an inpatient.

Pathway 1: People can return home with new or additional care packages of support from health and/or social care and be promptly assessed in their own environment to then inform any additional care package of support from health and/or social care. This includes people requiring intensive support or care at home that can be safely implemented.

Pathway 2: People are supported in a short-term facility to enable recovery, rehabilitation, reablement, assessment, care planning or short-term intensive support in a 24-hour bed-based setting, before returning home.

Pathway 3: People who require complex 24-hour support includes people discharged to their usual place of residency, a care home for the first time, existing care home residents returning to their care setting with an increased change in needs.

Current performance against trajectory:

The table below sets out actual performance against a local trajectory both in terms of the number of pathways of care delays and bed days. Since April 26 the number of pathways of care delays has exceeded the trajectory with over performance against the agreed reduction. There has been a deterioration in September 26 whereby the trajectory has not been achieved with a marked growth in the position, and a correlating growth in bed day utilisation. However, the average length of stay of this patient cohort is reduced. To note, in respect of the bed day and average length of stay, the ‘expected’ numbers mirror the ‘observed’ as the measures were only introduced in August 26.

| Ambition | Status | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| The number of Pathway of care delays should be <100 at any one time by 31 March 2027 | Expected | 210 | 200 | 190 | 180 | 170 | 160 | 150 | 140 | 130 | 120 | 110 | 100 |
|  | Observed | 200 | 192 | 173 | 159 | 172 |  |  |  |  |  |  |  |
| The sum of the total number of bed days that patients who are reported as having been delayed at the census date had been waiting up until that point (i.e. from start of delay not im month) | Expected | 9930 | 9879 | 8978 | 8615 | 9520 | 9280 | 9000 | 8680 | 8320 | 7920 | 7480 | 7000 |
|  | Observed | 9930 | 9879 | 8978 | 8615 | 8820 |  |  |  |  |  |  |  |
| Avg length of delay | Expected | 50 | 51 | 52 | 54 | 56 | 58 | 60 | 62 | 64 | 66 | 68 | 70 |
|  | Observed | 50 | 51 | 52 | 54 | 51 |  |  |  |  |  |  |  |

Risks to Delivery:

Despite the initial good performance against trajectory, the recent deterioration is a risk that delivery will fail during the Winter months. Historically, the pathway of care delays deteriorates during the winter with an increase in patient numbers and a growth in length of stay. The risks to delivery include:

- Workforce fragility and increased absence from work in critical teams both from a Health and Social Care perspective.

- A reduced level of Local Authority service provision over the Christmas and New Year period with a predictable recovery lag throughout January.

- Maintaining the current level of capacity to support Pathways 1 and 3 – potential for reduced capacity in both pathways as a result of staff absence and closure of beds in the Care Home sector resulting from Winter illness including Flu, Covid and norovirus.

- Delays in patients leaving hospital due to exposure to infection or recovery from infection, thus extending the length of stay in hospital beds.

Overview of the current position:

The graphs above sets out the clinically optimised position in respect of bed occupancy, patient numbers, Mental Health & Learning Disabilities (MH&LD) versus non-MH&LD and the bed days used by this patient cohort. These areas are explored below:

Bed day occupancy:

Bed day occupancy for the clinically optimised patient cohort is 220 bed days at the mean, with the range between 210 and 230. There has been a significant increase in September with bed day occupancy exceeding the upper control limit at 245-250 bed days used suggesting special cause variation. Local Authority partners have advised that this is due to:

- Annual Leave and sickness in Social Work teams

- Fluctuating capacity in community based social care teams due to staff absence

- Mismatch in care package availability versus the demand

- Increased discharge complexity

Average COP patients by date:

This graph mirrors the bed day trend indicating that the occupancy changes are driven by patient volume.

Average COP patients by type:

Non-MH&LD patients account for the majority of the clinically optimised patient occupancy. The MH&LD clinically optimised cohort is small but consistent in volume

Clinically optimised patient occupancy:

The clinically optimised patient cohort occupy between 15 – 20% of the Health Board bed pool. There has been a growth in occupancy in August and September with 20% of the bed pool currently occupied thus impacting system flow and increasing urgent care system pressures.

The impact of the clinically optimised patient cohort on system flow.

Clinically optimised patients occupy between 15 – 20% of the hospital bed pools. Operationally this impacts patient flow and contributes to the following:

- Overcrowding of the Emergency Department and front door Assessment services, including Acute Medical Assessment, Frailty and Surgical Assessment services.

- Prolonged length of stay for patients in the ED and assessment services impacting service delivery and providing poor patient experience.

- Patients being nursed in non-designated clinical settings including corridors, waiting rooms and boarded on ward areas.

- Poor performance against key urgent and emergency care performance metrics including 4 hr and 12 hr Emergency Department measures and ambulance handover within a maximum of 45 minutes.

- Elevated system escalation status resulting from poor flow and activation of triggers that are key indicators of system pressures, with a recent Business Continuity event for emergency pressures during September 26.

- Impact on the elective bed pools as patients are out lied into core elective capacity to alleviate pressure on the Emergency Department and assessment areas.

- Prolonged delays for transfer out of critical care beds which are high cost with patients being held in critical care environments in the absence of ward bed availability.

Patient impact of pathway delays

The impact of prolonged hospitalisation on elderly patients is well understood.

If you are 80 years old and in hospital for just one week you will experience a 20% loss of muscle power, 1.5 kg loss of muscle mass and 10% decrease in aerobic capacity. If this is combined with inactivity associated with non-value-added hospital stays then there is additional accelerated bone loss, respiratory and swallowing issues, incontinence in 50%, muscle weakness that persists for 3-5 years with a 48% increase in disability. These changes result in postural hypotension, falls, delirium, pneumonia, delayed recovery, poor nutrition and hydration and increased infections and result a 5-fold increase in the need for institutional care on discharge as well as an increased risk of death.

National figures show that 1:6 older people who normally walk independently need help with walking on discharge from hospital, 1:3 are discharged with a significant disability that was not present on admission and only 30% are back to their usual level of function within a year.

Reducing both the number of clinically optimised patients and the lengths of stay of this patient cohort will result in the following patient benefits:

- Avoidance of delay related harm and deconditioning from prolonged and non-value-added hospitalisation.

- More patients will get home or to their next destination earlier in their pathway.

- The patient’s likelihood of maintaining pre-hospital functionality /independence is increased if they can leave hospital when their acute care episode is completed.

Work programme to reduce the clinically optimised patient cohort:

There is an extensive work programme in place overseen by the UEC Programme Board and reporting into the regional Older Persons Board. The programme has focussed on pathway specific improvements, development of critical enabling policy documents and infrastructure to deliver a revised operating model to support this patient cohort.

Key achievements:

- Redesign of Pathway 1 with standardisation of the processes across the region.

- Development of the Health Board Discharge policy which encompasses optimal hospital flow, patient choice and reluctant discharge.

- Trusted assessment model agreed – partially implemented – dependant on a resourced Integrated Discharge Hub.

- Process mapping of all pathways with revised processes to reduce pathway delays.

- Revised clinically led pathway management for stroke rehabilitation.

- Reduced delays for reablement in the community with a standardised regional offer for Pathway 1.

- Development of an optimal hospital flow dashboard with key performance indicators that can be accessed by ward teams.

- Launch of a designated Pathway 3 ward in Neath Port Talbot Hospital in September 26 to test a revised model of working for an eligible group of pathway 3 patients. Social Work, designated Discharge Liaison Nurse resource and the Long-Term Care team are part of the ward operating model which is the first time this multi-disciplinary resource has been aligned to ward base.

Work in progress:

- Development of pathway event timescales with escalation framework for management of pathway delays.

- Development of an internal web page designed to support ward multi-disciplinary teams with navigation to pathway specific referral forms, policies and patient information.

- GOVERNANCE AND RISK MANAGEMENT

There is joint working between the Health Board and Local Authority partners aimed at reducing the number of clinically optimised patients and the length of stay of patients. The focus of the work programme has been based on pathway and process redesign, however, there has been no work in relation to right sizing community capacity. The performance and metrics associated with the clinically optimised patient cohort are monitored through Service Group performance meetings, UEC and Older Persons regional partnership Boards and at executive level through the Health Board Performance escalation meetings with NHS Performance and Improvement, (NHS P&I).

There is a monthly meeting with the Pillar 3 team, part of NHS P&I where the data and local actions are discussed and challenged with a particular emphasis on accurate reporting.

- FINANCIAL IMPLICATIONS

The total costs associated with the clinically optimised patients remaining in hospital beds and the failure response to open surge is circa £18.1m as at 25/26.

In terms of the financial challenge of the Health Board, the reduction of the clinically optimised patient cohort is a key enabler of patient flow and therefore patient safety and would serve to enable a reduction in in-patient capacity thus releasing money to contribute to the significant financial deficit.

- RECOMMENDATIONS

The Quality & Safety Committee are asked to take cognisance of;

- The content of the report.

- The growing clinically optimised patient position and the impact on individual patients.

- The impact of the clinically optimised position on urgent and emergency care access and flow.

- The cost of the clinically optimised patient cohort plus the surge costs associated with front door overcrowding.

- The actions the Health Board are taking with Local Authority partners to improve the number of patients in delay.

| Governance and Assurance |  |  |
| --- | --- | --- |
| Strategic Objectives |  |  |
| Strategic Objectives (please choose which is impacted) | People of Swansea Bay live healthier, fairer and more prosperous lives | ☐ |
|  | Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships | ☒ |
|  | Care is delivered in partnership with our communities in safe and appropriate setting, supported by innovation | ☐ |
|  | The health board is a great place to work where staff feel valued and work together towards a common goal | ☐ |
|  | The health board is a resilient, sustainable and responsible organisation | ☐ |
| Health and Care Standards |  |  |
| Standards (please choose which applies) | Safe Care | ☐ |
|  | Timely Care | ☒ |
|  | Effective Care | ☒ |
|  | Efficient Care | ☐ |
|  | Equitable care | ☐ |
|  | Person-centred Care | ☐ |
|  | Staff and Resources | ☐ |
| Enablers (please choose which applies) | Whole Systems Approach | ☒ |
|  | Leadership | ☐ |
|  | Workforce | ☐ |
|  | Culture | ☐ |
|  | Information | ☐ |
|  | Learning, Improvement and Research | ☐ |
| Quality, Safety and Patient Experience |  |  |
| The paper sets out the impact that clinically optimised patients may be exposed to as a result of prolonged stays in hospital. The paper also explores how this further impacts the organisations’ ability to provide timely urgent and emergency care with reference to overcrowding in the Emergency Department and associated potential harms. |  |  |
| Financial Implications |  |  |
| The financial implications associated with the clinically optimised cohort bed day utilisation and the failure response to the compromised patient flow is estimated at circa £18m, based on 25/26 calculations. |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |
| Staffing Implications |  |  |
| The staffing implications relate to the care and management of the clinically optimised patient cohort who do not benefit from acute hospital models of care and do not require the staffing models aligned to the ward areas where they are cared for. |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |
| Report History |  |  |
| Previous updates provided to both Performance and Finance Committee and Quality and Safety Committee. |  |  |
| Appendices |  |  |
| None. |  |  |