## 12 month HCAI Improvement Plan
Morriston Hospital Service Group Infection Prevention Improvement Plan 2023/24
Goal | Method | Baseline position | 3 month | 6 month | 9 month | 12 month | Outcome | Responsibility | Q1 Progress | Q2 Progress | Q3 Progress | Q4 Progress
Infection Prevention & Control Infection Prevention and Control(IPC):Reduction of HCAIs to achieve national expectations and improvement in training, audit, cleaning and decontamination standards. | Achieve reduction in 5 key healthcare associated infections through application of evidence-based practice and best practice guidance | Baseline for 22/23: C. difficile: 107 cases | Cumulative total to Q1: C. difficile: 11 cases | Cumulative total to Q2: C. difficile: 27 cases | Cumulative total to Q3: C. difficile: 39 cases | Cumulative annual total: C. difficile: 51 cases | Cumulative annual total: C. difficile: 51 cases | Service Group Senior Leadership Team | Cumulative total to Q1: C. difficile: 22 cases - above trajectory (22%á yr-on-yr increase)
|  | Baseline for 22/23: Staph. aureus bacteraemia: 73 cases | Cumulative total to Q1: Staph. aureus bacteraemia: 10 cases | Cumulative total to Q2: Staph. aureus bacteraemia: 19 cases | Cumulative total to Q3: Staph. aureus bacteraemia: 28 cases | Cumulative annual total: Staph. aureus bacteraemia: 37 cases | Cumulative annual total: Staph. aureus bacteraemia: 37 cases |  | Cumulative total to Q1: Staph. aureus bacteraemia: 14 cases - above trajectory (26%â yr-on-yr reduction)
|  | Baseline for 22/23: E. coli bacteraemia: 82 cases | Cumulative total to Q1: E. coli bacteraemia: 21 cases | Cumulative total to Q2: E. coli bacteraemia: 40 cases | Cumulative total to Q3: E. coli bacteraemia: 58 cases | Cumulative annual total: E. coli bacteraemia: 76 cases | Cumulative annual total: E. coli bacteraemia: 76 cases |  | Cumulative total to Q1: E. coli bacteraemia: 27 cases - above trajectory (29%á yr-on-yr increase)
|  | Baseline for 22/23: Klebsiella bacteraemia: 45 cases | Cumulative total to Q1: Klebsiella bacteraemia: 9 cases | Cumulative total to Q2: Klebsiella bacteraemia: 18 cases | Cumulative total to Q3: Klebsiella bacteraemia: 24 cases | Cumulative annual total: Klebsiella bacteraemia: 30 cases | Cumulative annual total: Klebsiella bacteraemia: 30 cases |  | Cumulative total to Q1: Klebsiella bacteraemia: 8 cases - below trajectory (27%â yr-on-yr reduction)
|  | Baseline for 22/23: Pseudomonas aeruginosa bacteraemia: 24 cases | Cumulative total to Q1: Pseudomonas aeruginosa bacteraemia: 3 cases | Cumulative total to Q2: Pseudomonas aeruginosa bacteraemia: 6 cases | Cumulative total to Q3: Pseudomonas aeruginosa bacteraemia: 9 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 12 cases | Cumulative annual total to Q4: Pseudomonas aeruginosa bacteraemia: 12 cases |  | Cumulative total to Q1: Pseudomonas aeruginosa bacteraemia: 3 cases - on trajectory (50%â yr-on-yr reduction)
| Sustained improved compliance with Antimicrobial Stewardship and Start Smart Then Focus Standards (SSTF) | Baseline position for Morriston @ March 2023: % appropriate choice - 92% % Indication documented - 89% % Stop Review - 65% % 72 hour review - 93% IV to Oral Switch @ 72 hours - 7% | Review results of antimicrobial stewardship audits for Morriston | Identify top 3 high antimicrobial prescribing wards/clinical specialties; undertake SWOT analysis and agree improvement plan with relevant clinical teams, engaging FP1 medical staff in undertaking SSTF audits. | Evaluate audit results (reports retrospective), identify potential interventions and implement actions | Re-audit | Improved compliance with Start Smart Then Focus antimicrobial stewardship key indicators, and audit results monitored by Service Group Clinical cabinet and Infection Control Committee | Service Group Senior Leadership Team | Position for Morriston to end Q1: % appropriate choice - 93%á % Indication documented - 87%â % Stop Review - 66%á % 72 hour review - 93%≡ IV to Oral Switch @ 72 hours - 10%á
| Achieve compliance with national training target for infection prevention & control-related mandatory training (all available staff). Working toward IP&C Training, Level 1 and Level 2 – ≥85% (available staff) | ESR Baseline March 2023: IPC Level 1: 81% (Nursing 89%; Medical & Dental - 46%; AHP - 93%) IPC Level 2: 26% (Nursing 36%; Medical & Dental - 11%; AHP - 27%) ANTT: 38% (Nursing 62%; Medical & Dental - 8%; AHP - 51%) | Evidence of improved compliance against baseline. | Evidence of improved compliance against Q1. | Improved compliance against Q2 | ≥85% compliance | Improved compliance with Level 1 and Level 2 IPC and other IPC-related training, progressing to national target level | Service Group Senior Leadership Team | ESR Position June 2023: IPC Level 1: 81% ≡ IPC Level 2: 28% á ANTT: 41% á
| Continue to report monthly IPC-related audit for clinical areas (currently reported via Nursing Metrics) and Matrons audits (to include an IPC-related focus), and identifying themes. Establish an assurance process to monitor and track results, actions, and improvements (to link with HB-wide development of proactive audit system utilising AMaT). | Currently, clinical areas report outcomes of IPC environmental audit via Nursing Metrics, but this does not identify areas of non-compliance and does not facilitate tracking of improvement actions. Nursing Metrics Baseline Position @ March 2023: Monthly IPC Audit Score - 92%; WHO 'My 5 Moments' compliance - 87% | Reporting via existing systems in Nursing Metrics whilst awaiting AMaT development | Pilot updated Standard Infection Control Precautions (SICP) audit tools at ward level in preparation for AMaT development. | Switch to AMaT tools when developed or continue in current format and report locally | Improvement in audit compliance, monitoring and tracking and establishment of a baseline for future improvement | Improvement in audit compliance, monitoring and tracking and establishment of a baseline for future improvement | Service Group Senior Leadership Team | Nursing Metrics @ June 2023: Monthly IPC Audit Score - 93%á; WHO 'My 5 Moments' compliance - 94%á
| Environment – Cleaning Compliance scoring matrix >95% | Baseline position for Morriston @ March 2023: Cleaning (Domestic Services) - 97.94%; Estate condition - 95.5%; Nursing cleaning - 100% | >95% | >95% | >95% | >95% | Maintain compliance with National Standards of Cleanliness | Service Group Senior Leadership Team | Position for Morriston @ June 2023: Cleaning (Domestic Services) - 98%; Estate condition - 97.7%; Nursing cleaning - 98%
| Work towards compliance with the National Decontamination Agenda and relevant Welsh Health Technical Memorandum documents. | Additional services transferred to Morriston Hospital Service Group following Acute Medical Service Redesign which requires a review of all decontamination services to establish the current situation | Agree a Service Group assurance framework which can deliver a Service Group position in relation to national decontamination standards | Formalise the assurance process through Service Group Management Board. | Decontamination sub-group, which will report into the Service Group Infection Control Committee, which brings together progress against the relevant key decontamination Quality Priorities | Evidence that the Service Group reports on progress against the relevant key decontamination Quality Priorities | Evidence that the Service Group reports on progress against the relevant key decontamination Quality Priorities | Service Group Senior Leadership Team | Initial discussions to agree the assurance framework. Formal process to be agreed by Service Group Management Board.