| Meeting Date | 24 September 2024 |  | Agenda Item |  |  | 6.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Management Report - Quality & Safety Risks |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Interim Director of Corporate Governance |  |  |  |  |  |
| Presented by | Hazel Lloyd, Interim Director of Corporate Governance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to inform the Quality & Safety Committee (QSC) of the risks from the Health Board Risk Register (HBRR) assigned to the Quality & Safety Committee. |  |  |  |  |  |
| Key Issues | - The Q&S Committee received an extract from the March 2024 HBRR at its May 2024 meeting. This report presents the position as recorded within the August 2024 HBRR. - Twelve risks are assigned to the Quality & Safety Committee for oversight. This includes two risks transferred to the Committee from another (HBR43 Deprivation of Liberty Safeguards & HBR91 Mental Capacity Act Assessments). - Recent changes of note: - One risk has increased in score (HBR52 Impact Assessment Requirements); - Two risks have closed (HBR81 Midwifery Critical Staffing Levels and HBR91 Mental Capacity Act Assessments). The first of these closed has followed the disaggregation of its elements into two new, separate risk entries (HBR102 & HBR103 – both reported within this report). - Nine of the risks are assessed to meet or exceed the Board’s risk appetite threshold. - Additional risks overseen by other committees are included for information. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - RECEIVE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Q&S Committee. - REVIEW & COMMENT on the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any. |  |  |  |  |  |

RISK MANAGEMENT REPORT – Quality & SAfety Risks

- INTRODUCTION

The purpose of this report is to inform the Quality & Safety Committee (QSC) of the risks from the Health Board Risk Register (HBRR) assigned to the Quality & Safety Committee.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular HBRR update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

Risk Register management is supported by a Risk Management Group (RMG) which meets quarterly and is responsible for overseeing the operational management of risk, ensuring local systems and processes are in place and are operating effectively to ensure appropriate reporting and escalation. The Group last met in May 2024. The next meeting is in October 2024.

Additionally, a Risk Scrutiny Panel is responsible for ensuring there is an appropriate and robust risk management system in place and working throughout the organisation. It is responsible for moderating new risks and risks escalated to the Health Board Risk Register (HBRR) and Board Assurance Framework (BAF) and recommending and advising the Management Board on the escalation and de-escalation of risks. The Panel last met in September 2024.

2.2 Risk Appetite

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating  lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

- GOVERNANCE & RISK

3.1 Action to Update the HBRR

Health Board risk register entries are circulated to lead Executive Directors monthly for review and updated where required. A consolidated, updated register is circulated to the Executive Team for agreement and final version issued. This report presents the position as recorded within the August 2024 HBRR. Key changes made in the most recent update are highlighted in red font.

3.2 HBRR Quality & Safety Risks

Twelve risks are assigned to the Quality & Safety Committee for oversight. The profile of risk scores is presented below:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 |
| --- | --- | --- | --- | --- | --- |
| Number of Risks | - | 1 | 5 | 6 | - |

Key movements are:

- New risks:

There are two new risk register entries reflecting the disaggregation of elements of the previous risk HBR81, which is has been closed this month:

  - HBR102 Inability to maintain Birthrate Plus compliant rosters

  - HBR103 High Quality Choices in Birth Place

Additionally, two risks that were previously overseen by the Mental Health Legislation Committee are now allocated to the Quality & Safety Committee, so included in this report:

  - HBR43 Deprivation of Liberty Safeguards

  - HBR91 Mental Capacity Act Assessments

- Risks with increased scores

There is one risk with increased score 1216:

  - HBR52 Impact Assessment Requirements

- Risks with reduced scores

There are no risks with recently reduced scores

- Risks closed/de-escalated

There are two risks closed within the August HBRR:

  - HBR81 Midwifery Critical Staffing Levels:

As noted above, this risk has been disaggregated, re-articulated and replaced by two risks: one describing the risk associated with maintenance of staffing levels in accordance with Birthrate Plus guidance; another describing the risk to service user experience arising from lack of choice of birth place. Both new risks are recorded within the risks assigned to the QSC.

  - HBR91 Mental Capacity Act Assessments:

Following action to address causes of the risk as described within the HBRR, the risk description and content has been refreshed. The current risk has been approved for closure within the HBRR and a new entry describing the risk associated with training/competency in relation to the Act, assessed at a lower level, has been opened for management within the operational risk register in PCT Service Group.

There are 9 risks meeting or exceeding the Health Board’s risk appetite thresholds in the August HBRR, for which action is required so that they may be reduced to acceptable levels. Table 1 below highlights recent changes / actions of note for those risks that are currently meeting or exceeding the thresholds.

Table 1: HBRR risks assigned to the QSC which meet or exceed the risk appetite threshold

| Risk Ref | Description of Risk (Summary) | Current Score | Exec Lead | Key Updates |
| --- | --- | --- | --- | --- |
| 4 (739) | Infection Control Risk of patients acquiring infection as a result of contact with the health care system, resulting in avoidable harm, impact on service capacity, and failure to achieve Tier 1 national infection reduction goals. | 20 | Executive Director of Nursing | The risk score currently remains unchanged. Update: Regular Executive Healthcare Acquired Infection (HCAI) scrutiny meetings with each Service Group continue. Service Group HCAI improvement plans were reviewed by the Infection Prevention & Control Strategic Group (IPCSG) and returned with proposals for revision. Revised HCAI Improvement Plans were resubmitted and approved by the IPCSG on 31/07/24. IPC training compliance at 13/08/24: Level 1 - 91.06 % Level 2 has increased to 79.86%. Tier 1 infection progress to Targeted Intervention de-escalation criteria to the end of July 2024: - C. difficile - 5 hospital onset cases (target 6). Combined (hospital onset and community onset) cumulative total – 75 cases. - Staph. aureus - 4 hospital onset cases (target 3). Combined cumulative total - 39 cases. - E. coli - 4 hospital onset cases (target 4). Combined cumulative total - 67 cases. - Klebsiella spp. - 4 hospital onset cases (target 4). Combined cumulative total - 42 cases. - Pseudomonas aeruginosa - (Not included within targeted interventions). Combined cumulative total - 3 cases. |
| 43 (1514) | Deprivation of Liberty Safeguards (DoLS) Due to a lack of Best Interest Assessor resource, there is a risk of failure to complete and authorise the assessments associated with Deprivation of Liberty/Liberty Protection Safeguards within the legally required timescales, exposing the health board to potential legal challenge and reputational damage. | 16 | Executive Director of Nursing | This risk was previously overseen by the Mental Health Legislation Committee. The risk score currently remains unchanged. Update: Breaches for Q1 are reported at 7. All substantive Best Interest Assessors have returned from sick leave. |
| 61 (1587) | Paediatric Dental GA Service – Parkway Medical Safety risk as general anaesthetics are performed on children outside of an acute hospital setting. Repatriation of service to acute site delayed due to theatre capacity which means the health board continues to commission services for delivery outside of national guidance (WHC 2018-09). There is also an associated risk in that the diagnosing clinician does not deliver the care to the patient. | 16 | Chief Operating Officer | The risk score currently remains unchanged. Update: The transfer of services from Parkway are now part of new theatre programme and the team are liaising with those coordinating the Theatre Transformation work. |
| 63 (1605) | Screening for Fetal Growth Assessment in line with Gap-Grow There is not enough Ultrasound scanning & clinic capacity within Swansea Bay UHB to offer all women serial ultrasound scan screening in the third trimester in line with the UK perinatal Institute Growth Assessment Programme (GAP). Welsh Government mandate fetal growth screening in line with the GAP programme. There is significant evidence of the increased risk for stillbirth or neonatal mortality/morbidity (hypoxic ischaemic encephalopathy (HIE)), where a fetus is growth restricted (IUGR) and/or small for gestational age fetus (SGA). Identification and appropriate management for IUGR/SGA in pregnancy will lead to improved outcomes for babies. | 20 | Executive Director of Nursing / Director of Therapies & Health Sciences | The risk score currently remains unchanged. Actions: - Achieved 85% Gap Grow training compliance at end March 2024. Target of 95% revised for achievement by end August 2024. (Target 31/08/2024) - Business case written, including administrative support for midwife sonographer clinics to be secured to ensure streamlined service - currently in circulation for comment with aim of discussion at Senior Management Team by revised date of end of August 2024. (Target 30/08/2024) Following a meeting with Radiology, a start date of w/c 14th October has been agreed to re-instate three weekly scanning in Singleton and Neath & Port Talbot hospitals. |
| 64 (2159) | Health and Safety Infrastructure Insufficient resource and capacity of the health, safety and fire function to maintain legislative and regulatory compliance for the workforce & sites across the Health Board. | 16 | Director of Finance & Performance | The risk score currently remains unchanged. Update: Health & Safety, Capital and Estates now sit under the umbrella of Finance. This is currently undergoing a restructure, with the H&S structure included within this and any changes to be phased in, with a target date of 31/03/2026. |
| 69 (1418) | Safeguarding Adolescents being admitted to adult MH wards resulting in potential safeguarding issues | 20 | Chief Operating Officer / Executive Director of Nursing | The risk score currently remains unchanged. After reviewing the ongoing issues and increased acuity on ward F for the previous 18 months MHLD management indicate that this risk is scored correctly, but will continue to be closely monitored. Next service group review of effectiveness of current controls is scheduled by 30/09/2024. |
| 80 (1832) | Discharge of Clinically Optimised Patients If the health board is unable to discharge clinically optimised patients there is a risk of harm to those patients as they will decompensate, and to those patients waiting for admission. | 20 | Chief Operating Officer | The risk score currently remains unchanged. This area is an integral component of the Health Board Targeted Intervention recovery plan. Action: Paper highlighting outputs and lessons learned from the implementation of the Patient Assessment Team to be considered by Urgent & Emergency Care Board to inform further actions / next steps. (Target 31/07/2024) Update: Multi Agency Discharge Event (MADE) undertaken at Morriston in August has highlighted key actions to be addressed by all Service Groups and an action plan has been developed. This has been supported by a 6As audit. The MADE will be repeated in October across all Service Groups to ensure shared learning and improvements across the system. This is all being monitored by the Urgent & Emergency Care (UEC) Targeted Intervention Board and into the UEC Programme Board. |
| 81 (2788) | Critical staffing levels – Midwifery Unplanned absences resulting from long and short-term sickness, alongside maternity leave, have resulted in critical staffing levels, which undermine the ability to maintain the full range of expected services safely, increasing the potential for harm, poor patient outcomes and/or choice of birthplace. Poor service quality or reduction in services could impact on organisational reputation. | Previously 20 See notes | Executive Director of Nursing | *Risk Closed* As noted earlier, this risk has been disaggregated, re-articulated and replaced by two risks: - HBR102 describing the risk associated with maintenance of staffing levels in accordance with Birthrate Plus guidance; - HBR103 describing the risk to service user experience arising from lack of choice of birth place. Both new risks are recorded within the risks assigned to the QSC. |
| 85 (2561) | Non-Compliance with ALNET (Additional Learning Needs & Education Tribunal) Act There are risks to the Health Board’s ability to meet its statutory duties and establish the effective collaborative arrangements required by the ALNET Act, which is being implemented through a phased approach. | 20 | Director of Therapies & Health Sciences | The risk score currently remains unchanged. Update: Meeting is scheduled in September with Digital colleagues to establish timescales for completion of work that is progressing to develop digital infrastructure needed for the Health Board to reliably capture its compliance with its legal duties under the ALN Act. Deadlines may require adjustment following this. Deadline for development and implementation of operational systems needed for services to make use of the digital infrastructure is also likely to require adjustment based on the above. Activity is being progressed to establish the job role for project management support but this has not been finalised. Pending updates regarding finalisation of the job role and recruitment timescales over the next 2 weeks, deadline for having the required capacity in place will be adjusted. |
| 89 (3071) | HMP Swansea There is a risk that the men in HMP Swansea will not receive the appropriate standard of care. This is due to the fact that the nursing establishment within the prison no longer fully meets the changed demographics and numbers of men being detained. The maximum operational capacity of the Prison can reach circa 480 men. The Health Board investment into the Prison is based on delivering services to 250 men. This was also highlighted as a risk in the recent HIW governance review. In addition there is no headroom built into the Prison nursing establishment so periods of sickness, leave and study renders the roster short. | 20 | Executive Director of Nursing | The risk score currently remains unchanged. Update: Investment in team is expected by September 2024. Risk will be reviewed following this. |
| 91 | Mental Capacity Act Assessments There is a risk that assessments under the Mental Capacity Act (MCA) are not undertaken and recorded as required. | Previously 16 See notes | Executive Director of Nursing | This risk was previously overseen by the Mental Health Legislation Committee. *Risk now closed* Update: The responsibility for Mental Capacity Act transferred to PCT Service Group to align with the DoLS service from 01/04/2024. The MCA/Lead has completed their induction. Processes and the MCA/DoLS structure are now in place to ensure MCA is implemented across the Health Board. New in-house Level 3 MCA/DoLS Training has been implemented with up to 4 half day sessions a month. Training commenced May 2024. Risk regarding assurance for MCA assessment compliance within SBU remains under review. Outcome from training evaluation feedback forms to be reviewed. Noting the progress above in respect of structures and processes, it was agreed to close this risk entry and consider the risk afresh with focus on its remaining causes – training/competency. The residual risk has been assessed at a lower level and agreed for management within the operational service register in PCT Service Group (ref 3835). |

Table 2 below lists additional risks assigned to the Quality & Safety Committee whose risk levels do not meet the threshold currently set within the Health Board’s risk appetite. However, in line with the Board’s aspiration that thresholds could be reduced in the future, these risks are presented for information:

Table 2: HBRR risks assigned to the QSC that do not currently meet the risk appetite threshold

| Risk Reference | Description of risk identified (Summary) | Current Score | Exec Lead | Key Update |
| --- | --- | --- | --- | --- |
| 66 (1834) | Access to Cancer Services Delays in access to SACT (Systemic Anti-Cancer Therapy) treatment in Chemotherapy Day Unit | 15 | Executive Medical Director | The risk score currently remains unchanged. |
| 102 | Inability to maintain Birthrate Plus ® complaint rosters Birthrate Plus® enables health boards to calculate their midwifery staffing requirements based on their specific activity, case mix, demographics and skill mix. There is a risk non-compliance with roster templates due to increased acuity, unplanned staff absence and vacancies. The potential impact of this may be reduced staffing levels against the agreed Birthrate Plus ®, staffing template resulting in poor patient outcomes and experience, and potential suspension of services. | 16 New Risk | Executive Director of Nursing | This new risk is one of two that has replaced the former HBR81 (not closed) Update: Midwifery staffing increased at financial risk in the Antenatal Assessment Unit to comply with the Royal College of Obstetrics & Gynaecology (RCOG) Good Practice Guideline for maternity triage. Gateway review in place in relation to reinstatement of community services, recruitment of band 7 community team leaders completed. Paper being presented to Management Board 05/09/2024. Initial issues raised by staff side for job evaluation and approved job descriptions with competency frameworks for the un-registered workforce agreed and approved. Implementation plan in place expected to complete end of September (target 30/09/2024). Recruitment of Band 2 HCA (health care assistant) positions at Singleton was suspended pending the outcome of the job evaluation. On completion of the implementation plan the 6.27 whole time equivalent band 2 Health Care Support Workers will commence. Business case to support implementation of BSOTS (Birmingham Symptom Specific Obstetric Triage System) in the Ante Natal Assessment Unit to be developed. The service plans to implement a new AAU pathway and documentation process (target 30/09/2024). |
| 103 | High Quality Choices in Place of Birth The Community Intrapartum services remain suspended There is a risk of not being able to provide high quality choices in place of birth (via appropriately staffed and resourced community midwifery teams, the freestanding midwifery unit at Neath Port Talbot Hospital, the alongside midwifery unit and obstetric unit at Singleton Hospital). The potential impact of this is poor patient experience and birth outcomes, poor staff morale and increased attrition of community midwives, increased acuity within obstetric services at Singleton Hospital, and the reduction of services could impact on organisational reputation. | 16 New Risk | Executive Director of Nursing | This new risk is one of two that has replaced the former HBR81 (not closed) Update: A measured re-introduction of community intrapartum pathways has been completed with six safety gateways having been met. A paper is going to Board in September 2024, the outcome of which may alter the scoring of this risk. The paper outlines new risk of continued closure of the pathways for women that previous risk scoring did not capture. These include: • A disaffected workforce unable to work to licence. • Staff in post unable to support women’s choices for birth and underutilisation of their skill set • Staff employed specifically to operationalise community midwifery services not able to fulfil their job descriptions and contract of employment • An increase in complaints relating to community intrapartum care • Increase in women choosing freebirth or to employ independent midwives to support their birth choices • Women choices to transfer care to neighbouring health boards to achieve their birth choices • Reputational damage of not offering full birth choices to the population of Swansea Bay |

3.3 Risks Assigned to Other Committees

There are some risks assigned to other Committees in terms of overseeing actions to mitigate the risks, as outlined in table 2 below, noted here for information. As noted earlier, the detailed HBRR entries are also included in Appendix 1 for information. In view of the consequence to patients if the risks materialise, the Committees have requested that the Quality & Safety Committee be made aware of these risks.

Table 2: Risks Assigned to Other Committees with Referral to Q&S Committee for Information

| Ref | Description of Risk Identified (Summarised) | Current Score | Exec Lead | Committee |
| --- | --- | --- | --- | --- |
| 1 (738) | Access to Unscheduled Care Service If we fail to provide timely access to Unscheduled Care then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. (This risk includes ED, AMU and impact in community from ability to release ambulances at both front doors.) | 25 | Chief Operating Officer | Performance & Finance Committee |
| 16 (840) | Access to Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. | 20 | Chief Operating Officer | Performance & Finance Committee |
| 36 (1043) | Paper Record Storage Lack of a single electronic record means there is greater reliance on the provision of the paper record. If we fail to provide adequate storage facilities for paper records, then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. There is an increased fire risk where medical records are stored outside of the medical record libraries. | 16 | Director of Digital | Workforce OD & Digital Committee |
| 50 (1761) | Access to Cancer Services A backlog of patients now presenting with suspected cancer has accumulated during the pandemic, creating an increase in referrals into the health board which is greater than the current capacity for prompt diagnosis and treatment. Because of this there is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. | 25 | Chief Operating Officer | Performance & Finance Committee |
| 94 (3516) | CAMHS failure to meet required standards of performance The CAMHS service is unable to meet the required level of performance due to workforce deficits in the team across all staff groups including medics, psychological therapies and nursing. This is further hindered by poor data quality which presents a risk to reporting until validation is complete. | 12 | Chief Operating Officer | Performance & Finance Committee |

3.4 Operational Quality & Safety Risks

Each Service Group and Directorate hold their own risk registers, which outline the operational risks facing each Service Group/directorate.

Operational risks relating to quality and safety that may need to be escalated for inclusion on the HBRR are brought to the attention of the Risk Management Group and/or Risk Scrutiny Panel for review and where appropriate added to, or linked to existing risks in, the Health Board Risk Register.

- FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information.

- RECOMMENDATION

Members are asked to:

- RECEIVE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Q&S Committee.

- REVIEW & COMMENT on the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - This report provides an update on the risk profile last reported to QSC in May 2024. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) Risks Assigned to the Quality & Safety Committee |  |