Date	13/10/2026

Time	9:30 AM - 12:30 PM

Location	In Person Meeting at The Beacon Centre of Enterprise, Dafen, Llanelli SA14 8LQ

Regional Joint Committee

HDdUHB and SBUHB RJC

NHS Wales

###### Agenda - 13 October 2026

| 1 | Preliminary Matters 9:30 AM, 0 min |
| --- | --- |

| 1.1 | RJC/35: Welcome and Apologies 9:30 AM, 5 min Neil Wooding (Hywel Dda UHB - Chair of Hywel Dda University Health Board), Jan Williams (Swansea Bay UHB - Corporate) |
| --- | --- |

| 2 | To Consider Future Direction Reports 9:35 AM, 0 min |
| --- | --- |

| 2.1 | RJC/36: Benefits of Combining the Finance/ Contracting and Data/Digital Work Streams Together 9:35 AM, 45 min Huw Thomas (Hywel Dda UHB - Director of Finance) |
| --- | --- |

| 3 | To Receive Sub-Group Assurance Reports 10:20 AM, 35 min |
| --- | --- |

| 3.1 | 03 1.01 - RJC/37a: Clinical Services Planning Subgroup Update 10:55 AM, 0 min Marie Davies (Swansea Bay UHB - Executive Director of Planning and Partnerships) |
| --- | --- |

| 3.2 | RJC/37c: Developing a Regional Approach to Cancer Care: Proposed Inclusion within the RJC Work Programme 10:55 AM, 0 min Abigail Harris (Swansea Bay UHB - CEO), Philip Kloer (Hywel Dda UHB - Chief Executive) |
| --- | --- |

| 3.3 | RJC/37d: South West Wales Cancer Centre Update – Future Radiotherapy Infrastructure 10:55 AM, 0 min Russell Banner (Swansea Bay UHB - Haematology & Oncology) |
| --- | --- |

| 3.4 | RJC/37e: Cellular Pathology Update |
| --- | --- |

10:55 AM, 0 min

Lee Davies (Hywel Dda UHB - Executive Director of Strategy and Planning)

Break

10:55 AM, 15 min

| 4 | RJC/38: Regional Health Economy Subgroup Update 11:10 AM, 10 min Ardiana Gjini (Hywel Dda UHB - Executive Director of Public Health) |
| --- | --- |

| 5 | RJC/39a: Research, Innovation and Excellence Subgroup Update 11:20 AM, 15 min Mark Henwood (Hywel Dda UHB - Executive Medical Director) |
| --- | --- |

| 5.1 | RJC/37c: Outline Programme 11:35 AM, 0 min Leighton Phillips (Hywel Dda UHB - Interim Regional Director for Research and Innovation (South West Wales)) |
| --- | --- |

| 6 | RJC/40: Workforce and OD Subgroup Update 11:35 AM, 10 min Lisa Gostling (Hywel Dda UHB - Director of Workforce & OD/Deputy CEO) |
| --- | --- |

| 7 | Governance 11:45 AM, 0 min |
| --- | --- |

| 7.1 | RJC/41: Annual Review of Terms of Reference 11:45 AM, 5 min Hazel Lloyd (Swansea Bay UHB - Corporate Governance), Joanne Wilson (Hywel Dda UHB - Director of Corporate Governance/Board Secretary) |
| --- | --- |

| 7.2 | RJC/42: Board to Board Proposal 11:50 AM, 5 min Hazel Lloyd (Swansea Bay UHB - Corporate Governance), Joanne Wilson (Hywel Dda UHB - Director of Corporate Governance/Board Secretary) |
| --- | --- |

| 7.3 | RJC/43: RJC Internal Audit Report and Response 11:55 AM, 5 min Hazel Lloyd (Swansea Bay UHB - Corporate Governance), Joanne Wilson (Hywel Dda UHB - Director of Corporate Governance/Board Secretary) |
| --- | --- |

| 7.4 | RJC/44: RJC Strategic Risk Register 12:00 PM, 5 min Hazel Lloyd (Swansea Bay UHB - Corporate Governance), Joanne Wilson (Hywel Dda UHB - Director of Corporate Governance/Board Secretary) |
| --- | --- |

| 7.5 | RJC/45: RJC 2026/2027 Work Programme and Maturity Matrix 12:05 PM, 10 min Abigail Harris (Swansea Bay UHB - CEO), Philip Kloer (Hywel Dda UHB - Chief Executive) |
| --- | --- |

| 8 | Minutes and Actions, Closing Remarks and Future Meetings 12:15 PM, 0 min |
| --- | --- |

| 8.1 | RJC/46: Minutes of Previous Meeting held on 16th April 2026 12:15 PM, 5 min Jan Williams (Swansea Bay UHB - Corporate), Neil Wooding (Hywel Dda UHB - Chair of Hywel Dda University Health Board) |
| --- | --- |

| 8.2 | RJC/47: Table of Actions 12:20 PM, 5 min Jan Williams (Swansea Bay UHB - Corporate), Neil Wooding (Hywel Dda UHB - Chair of Hywel Dda University Health Board) |
| --- | --- |

| 8.3 | RJC/48: Closing Remarks 12:25 PM, 5 min Jan Williams (Swansea Bay UHB - Corporate), Neil Wooding (Hywel Dda UHB - Chair of Hywel Dda University Health Board) |
| --- | --- |

| 8.4 | RJC/49: Date of Next RJC Meetings: 12:30 PM, 0 min Jan Williams (Swansea Bay UHB - Corporate), Neil Wooding (Hywel Dda UHB - Chair of Hywel Dda University Health Board) |
| --- | --- |

Table of contents

13/10/2026-9:30 AM - 12:30 PM-

- - Preliminary Matters	9

  - - RJC/35: Welcome and Apologies	10

- - To Consider Future Direction Reports	11

  - - RJC/36: Benefits of Combining the Finance/ Contracting and

Data/Digital Work Streams Together	12

Attachments

RJC 36a Regional finance and digital collaboration SBAR	13

RJC 36b Presentation Finance Digital Transformation	21

- - To Receive Sub-Group Assurance Reports	27

  - - 03 1.01 - RJC/37a: Clinical Services Planning Subgroup Update	28

Attachments

RJC 37a(i) Clinical Services Planning Subgroup (AAA) Update Report	29

RJC 37a(ii) Clinical Services Planning Subgroup (AAA) Appendix 1 Regional ~	34

RJC 37a(iii) Clinical Services Planning Subgroup (AAA) Appendix 2 Regional~	47

RJC 37a(iv) Clinical Services Planning Subgroup (AAA) Appendix 3 Regional ~	60

RJC 37b Clinical Services Planning Subgroup Work Programme Summary	67

  - - RJC/37c: Developing a Regional Approach to Cancer Care: Proposed Inclusion within the RJC Work Programme	74

Attachments

RJC 37c Developing A Regional Approach to Cancer Care RJC SBAR	75

  - - RJC/37d: South West Wales Cancer Centre Update – Future

Radiotherapy Infrastructure	79

Attachments

RJC 37d South West Wales Cancer Centre - Future Radiotherapy Infrastructur~	80

  - - RJC/37e: Cellular Pathology Update	86

Attachments

RJC 37e Regional Cellular Pathology Update SBAR Report	87

- - RJC/38: Regional Health Economy Subgroup Update	96

Attachments

RJC 38a Regional Health Economy Subgroup AAA Report	97

RJC 38b Regional Health Economy RJC Subgroup Work Programme Summary	101

- - RJC/39a: Research, Innovation and Excellence Subgroup Update	107

Attachments

RJC 39a Research, Excellence and Innovation Subgroup (AAA) Update Report	108

RJC 39b Research, Excellence and Innovation Subgroup Work Programme Summary	111

  - - RJC/37c: Outline Programme	117

Attachments

RJC 39c Research, Innovation and Excellence Subgroup Outline Programme	118

- - RJC/40: Workforce and OD Subgroup Update	123

Attachments

RJC 40a Workforce and OD Subgroup (AAA) Update Report	124

- - Governance	126

  - - RJC/41: Annual Review of Terms of Reference	127

Attachments

RJC 41a Draft RJC ToR	128

RJC 41b Regional Clinical Services Planning Subgroup ToR	138

RJC 41c Draft Research, Innovation and Excellence Subgroup ToR	145

RJC 41d Draft RFCDDG Group ToR v0.4	150

RJC 41e Draft Regional Worforce and OD Subgroup ToR	157

RJC 41f Regional Health Economy Subgroup ToR	162

  - - RJC/42: Board to Board Proposal	168

  - - RJC/43: RJC Internal Audit Report and Response	169

Attachments

RJC 43a IA Advisory Review SBAR Report	170

RJC 43b RJC Governance Arrangements Final Advisory Report 2025-26	174

RJC 43c IA RJC Governance Management Response	185

  - - RJC/44: RJC Strategic Risk Register	191

Attachments

RJC 44 RJC Strategic Risk Register	192

  - - RJC/45: RJC 2026/2027 Work Programme and Maturity Matrix	202

Attachments

RJC 45a RJC Work Programme 2026-2027	203

RJC 45b RJC Subgroup Maturity Matrix	244

- - Minutes and Actions, Closing Remarks and Future Meetings	245

  - - RJC/46: Minutes of Previous Meeting held on 16th April 2026	246

Attachments

RJC 46 DRAFT Minutes Swansea Bay and Hywel Dda University Health Boards Re~	247

  - - RJC/47: Table of Actions	258

Attachments

RJC 47 Regional Joint Committee Table of Actions 13102026	259

  - - RJC/48: Closing Remarks	263

  - - RJC/49: Date of Next RJC Meetings:	264

1

9:30 AM, 0 Mins

## - Preliminary Matters

#### 9:30 AM, 5 Mins

  - - RJC/35: Welcome and Apologies	Neil Wooding (Hywel

Dda UHB - Chair of

Hywel Dda University Health Board), Jan Williams (Swansea

Bay UHB -

Corporate)

2

9:35 AM, 0 Mins

## - To Consider Future Direction Reports

#### 2.1	9:35 AM, 45 Mins

## - RJC/36: Benefits of Combining the Finance/ Contracting and Data/Digital Work Streams Together

Huw Thomas (Hywel Dda UHB - Director

of Finance)

Attachments

RJC 36a Regional finance and digital collaboration SBAR.pdf RJC 36b Presentation Finance Digital Transformation.pdf

JOINT HYWEL DDA/SWANSEA BAY UNIVERSITY HEALTH BOARD COMMITTEE CYD-BWRDD IECHYD PRIFYSGOL HYWEL DDA/BAE ABERTAWE PWYLLGOR

| DYDDIAD Y CYFARFOD: DATE OF MEETING: | 13 October 2026 |
| --- | --- |
| TEITL YR ADRODDIAD: TITLE OF REPORT: | Regional finance and digital collaboration |
| CYFARWYDDWR ARWEINIOL: LEAD DIRECTOR: | Huw Thomas, Director of Finance, Hywel Dda UHB Claire Osmundsen-Little, Director of Finance, Swansea Bay UHB |
| SWYDDOG ADRODD: REPORTING OFFICER: | Huw Thomas, Director of Finance, Hywel Dda UHB Claire Osmundsen-Little, Director of Finance, Swansea Bay UHB |

Pwrpas yr Adroddiad (dewiswch fel yn addas) Purpose of the Report (select as appropriate)

Ar Gyfer Penderfyniad/For Decision

ADRODDIAD SCAA SBAR REPORT

Sefyllfa / Situation The Regional Joint Committee is asked to support the bringing of Finance and Contracting and Data and Digital together in a single regional subgroup, and to endorse the adoption of a common value-based approach to collaboration and Long Term Agreements (LTAs). The purpose is to connect decisions about resources, technology and service delivery with better outcomes and experience for patients across Hywel Dda and Swansea Bay University Health Boards. The proposal has three connected elements: joint oversight of finance and digital; a value logic framework for how teams work together; and a regional funding approach that enables agreed pathway changes between the two organisations. Orthopaedics is proposed as the first LTA pilot, with shadow testing in the second half of 2026/27 and implementation from 2027/28 subject to evaluation and the necessary approvals.

Asesiad / Assessment Benefits of bringing finance and digital together A combined subgroup would align regional oversight with executive accountability and provide one route for prioritising investment, testing affordability and tracking benefits. It would reduce duplicate discussion and make the costs, dependencies and consequences of digital and service changes visible before decisions are taken. For teams, joint working would combine finance, contracting, digital, analytical, clinical and operational expertise around a shared approach. Common data definitions and a shared view of performance would support open-book discussions. Shared specialist capability, standards and infrastructure could improve resilience and reduce avoidable duplication. Better information and coordinated investment can support timely access, consistent pathways and patient experience. Digital and artificial intelligence proposals would be assessed against demonstrable outcomes, whole-life costs, delivery capacity and risk. These are expected benefits to be tested and measured; combining governance alone does not establish a saving. This approach will leverage national priorities for regional benefit, for example, leaning into the opportunities arising from the National Data Repository or other products and capabilities which are developed through DHCW. We will ensure we are responsive to our organisational requirements for data intelligence and modelling. Update The finance and digital teams have been working together for well over 12 months, and this has now culminated in: - The first regional whole-finance team conference held on 15 September to determine a plan to implementing a regional Finance Operating Model embedded across the two teams. - A value based procurement workshop, hosted by Swansea University on 28 September, so that the region becomes an early-adopter of the Value Based Procurement principles which have been developed by the Department of Health and Social Care (UK Government), and supported by Swansea University. - Commissioning of a regional baselining of digital capabilities which will enable a detailed assessment of regional opportunities and alignment of our plans. A value logic framework for collaboration (See Appendix 1) As our teams are working through our collaboration, we are clearly starting with the patient or service problem and agree a value hypothesis: if we make a specified change together, using identified resources and capabilities, we expect defined improvements within an agreed period. We are approaching this through six dimensions: patient outcomes, experience and equitable access; efficiency and scale; quality and standardisation; resilience; knowledge and capability; and innovation with explicit management of risk. The collaboration spectrum offers a number of options: learning and alignment; coordination and standardisation; joint projects and programmes; shared functions or services; a provider collaborative; managed or outsourced delivery; to a single integrated operational team. It is a set of choices for individual services, not a required progression or an assumption on the ultimate destination. We recognise that we are two statutory bodies serving our own populations.

Page 2 of 8

Teams should choose the least complex arrangement capable of delivering the required value safely. They should ask what value is sought, which mechanism delivers it most effectively, and what is lost through too little or too much integration. Any external delivery option requires a separate appraisal and the relevant approvals. Applying the framework to regional LTAs We have commenced work on our LTAs alongside colleagues from Powys HB. This has begun to develop a number of principles. These include: - LTAs should enable agreed care pathways and fund the work needed to deliver them. The starting point should be population need, demand and capacity, including equity of access, rural provision and opportunities for prevention or care closer to home. - Organisations should agree what good looks like across the whole pathway before negotiating the funding mechanism. - A shared baseline should distinguish price from cost and reconcile current funding, activity, delivery locations and outcomes. - Open-book cost information and consistent definitions should make the consequences for each organisation visible. - Where a change creates a regional benefit but leaves one organisation with stranded costs or lost income, the transition and benefit-sharing arrangement should be explicit. - Decisions should consider the pathway portfolio to avoid selecting only financially attractive elements. - The LTA should specify the service and population covered, planned activity and outcomes, responsibilities, funding and adjustment rules, data requirements, review points and dispute resolution. - Digital teams should enable a shared data repository and reporting approach; finance and contracting teams should agree the baseline and payment rules; clinical and operational teams should own pathway design, capacity and delivery. - Outcome measures must sit alongside financial and activity measures. An orthopaedics pilot for the funding model Teams are currently working on a pilot to enable regional orthopaedic working. While the immediate challenges are to address practical, such as enabling access to regional procurement to allow prostheses to be used across our sites and to support travel and logistics arrangements between our sites, there are more significant opportunities which require exploring. These include: - Shadow pooled budgeting: a combined view of the resources committed by both organisations, while retaining their existing financial accountabilities. This would allow the partners to examine distributional effects before changing live payment arrangements. - Sharing orthopaedics budgets and agree the 2026/27 planned activity baseline by provider, point of delivery and relevant service category. - Validate demand, waiting lists, workforce, theatre and outpatient capacity, sub-specialty provision and delivery locations. - Agree the model of care and develop a shared waiting list approach with clear clinical prioritisation. - Model adjustments for activity above or below plan using agreed tariffs and marginal rates. - Test a value-based payment element, potentially using patient-reported outcome measures (PROMs), alongside quality, access and productivity measures. This requires

Page 3 of 8

adjusting for case mix, data completeness, measurement timing and the risk of disadvantaging complex patients. - Manage risks transparently with financial caps aligned with the resources available in the shadow pool. - Shadow testing is proposed for Quarter 4 26/27, with regular joint review of affordability, payment effects, outcomes, access and delivery behaviour. Governance and delivery risks The combined subgroup will be led jointly by the Directors of Finance, with defined digital leadership and clinical, operational, analytical and contracting participation. Commissioning will be kept separately as a defined planning responsibility based on service need. The principal risks are an overloaded agenda, finite specialist capacity, uneven maturity of finance and digital governance, unreliable data and incentives that shift cost or activity without improving value. Mitigations are a phased programme, named owners, protected technical scrutiny, common data standards and shadow testing before live financial change. Cybersecurity, information governance, procurement and commercial proposals require their established specialist scrutiny and approval routes. Combining the workstreams does not itself merge operational teams, or authorise an external partnership. Those decisions need service-specific evidence and the appropriate approvals. The subgroup will bring back updates and plans to the RJC.

Argymhelliad / Recommendation The Committee is asked to: - Agree to combine the Finance and Contracting and Data and Digital workstreams into one regional Finance and Digital subgroup, jointly led by the Directors of Finance, retaining specialist groups and clear digital, clinical and operational participation. - Endorse the value logic framework as the common basis for team working, options appraisal and benefits and resilience. - Endorse the proposed regional LTA principles: pathway-led planning, open-book baselines, shared measures, transparent allocation of costs and benefits, and clear review and escalation arrangements, with Powys engaged where relevant. - Agree development and shadow testing of the orthopaedics funding model in Q4 of 2026/27. This does not approve a marginal tariff, outcome-payment weighting or live pooled budget at this stage.

Page 4 of 8

Appendix 1: Value-based collaboration spectrum

- Introduction

This appendix describes a framework which could be utilised for regional working, and proposes a value logic model for decision making.

The framework recognises a broad evidence base:

  - There are various NHS England documents which through guidance and policy literature consistently describe collaboration as a range of arrangements, from informal cooperation through to formal integration, with governance needing to vary accordingly1.

  - NAO and Audit Wales have, in various reports, highlighted that financial constraint changes the decision context: maintaining duplication or autonomy is increasingly

challenging to justify.

  - The literature emphasises that collaboration should be justified by outcomes, value, and system benefit, not structural preference2. NHS England (2021) and The King’s Fund (2022) specifically recognise collaboratives as intended to address unwarranted variation, increase resilience, address fragility and create efficiency opportunities.

  - There is strong precedent in NHS and public sector practice for requiring collaborations to explicitly state how value will be created, measured, and shared3.

  - The literature consistently stresses that governance arrangements must be proportionate to risk, scale, and interdependence, and that informal arrangements become unsafe as risk increases (again, NHS Providers, 2023 and NHS Confederation 2023, see 1).

  - Managed or outsourced delivery is recognised in the NHS as a tactical option to address capacity, performance, or capability constraints, but requires strong governance and commissioning discipline. The BMA highlight that outsourcing can deliver short-term capacity and performance benefits but carries risks around dependency and capability loss4. NHS England sets out the importance of contract management, outcome specification, and exit planning when external delivery models are used5.

This framework is therefore an integration of multiple well-established strands of NHS policy, governance, and implementation thinking into a single coherent decision framework.

- Collaboration spectrum

1 NHS Providers (2023). Provider Collaboration: A practical guide to lawful, well-governed collaboratives NHS Confederation (2023). The evolution of provider collaboration | NHS Confederation

2 NHS England (2021). B0754-working-together-at-scale-guidance-on-provider-collaboratives.pdf

The Kings Fund (2022). Provider Collaboratives: Explaining Their Role In System Working | The King's Fund

3 NHS England (2023). Value Sharing Framework for NHS data partnerships - The Centre for Improving Data Collaboration - NHS Transformation Directorate SCIE (2024). Logic model for integrated care - SCIE

4 BMA (2022). bma-nhs-outsourcing-report-september-2024.pdf

5 NHS England (2019). NHS England policy template 3 - no photo

Taken together, the evidence indicates that collaboration in the NHS is most effective when treated as a spectrum of options rather than a single structural solution. NHS England guidance consistently emphasises that different collaboration models are appropriate for different purposes, levels of risk, and degrees of interdependence, and that governance should be proportionate to both the value being pursued and the risk being shared.

In a context of sustained financial pressure, collaboration must also be assessed through an explicit value lens, with clarity about what value is expected, over what timeframe, and with what consequences if that value is not realised. The spectrum set out below translates this evidence into a practical decision framework, enabling services to be positioned at the lowest level of collaboration capable of delivering the required value, while providing a clear and disciplined basis for progression where lighter-touch arrangements are insufficient.

| Level | Model | How it Works | Value Extraction Logic | Evidence / Notes |
| --- | --- | --- | --- | --- |
| 1 | Learning and Alignment | Benchmarking, joint reviews, communities of practice, peer networks | Low structural investment, knowledge flows reduce unwarranted variation; strengthens capability over time | Shared learning as a technique to reduce unwarranted variation and build trust among partners. |
| 2 | Coordination & Standardisation | Agreed pathways, shared clinical guidelines or performance dashboards but separate delivery | Standardisation reduces avoidable inefficiency and variation, improves interoperability | Largely descriptive in service frameworks; supported by experience with standardized pathways across partners. |
| 3 | Joint Projects & Programmes | Time-limited cross-organisation delivery (eg redesign) | Delivers targeted benefits without long-term structural commitment; early wins build confidence | Widely used in transformation programmes but requires explicit handover of learning. |
| 4 | Shared Functions / Shared Services | One partner hosts services (finance, digital infrastructure, procurement) for both | Economies of scale, lower unit cost, common platform reduces duplication | Shared services frameworks are part of NHS strategy; national shared services reviews emphasise standardisation and governance discipline. |
| 5 | Provider Collaborative | Formal partnership with shared aims, joint committees, some pooled planning for defined service sets | Combines resources to reduce variation, improve access, build resilience; sharing clinical and corporate learning | Provider collaboratives improve sustainability and efficiency and are being mandated in England, although strong empirical evidence is still emerging. |
| 6 | Managed / Outsourced Delivery | Commission both organisations’ services to an external managed provider (public or private) under performance or outcomes-based contract | External provider brings specialised capability, performance risk sharing, clear KPIs, outcomes-based payments, potential cost reduction | Outsourcing has evidence of short-term capacity benefit (e.g., waiting lists) but also caution about long-term sustainability and NHS capacity effects. |
| 7 | Single Integrated | Single leadership layer, shared SOPs, staff working across both boards (host-employer or joint appointments) | Reduces fragmentation, creates seamless patient pathways, single performance culture | Integration ladders emphasise need for strong governance, shared metrics and trust. |

| Level | Model | How it Works | Value Extraction Logic | Evidence / Notes |
| --- | --- | --- | --- | --- |
|  | Operational Team |  |  |  |
| 8 | Merger (One Organisation) | Full organisational integration under single legal entity, outwith the regional scope for consideration as this would be a Welsh Government policy decision. | Deepest integration, single operating model; potential scale benefits but high transition cost and risk | Merger evidence shows mixed operational benefits and substantial integration costs; careful case justification is critical. |

- Value logic

Value is extracted through the following key opportunities across the spectrum:

| Theme | Opportunity |
| --- | --- |
| Patient outcomes | How does regional working improve patient outcomes by designing services around patient need? |
| Efficiency & Scale | As integration deepens, unit cost reduction via scale, better utilisation of workforce, and reduced duplication in corporate functions. |
| Outcomes & Standardisation | Intermediate models (4, 5) focus on shared standards and pathways which reduce unwarranted clinical variation and improve quality of care, which is in turn linked to better outcomes and lower avoidable costs. |
| Risk Transfer & Innovation | Managed delivery (Level 6) can transfer performance risk and bring specialist expertise. Payments can be configured as outcome-based contracts; evidence notes that NHS has experimented with these contractual forms to incentivise collaboration. |
| Resilience | Collaborative models enhance resilience by pooling workforce, surge capacity and mutual aid, lowering variability in service delivery. |
| Knowledge and Capability | Even the “lighter” levels generate value by building organisational capability and trust, which are precursors for effective deeper collaboration. |

- Governance matrix

The need for governance arrangements will vary across the spectrum, with a summary provided below:

| Spectrum level | Governance requirement |
| --- | --- |
| 1-2 | Both organisations retain local governance with informal steering groups, and no structural hosting. |
| 3-4 | Lead organisation or hosted service with clear service levels, budgets, escalation. |
| 5 | Joint committee with shared planning and accountability. |
| 6 | Commissioning governance with contract and performance oversight (ICS-type arrangements in NHS England) |
| 7-8 | Integrated governance under a shared executive or Board. |

- Summary

This framework supports a shift from a structural debate into a value extraction discussion. Collaboration only matters insofar as it produces better value: better outcomes, lower risk, greater resilience or released capacity. This is a spectrum and not a roadmap: with learning, shared services, managed delivery, and integration as options, there is no single universal destination (unless the policy landscape changes). The value extraction framework needs to be utilised for each service.

This will support and mitigate the risk that ideological preferences will drive the organisational model, not the optimal value choice. That said, this does create a risk of a patchwork of governance arrangements across services. This may need to be further rationalised at a future date. Inherently, governance tightens as value and risk increase. This requires us to ensure that we say no to loose arrangements where there is material risk.

The emphasis on a value challenge aligns with the evidence that collaboration should deliver tangible benefits. The approach itself is a practical application of established logic-model thinking, adapted to collaboration and service delivery decisions.

Title Regional benefits of Collective Finance , Data , Digital and Contracting

Page 21

Regional Joint Committee

Hywel Dda/Swansea Bay University Health Boards

Cyd-bwyllgor Rhanbarthol

Byrddau Iechyd Prifysgol Hywel Dda/Bae Abertawe

The finance and digital teams have been working together for well over 12 months, and this has now culminated in:

    - The first regional whole-finance team conference held on 15 September to determine a plan to implementing a regional Finance Operating Model embedded across the two teams.

    - A value based procurement workshop, hosted by Swansea University on 28 September, so that the region becomes an early-adopter of the Value Based Procurement principles which have been developed by the Department of Health and Social Care (UK Government), and supported by Swansea University.

    - Commissioning of a regional baselining of digital capabilities which will enable a detailed assessment of regional opportunities and alignment of our plans.

    - Work on the recalibrating the LTA arrangements to shape a future way of working with the focus initially on Orthopaedics.

Page 22

Finance Timelines & Actions

Senior Team Updates

Launch with both senior teams sharing plan and approach

DoF Agreement

To progress a regional FoM approach and workplan

May 2026

Full Launch

Launch of regional collaboration and operating model priorities to all teams

October to December 2026

Senior Review

Insight shared with senior teams and feedback sought

January 2027

May 2026

Framework

Approach

DDoFs align on scope and expectations

July 2026

August 2026

Senior Review

Confirm ways of working and priority activities

September 2026

Discovery

Joint priority sessions to undertake baseline and gather views

December 2026

Design

Senior team prepare design and set out future actions

Page 23

3

Procurement Value Timelines & Actions

Establish a collective approach to Procurement

To progress a regional approach and workplan

###### Value based Procurement Workshop

Case study and approach to Value based procurement

###### October to December 2026

###### Senior Review

Insight shared with senior teams and feedback sought

###### January 2027

May 2026

###### August

###### Regional resource

Evaluate ways of working and resources regionally

###### September 2026

###### Discovery

Consolidated regional approach to procurement sessions to establish the pipeline and priorities for collaborative procurement

###### December 2026

###### Design

Senior team set out future procurements to target within IMTP planning framework

Digital & Data Timelines & Actions

Senior Review

DoD Agreement

To progress a regional understanding of the digital and AI potential opportunities

Monthly Digital Meeting

Reset the agenda including the national DHCW insights

Commission CGI Work

To provide a common understanding of the digital architecture and the areas commonality

October to December 2026

Insight shared with senior teams with options for future joint opportunities presented

January 2027

May 2026

July 2026

August 2026

Digital

competencies

Exploring the role of digital team and organisation competence development with Gartner

September 2026

Discovery

Undertake the CGI work

Evaluate the findings

December 2026

Forward plan

Senior team prepare design and set out future actions inline with IMTPs

3

10:20 AM, 35 Mins

## - To Receive Sub-Group Assurance Reports

#### 10:55 AM, 0 Mins

## - 03 1.01 - RJC/37a: Clinical Services Planning Subgroup Update

Marie Davies (Swansea Bay UHB - Executive Director of

Planning and Partnerships)

Attachments

RJC 37a(i) Clinical Services Planning Subgroup (AAA) Update Report.pdf

RJC 37a(ii) Clinical Services Planning Subgroup (AAA) Appendix 1 Regional ~.pdf RJC 37a(iii) Clinical Services Planning Subgroup (AAA) Appendix 2 Regional~.pdf RJC 37a(iv) Clinical Services Planning Subgroup (AAA) Appendix 3 Regional ~.pdf RJC 37b Clinical Services Planning Subgroup Work Programme Summary.pdf

#### CLINICAL SERVICES PLANNING SUBGROUP UPDATE REPORT/ ADRODDIAD DIWEDDARU’R PWYLLGOR

#### Regional Joint Committee

Date of last meeting/ Dyddiad y cyfarfod diwethaf: 15 September 2026

Quoracy/ Cworwm: Met

Report by/ Adroddiad gan: Marie Davies, Executive Lead

KEY DISCUSSION POINTS AND MATTERS FROM THE DISCUSSION AT THE MEETING/ PWYNTIAU TRAFOD ALLWEDDOL A MATERION I’W

HUWCHGYFEIRIO O’R DRAFODAETH YN Y CYFARFOD:

Alert1 / Rhybuddio

The Regional Clinical Services Planning Subgroup (RCSPG) had no items of which to alert members of the RJC.

Advise2 / Cynghori

The RCSPG wish to advise members of the RJC that:

- Through June / September 2026 the RCSPG has undertaken a full review and refresh of the Regional Orthopaedics, Eye Care, and Stroke programmes.

- Since these programmes were initiated the clinical, operational, and regional programme teams have focused on setting the foundations for regional services – getting the basics right – whilst working towards a broad regional strategy and maintaining a sharp focus on achieving operational standards and targets, such as the 104-week waiting target. Good progress has been made as previously reported to the RJC.

- The programme boards and RCSPG have taken stock of progress, sought to be more ambitious through regional collaboration, reflected on changes in context such as national elections, looked to the future, and set a renewed, invigorated and purposeful course towards a more strategic regional solutions that achieve the ministerial 36-week waiting target by 2030; respond positively to GIRFT; tackle the strategy and quality standard recommendations and respond to emerging Ministerial challenges to implement Regional Surgical Hubs.

1 There is a lack of confidence that any action in place is sufficient to address the issue satisfactorily and/or within the scope of the operational team or executive to resolve. Engagement, action or intervention required. 2 There are areas of concern where assurance has been taken on actions in place but requires close monitoring. An early warning of an emerging and potentially serious concern.

The agreed Programme Initiation Documents (PID) are provided with this AAA report for assurance and comment.

Regional Eye Care Programme: Progress has been made in developing the 2026/27 roadmap and modelling potential cataract service options. However, the intended regional approach, implementation plan and achievable delivery trajectory require further clarification. In addition, the Welsh Government funding confirmed for planned care recovery is lower than the amount bid for, creating a risk that the intended improvement and equalisation of cataract waiting times may not be achieved within the current funding envelope. The Programme Board is reviewing the implications for scope, trajectory and deliverability, with a clarified plan to be reported through regional governance.

Regional Orthopaedics Programme: Historically, issues related to regional finance and contracting have impeded or delayed progress. Whilst there are no current/immediate issues to be resolved, there remains a risk that addressing finance and contracting models as part of the broader service model and strategy development may delay or restrict options such as shared capacity, pooled waiting-list arrangements, and a sustainable regional service model. The Directors of Finance for both Health Boards through the Regional Finance and Contracting Subgroup will lead the development of the required regional financial, commissioning and contracting framework, with progress and any decisions requiring escalation in collaboration with the RCSPG.

Dependencies on data and digital systems enabling regional working remain a potential barrier as the Orthopaedics Programme seeks to adopt a more regional approach and longer term strategy development, alongside immediate and short term performance improvement. Directors of Data Digital will join the Orthopaedics Programme board to ensure dependencies on digital subgroup delivery are effectively managed and delivered.

Building on delivery of the regional dashboard in July, the Regional Orthopaedics Programme Board has agreed to review the combined performance of Hywel Dda and Swansea Bay at its monthly meetings. This provides a shared evidence base to support delivery of the Planned Care Recovery and Sustainability Plans, identify targeted short-term interventions and inform longer-term regional planning, including opportunities to improve equity of access and outcomes.

South West Wales Cancer Centre - Radiotherapy planning has identified a gap between the required replacement of Linac 1 in March 2028 and the earliest potential availability of new bunker capacity. Development of an interim operational plan is being managed through the relevant programme and Health Board governance arrangements.

Separate papers on the proposed 6th–7th bunker development and the emerging regional approach to cancer services are scheduled for consideration at the October 2026 Regional Joint Committee meeting.

Assure3 (to note)/ Sicrhau (i nodi)

The RCSPG wish to assure members of the RJC that:

Planned Care Recovery and Sustainability Plans were developed in collaboration and submitted separately by both Health Boards to Welsh Government in summer 2026. Initial funding has been confirmed, although the funding available is lower than the amount bid for. The implications for individual schemes, delivery trajectories and regional programme assumptions are being assessed through Health Board and programme governance. As the plans and funding are Health Board-specific, they guide immediate 2026/27 local recovery but do not represent an agreed regional service model. Funding allocations are linked to approved schemes and recovery trajectories, with continued support dependent on delivery, core activity, internal capacity and national monitoring; detailed values and scheme allocations remain within Health Board governance and are not included here. Regional programmes will use them to align assumptions, identify any recurrent regional capacity gap, distinguish short-term recovery from sustainable models, and requires monitoring to ensure alignment.

Regional Orthopaedics Programme:

The programme reset has established a proposed sequence of work covering refreshed demand and capacity analysis, confirmation of current and potential regional capacity, options development and appraisal, and development of a clinically led regional strategy and delivery plan. Governance arrangements and Terms of Reference have been refreshed in line with the revised regional governance arrangements.

As an initial practical step towards more integrated regional working, the programme is considering the introduction of a single patient treatment list for selected parts of the Orthopaedic pathway. This would provide a controlled opportunity to test the approach, understand the implications for equitable access and patient choice, and apply the learning before any wider implementation. Further detail on scope, timing, patient volumes and governance requirements will be developed through the Programme Board and relevant Health Board governance arrangements.

The Regional Orthopaedics PID is provided for comment.

Regional Eye Care Programme:

3 There is confidence that actions are robust and will be sufficient to address the issue or generally operating effectively. Routine monitoring.

Progress has been made in developing the 2026/27 roadmap, including work on demand and capacity, theatre utilisation, expenditure, workforce, OpenEyes readiness, performance reporting and priority pathways covering vitreoretinal, IVT, glaucoma, cataract and medical retina. Governance arrangements and Terms of Reference have also been refreshed in line with the revised regional governance arrangements.

A handover is also underway to the newly appointed SBUHB Eye Care Clinical Lead, who will support the next phase of programme development and clarification of the regional delivery approach.

Cataract modelling has been completed for two service-developed options. The initial approach is intended to reduce waiting times for Hywel Dda residents towards the Swansea Bay position before moving towards a potential pooled regional model, while avoiding disadvantage to residents of either Health Board area. However, further work is required to confirm the preferred regional approach, implementation plan and achievable delivery trajectory. Welsh Government funding confirmed for planned care recovery is lower than the amount bid for, and the Programme Board is assessing the implications for scope and pace of delivery. The Regional Eye Care PID is provided for comment.

Regional Stroke Programme has completed the baseline against the National Stroke Standards. Work on the immediate priority of providing a stroke consultant Out of Hours service is progressing as planned. This work enables next steps: increased use of CT Perfusion and reduced time to scan. Programme management capacity is being monitored following the end of Welsh Government funding for the Regional Stroke Programme Manager on 30 June 2026. Without central funding to support delivery, regional support seems unlikely to continue beyond the current Out of Hours project. The Regional Stroke PID is provided for assurance / comment.

Cellular Pathology continues to progress at pace. A separate paper on programme progress including the proposed capital programme timeline, key decision points and next steps for consideration will be presented to the Regional Joint Committee in October 2026.

South West Wales Cancer Centre – The 5th Linac business case received approval through both Health Boards’ governance arrangements in July 2026. Subsequent implementation and Welsh Government assurance activity is progressing.

The updated Clinical Services Planning Subgroup Work Programme Summary now brings together programme milestones, risks, dependencies and forthcoming deliverables across the portfolio. The Subgroup Terms of Reference have been refreshed in line with the updated Regional Joint Committee Terms of Reference and governance arrangements.

Review of Risks/ Adolygiad o Risgiau

- Risks and dependencies remain under regular review through programme governance. The Regional Eye Care funding and programme-plan position, service change dependencies on data and digital enablement, together with the unresolved longer term Regional Orthopaedics finance, commissioning and contracting arrangements are highlighted for RJC attention, whilst noting that the inter-subgroup dependencies are being effectively and proactively managed.

- Other portfolio risks continue to be managed through the relevant programme and Health Board governance arrangements. Increasing levels of maturity can be seen where inter-subgroup dependencies are being raised, shared, and jointly managed.

Sharing of learning/ Rhannu dysgu

- Learning and best practice continue to be shared across programmes, Health Boards and clinical networks to support regional improvement and planning.

Recommendation/ Argymhelliad

Members of the RJC are asked to:

- Be assured by the progress made in refreshing the Regional Orthopaedics, Eye Care, and Stroke programmes and receive the updated Programme Initiation Documents for comment.

- Be assured that the advisory updates relating to the Regional Eye Care programme plan and funding, and the Regional Orthopaedics finance, commissioning and contracting, and data and digital implications dependencies, are being progressed through programme, RCSPG, the Regional Finance and Contracting Subgroup, and the Regional Data and Digital governance.

- Consider updates and papers from Regional Pathology, and Regional Cancer where these are separately addressed on the agenda.

Date of next meeting/ Dyddiad y cyfarfod nesaf: 20th October 2026

Attachments:

RJC 37a Appendix 1 Regional Orthopaedics PID RJC 37a Appendix 2 Regional Eye Care PID RJC 37a Appendix 3 Regional Stroke PID

Programme Initiation Document

| Project name | Regional Orthopaedics Programme |
| --- | --- |
| Project SRO | Andrew Carruthers |
| Project manager / lead | Berian Allcock |
| Document owner | Regional Joint Committee (RJC) |
| Version | Draft v0.4 |
| Date | 25.09.2026 |

Regional Orthopaedic Project Initiation Document 08/09/2026

### Summary

This Programme Initiation Document (PID) sets out the proposed reset of the Regional Orthopaedics Programme across Swansea Bay University Health Board (SBUHB) and Hywel Dda University Health Board (HDUHB).

The programme's renewed ambition is to develop a clinically led regional orthopaedic service model capable of achieving the Ministerial 36-week waiting time target by 2030, responding positively to Getting It Right First Time (GIRFT) recommendations, implementing the National Clinical Strategy for Orthopaedic Surgery (NCSOS), and preparing the region to respond to the emerging Regional Surgical Hub agenda.

### Programme Background Context

Significant progress has already been achieved in establishing foundations for regional collaboration, including pathway standardisation, workforce development, regional clinical networks, operational collaboration, development of a regional dashboard, and executive agreement of a shared strategic direction and guiding principles.

The Clinical Services Planning Sub-group is asked to endorse the programme reset and support delivery of the next phase of regional orthopaedic transformation.

Since its inception, the Regional Orthopaedics Programme has focused on achieving the Welsh Government 104-week waiting time target while simultaneously establishing the foundations required for regional working.

Clinical teams, operational teams and programme staff have successfully implemented a range of initiatives that have improved collaboration across South West Wales and laid the groundwork for future regional service delivery. Progress has included regional pathway development, introduction of shared ways of working, establishment of regional networks and enhanced operational coordination.

Following a review of progress and consideration of emerging national policy drivers, the programme has recognised the need to be more ambitious. This PID therefore marks the beginning of a programme reset intended to refresh the evidence base.

Progress to date includes establishing the foundations for regional services and developing the operational arrangements required to support greater collaboration between both Health Boards; implementing regional arthroplasty SOP; adopting shared pathway approaches; recruiting to roles with regional responsibilities; establishing regular Regional Operations Group meetings, and developing regional clinical networks across a number of orthopaedic sub-specialties.

Regional Orthopaedic Project Initiation Document 08/09/2026

Further progress has been made through cross-Health Board theatre activity, regional multidisciplinary working, shared approaches to patient preparation and risk stratification, and improved visibility of regional activity through the Regional Dashboard. Executive agreement in October 2025 on the strategic direction and guiding principles for regional orthopaedics provided a shared framework for the next phase of development, supporting continued alignment of clinical pathways, workforce, theatre capacity, demand and capacity planning, and regional performance oversight and is reflected in this PID.

### Programme Ambition Statement

To develop a clinically led regional orthopaedic service model that achieves the Ministerial 36-week waiting time target by 2030, responds positively to GIRFT, implements National Clinical Strategy for Orthopaedic Surgery recommendations, and establishes South-West Wales as a leading example of integrated regional orthopaedic care.

### Desired Programme Outcomes - Objectives / Aims / Benefits

Aims and Objectives

−	Achieve the ministerial ambition of 36-week waits by 2030.

−	Respond positively to GIRFT recommendations.

−	Deliver against NCSOS recommendations.

−	Prepare for regional surgical hub developments.

−	Develop a long-term clinically led regional orthopaedic model.

Patient Benefits

−	Reduced waiting times.

−	Improved and equitable access to services.

−	Consistent clinical standards across the region.

−	Reduced unwarranted variation in treatment.

−	Improving transparency, communication, and outcomes throughout the patient journey.

Clinical Benefits

−	Increased regional collaboration.

−	Improved access to specialist expertise.

−	Enhanced multidisciplinary working.

Regional Orthopaedic Project Initiation Document 08/09/2026

−	Stronger clinical leadership.

Organisational Benefits

−	Improved utilisation of workforce and theatre capacity.

−	Better demand and capacity planning.

−	Improved regional performance management.

−	Increased system-wide efficiency.

−	Stronger regional accountability.

Strategic Benefits

−	Supports delivery of the RJC agenda.

−	Supports national policy direction.

−	Creates foundations for Regional Surgical Hubs.

−	Establishes a sustainable regional model of care.

### Programme Scope

Sub-specialities – In-scope

The programme will consider opportunities for regional collaboration and service optimisation across orthopaedic sub-specialities, including but not limited to:

−	Hip and Knee Surgery.

−	Foot and Ankle Services.

−	Shoulder and Elbow Services.

−	Hand and Wrist Surgery.

−	Spinal Services.

−	Paediatric Orthopaedics.

−	Orthopaedic Trauma.

−	Revision and Complex Reconstruction Surgery.

−	Musculoskeletal Interface and Community-Based Services.

Sites/Locations – In-scope

The programme will include consideration of:

−	Bronglais

−	Morriston

Regional Orthopaedic Project Initiation Document 08/09/2026

−	Neath Port Talbot

−	Glangwili

−	Prince Philip

−	Withybush

Sites/Locations – Out of scope

−	Singleton Hospital

Geography – In-scope

The programme will include consideration of patient flows:

−	Hywel Dda UHB

−	Swansea Bay UHB

−	Powys THB

−	BCUHB

−	Cwm Taf Morgannwg UHB

−	Cardiff and Vale UHB

Pathway – In-scope

−	Initial assessment

−	Preventative/Conservative care — information, supported self-management, exercise or physiotherapy, pain management and lifestyle support.

−	Specialist triage — such as an experienced MSK clinician reviewing cases that persist, deteriorate or may require specialist treatment.

−	Orthopaedic assessment — imaging where clinically necessary, diagnosis and shared decision-making.

−	Treatment — continued non-operative care, injection or surgery.

−	Recovery and follow-up — rehabilitation, outcome measurement and discharge back to primary or community care

Pathway – Out of scope

−	Access / First contact — GP, physiotherapist, NHS 111 or emergency department.

The programme will explore:

−	Standardised Clinical Pathways and Protocols.

−	Integrated Digital Enabling Infrastructure, transformation and interoperability

Regional Orthopaedic Project Initiation Document 08/09/2026

−	Centralised Operational Functions.

−	Unified Governance and Leadership.

−	A Regional Workforce planning and strategy.

−	Clinical pathway standardisation.

−	Financial and contractual arrangements.

−	Single regional waiting list development.

−	Patient outcomes and experiences.

−	Regional Surgical Hub planning

−	Capital infrastructure investment.

−	Governance, quality, and performance management arrangements.

### Programme Deliverables

The programme reset uses a dual-track approach during 2026/27:

Track 1 – Setting the future direction – reflecting the need for a clear and agreed evidence-based strategy.

| Deliverable | Description |
| --- | --- |
| Demand & Capacity Model | Regional modelling refresh informing future service design |
| Financial Framework | Regional funding and contracting model |
| Strategic vision and plans for 2027/28, including a Digital Enablement Plan | Strategic plan for 2027/28 onwards and roadmap for integrated regional digital systems |

Track 2 – Setting the foundations for the future – because we don’t need to wait for the

strategy to make progress

| Deliverable | Description |
| --- | --- |
| Single Waiting List Design | Patient pooling and central PTL model |
| Electronic Pre-Operative Assessment (EPOA) | Implementation and Support of (EPOA) for Hywel Dda University Health Board |

### Programme Plan and Key Milestones

The programme reset uses a dual-track approach during 2026/27:

Regional Orthopaedic Project Initiation Document 08/09/2026

Track 1 – Setting the future direction – reflecting the need for a clear and agreed evidence-based strategy.

| Action / Deliverable | Lead | By when |
| --- | --- | --- |
| Governance Review Complete | RJC PMO | Complete |
| Booking Process Mapping | Mollie Preece | Complete |
| Regional Dashboard | Lee Talbot | Complete |
| Demand & Capacity Modelling First Cut | Andrew Nelson | 30 September 2026 |
| Multi stakeholder clinically led regional design workshop | RJC PMO | November 2026 |
| Strategic vision and plans for 2027/28. | Programme Board | March 2027 |

Track 2 – Setting the foundations for the future – because we don’t need to wait for the

strategy to make progress

| Action / Deliverable | Lead | By when |
| --- | --- | --- |
| Pathway Mapping Arthroplasty & Hands | Operational Teams | September 2026 |
| Pathway Mapping Foot, Ankle & Shoulder | Operational Teams | October 2026 |
| Electronic Pre-Operative Assessment (EPOA) | Craig Toutt | March 2027 |

### Programme Governance

Programme Governance sits within the RJC governance structure. Members of the Orthopaedics Governance are provided at Appendix 1.

Regional Clinical Services Planning Group

Strategic direction and assurance to the Regional Joint Committee.

Orthopaedic Programme Board (Terms of Reference Appendix 2)

Programme oversight, performance management and direction.

Orthopaedic Operational Delivery Group (Terms of Reference Appendix 3)

Day to day management of delivery, issues, performance and risk. Developing and delivering plans.

Regional Orthopaedic Project Initiation Document 08/09/2026

The Orthopaedic delivery group can establish specific deliverables

### Roles and Responsibilities

Roles and responsibilities are detailed at Appendix 1.

### Budget

The Regional Orthopaedic Programme does not have an allocated budget. Any funding requirement will be subject to separate proposals. At present, programme activities are being supported through existing regional programme resources and Health Board contributions.

Work is required during the first phase of delivery to:

−	Define regional funding requirements.

−	Explore Regional Surgical Hub funding opportunities.

−	Establish future pooled budget arrangements.

−	Develop a regional financial framework.

### Dependencies

| Dependencies | Impact / relevance | Owner |
| --- | --- | --- |
| Finance and contracting | Resolving the ongoing financial and contracting challenges linked to the additional funding credited to health boards in 2023 and set out a regional approach to funding orthopaedics. | Finance and Contracting Subgroup |
| Digital solution development and delivery | Regional Orthopaedics solution delivery will be dependent on delivering regional solutions | Data and Digital Subgroup |

### Risks and Mitigations

Whilst considerable progress has been achieved, barriers to wider transformation have included:

−	A focus on individual Health Board performance rather than regional performance.

−	Challenges associated wit

−	h funding flows and planned care recovery funding.

−	Variable clinical engagement.

−	Lack of an agreed long-term regional service model.

Regional Orthopaedic Project Initiation Document 08/09/2026

| Risk | Score | Mitigation / response | Owner |
| --- | --- | --- | --- |
| Ongoing financial and contracting challenges linked to the additional funding credited to health boards in 2023 remains unresolved | High | Prioritised Finance and Contracting Subgroup workplan | Regional Finance and Contracting Subgroup |
| Digital Constraints – Orthopaedics activity is not currently in the Data and Digital Teams’ work programmes for 2026/27. | Medium | Build digital developments in to plans | Regional Data and Digital Subgroup |
| Clinical Services Planning alignment | Medium | Ongoing planning engagement to ensure that plans work with the recently agreed Hywel Dda CSP and the current work on the Swansea Bay CSP. | Programme Board |
| Organisational Priorities Conflict | High | Executive oversight and escalation | Programme Board |
| Variation in Welsh Government and NHS Wales priorities are assumed to remain broadly aligned with the Orthopaedic Optimisation Framework | Medium | Manage relation with WG and National Orthopaedic Programmes to positively influence policy direction. | Programme Board |

Regional Orthopaedic Project Initiation Document 08/09/2026

### Appendix 1 – Roles, Responsibilities, Governance

Orthopaedics Programme Board

| Role | Org | Name | Responsibility |
| --- | --- | --- | --- |
| Chief Operating Officer | Hywel Dda University Health Board | Andrew Carruthers | SRO- Accountable for programme vision, governance, benefits realisation, funding, risk management, and successful delivery of strategic outcomes. |
| Members | Organisation |  |  |
| Assistant Director of Operations – Planned Care | Swansea Bay University Health Board | Hannah Parsons | Planned Care Programme Board and Organisational alignment |
| Service Director for Planned and Specialist Care | Hywel Dda University Health Board | Paula Goode | Clinical Care Group and Organisational alignment |
| Clinical Lead for the Orthopaedics Programme | Swansea Bay University Health Board | Mark Pritchard | Represents clinical body. Clinical decision making and assurance. |
| Clinical Lead, Trauma and Orthopaedics | Hywel Dda University Health Board | Owain Ennis | Deputy Clinical Lead. Represents Hywel Dda clinical body. Clinical decision making and assurance. |
| Director of Operational Planning & Performance | Hywel Dda University Health Board | Keith Jones | Regional planning lead Hywel Dda |
| Data and Digital Directors (two invitations, one attends) | Hywel Dda University Health Board Swansea Bay University Health Board | Anthony Tracey Matt John | Represent regional Data and Digital subgroup Alignment with Organisational Data Digital plans Data and Digital governance and Decision making Accountable for regional data and digital delivery |
| In Attendance |  |  |  |
| General Manager Planned Care and Cancer | Hywel Dda University Health Board | Lisa Humphrey | Operational Delivery Group Lead. Leads organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |

Regional Orthopaedic Project Initiation Document 08/09/2026

| Associate Service Group Director – NPTSSG | Swansea Bay University Health Board | Rhodri Davies | Operational Delivery Group Lead. Leads organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| --- | --- | --- | --- |
| Clinical Lead - Wales Orthopaedic Network | Swansea Bay University Health Board | Navin Verghese | Wales Orthopaedic Network Clinical Representative |
| Assistant Director - Planned Care | NHS P&I | Loretta Reilly Brett Denning |  |
| RJC Head of Strategy and Service Planning | Regional Joint Committee | Siôn Charles | Regional Programme, dependencies, coordination |
| Regional Orthopaedics Programme Manager | RJC PMO | Berian Allcock | Programme Management |
| Senior Project Support Officer | RJC PMO | Lucy Blackman | Programme Management |

Orthopaedics Operational Delivery Group

| Role | Org | Name | Responsibility |
| --- | --- | --- | --- |
| T&O Service Delivery Manager | Hywel Dda University Health Board | Lianne Gregory | Delivering organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Trauma, Orthopaedic and Spinal Directorate Manager | Swansea Bay University Health Board | Sam Jenkins | Delivering organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Patient Booking Team Waiting List Team | Swansea Bay University Health Board Hywel Dda University Health Board | Clare Taylor Mollie Preece | Patient pathway and waiting list changes |

Regional Orthopaedic Project Initiation Document 08/09/2026

| Healthcare Programme Manager | Wales Orthopaedic Network | Amanda Willacott | Wales Orthopaedic Network programme management |
| --- | --- | --- | --- |
| Digital | Swansea Bay University Health Board Hywel Dda University Health Board | Rachael Levi Carolyn Williams | Data and Digital Workstream leads – leading change to digital arrangements, planning and delivery |
| Head of Strategic Commissioning Head of Commissioning | Hywel Dda University Health Board Swansea Bay University Health Board | Anne Simpson Joshua Griffiths | Contracting and Commissioning workstream leads – leading change to contracting and commission arrangements, planning and delivery |
| Assistant Director of People Planning Project Managers - Workforce Planning Senior Planning and OD Manager | Hywel Dda University Health Board Hywel Dda University Health Board Swansea Bay University Health Board | Tracey Walmsley Wendy Davies Mark Turp | Workforce and OD workstream leads |
| Project Manager | Hywel Dda University Health Board | Carly Tucker-Williams | Hywel Dda Clinical Service Plan connections, dependencies, impacts etc. |
| Data, Modelling and Analysis | Hywel Dda University Health Board Hywel Dda University Health Board Swansea Bay University Health Board Swansea Bay University Health Board | Gareth Beynon Gareth Jenkins Andrew nelson Chris Jones Lee Talbot | Modelling and Analysis workstreams |
| ADD Finance | Hywel Dda University Health Board Swansea Bay University Health Board | Richard Jenkins Catherine Hunt | Finance Workstream lead, linking with the Regional Subgroup |

Regional Orthopaedic Project Initiation Document 08/09/2026

| Public Engagement | Swansea Bay University Health Board Hywel Dda University Health Board | Nic O’Sullivan Alwena Hughes-Moakes | Public engagement - leading change to public engagement arrangements, planning and delivery |
| --- | --- | --- | --- |
| Clinical Representative | Swansea Bay UHB – Orthopaedics Hywel Dda | Mark Pritchard Owen Ennis | Clinical Representative Role – input into and guide all workstream plans and decision making. Identify where specific clinical input and guidance is needed and identify who will provide that. |
| Deputy Director of Allied Health Professions | Hywel Dda University Health Board Swansea Bay University Health Board | Jo Bradburn Jordanna Roberts | Therapies representatives – input into and guide all workstream plans and decision making. Identify where specific therapies input and guidance is needed and identify who will provide that. |

Regional Orthopaedic Project Initiation Document 08/09/2026

Programme Initiation Document

Project Initiation Document

| Programme name | Regional Eye Care Programme |
| --- | --- |
| Programme sponsor | Craige Wilson |
| Programme manager / lead | Berian Allcock |
| Document owner | Berian Allcock |
| Version | 0.3 |
| Date | 21 September 2026 |

Draft for Programme Board review

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

### Summary

Project Initiation Document

This Programme Initiation Document (PID) sets out a joint programme across Swansea Bay and Hywel Dda University Health Boards. It responds to sustained growth in demand, workforce fragility, capacity constraints, increasing waiting times and risks to patients requiring timely intervention, including those at highest risk of irreversible sight loss. Established in November 2024, the programme has a dual purpose: to deliver short-term recovery and operational resilience, and to build the foundations for a more integrated and sustainable regional Eye Care Service.

Delivery in 2026/27 is structured around three linked programmes: Intelligence, Productivity and Recovery; Workforce and Service Resilience; and Development of the Future Regional Service Model. Immediate work will establish validated regional baselines, improve productivity and recovery, strengthen workforce resilience, progress digital convergence and develop standardised pathways. More advanced service changes will proceed only after evidence, clinical agreement, affordability assessment, governance review and formal approval.

No overall programme budget has been identified at this stage. Funding requirements will be defined through evidence, options appraisal and business cases. Principal risks relate to workforce capacity, demand-capacity imbalance, funding and affordability, digital readiness, theatre capacity, on-call deliverability, patient equity, clinical engagement and alignment of local plans.

### Programme Background Context

Eye Care services across South West Wales have a long history of collaboration, including long-term agreements, joint recruitment, workforce development, emergency cover and sharing specialist expertise. Despite this, services remain fragile, with workforce shortages, capacity constraints and rising demand, contributing to increasing waits and risks to timely treatment.

The current programme was established in November 2023, and followed on from long-standing regional collaboration for Eye Care under ARCH. Key milestones include agreement of regional Principles and Intentions and priority pathway areas in May 2025; establishment of a Regional Operational Group in July 2025; regional workforce recruitment; development of vitreoretinal, glaucoma, cataract and medical retina/intravitreal therapy pathway proposals; OpenEyes implementation and planning; and alignment with planned care recovery work.

The programme has moved from mobilisation into early delivery. Progress remains constrained by workforce shortages, variation in theatre capacity and utilisation, digital dependencies, operational pressures and the need for a shared regional understanding of demand and capacity.

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

### Programme Ambition Statement

Project Initiation Document

To develop a clinically led, integrated Regional Eye Care Service that improves resilience, equity of access and patient outcomes; reduces avoidable sight loss and long waits; makes best use of regional capacity and expertise; and is supported by aligned pathways, digital systems, governance and workforce arrangements.

### Desired Programme Outcomes - Objectives / Aims / Benefits

Aims and Objectives

−	Achieve the ministerial ambition of 36-week waits by 2030.

−	Establish a single regional evidence base for demand, capacity, performance, workforce and expenditure

−	Respond positively to GIRFT recommendations.

−	Deliver against NCSOS recommendations.

−	Deliver immediate planned care recovery and productivity improvements

−	Develop a long-term clinically led regional orthopaedic model.

Patient Benefits

−	Reduced waiting times.

−	Improved and equitable access to services.

−	Consistent clinical standards across the region.

−	Reduced unwarranted variation in treatment.

−	Improving transparency, communication, and outcomes throughout the patient journey.

−	Embed person-centred support within eye care pathways, including accessible information, emotional support, certification support, and referral to statutory and third-sector services,

−	Identify and reduce inequalities associated with geography, disability, language, culture, ethnicity, deprivation and digital exclusion

−	Assess and mitigate barriers associated with transport and travel, particularly for patients who cannot drive or who rely on public transport.

Clinical Benefits

−	Increased regional collaboration.

−	Improved access to specialist expertise.

−	Enhanced multidisciplinary working.

−	Stronger clinical leadership.

Organisational Benefits

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

Project Initiation Document

−	Improved utilisation of workforce and theatre capacity.

−	Better demand and capacity planning.

−	Improved regional performance management.

−	Develop evidence-based options for sustainable regional on-call, cataract and wider service models.

−	Progress Digital convergence and OpenEyes enablement.

−	Increased system-wide efficiency.

−	Stronger regional accountability.

Strategic Benefits

−	Supports delivery of the Regional Clinical Services Planning Subgroup objectives set by the RJC by progressing aligned, evidence-led regional service planning and delivery that improves resilience, equity, outcomes and value, while managing dependencies, risks and governance across partner organisations.

−	Supports national policy direction.

−	Creates foundations for Regional Eye Care provision.

−	Establishes a sustainable regional model of care.

Benefits will be demonstrated through Programme Board-approved measures covering access and equity, high-risk pathways, cataract recovery, theatre productivity, outpatients, workforce, digital delivery, finance and value, and quality and outcomes. Baselines, targets, data sources, owners and reporting frequency are to be confirmed through the performance and benefits framework.

### Programme Scope

  - In-Scope

The programme will consider opportunities for regional collaboration and service optimisation, including but not limited to:

−	Regional VR on-call assessment and wider ophthalmology on-call strategy.

−	Medical retina recruitment and regional onboarding.

−	Ophthalmic nursing resilience and regional workforce principles/strategy.

−	Waiting-list validation, outpatient productivity, referral triage, virtual review and PIFU/SOS opportunities.

−	Regional demand and capacity modelling and validation.

−	Regional performance and benefits framework and routine comparative reporting.

−	Theatre utilisation, productivity improvement and benefits monitoring.

−	Cataract recovery delivery, subject to formal funding decisions.

−	Regional expenditure baseline and definition of residual investment requirements.

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

Project Initiation Document

−	Governance reset, digital convergence, standardised priority pathways and development of future regional service-model options.

−	Development of a regional patient experience framework.

−	Regional standards for accessible information and communications.

−	Regional referral pathways into support services, including ECLO and third-sector provision.

−	Assessment of patient transport and travel implications associated with service redesign.

−	Equity assessments addressing language, culture, deprivation and protected characteristics.

  - Out of Scope

Detailed local operational delivery remains the responsibility of the constituent Health Boards, except where explicitly agreed as part of the regional programme.

### Programme Deliverables

| Deliverable | Description | Proposed Owner | Proposed Target date |
| --- | --- | --- | --- |
| Programme Governance Reset | Leadership, decision rights, reporting, risk and escalation arrangements implemented following Programme Board agreement. | Proposed Craige Wilson | Nov 2026 |
| Regional Evidence Baseline | Validated demand and capacity, theatre utilisation, waiting-list, workforce and expenditure baselines. | Proposed Andrew Nelson | Dec 2026 to Jan 2027 |
| Performance and Benefits Framework | Agreed measures, definitions, data sources and owners, with prototype dashboard and first routine report. | Proposed: Anthony Tracey | Dec 2026 |
| Recovery and Productivity Plans | Cataract recovery controls, theatre improvement plans and outpatient productivity actions. | Proposed Rhodri Davies and Lisa Humphries | Dec 2026, then ongoing |
| Workforce and Resilience Package | VR on-call recommendation, nursing resilience plan and regional workforce strategy. | Proposed Huw Jenkins and David Janicek | Dec 2026 to Apr 2027 |
| Digital Convergence Roadmap | Integrated digital roadmap and priority pathway readiness assessment. | Proposed Nerys James and Sarah Dunderdale | Mar 2027 |
| Standardised Pathway proposals | Current-state maps, common standards, outcome measures and phased decisions. | Proposed: David Janicek and Huw Jenkins | Apr 2027 |
| Future Regional Service Model | Evidence pack, clinically led design, draft 2030 model and formal approval route, co-produced | Proposed: Craige Wilson | Apr 2027 |

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

Project Initiation Document

| Deliverable | Description | Proposed Owner | Proposed Target date |
| --- | --- | --- | --- |
|  | with patients, carers and representative organisations. |  |  |
| Regional patient support framework | Agreed standards covering accessible information, ECSP implementation, support referrals, care transfers and patient communications |  |  |
| Equity and accessibility Framework | Agreed measures and actions relating to language, culture, transport, digital inclusion, disability and geographic access |  |  |

### Programme Plan and Key Milestones

The programme outlines a need for a clear and agreed evidence-based strategy for 2026/27:

| Milestone / Activity | By When | Lead | Status / notes |
| --- | --- | --- | --- |
| Confirm leadership, meeting cycle and mobilisation | Sep 2026 | Proposed: Craige Wilson | For Programme Board agreement |
| Agree measures, definitions and evidence scope | Sep 2026 | Proposed Berian Allcock | Leads and dates remain recommended |
| Complete initial baselines and prototype reporting | Oct to Nov 2026 | Proposed Andrew Nelson | Subject to data quality |
| Validated baseline and first routine report | Dec 2026 | Proposed Anthony Tracey | Gateway for later design work |
| VR on-call implementation recommendation | Dec 2026 | Proposed: David Janicek | Subject to full review |
| Workforce resilience plan and evidence integration | Jan 2027 | Proposed Huw Jenkins and David Janicek | Informed by Programme 1 |
| Future model options and design engagement | Feb to Mar 2027 | Proposed: Craige Wilson | Evidence before design |
| Regional patient and stakeholder engagement programme completed |  |  |  |
| Patient support framework approved |  |  |  |
| Phased model and formal approval route | Apr 2027 | Proposed: Craige Wilson | Requires organisational approvals |

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

### Programme Governance

Project Initiation Document

Programme Governance sits within the RJC governance structure. Members of the Eye Care Governance are provided in Appendix 1. Patient and third-sector representation will be incorporated into programme governance and service redesign activity.

Regional Clinical Services Planning Group

Strategic direction and assurance to the Regional Joint Committee.

Eye Care Programme Board (Terms of Reference Appendix 2)

Programme oversight, performance management and direction.

Eye Care Operational Delivery Group (Terms of Reference Appendix 3)

Day to day management of delivery, issues, performance and risk. Developing and delivering plans.

The Eye Care Delivery Group can establish specific deliverables

### Roles and Responsibilities

Roles and responsibilities are detailed at Appendix 1.

### Budget

The Regional Eye Care Programme does not have an allocated budget. Any funding requirement will be subject to separate proposals. At present, programme activities are being supported through existing regional programme resources and Health Board contributions. Work is required during the first phase of delivery to:

−	Define regional funding requirements.

−	Explore Regional Capital funding opportunities.

−	Establish future pooled budget arrangements.

−	Develop a regional financial framework.

### Dependencies

| Dependencies | Impact / relevance | Owner |
| --- | --- | --- |
| Finance and contracting | Resolving the ongoing financial and contracting challenges linked to the additional funding credited to health boards in 2023 and set out a regional approach to funding Eye Care | Finance and Contracting Subgroup |

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

Project Initiation Document

| Dependencies | Impact / relevance | Owner |
| --- | --- | --- |
| Digital solution development and delivery | Regional Eye Care solution delivery will be dependent on delivering regional solutions | Data and Digital Subgroup |
| Availability of support services, including ECLO provision, low vision services, vision rehabilitation services and third-sector support. | The programme’s ability to deliver person-centred outcomes depends on patients receiving timely access to information, emotional and practical support, certification and registration advice, rehabilitation, and onward referral. Gaps in provision or weak referral arrangements could result in unmet need and inconsistent support between pathways or locations. |  |
| Accessible, bilingual and inclusive patient communication arrangements. | Patients must be able to receive, understand and act on information about appointments, treatment, waiting times, pathway transfers and service changes. This requires information in patients’ preferred accessible format and language, with interpretation, translation and communication support available where needed. |  |
| Availability of accessible and affordable transport, and coordination between regional service locations and patient transport arrangements. | Greater regional working may increase the distance or complexity of travel for some patients. Inadequate transport could contribute to missed or delayed appointments, reduce access to treatment and support, and disproportionately affect people who cannot drive, have limited mobility, live in rural communities or rely on family and carers. |  |

### Risks and Mitigations

Whilst considerable progress has been achieved, barriers to wider transformation have included:

−	A focus on individual Health Board performance rather than regional performance.

−	Challenges associated with funding flows and planned care recovery funding.

−	Variable clinical engagement.

−	Lack of an agreed long-term regional service model.

| Risk | Score | Mitigation / response | Owner |
| --- | --- | --- | --- |
| Ongoing financial and contracting challenges linked to the additional funding credited to health boards in 2023 remains unresolved | High | Prioritised Finance and Contracting Subgroup workplan | Regional Finance and Contracting Subgroup |
| Digital Constraints – Eye Care activity is not currently in the Data and Digital Teams’ work programmes for 2026/27. | Med | Build digital developments in to plans for 2026/27. | Regional Data and Digital Subgroup |
| Clinical Services Planning alignment | Med | Ongoing planning engagement to ensure that plans work with the recently agreed Hywel Dda CSP and the current work on the Swansea Bay CSP. | Programme Board |
| Organisational Priorities Conflict | High | Executive oversight and escalation | Programme Board |

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

Project Initiation Document

| Risk | Score | Mitigation / response | Owner |
| --- | --- | --- | --- |
| Variation in Welsh Government and NHS Wales priorities are assumed to remain broadly aligned with the Eye Care Optimisation Framework | Med | Manage relation with WG and National Eye Care Programmes to positively influence policy direction. | Programme Board |
| Theatre capacity | High | Validated baseline and accountable improvement plans. | Amorelle Jones and Sam Jenkins |
| On-call deliverability | High | Phase VR first; assess quality, feasibility and affordability. | Rhodri Davies and Lisa Humphrey |
| Clinical engagement | High | Named leadership, documented decisions and visible progress. | Louise King + Cheryl Madeira Cole |
| Demand-capacity imbalance | High | Validated modelling to define productivity opportunity and structural gap. | Andrew Nelson and Anthony Tracey |
| Patient equity | Significant impact; likelihood to be rated. | Comprehensive equality and equity impact assessment, including assessment of geography, transport, disability, language, ethnicity, culture, deprivation and digital exclusion. Ongoing monitoring of patient experience and access outcomes. |  |
| Patients do not receive adequate information, emotional support or onward referral during pathway redesign and service change. |  | Regional implementation of Eye Care Support Pathway principles and support referral standards. |  |
| Service redesign unintentionally increases travel burden or creates barriers for patients unable to access transport. |  | Patient transport assessment included in all pathway redesign and service change proposals. |  |

### Appendix – Roles, Responsibilities, Governance

Appendix 1 – Regional Eye Care Programme Board (Attendees + Responsibilities)

| SRO |  |  | Responsibility |
| --- | --- | --- | --- |
| Deputy Chief Operating Officer | Swansea Bay University Health Board | Craige Wilson | Accountable for programme vision, governance, benefits realisation, funding, risk management, and successful delivery of |

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

Project Initiation Document

|  |  |  | strategic outcomes. |
| --- | --- | --- | --- |
| Members | Organisation |  |  |
| Assistant Director of Operations – Planned Care | Swansea Bay University Health Board | Hannah Parsons | Planned Care Programme Board and Organisational alignment |
| Service Director for Planned and Specialist Care | Hywel Dda University Health Board | Paula Goode | Clinical Care Group and Organisational alignment |
| Clinical Lead for Eye Care | Swansea Bay University Health Board | David Janicek | Represents clinical body. Clinical decision making and assurance. |
| Clinical Lead for Eye Care | Hywel Dda University Health Board | Huw Jenkins | Deputy Clinical Lead. Represents Hywel Dda clinical body. Clinical decision making and assurance. |
| Director of Operational Planning & Performance | Hywel Dda University Health Board | Keith Jones | Regional planning lead Hywel Dda |
| Data and Digital Directors (two invitations, one attends) | Hywel Dda University Health Board Swansea Bay University Health Board | Anthony Tracey Matt John | Represent regional Data and Digital subgroup Alignment with Organisational Data Digital plans Data and Digital governance and Decision making Accountable for regional data and digital delivery |
| In Attendance |  |  |  |
| General Manager Planned Care and Cancer | Hywel Dda University Health Board | Lisa Humphrey | Operational Delivery Group Lead. Leads organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Associate Service Group Director – NPTSSG | Swansea Bay University Health Board | Rhodri Davies | Operational Delivery Group Lead. Leads organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Ophthalmology Service Delivery Manager | Hywel Dda University Health Board | Amorelle Jones | Delivering organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Interim Divisional Manager • | Swansea Bay University | Sam Jenkins | Delivering organisational change, stakeholder engagement, communications, training, |

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

Project Initiation Document

| NPTSSG Surgery Division | Health Board |  | adoption, and benefits realisation to embed new ways of working. |
| --- | --- | --- | --- |
| Director of Performance and Business Intelligence | Swansea Bay University Health Board | Andrew Nelson | Data Workstream leads – leading change to data modelling arrangements, planning and delivery |
| RJC Head of Strategy and Service Planning | Regional Joint Committee | Siôn Charles | Regional Programme, dependencies, coordination |
| Regional Orthopaedics Programme Manager | RJC PMO | Berian Allcock | Programme Management |
| Senior Project Support Officer | RJC PMO | Lucy Blackman | Programme Management |

Appendix 2 – Regional Eye Care Operational Delivery Group (Attendees + Responsibilities)

| Operational Delivery Group |  |  |  |
| --- | --- | --- | --- |
| Ophthalmology Service Delivery Manager | Hywel Dda University Health Board | Amorelle Jones | Delivering organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Interim Divisional Manager • NPTSSG Surgery Division | Swansea Bay University Health Board | Sam Jenkins | Delivering organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Ophthalmology Service Manager | Swansea Bay University Health Board | Suzanne James | Delivering organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Ophthalmology Service Manager | Hywel Dda University Health Board | Louise King | Delivering organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Ophthalmology Clinical Service Manager | Swansea Bay University Health Board | Cheryl Madeira-Cole | Delivering clinical organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Senior Nurse Manager | Hywel Dda University Health Board | Marta Barreiro Martins | Delivering clinical organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Orthoptist • Surgical Specialties | Swansea Bay University Health Board | Claire Shaw | Orthoptist Workstream – leading change to optometry arrangements, planning and delivery |
| Orthoptist • Outpatients | Hywel Dda University Health Board | Anwen Coughlan | Orthoptist Workstream – leading change to optometry arrangements, planning and delivery |
| Optometric Advisor • | Swansea Bay | Mohammed | Optometry Workstream – leading change to optometry |

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

Project Initiation Document

| Primary Care | University Health Board | Islam | arrangements, planning and delivery |
| --- | --- | --- | --- |
| Optometric Advisor | Hywel Dda University Health Board | Sally Hodson | Optometry Workstream – leading change to optometry arrangements, planning and delivery |
| Head of Primary Care • Primary and Community Services | Swansea Bay University Health Board | Sam Page | Delivering primary care and community organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Assistant Director of Primary Care | Hywel Dda University Health Board | Rhian Bond | Delivering primary care and community organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Data and Digital | Swansea Bay University Health Board Hywel Dda University Health Board | Nerys James Sarah Dunderdale | Data and Digital Operational leads – leading change to digital arrangements, planning and delivery |
| Assistant Director of People Planning Project Managers - Workforce Planning Project Managers - Workforce Planning Senior Planning and OD Manager | Hywel Dda University Health Board Hywel Dda University Health Board Hywel Dda University Health Board Swansea Bay University Health Board | Tracey Walmsley Wendy Davies Daniel Owen Mark Turp | Workforce and OD workstream leads |
| Modelling and Analysis | Hywel Dda University Health Board Hywel Dda University Health Board Swansea Bay University Health Board Swansea Bay University Health Board | Gareth Beynon Gareth Jenkins Andrew Nelson Lee Talbot | Modelling and Analysis workstreams |
| Equality Leads |  |  | Coordination of actions relating to language, culture, transport, digital inclusion, disability and geographic access |
| Patient Experience Leads |  |  | Patient and stakeholder engagement, development of patient support framework |
| Invitation to attend to discuss work programme areas requiring wider |  |  |  |

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

collaboration (as and when required)

Project Initiation Document

Regional Eye Care Programme | Project Initiation Document | Draft 0.1 | 02 September 2026

Project Initiation Document

| Project name | Regional Stroke Project |
| --- | --- |
| Project SRO | James Severs |
| Project lead | Siôn Charles |
| Document owner | Regional Joint Committee (RJC) |
| Version | v1.0 |
| Date | 23.09.2026 |

Regional Stroke PID

### Summary

This Project Initiation Document (PID) sets out proposals for a Regional Stroke Project for Swansea Bay University Health Board (SBUHB) and Hywel Dda University Health Board (HDUHB).

Stroke Consultant Out of Hours (OOH) Rota – where patients present to an acute hospital in Swansea Bay or Hywel Dda (CTP, Thrombosis, Thrombolysis)

### Project Background / Context

There has been a regional collaboration for stroke in West Wales since 2022. Initial work focused on developing a business case for a comprehensive regional stroke centre, which has been helpful in setting the foundations for this current project.

There is ongoing work being led by the Stroke implementation Network (lead by NHS P&I) guided by the Welsh Government’s Stroke Quality Statement, including baselining against national standards, which currently waiting on national programme reviews and standardisation of data. This may require future regional activity and coordination. Hywel Dda’s ongoing work on the CSP for stroke and Swansea Bay emerging CSP work also provide a backdrop this project.

Plans are set within this context and limitations on resources operational and project resources to support regional project delivery at this time.

### Project Ambition Statement

Develop proposals for an Out of Hours solution for where patients present to an acute hospital in Swansea Bay or Hywel Dda (CTP, Thrombosis, Thrombolysis).

### Desired Outcomes - Objectives / Aims / Benefits

Patient Outcomes

−	Timely access to specialist stroke consultant assessment and treatment decision-making, irrespective of time of presentation or hospital site.

−	Improved access to time-critical reperfusion treatments, including thrombolysis and referral for mechanical thrombectomy where clinically appropriate.

−	Reduced delays in diagnosis, treatment and onward transfer, supporting better functional outcomes and reduced disability.

Regional Stroke PID

−	More equitable and consistent access to specialist stroke care across Swansea Bay and Hywel Dda.

−	Improved patient and family experience through clearer, timely senior clinical decision-making and communication.

Clinical Outcomes

−	Improved compliance with evidence-based stroke pathways and time-critical treatment standards.

−	Earlier specialist review of imaging, including CT/CTP, enabling rapid identification of patients suitable for thrombolysis and/or thrombectomy.

−	Consistent senior decision-making for complex stroke presentations, including treatment eligibility, contraindications and differential diagnoses.

−	Reduction in unwarranted variation in stroke management between hospital sites and between in-hours and out-of-hours periods.

−	Improved clinical outcomes through faster treatment, including reduced time to thrombolysis and thrombectomy referral.

−	Strengthened clinical governance, escalation and shared decision-making for high-risk stroke presentations.

Organisational Outcomes

−	Provision of a resilient, clearly defined cross-health-board OOH stroke consultant service.

−	More effective use of specialist stroke consultant capacity across Swansea Bay and Hywel Dda.

−	Reduced reliance on ad hoc consultant availability and informal escalation arrangements.

−	Clearer accountability, communication and escalation pathways between Emergency Departments, stroke teams, radiology, ambulance services and thrombectomy centres.

−	Improved patient flow through earlier treatment decisions, appropriate admission, repatriation or transfer to specialist services.

−	Potential reduction in avoidable length of stay and longer-term care requirements through earlier access to effective reperfusion treatment.

−	Improved rota resilience, workforce planning and sustainability for participating stroke services.

Strategic Benefits

−	Supports the development of an equitable, regionalised approach to hyperacute stroke care across South West Wales.

Regional Stroke PID

−	Aligns with national priorities to improve access to 24/7 specialist stroke assessment, thrombolysis and mechanical thrombectomy pathways.

−	Supports delivery of consistently high-quality stroke services regardless of geography, hospital of presentation or time of day.

−	Strengthens collaboration and shared working between Swansea Bay University Health Board and Hywel Dda University Health Board.

−	Provides a platform for future development of regional stroke pathways, including telemedicine, imaging access and networked specialist decision-making.

−	Supports improved population outcomes by reducing stroke-related mortality, disability and long-term dependence.

−	Contributes to more efficient use of NHS resources by preventing avoidable disability and reducing subsequent rehabilitation, social care and long-term healthcare requirements.

### Project Scope

Out of Hours access to Stroke Consultant advice, guidance and decision making Where patients present to an acute hospital in Swansea Bay or Hywel Dda

CTP, Thrombosis, and thrombolysis

### Project Deliverables

| Action / Deliverable | Lead | By when |
| --- | --- | --- |
| OOH Stroke Consultant provision proposal | Siôn Charles | 17 November |

### Project Plan and Key Milestones

| Action / Deliverable | Lead | By when |
| --- | --- | --- |
| Baseline Performance Data | Christine Owen | Complete |
| Insights from other systems gathered and reported – Models of Service and Resourcing | Garry Smith | Complete |
| Insight from the sector – emerging technologies and systems | Rhodri Griffiths | 30 August |
| Future Service Requirement Spec (Performance expectations, Quality Standards etc.) | Christine Owen | 15 September |
| Baseline Activity, Resources, Costs, Model, SLAs, Governance Arrangements, and Digital Systems – Hywel Dda | Bethan Andrews | 18 September |

Regional Stroke PID

| Baseline Activity, Resources, Costs, Model, SLAs, Governance Arrangements, and Digital Systems – Swansea Bay | Abi Landeg | 18 September |
| --- | --- | --- |
| Options Template | Siôn Charles | 22 September |
| Options Development (including baseline) | Ops Teams | 26 October |
| Workshop (funding and facilitation by Stroke Association) – National Botanical Gardens (13:00-16:00) – Options analysis and preferred option selection | Siôn Charles | 26 October |
| Proposal development by | Siôn Charles | 17 November |
| Governance and Decision Making | Lead | By when |
| Regional Clinical Services Planning Group Support Agree Decision Making Criteria | Siôn Charles | 20 October |
| Regional Clinical Services Planning Group Decision | Siôn Charles | 17 November |
| Further Decision-Making process requires clarification | Siôn Charles | December 2026 |

### Project Governance

Stroke Operational Delivery Group

Day to day management of delivery, issues, performance and risk. Developing and delivering plans.

Stroke Programme Board

Project oversight, performance management and direction.

Regional Clinical Services Planning Group

Strategic direction and assurance to the Regional Joint Committee.

### Roles and Responsibilities

A table of key project roles and responsibilities is provided in Appendix 1.

### Budget

The Regional Stroke Programme does not have an allocated budget. Any funding requirement will be subject to separate proposals. At present, programme activities are being supported through existing regional programme resources and Health Board contributions.

The regional workshop is funded in full by the Stroke Association.

Regional Stroke PID

### Dependencies

| Dependencies | Impact / relevance | Owner |
| --- | --- | --- |
| There are currently no dependencies on programme delivery. |  |  |

### Risks and Mitigations

Key risks to programme delivery are:

| Risk | Score | Mitigation / response | Owner |
| --- | --- | --- | --- |
| Programme management support – there has been no funding from programme management and national coordination since June 2026. Further funding currently seems unlikely. Support from the RJC PMO cannot be sustained in the longer-term | High | In the short term the RJC PMO is committed to supporting this phase of the project and developing a proposal. Engagement with the national team for programme management funding and support. | Siôn Charles |
| The National Programme team have been developing plans independently of the regional local teams. This includes Stroke being a strong contender for being a pathfinder project for the national Service Change Operating Framework T&F Group | Med | Maintain connection with national team to influence planning. Member of the national Service Change Operating Framework T&F Group | Siôn Charles |
| Hywel Dda CSP. Regional ambitions may challenge or affect Hywel Dda CSP. | Low | Avoid developing regional solution that are in conflict with the Hywel Dda CSP. Include representative from Hywel Dda CSP team in options development and analysis. | Siôn Charles |
| Operational and Clinical resource availability challenges. | Med | Build programme plans around operational and clinical teams’ availability. Maintain pressure on delivering against targets through programme boards and operation group meetings | Siôn Charles |
| Stakeholder engagement and decision making. | Med | Ensure that stakeholders are a part of options and development and analysis to ensure buy-in, that solutions are fit for purpose and context sensitive, and that delivery plans are developed jointly. | Siôn Charles |

### End

Regional Stroke PID

### Appendix 1 – Roles and Responsibilities Table

| Role | Name / team | Key responsibilities |
| --- | --- | --- |
| SRO | James Severs | Accountable for programme vision, governance, benefits realisation, funding, risk management, and successful delivery of strategic outcomes. Executive Lead for Hywel Dda. |
| Deputy SRO | Craige Wilson | Accountable for programme vision, governance, benefits realisation, funding, risk management, and successful delivery of strategic outcomes. Executive Lead for Swansea Bay. |
| Project Lead | Siôn Charles | Project delivery |
| Clinical Lead (Hywel Dda) | Senthil Kumar | Represents clinical body. Clinical decision making and assurance. |
| Clinical Lead Swansea Bay | Peter Slade | Represents clinical body. Clinical decision making and assurance. |
| Operational Lead Hywel Dda | Bethan Andrews | Delivering organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| Operational Lead Swansea Bay | Abi Landeg | Delivering organisational change, stakeholder engagement, communications, training, adoption, and benefits realisation to embed new ways of working. |
| NHS P&I | Christine Owen | Supporting project with practical improvement, modelling, facilitation and insights. |
| NHS P&I | Garry Smith | Supporting project with practical improvement, modelling, facilitation and insights. Links to broader networks and service model insights. |
| Stroke Association | Katie Chappelle | Supporting the project. Facilitation. Patient perspective. Workshop and proposal delivery. |
| Stroke Association | Kate Yearsley | Supporting the project. Facilitation. Patient perspective. Workshop and proposal delivery. |
| Life Science Hub | Rhodri Griffiths | Sector insights and emerging technologies |

Regional Stroke PID

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

Clinical Services Planning Subgroup Work Programme Summary

- Subgroup Summary

| Reporting Period | April – September 2026 |
| --- | --- |
| Subgroup Name | Clinical Services Planning Subgroup |
| Subgroup Lead(s) | Marie Davies |
| Operational Lead(s) | Andrew Carruthers and Jon Scott |
| Clinical Lead(s) | N/A |
| Programme Lead | Siôn Charles |
| Reports To | RJC |
| Receives Reports From | Regional Clinical Services Programmes |
| Meeting Frequency | Monthly |
| ToR Agreed | Yes subject to amendment |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

- Subgroup Scope

| Programme / initiative | Stage | Executive lead / SRO | Summary scope |
| --- | --- | --- | --- |
| Regional Orthopaedics Programme | Develop / reset | Andrew Carruthers | Clinically led regional orthopaedic model; 36-week ambition by 2030; surgical hub response; pathway, governance, finance and digital foundations. |
| Regional Eye Care Programme | Early delivery / develop | Craige Wilson | Service resilience, productivity and equity; priority pathways VR, IVT, glaucoma, cataract and medical retina; roadmap to regional service model. |
| South West Wales Cellular Pathology Programme | Define / delivery | Lee Davies | Single regional cellular pathology hub laboratory and consolidated cellular pathology and mortuary service model hosted by Swansea Bay UHB. |
| South West Wales Cancer Centre Programme | Develop | Marie Davies | Regional radiotherapy and oncology outpatient services modernisation; 5th Linac / future bunker capacity; regional cancer model development. |
| Regional Stroke Programme | Develop / reset | James Severs | Regional consultant rota, increased use of CT Perfusion and reduced time to scan. |

- Ambition Statement(s)

Ambition Statement(s)

Provide joint leadership across Swansea Bay and Hywel Dda University Health Boards to plan, commission and deliver sustainable, high-quality and efficient regional clinical services. The subgroup will use a regional, data-led approach to baseline activity, quality, outcomes, cost efficiency, service fragility, workforce sustainability, financial sustainability and population health need. It will support short- to medium-term operational planning and longer-term transformational collaboration, including regional capital prioritisation and clinically led service redesign, where regional working improves resilience, equity of access and outcomes for South West Wales.

- Objective / Output Statements

| Objective / Output | Target Date | RAG |
| --- | --- | --- |
| Develop strategic regional orthopaedic plan for 2027/28 and 36-week ambition by 2030 | March 2027+ |  |
| Reduce waiting times for oncology treatments through radiotherapy capacity expansion | March 2027+ |  |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

- Milestones & Deliverables

| RJC Subgroup Objective | Milestone / Deliverable | Target Date | This Period (RAG) | Comments / Notes |
| --- | --- | --- | --- | --- |
| Bring together, through the RCSPG work programme, clinical service projects that will deliver significant in-year progress and pace in delivery for the regional health and care system. Drive forward clinical service priorities identified by partner organisations for joint working at pace, ensuring alignment with Ministerial Priorities, the strategic aims agreed by the RJC, and ratification requirements of both sovereign Boards. Provide assurance that regional clinical service programmes and models are developed and delivered to improve resilience, equity of access and outcomes across South West Wales. | Orthopaedics: develop strategic regional solution supporting 36-week waits by 2030 and Regional Surgical Hub response | 2026/27 into 2030 |  |  |
| Bring together, through the RCSPG work programme, clinical service projects that will deliver significant in-year progress and pace in delivery for the regional health and care system. Drive forward clinical service priorities identified by partner organisations for joint working at pace, ensuring alignment with Ministerial Priorities, the strategic aims agreed by the RJC, and ratification requirements of both sovereign Boards. Provide assurance that regional clinical service programmes and models are developed and delivered to improve resilience, equity of access and outcomes across South West Wales. | Eye Care: build toward OpenEyes-enabled regional pathways, standardised waiting list management, regional cataract model and longer-term regional service model | 2027/28 onwards |  |  |
| Provide assurance that regional Cellular Pathology and South West Wales Cancer capital planning programmes are delivered to plan and cost, aligned with regional priorities, deliver efficiency gains, and positively impact patient services and outcomes. | Cellular Pathology: submit fully tendered business case to Welsh Government | Q3 2027/28 |  |  |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

| RJC Subgroup Objective | Milestone / Deliverable | Target Date | This Period (RAG) | Comments / Notes |
| --- | --- | --- | --- | --- |
| Provide assurance that regional Cellular Pathology and South West Wales Cancer capital planning programmes are delivered to plan and cost, aligned with regional priorities, deliver efficiency gains, and positively impact patient services and outcomes. Provide assurance that regional clinical service programmes and models are developed and delivered to improve resilience, equity of access and outcomes across South West Wales. | South West Wales Cancer Centre: deliver radiotherapy capacity pathway including 5th Linac, future bunker capacity and seven-Linac model / satellite centre scoping | 2026/27 to 2030/31 |  |  |
| Develop and maintain regional clinical services plans that are aligned to Health Board plans and support delivery of the benefits of a regional health economy for a population of circa 800,000. Provide assurance that the Health Boards’ Clinical Services Strategic Plans are aligned with Ministerial Priorities and the delivery of A Healthier Wales. Provide assurance that regional clinical service programmes and models are developed and delivered to improve resilience, equity of access and outcomes across South West Wales. | Subgroup: maintain alignment with both Health Boards clinical service plans, planned care recovery, capital prioritisation and regional commissioning / finance arrangements | Ongoing |  |  |

- Resource / Funding Considerations

| Resource / Funding Requirement | Current Position | Impact / Mitigation |
| --- | --- | --- |
| Regional programme capacity (Stroke) | Dedicated programme management capacity reduced following the end of Welsh Government funding for the Regional Stroke Programme Manager. | Risk to pace and coordination of programme delivery. Prioritisation of key workstreams and consideration of future resource arrangements through programme governance. |
| Planned Care recovery funding and delivery capacity | Initial Welsh Government funding has been confirmed, but the funding available is lower than the amount bid for. The implications for individual schemes, agreed trajectories and regional programme assumptions are being assessed. | This may constrain the scope or pace of planned recovery activity, including the intended improvement and equalisation of cataract waiting times. Health Board and programme governance will review deliverability, prioritisation and any residual funding or capacity gap. |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

| Resource / Funding Requirement | Current Position | Impact / Mitigation |
| --- | --- | --- |
| Capital investment (Cancer and Cellular Pathology) | Capital planning and business-case development continue for both programmes, with separate papers being presented to the October RJC. | Timely approval and delivery are required to support long-term service sustainability. Progress is being managed through programme governance, Health Board approval routes and Welsh Government engagement. |

- Risks

| Ref | Risk Description | Impact | Mitigation | Action Owner | RAG | Risk Owner | Residual Risk |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Programme delivery capacity and competing operational priorities | Reduced pace, weaker coordination and delayed implementation across multiple programmes. | Maintain portfolio prioritisation; confirm programme management arrangements; use exception reporting for unresolved capacity issues. | Marie Davies/Lee Davies |  | Marie Davies/Lee Davies |  |
|  | Regional Orthopaedics finance, commissioning and contracting arrangements remain unresolved. | Prevents or delays agreement of cross-boundary activity, shared capacity, pooled waiting-list arrangements and implementation of a sustainable regional orthopaedic model. | Directors of Finance to lead development of the required regional finance, commissioning and contracting framework, supported by finance, contracting and programme leads. Progress and unresolved decisions will be escalated through the Clinical Services Planning Subgroup and RJC as appropriate. | Huw Thomas/Claire Osmundsen-Little |  | Huw Thomas/Claire Osmundsen-Little |  |
|  | Regional Eye Care delivery plan and available funding are not yet sufficiently aligned to provide assurance on the intended regional approach and delivery trajectory. | The scope or pace of planned improvements, including progress towards a more equitable cataract waiting-time position, may need to be revised. | The Programme Board will clarify the preferred approach, implementation plan, achievable trajectory and implications of the confirmed funding position, with exception reporting through regional governance. | Craige Wilson |  | Craige Wilson |  |
|  | Workforce fragility across specialist services | Constrains service resilience, rota models, theatre productivity, regional pathways and sustainable delivery. | Develop programme-specific workforce plans; align with Workforce and OD subgroup; prioritise critical clinical, nursing and programme roles. | Marie Davies/Lee Davies |  | Marie Davies/Lee Davies |  |
|  | Digital and data dependencies | May delay dashboards, single PTL approaches, EPR alignment, pathway standardisation and benchmarking. | Build digital requirements into each roadmap; align with Data / Digital workstreams; agree data definitions and validation routes. | Marie Davies/Lee Davies |  | Marie Davies/Lee Davies |  |
|  | Capital infrastructure and theatre capacity | Risk to radiotherapy capacity, Eye Care theatre productivity, Pathology laboratory development and orthopaedic surgical hub ambitions. | Maintain regional capital prioritisation; produce clear evidence base and option appraisals; escalate time-critical capital decisions. | Marie Davies/Lee Davies |  | Marie Davies/Lee Davies |  |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

- Dependencies

| Description | How Dependency is Managed | Action Owner | RAG | Dependency Owner |
| --- | --- | --- | --- | --- |
| Finance and Contracting | Directors of Finance will oversee development of the regional finance, commissioning and contracting arrangements required for cross-boundary service delivery. Progress and unresolved decisions will be reported through programme governance, the Clinical Services Planning Subgroup and, where senior intervention is required, the RJC. | Huw Thomas/Claire Osmundsen-Little |  | Huw Thomas/Claire Osmundsen-Little |
| Data and Digital | Managed through regional programme workstreams, data validation processes, dashboard development and alignment of digital and interoperability requirements across both Health Boards. | Marie Davies/Lee Davies |  | Marie Davies/Lee Davies |
| Workforce and OD | Monitored through programme governance, workforce planning activity, clinical engagement and Health Board workforce leads to support recruitment, rota development and service sustainability. | Marie Davies/Lee Davies |  | Marie Davies/Lee Davies |
| Capital and Estates | Managed through programme boards, business case development, Health Board approval processes and Welsh Government engagement for major capital schemes and infrastructure requirements. | Marie Davies/Lee Davies |  | Marie Davies/Lee Davies |

- Issues

| Ref | Issue Description | Impact | Action Owner | Target Resolution Date | Status |
| --- | --- | --- | --- | --- | --- |
|  | Regional Orthopaedics finance, commissioning and contracting arrangements remain unresolved. | Delays agreement and implementation of cross-boundary delivery arrangements and the future regional model. | Huw Thomas/Claire Osmundsen-Little | TBC through finance, commissioning and contracting work | Open |
|  | Regional Eye Care Programme requires clarification of its intended plan and an assessment of the implications of Welsh Government funding being lower than the amount bid for. | May affect programme scope, delivery trajectory and the intended improvement and equalisation of cataract waiting times. | Craige Wilson | TBC following Programme Board review | Open |

RAG Definitions and Scoring Guidance

Delivery RAG Definitions

| RAG | Definition |
| --- | --- |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

| Black | Activity has yet to commence. |
| --- | --- |
| Red | Objective/output/milestone will not be delivered within agreed timeline. Immediate corrective action required or formal change action initiated. Report as Advise or Alert. |
| Amber | Forecasting that there is a significant risk that objective/output/milestone will not be delivered. Mitigating action is being taken. |
| Green | Objective/output/milestone forecast to be on time or early. |
| Blue | Task complete. |

Risk RAG Definitions

| RAG | Definition |
| --- | --- |
| Red | High likelihood and/or high impact risk requiring active management. |
| Amber | Moderate risk requiring monitoring and mitigation. |
| Green | Low risk with routine monitoring. |

Risk Scoring Matrix

| Likelihood / Impact | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| Almost Certain (5) | 5 | 10 | 15 | 20 | 25 |
| Likely (4) | 4 | 8 | 12 | 16 | 20 |
| Possible (3) | 3 | 6 | 9 | 12 | 15 |
| Unlikely (2) | 2 | 4 | 6 | 8 | 10 |
| Rare (1) | 1 | 2 | 3 | 4 | 5 |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

#### 10:55 AM, 0 Mins

## - RJC/37c: Developing a Regional Approach to Cancer Care: Proposed Inclusion within the RJC Work Programme

Abigail Harris (Swansea Bay UHB - CEO), Philip Kloer (Hywel Dda UHB - Chief Executive)

Attachments

RJC 37c Developing A Regional Approach to Cancer Care RJC SBAR.pdf

JOINT HYWEL DDA/SWANSEA BAY UNIVERSITY HEALTH BOARD COMMITTEE CYD-BWRDD IECHYD PRIFYSGOL HYWEL DDA/BAE ABERTAWE PWYLLGOR

| DYDDIAD Y CYFARFOD: DATE OF MEETING: | 13 October 2026 |
| --- | --- |
| TEITL YR ADRODDIAD: TITLE OF REPORT: | Developing a Regional Approach to Cancer Care: Proposed Inclusion within the RJC Work Programme |
| CYFARWYDDWR ARWEINIOL: LEAD DIRECTOR: | Executive Medical Directors |
| ARWEINYDD CLINIGOL: CLINICAL LEAD: | Dr Russell Banner, Clinical Director, Oncology & Haematology |
| SWYDDOG ADRODD: REPORTING OFFICER: | Abi Harris, Chief Executive, Swansea Bay University Health Board Phil Kloer, Chief Executive, Hywel Dda University Health Board |

Pwrpas yr Adroddiad (dewiswch fel yn addas) Purpose of the Report (select as appropriate)

Ar Gyfer Penderfyniad/For Decision

ADRODDIAD SCAA SBAR REPORT

Sefyllfa / Situation The Regional Joint Committee (RJC) is asked to endorse the inclusion of work to develop a Regional Approach to Cancer Care within its 2026/27 work programme and support the proposed direction of travel set out in this paper. The work would provide a strategic framework for Swansea Bay and Hywel Dda University Health Boards to explore greater alignment in cancer planning, while recognising the distinct role of the South West Wales Cancer Centre (SWWCC) in delivering specialist oncology services across the region, each Health Board’s separate cancer strategies, improvement plans and operational accountabilities, and the shared aim of improving service sustainability, quality and patient outcomes. This paper deliberately does not present a predetermined regional service model or seek approval of a full Programme Initiation Document. Its purpose is to secure an RJC mandate for proportionate development work, including clarification of scope, governance, leadership, stakeholder involvement and resource requirements. Subject to RJC endorsement, a workshop proposal will be developed during autumn 2026 and presented to the next Regional Drive and Delivery Group. This will set out the proposed purpose, scope, participants, governance, resource requirements and timing for focused stakeholder engagement and workshop activity during Quarter 4 of 2026/27. A progress update will subsequently return to the RJC in accordance with the agreed work programme, taking account of the national cancer strategy expected in February 2027. The work will be overseen through the Regional Clinical Services Planning portfolio and will use existing Health Board leadership, clinical planning and governance arrangements. The scope and pace of development will remain proportionate to available leadership and programme capacity. The wider strategic work remains separate from the proposed sixth and seventh radiotherapy bunker development, which will continue through its own governance and business-case route under the Clinical Services Planning portfolio. Capacity remains a key dependency and will determine the scope, pace and deliverability of the work. The RJC PMO will provide immediate enabling support to develop the workshop proposal, arrange the proposed workshops and support development of the regional cancer work programme. However, the PMO is a small team with finite capacity and an established portfolio of regional priorities and cannot provide the sustained programme management resource required for full programme development and delivery. Dedicated leadership and ongoing programme management will therefore need to be secured, alongside relevant clinical, operational, finance, contracting, data, digital, workforce and engagement input. Previous requests for programme support through the national cancer programme within NHS Performance and Improvement have not

Page 1 of 4

ADRODDIAD SCAA SBAR REPORT

yet secured additional capacity. The proposed scope, pace and timing will remain proportionate to the resource available.

Cefndir / Background Cancer services are facing increasing demand, workforce pressures, diagnostic and treatment capacity challenges, and continued advances in areas such as precision medicine, genomics, digital technologies, radiotherapy and Systemic Anti-Cancer Treatment (SACT). These developments create opportunities to improve outcomes and patient experience whilst also increasing the complexity of service planning and delivery. Cancer services across South West Wales already operate through a mixture of regional, local and networked arrangements. The South West Wales Cancer Centre provides an established regional foundation for non-surgical oncology, with collaboration across radiotherapy, oncology outpatients, diagnostics and selected pathways. However, strategic planning, governance, commissioning, data and delivery arrangements are not consistently aligned across the whole cancer system. Discussions to date have highlighted the need to keep two related but distinct areas separate but in view: - The first is how the South West Wales Cancer Centre and its future role should develop in response to increasing demand, changing treatment models and wider developments in cancer centre provision, including the new Velindre Cancer Centre and the need for appropriate alignment across South Wales. - The second is whether, and in which areas, the two Health Boards should move towards a wider regional strategic cancer framework and greater alignment of cancer planning arrangements. Members also identified the need for both Health Boards to share their current strategic cancer plans. Swansea Bay’s Cancer Strategy and Cancer Improvement Framework has been approved by its Public Board and is further advanced in development, while Hywel Dda’s Cancer Strategy and Cancer Improvement Framework are currently being developed. Regional work should therefore build on both organisations’ positions without replacing, pre-empting or assuming identical local arrangements. Development of a regional approach should connect with the existing cancer leadership and clinical planning arrangements in both Health Boards and with the Regional Clinical Services Planning portfolio. It should not create a separate structure disconnected from local cancer strategies, clinical service plans or established operational governance. The case for a wider strategic conversation is reinforced by: - Growing demand and complexity, with more people referred and treated, longer survival and increasing pressure from systemic anti-cancer therapy, radiotherapy, acute oncology and new treatment models. - Performance and sustainability pressures, including diagnostic constraints, pathology delays, workforce fragility, treatment capacity and variation across pathways. - Cancer audit findings calling for longer-term strategy, costed and resourced improvement planning, stronger whole-system governance, improved prevention and screening intelligence, and clearer accountability. - The forthcoming 10-year National Cancer Strategy, expected in February 2027, which will influence future expectations for cancer planning and delivery.

Asesiad / Assessment Purpose of the RJC decision The RJC is asked to confirm that development of a Regional Approach to Cancer Care should be included within its 2026/27 work programme and to endorse the proposed high-level direction of travel. Detailed consideration of scope, priorities, deliverability, governance and resource requirements will be undertaken through subsequent development work and brought back through established regional governance; returning to the RJC in February with an update and sense check. Indicative areas for subsequent development Subject to RJC endorsement, the following areas provide an indicative starting point for development and stakeholder testing. The workshops would draw on Swansea Bay’s five-part Cancer Improvement Framework and Hywel Dda’s developing Cancer Strategy and Cancer Improvement Framework, supported by Hywel Dda’s 20four7 Prevention Model. They are not proposed as an agreed programme scope and may be refined through the workshop-planning process:

Page 2 of 4

ADRODDIAD SCAA SBAR REPORT

- Prevention and earlier diagnosis: shared opportunities in prevention, screening, population health, health inequalities and earlier diagnosis. - Diagnostics and timely access: regional dependencies and opportunities in diagnostics, pathology, pathway flow and access to specialist expertise. - Tumour-site improvement: a limited number of pathways where shared expertise, regional multidisciplinary working or common improvement approaches could add value. - Sustainable services, research and innovation: the future role of the Regional Cancer Centre; workforce and treatment capacity; oncology, radiotherapy, systemic anti-cancer therapy and acute oncology; research; and evidence-based networked or satellite models. - Personalised care and living well with and beyond cancer: opportunities for more consistent access to personalised care, rehabilitation, survivorship, palliative and end-of-life care. Cross-cutting enablers and dependencies: workforce; leadership and governance; finance and contracting; data, digital and information governance; estates and infrastructure; research and innovation; engagement; quality improvement; and equality. Relevant RJC subgroups would be engaged where their contribution is required. Proposed boundaries The proposed work would not: delay immediate infrastructure or service decisions already progressing through agreed governance; assume a single regional operating model; replace either Health Board’s local cancer strategy, improvement plan or operational accountability; commit the organisations to investment or service change before the relevant business case, engagement and approval processes; or create a new standalone cancer governance or delivery structure where existing Health Board and regional arrangements can be used. Proposed development pathway and governance REGIONAL CLINICAL SERVICES PLANNING SUBGROUP Directs the work and maintains oversight of scope and deliverability October 2026 RJC November 2026 RDDG Quarter 4 2026/27 April 2027 RJC Endorse and initiate Develop and review Engage and test Return a developed regional proposition - Endorse inclusion  Develop the workshop  Undertake focused in the RJC work proposal workshops and  Prioritised programme  Confirm scope, engagement programme of - Support the participants and  Test priorities and work proposed direction intended outputs deliverability  Resource of travel  Review governance,  Identify dependencies requirements and - Confirm the next capacity and timing and resource next steps stage of  Agree readiness to requirements  Aligned with development proceed, governance  Develop the regional National and local options and resource work programme Cancer Strategies requirements  Return to RJC with an update and sense check Figure 1 summarises the proposed route from RJC endorsement in October 2026, through development and review of the workshop proposal at the November RDDG, to focused engagement and workshop activity during Quarter 4 of 2026/27. A subsequent progress update will return to the RJC in February 2027, to a developed and prioritised regional cancer proposition returning to the RJC in April 2027, with Regional Clinical Services Planning Subgroup oversight throughout. Key dependency and risk Leadership and programme capacity remain key dependencies. The RJC PMO can support the initial workshop-planning process, but the detailed clinical, operational, analytical, financial, digital, workforce and engagement contributions will need to be provided through the relevant Health Board and regional arrangements. The proposed scope, pace and timing should therefore remain proportionate to the capacity available. The workshop proposal will identify the required contributions and any material gaps before substantive development work commences.

Page 3 of 4

ADRODDIAD SCAA SBAR REPORT

Argymhelliad / Recommendation The Regional Joint Committee is asked to: - ENDORSE the inclusion of work to develop a Regional Approach to Cancer Care within the RJC 2026/27 work programme and support the proposed direction of travel described in this paper. - SUPPORT the development of a proportionate workshop proposal through the Clinical Services Planning portfolio, with the Regional Drive and Delivery Group providing coordination and oversight of the work and reviewing the proposal before substantive engagement begins. The work will use existing Health Board and regional arrangements and take account of wider South Wales alignment, available capacity and the forthcoming national cancer strategy.

Page 4 of 4

#### 10:55 AM, 0 Mins

## - RJC/37d: South West Wales Cancer Centre Update – Future Radiotherapy Infrastructure

Russell Banner (Swansea Bay UHB - Haematology &

Oncology)

Attachments

RJC 37d South West Wales Cancer Centre - Future Radiotherapy Infrastructur~.pdf

JOINT HYWEL DDA/SWANSEA BAY UNIVERSITY HEALTH BOARD COMMITTEE CYD-BWRDD IECHYD PRIFYSGOL HYWEL DDA/BAE ABERTAWE PWYLLGOR

| DYDDIAD Y CYFARFOD: DATE OF MEETING: | 13 October 2026 |
| --- | --- |
| TEITL YR ADRODDIAD: TITLE OF REPORT: | Future Radiotherapy Infrastructure and LINAC Replacement Resilience at the South West Wales |
| CYFARWYDDWR ARWEINIOL: LEAD DIRECTOR: | Executive Directors of Planning |
| SWYDDOG ADRODD: REPORTING OFFICER: | Dr Russell Banner, Clinical Director, Oncology & Haematology |

Pwrpas yr Adroddiad (dewiswch fel yn addas) Purpose of the Report (select as appropriate)

Ar Gyfer Penderfyniad/For Decision

ADRODDIAD SCAA SBAR REPORT

Sefyllfa / Situation The Regional Radiotherapy Programme requires agreement to change the scope and sequencing of the previously agreed BJC2 before both Health Boards consider the proposal formally in November 2026 and Welsh Government is approached to commence the next programme stage. The 5th LINAC will occupy the final vacant bunker at Singleton Hospital in Q1/2 2027. LINAC 1 reaches its latest replacement date in March 2028 and LINAC 2 in March 2030. Current programme assumptions indicate that new bunker capacity cannot be delivered before these dates, creating a material replacement gap and requiring interim operational mitigation. The proposed approach is to develop twin bunkers with essential support accommodation and to integrate the replacement LINACs into the same programme. Replacement of LINACs 1 and 2 would be sequenced ahead of an additional 6th operational LINAC. This is intended to protect replacement and clinical service resilience while avoiding further delay to the enabling design and business case work. The RJC is asked to endorse the change in regional direction and support the proposal proceeding through each Health Board’s governance route for formal Board consideration at the end of November 2026. Subject to Board approval, the Health Boards would then engage Welsh Government on the business case route for approximately £1m of design development funding. The RJC is not being asked to approve construction, the purchase or operation of replacement or additional LINACs, workforce growth, recurrent revenue, cost sharing or the final long-term regional service configuration.

Page 1 of 6

| Case | Original scope | Revised strategic role |
| --- | --- | --- |
| BJC1 | 5th LINAC in the existing vacant bunker at Singleton. | Approved by both Health Boards in July 2026. No change proposed. |
| BJC2 | Single 6th decant bunker at Singleton. | Proposed twin-bunker and support accommodation development, integrating the replacement LINACs and protecting the rolling replacement programme. |
| BJC3 | Additional LINAC capacity and future regional configuration. | Longer-term programme, including the Hywel Dda satellite ambition and future capacity decisions. |

Cefndir / Background Existing programme architecture Why the scope has changed Once the 5th LINAC occupies the current vacant bunker, SWWCC will have no decant capacity. Replacing a LINAC without a spare bunker would require the service to operate with one fewer treatment machine during removal, installation, commissioning and clinical activation (which typically takes 9-12 months). In a five-LINAC model this represents a material temporary loss of capacity. Demand modelling in the original paper shows demand rising to approximately 57,900 treatment slots by 2030/31, indicating the need for an additional 6th LINAC by 2029/30 and a potential 7th by 2030/31. Replacement pressure and demand growth therefore overlap. The estate solution needs to protect the replacement programme while preserving options for additional capacity. Relationship with the Hywel Dda satellite ambition A Hywel Dda satellite remains strategically desirable and is not displaced by the proposed Singleton development. However, the original paper indicates that a satellite would take at least 5 to 5.5 years from site identification and no site has yet been confirmed. It therefore cannot address the immediate Singleton replacement risk. The satellite should continue as a complementary longer-term workstream through separate joint planning and business case governance. Work undertaken to date - October 2025: Welsh Government scoping discussions agreed progression of BJC1, BJC2 and BJC3. - December 2025 to May 2026: the Radiotherapy Modernisation Group, clinical leads, Capital Planning and architects considered single and twin-bunker feasibility, developed the schedule of accommodation and identified a preferred site adjacent to SWWCC. - April to May 2026: the Radiotherapy Modernisation Group confirmed the twin-bunker approach as the preferred strategic direction. - June to July 2026: independent cost advice was developed and the potential BJC2 scope change was flagged in executive and Board papers linked to the 5th LINAC. - July 2026: BJC1 for the 5th LINAC was approved by both Health Boards.

Page 2 of 6

- 28th September 2026: Regional Drive and Delivery Group (RDDG) review and recommendation to proceed with paper to RJC 13th October 2026.

Asesiad / Assessment Strategic sequencing

- Priority 1: protect treatment capacity and replace ageing LINACs without avoidable loss

of operational capacity.

- Priority 2: introduce the 6th operational LINAC when demand, affordability, workforce and recurrent funding are confirmed.

- Longer term: determine the regional distribution of capacity, including the Hywel Dda satellite ambition.

Single versus twin-bunker assessment

| Option | Assessment | Strategic implication |
| --- | --- | --- |
| Do nothing | Not recommended. | No decant capacity and significant service resilience risk. |
| Single bunker | Addresses decant need but remains late against LINAC 1 and may under-build the constrained site. | Could require a second development, repeat mobilisation and further disruption and higher cost. |
| Twin bunkers + support accommodation | Preferred strategic direction, subject to affordability and deliverability. | Protects replacement flexibility and preserves future capacity options without approving additional operational LINACs. |
| Hywel Dda satellite only | Important longer-term ambition but not deliverable in the immediate timeframe. | Complementary to, not a substitute for, the urgent replacement solution. |

Why an integrated programme is proposed

- Replacement sequencing: LINACs 1 and 2 are the most urgent requirement and should drive the programme before additional capacity is commissioned.

- Design and interface risk: the bunkers, building services, equipment interfaces and replacement installations need to be developed coherently to reduce later redesign, duplicated approvals or incompatible assumptions.

- Procurement and contractual position: programme advice indicates that bunker and replacement LINAC packages may need to be bundled to manage design responsibility, handover, equipment interfaces and possible intellectual property requirements. Capital Planning and procurement/legal advisers must confirm the precise basis before submission to Welsh Government.

- Time: no option eliminates the immediate replacement gap, but an integrated approach reduces the risk of further avoidable delay once approvals and funding are available.

Page 3 of 6

Indicative programme position Figure 1. Indicative LINAC replacement and bunker delivery timeline. Planning dates remain subject to approvals, design, business case and procurement. Risks and mitigations

| Risk | Potential impact | Control |
| --- | --- | --- |
| Replacement gap | Loss of capacity, increased waits and service continuity risk. | Maintain a formally governed interim operational mitigation plan. |
| Programme delay | Bunker delivery moves further beyond replacement dates. | Early WG engagement, confirmed critical path, procurement route and design funding. |
| Scope misunderstanding | Estate approval is read as approval for equipment or revenue. | Repeat the boundary of the current decision and use staged business cases. |
| Under-building | Single bunker requires a second project on a constrained live site. | Test whole-life value and strategic optionality through the business case. |
| Workforce | Specialist workforce becomes the critical path. | Develop a phased workforce plan before any operational LINAC approval. |
| Regional access | Hywel Dda patients continue to travel pending satellite development. | Continue the satellite workstream and complete equality/travel impact assessment. |

Page 4 of 6

CONSEQUENCES OF THE 6TH AND 7TH BUNKERS NOT BEING AVAILABLE PRIOR TO THE PLANNED REPLACEMENT OF LINAC 1 Failure to deliver the 6th and 7th bunkers in line with the planned replacement schedule for linac 1 would create significant operational, clinical and strategic risks for the South West Wales Cancer Centre. MITIGATING ACTIONS REQUIRED: - There may be a requirement to continue operating existing LINACS beyond their planned replacement period and recommended life expectancy. Whilst this may provide short-term capacity resilience, it carries an increased risk of equipment failure, unplanned downtime, higher maintenance costs, challenges in sourcing replacement parts, and potential impacts on service continuity and patient access to treatment. - Consider extending operational hours using the existing workforce, where this can be achieved safely, sustainably and with appropriate staff support. This would be a short-term mitigation measure, reliant on staff undertaking additional paid overtime. Prolonged reliance on this approach may impact workforce wellbeing, sustainability, and staff retention. - Expedite recruitment and onboarding of additional staff to increase treatment capacity on current linacs as early as possible. - Explore outsourcing and collaborative arrangements with neighbouring radiotherapy providers, including Velindre Cancer Centre (VCC) and ICON, to provide additional treatment capacity where appropriate. - Continue to review service delivery models and treatment pathways to maximise the efficient use of available capacity. RESIDUAL RISK Even with the above mitigations in place, a delay to the delivery of the 6th and 7th bunkers would represent a significant residual risk to service resilience. Whilst short-term measures may partially offset capacity constraints, they would not provide a sustainable alternative to the planned infrastructure expansion and replacement programme. The timely delivery of the bunkers remains the preferred and most effective solution for maintaining service continuity, replacing ageing equipment, supporting workforce growth, and ensuring sufficient radiotherapy capacity to meet current and future demand. Financial Implications No final capital construction, equipment procurement or recurrent revenue approval is requested at this stage. The immediate requirement is agreement to proceed with the revised programme scope and seek Welsh Government agreement on the business case route and design development funding, currently estimated at approximately £1 million. Members should note, however, that the preferred strategic direction is expected to generate future capital and recurrent funding requirements for both Swansea Bay University Health Board and Hywel Dda University Health Board. These are likely to include replacement LINAC investment, future operational LINAC capacity, workforce growth, maintenance support, digital infrastructure and associated service costs. Detailed affordability assessments, recurrent revenue implications, funding arrangements and any proposed cost-sharing arrangements between the Health Boards have not yet been developed and will be presented through subsequent business case(s) for separate consideration and approval.

Page 5 of 6

Proposed Governance Route - 13th October 2026: Regional Joint Committee consideration of the proposed change in regional direction and support for progression through each Health Board's governance arrangements. - October to November 2026: completion of Swansea Bay University Health Board and Hywel Dda University Health Board internal governance and assurance processes. - 26th November 2026: formal consideration by both Health Boards26 November 2026. - Subject to endorsement by both Health Boards, engagement with Welsh Government to confirm the business case route and seek design development funding. - Development of the subsequent business case(s), which will return through both Health Boards for decisions relating to capital investment, equipment procurement, workforce growth, recurrent revenue and affordability

Argymhelliad / Recommendation The Regional Joint Committee is asked to: - ENDORSE the proposed change in BJC2 scope from a single decant bunker to an integrated twin-bunker and support accommodation development at Singleton. - ENDORSE the proposed sequencing, with replacement resilience and timely replacement of LINACs 1 and 2 prioritised ahead of commissioning additional operational capacity. - SUPPORT the proposal proceeding through each Health Board’s governance route for formal Board consideration at the end of November 2026. - SUPPORT, subject to approval by both Health Boards, joint engagement led by SBUHB with Welsh Government to confirm the business case route and seek approximately £1m of design development funding. - NOTE that the detailed procurement, design responsibility, handover and intellectual property position will be confirmed through SBUHB Capital Planning and procurement/legal advice before submission to Welsh Government. - NOTE that this decision does not approve construction, purchase or operation of a 6th or 7th LINAC, workforce growth, recurrent revenue, cost sharing or the final regional service configuration. - NOTE that future business case(s) are expected to include proposals requiring capital and recurrent investment from both Swansea Bay University Health Board and Hywel Dda University Health Board associated with replacement LINACs, future operational LINAC capacity, workforce and supporting infrastructure requirements. The scale, timing and phasing of these commitments remain to be determined and will be subject to separate affordability assessment and approval by both Health Board. - REAFFIRM that a Hywel Dda radiotherapy satellite remains a complementary longer- term regional ambition and will progress through separate joint planning and business case governance.

Page 6 of 6

#### 10:55 AM, 0 Mins

  - - RJC/37e: Cellular Pathology Update	Lee Davies (Hywel

Dda UHB - Executive

Director of Strategy and Planning)

Attachments

RJC 37e Regional Cellular Pathology Update SBAR Report.pdf

JOINT HYWEL DDA/SWANSEA BAY UNIVERSITY HEALTH BOARD COMMITTEE CYD-BWRDD IECHYD PRIFYSGOL HYWEL DDA/BAE ABERTAWE PWYLLGOR

| DYDDIAD Y CYFARFOD: DATE OF MEETING: | 13 October 2026 |
| --- | --- |
| TEITL YR ADRODDIAD: TITLE OF REPORT: | Regional Cellular Pathology Programme |
| CYFARWYDDWR ARWEINIOL: LEAD DIRECTOR: | Lee Davies, Executive Director of Strategy and Planning, Hywel Dda University Health Board |
| SWYDDOG ADRODD: REPORTING OFFICER: | Rose Turrell, Pathology Programme Manager, RJC PMO Heather Edwards, Business Planning Manager, Swansea Bay UHB |

Pwrpas yr Adroddiad (dewiswch fel yn addas) Purpose of the Report (select as appropriate)

Er Sicrwydd/For Assurance

ADRODDIAD SCAA SBAR REPORT

Sefyllfa / Situation This report provides the Regional Joint Committee (RJC) with an update on the development of the Full Business Case (FBC) for the Regional Cellular Pathology Programme, including the establishment of a single integrated laboratory facility at Swansea University Bay Campus to serve the Mid, South and West Wales population. The report outlines progress made since the preferred laboratory development option was endorsed by the Regional Joint Committee and approved by the constituent Health Boards in February 2026. It highlights the key decisions, risks, dependencies and next steps required to support programme delivery.

Cefndir / Background The Regional Cellular Pathology Programme originated from a wider South-West Wales Centre of Excellence proposal at Morriston Hospital, for which a Strategic Outline Case (SOC) was endorsed by Welsh Government in 2020. Although the programme subsequently progressed through outline design development, Welsh Government withdrew support for completion of the Outline Business Case in January 2025 following national capital prioritisation decisions. In response, Swansea Bay University Health Board and Hywel Dda University Health Board reviewed the programme and reaffirmed their commitment to regional service integration. During 2025, both organisations agreed a revised and more focused strategic direction centred on the development of a single integrated Cellular Pathology Laboratory serving South-West Wales, supported by Welsh Government. This reduced scope reflected the opportunity to deliver the core service transformation objectives through a more affordable and deliverable investment. A structured site selection process was subsequently undertaken, supported by regional clinical, operational, finance, capital and specialist advisors. Following comprehensive technical, operational and financial assessment.

Page 1 of 9

Swansea University Bay Campus was identified as the preferred location, offering the strongest strategic fit, opportunities for workforce development and research collaboration, existing laboratory infrastructure and a lower capital investment requirement. Approval of the preferred site established the basis for further design and feasibility, but remains subject to confirmation of affordability, funding and a satisfactory Full Business Case. Since agreement of the preferred site in February 2026, the programme has transitioned from option appraisal into Full Business Case development. Work is now focused on defining the operational model, laboratory design, workforce requirements, affordability, commercial arrangements, benefits realisation and governance framework required to support delivery of a single, co-located Regional Cellular Pathology Laboratory at Swansea University Bay Campus. Welsh Government funding has been secured to support Full Business Case development, providing the external specialist expertise and technical resources required to progress the programme through design, affordability, procurement and business case assurance activities.

Asesiad / Assessment The Regional Cellular Pathology Programme remains a complex transformation programme, encompassing both the development of a new regional laboratory facility and the consolidation of services across organisational boundaries. Progress has been influenced by a wide range of interdependencies across workforce, finance, digital, operational, commercial, estates and governance workstreams, all of which are critical to ensuring the development of a robust and evidence-based FBC capable of withstanding internal scrutiny and approval processes, estimated to be completed by September 2027. While mobilisation of the capital and infrastructure elements of the programme progressed rapidly following agreement of the preferred site, the service transformation and consolidation work has proven more complex, reflecting the need to align different organisational processes, operating models, workforce arrangements, contractual positions and information governance requirements. A significant challenge has been the recognised resource gap which has constrained the pace at which some business case workstreams can be progressed, alongside the significant operational service delivery pressures. Notwithstanding these challenges, the programme has prioritised the establishment of strong foundations to support successful delivery. This has included the development of information-sharing agreements and governance arrangements, establishment of clear Terms of Reference, project teams, mobilisation of specialist function groups, development of detailed workplans, and progression of the baseline activity, workforce, operational and financial information required to underpin the strategic, economic, commercial, financial and management cases. Collectively, this work is providing the framework necessary to support the development of a comprehensive and deliverable Full Business Case detailing the full revenue consequences of the cost of the transition, and the ongoing sustainable service cost. Governance The Regional Cellular Pathology Steering Group provides strategic regional leadership and oversight to the programme. Supporting operational and specialist project groups have been established to complete and support critical work within the programme on both the capital development tranche of work and the service consolidation. The programme Governance structure can be seen here.

Page 2 of 9

The Memorandum of Understanding (MoU) which strengthens the transitional framework for joint working was signed by both Chief Executives in July 2026. Subsequently, further Information Governance and legal documents have been completed to ensure the safe sharing of information between organisations, these include a change to both local Health Board Privacy Notices, a programme specific Data Protection Impact Assessment (DPIA), and a Welsh Accord on the Sharing of Personal Information (WASPI). National Policy and Programme Context The Regional Cellular Pathology Programme remains aligned with the strategic direction established through the Pathology Statement of Intent, National Pathology Programme, Diagnostics Recovery and Transformation Strategy and the All-Wales Digital Cellular Pathology Programme. Collectively, these initiatives promote greater regional collaboration, service standardisation, digital transformation, workforce sustainability and improved quality and performance across pathology services in Wales. National policy and performance reviews continue to highlight common challenges across pathology services, including increasing demand, workforce constraints, ageing estate and equipment, and pressures on service resilience and delivery performance. In response, there is a clear expectation that Health Boards work collaboratively to develop sustainable regional service models supported by digital pathology and modernised infrastructure. The FBC is being developed within this national context and is intended to demonstrate how the proposed regional laboratory will contribute to improved service resilience, diagnostic turnaround times, cancer pathway performance, workforce sustainability, productivity and equitable access to specialist pathology services. Concurrently, the programme is working to establish robust baseline measures for activity, performance, workforce and financial metrics to support benefits realisation and the future evaluation of programme outcomes. South-East Wales Development of a regional cellular pathology service in South-East Wales continues to progress through a partnership between Aneurin Bevan, Cardiff and Vale and Cwm Taf Morgannwg University Health Boards. A preferred site has been identified, and the programme is currently finalising its SOC which is expected to be presented to the respective Health Boards for approval during autumn 2026. A discussion is due to take place at the Chief Executive Management Team (CEMT) on 6th October regarding the progress of both Laboratory developments in the South of Wales. The clinical lead for Performance and improvement has been invited to inform and facilitate a discussion regarding the plans, including the important strategic question: whether Welsh Government investment is more likely to be secured through a single South Wales laboratory development rather than through two distinct regional proposals. To support the discussion a brief has been provided to the two Chief Executives ahead of the CEMT meeting. While there are understandable reasons why a single South Wales facility would be considered, revisiting this question at this stage of the process risks significant delay to the programme and the mitigation of the substantial service risks. Capital Programme In February 2026, the preferred site was agreed by both Health Boards at the RJC and subsequently a special Swansea Bay Board and an extraordinary Hywel Dda Board. This site is an existing building at Swansea University Bay Campus. There is a pre-design forecast outturn of £12.482m, including £7.511m works costs. This remains subject to design development, surveys, equipment decisions, procurement, and tendered cost validation. RIBA Stage 1 (setting the brief) is almost complete. This involved several key stakeholder end-user meetings, site visits and design development workshops which have informed the process iteratively

Page 3 of 9

and further clarified design. The schedule of accommodation and laboratory layouts are being refined with service representatives. Current information indicates ground and first floor requirements, 13 clinical reading rooms capable of accommodating two occupants each, and potential future use or sub-letting of the second floor to mitigate revenue impact. Once the laboratory footprint and clinical adjacencies have been agreed, and RIBA Stage 1 signed off, the project will progress into RIBA Stage 2 (outline design). Current technical matters include assessing roof replacement options, laboratory category specification, building regulations requirements effective from 1 July 2026, building control and NEC supervisor appointments, IM&T and digital infrastructure, equipment configuration, drainage and services, and the condition and apportionment of cost to support replacement of existing plant. The roof replacement is currently outside the agreed scope, pending evaluation. Draft Head of Terms (HoTs) are under legal review. Matters still to be concluded include roof works and cost apportionment, the level of university strip-out and lease arrangements. Lease costs are agreed at £16 per sqft and service charges at £4.50 per sqft over an area of 28,389 sqft (2,637 m2). The requested additional three-month rent-free extension above the current 18-month rent-free period was declined (NB the rent-free period commences from Welsh Government approval of the business case). The proposed Containment Level (CL) for the Cytology Laboratory has been challenged by the service. The current scope includes CL2 space, while urgent work is developing the service justification, functional requirements, risk assessment for CL3 disease requirements, regulatory position and views from Public Health Wales and the National Programme. A firm recommendation is expected to be presented to the Steering Group on 12th October 2026. If accepted, this will represent an increase in scope. Current equipment specifications have been provided to the Supply Chain Partner. Future equipment requirements remain dependent on emerging national Digital and Automated Microtomy programmes and agreement on the approach to equipping the consolidated service. This work is progressing through the Finance Project Team, led by procurement leads. Operational availability and the ambitious timeline for constructor outputs remain significant risks. Existing laboratory site visits have taken place during August and September, including several visits to the proposed new laboratory site to inform design specifications, functional adjacencies, key constraints and a high-level test-for-fit.

Page 4 of 9

File available in larger view here. Project Risks The strategic project risks identified as 16 or above are as follows:

| Risk Description | Probability | Impact | Score |
| --- | --- | --- | --- |
| Risk the resource schedule to support draw-down of WG funds for internal fees to develop FBC is inadequate | 4 | 5 | 20 |
| Risk that revenue requirement for ongoing service consolidation and sustainability is not affordable. | 4 | 5 | 20 |
| Risk of programme delays | 4 | 5 | 20 |
| Risk that procurement process timeline/complexity is underestimated | 4 | 4 | 16 |
| Risk that capital requirements are under/over estimated | 4 | 4 | 16 |
| Risk that equipment requirements/costs will be under- estimated | 4 | 4 | 16 |
| Risk that digital equipping requirements (hardware & fibre cabling) could be underestimated | 4 | 4 | 16 |
| Risk that late confirmation of Lab eqpt requirements / configuration will delay design process | 4 | 4 | 16 |
| Risk that Laboratory configuration and design is poorly informed/planned | 4 | 4 | 16 |
| Risk that new Building Control regulations (effective from the 1st of July 2026) approvals will be more onerous extending project timelines. | 4 | 4 | 16 |

Page 5 of 9

Business Case Development and Benefits Realisation The Regional Pathology Laboratory Full Business Case (FBC) continues to progress as planned, with the Strategic Case nearing completion. The Economic, Commercial and Management Cases are well advanced. Ongoing programme activity is informing the development of the remaining cases, including demand, capacity, affordability, and strategic benefits realisation requirements. Benefits realisation is now profiled over 1-2 years, 3-4 years and 5 year+ as appropriate to a transitional project. Benefits are profiled expected through improved resilience, compliance, and risk reduction, with longer-term transformational opportunities focused on service standardisation, workforce redesign, digital pathology and efficiency improvements. Further work is underway to finalise benefits, affordability assumptions and supporting governance arrangements. Resource The Programme identified the need for an interim Regional Service Director in November 2025 to provide dedicated leadership and coordination across the Regional Cellular Pathology Programme. However, neither Health Board had sufficient funding within existing service establishment budgets to support the appointment. Following confirmation of Welsh Government funding to support FBC development, it was agreed that a proportion of this allocation would be used to fund the interim post and associated backfill arrangements. This approach was intended to mitigate operational pressures within service teams, enabling continued contribution to programme development whilst establishing a single point of regional leadership. Progression of the appointment was subject to a period of due diligence, resulting in some delay to the recruitment process. Subsequently, Hywel Dda University Health Board, working collaboratively with service directors and Workforce representatives from both Health Boards, led the recruitment process. Interviews were held on 25 September, with a panel comprising senior representatives from both Health Boards, including programme and performance leads. A stakeholder panel was also convened, including representatives from workforce, pathology, regional programme management office and finance teams. Following a robust recruitment process, an appointment was made to the post of Regional Service Director. The appointment represents a critical milestone for the programme and will provide the leadership capacity required to maintain momentum, support delivery of key programme dependencies, and drive completion of the FBC over the coming twelve months. The resource requirement submitted to Welsh Government was developed in March 2026 and reflected the anticipated programme management, service consolidation, operational, clinical and specialist functional support required to develop a robust Full Business Case. The estimated resource requirement was valued at £800k. Welsh Government subsequently approved a sum of £1.7 million to support business case development, with an agreed proportion of the allocation ringfenced for internal resource costs and specialist internal support, to the value of £300k. This funding has been instrumental in progressing programme activity to date, including establishment of the interim Regional Service Director role and supporting key workstreams across the programme. Whilst this investment has significantly strengthened programme capacity, there remains a residual resource gap across operational and specialist functions. This shortfall continues to be managed through contributions from RJC resources, operational service teams and Health Board functional specialists. As programme activity accelerates and interdependencies become increasingly complex, the continued reliance on existing capacity presents an ongoing delivery risk which may impact programme timelines if additional support cannot be secured.

Page 6 of 9

Service Consolidation Baselining To support the development of a robust and evidence-based FBC, the programme has commissioned the Healthcare Systems Engineering(HCSE) Team at Swansea Bay University Health Board to undertake a comprehensive activity and demand baselining exercise. This has been funded from within the WG internal resourcing allocation. This work has focused on establishing a consistent methodology, common datasets and agreed performance metrics across both organisations, ensuring that future planning, capacity modelling, workforce assessments and financial appraisals are based on comparable and reliable information. The exercise will provide a single version of the truth for the programme, improving confidence in the underlying assumptions and enabling informed decision-making as the regional service model and business case are developed. Initial work has highlighted the importance of data validation and standardisation across systems, reinforcing the need for a structured and independent approach to baseline development. HCSE were on site at Glangwili General Hospital on 9th of September and have since produced a report on their findings including a comparative analysis for Swansea Bay and Hywel Dda’s Cellular Pathology operations. The next steps for this piece of work, is service scrutiny and validation followed by sharing the findings with the Finance and Workforce leads for inclusion in their work programme. This is due to take place week commencing 12th October. Finance A combined Finance and Procurement Group has been formed over the summer to enable coordination of the associated workstreams and ensure the appropriate engagement and crossover, with a clear workplan currently being finalised to assure the required outputs. The financial planning and affordability assessment continues to progress, with work underway to establish the baseline activity, demand, workforce and financial position that will inform development of the FBC. Key dependencies, assumptions and information requirements have been identified across all finance workstreams, supporting greater clarity regarding programme costs, delivery timescales and affordability considerations. In parallel, information governance arrangements, including supporting data-sharing documentation, have been completed, enabling several interdependent workstreams to progress. The output of the HCSE baseline assessment will be a key data set to feed into the finance workstreams. This combined with the financial assessment and clarity on service scope, are key to inform options for the ongoing inter Health Board contractual arrangements which will be framed through the finance work programme, taking into account the reality of activity reporting arrangements which will be key performance metrics. Development of the future procurement approach is also advancing. A regional managed service contract is emerging as a critical enabler of the consolidated service, recognising that the two Health Boards currently operate different equipment, maintenance and consumables models via separate suppliers and to different timelines. The FBC will therefore need to confirm the preferred procurement strategy and define associated contractual arrangements, including contract interfaces, charging mechanisms, change control processes, risk allocation and the treatment of equipment replacement and lifecycle costs. Procurement and contracting options are currently being developed to inform future decision-making and support alignment between programme delivery and procurement timescales. Commercial discussions relating to the proposed Bay Campus accommodation are continuing. A number of key matters require resolution through the Heads of Terms and lease negotiations,

Page 7 of 9

including lease duration, service charges, facilities management, rent-free arrangements, landlord and tenant responsibilities, treatment of existing assets, liabilities associated with roof and plant infrastructure, strip-out requirements, access and parking arrangements, and the use of any shared university facilities. These discussions will be critical to establishing the long-term affordability and operational viability of the proposed solution. Revenue affordability remains a significant programme risk. Further work is required to quantify the full financial implications of service consolidation and occupation of the proposed facility, including accommodation, facilities management, operational support and future service delivery costs. While opportunities to offset costs through service consolidation, operational efficiencies, digital transformation and potential commercial income streams continue to be explored, the overall affordability position will only be confirmed once the future operating model, procurement arrangements and infrastructure requirements have been fully defined through the FBC process. Workforce The future regional model is intended to bring together the two laboratory services through a single regional workforce arrangement, supported by unified governance, standardised processes and digital working. The workforce case is central because consultant vacancies, recruitment and retention difficulties, ageing workforce risks, training capacity constraints and reliance on overtime, agency support and outsourcing affect sustainability. The workforce resilience was a key component in the service led discussion on site preference in February 2026. The working assumption is that the service will be hosted by Swansea Bay UHB and that a relevant transfer under TUPE may apply to existing staff following a transitional phase. This requires formal legal, HR and organisational change validation. The workforce plan must confirm current WTE and vacancy baselines, future establishment and skill mix, leadership and management arrangements, training capacity, succession planning, harmonisation implications, staff engagement and consultation, transfer arrangements and the workforce revenue requirement. The university location is expected to support recruitment, education, research and advanced practice, but these benefits must be evidenced and measured. This workplan has been drafted and is currently sat with workforce leads for scrutiny, validation and finalisation. Staff Engagement A communication and engagement plan has been developed to support delivery of the Regional Cellular Pathology Programme, ensuring timely, transparent and consistent engagement with staff, clinical leaders, partner organisations and key stakeholders throughout the development of the Full Business Case (FBC). The approach is underpinned by principles of early engagement, two-way communication and workforce involvement to build understanding, address concerns and support organisational readiness for change. Initial engagement with Cellular Pathology Section Managers was undertaken in September 2026 to introduce the programme, and to gather feedback on design information for laboratory adjacencies and flow. This took place on two consecutive site visits and follow up meeting at Morriston hospital. A wider staff engagement session is scheduled for 6 October 2026, during which programme leads will provide an overview of progress since Board endorsement in February 2026, share emerging information regarding the proposed laboratory site, including external visualisations, and outline the programme timeline through to FBC submission.

Page 8 of 9

Feedback received through this and subsequent engagement activity will be used to shape and inform the ongoing communications and engagement programme, ensuring that staff perspectives are appropriately considered as the programme progresses.

Argymhelliad / Recommendation The Regional Joint Committee is asked to: - TAKE ASSURANCE from the progress made in developing the Full Business Case and Regional Cellular Pathology Programme since approval of the preferred site in February 2026. - ACKNOWLEDGE AND DISCUSS the key programme risks, dependencies and mitigations - ENDORSE the continued development of the Full Business Case and associated programme workstreams. - ENDORSE a further update to the RJC in February 2027.

Page 9 of 9

4

11:10 AM, 10 Mins

## - RJC/38: Regional Health Economy Subgroup Update

Ardiana Gjini (Hywel Dda UHB - Executive Director of Public

Health)

Attachments

RJC 38a Regional Health Economy Subgroup AAA Report.pdf

RJC 38b Regional Health Economy RJC Subgroup Work Programme Summary.pdf

#### REGIONAL HEALTH ECONOMY SUBGROUP UPDATE REPORT/ ADRODDIAD DIWEDDARU’R PWYLLGOR

#### Regional Joint Committee

Date of last meeting/ Dyddiad y cyfarfod diwethaf: 14 September 2026

Quoracy/ Cworwm: Met

Report by/ Adroddiad gan: Ardiana Gjini, Executive Lead supported by Hugo Van Woerden

KEY DISCUSSION POINTS AND MATTERS FROM THE DISCUSSION AT THE MEETING/ PWYNTIAU TRAFOD ALLWEDDOL A MATERION I’W

HUWCHGYFEIRIO O’R DRAFODAETH YN Y CYFARFOD:

Alert1 (may require discussion. e.g. include significant risks, issues, decisions required, change requests for timescales, scope or milestones within subgroup work programmes and matters requiring escalation.)/ Rhybuddio (efallai y bydd angen trafodaeth. e.e. cynnwys risgiau sylweddol, materion, penderfyniadau sydd eu hangen, ceisiadau am newid ar gyfer amserlenni, cwmpas neu gerrig milltir o fewn rhaglenni gwaith is-grŵp a materion sydd angen eu huwchgyfeirio)

The Regional Health Economy Group had no items of which to alert members of the RJC.

Advise2 (to monitor)/ Cynghori (i fonitro)

The Regional Health Economy Subgroup wishes to advise members of the RJC that this report provides a cumulative update since the RJC meeting in April 2026. As the July RJC meeting was stood down, activity previously prepared for July has been retained where it remains relevant, with substantive progress since then highlighted below.

- Across the programme, the subgroup has moved from initial scoping towards a clearer set of products and delivery priorities. These include a phased Regional Health Intelligence product, a shared regional health equity framework, a product-development roadmap for the long-term plan, practical procurement and preventative-spend activity, and delivery of the Warm and Healthy Homes programme.

- Governance and strategic direction

The subgroup reviewed its refreshed Terms of Reference on 14 September 2026. The revised purpose and objectives align with the updated RJC Terms of Reference and strategic

objectives. Members supported the document in principle, subject to minor amendments. The wording will recognise the subgroup’s sphere of influence and the wider role of health, care, public services, communities, economic partners, local authorities and universities.

- Regional Health Intelligence and outcomes

The subgroup endorsed a phased Regional Health Intelligence approach. The initial product will be a proportionate refresh of the previous regional ARCH Health Needs Assessment, drawing on the latest accessible evidence from both health boards, Public Health Wales and

1 There is a lack of confidence that any action in place is sufficient to address the issue satisfactorily and/or within the scope of the operational team or executive to resolve. Engagement, action or intervention required. 2 There are areas of concern where assurance has been taken on actions in place but requires close monitoring. An early warning of an emerging and potentially serious concern.

Page 1 of 4

wider partners, while recording material gaps and limitations. Equalities information will be integrated throughout. A Regional Equity Plan will continue as a separate but interdependent workstream. The next phase will clarify the ownership, delivery leadership and capacity, and develop an indicator and outcomes framework. A focused discussion will also consider

practical options for modelling and prioritising population health investment, including health economics methods, cluster-level risk prioritisation and programme evaluation.

- Regional health equity framework

Following review of current activity across both health boards, the subgroup agreed to develop a shared regional health equity framework rather than a single uniform health equity delivery plan. The framework will establish common principles, assessment methods and regional priorities while allowing delivery to be adapted to local population needs and organisational arrangements. The existing equity-informed health impact assessment toolkit will be reviewed for regional use. A small number of potential regional pilots will be explored where there is clear added value, including scoping poverty training, subject to agreed resource, funding and governance arrangements.

- Long-term Regional Health Economy Plan

Development of the long-term plan is now managed through a product-development roadmap covering strategic analysis, the plan structure, engagement outputs, health intelligence, health equity, procurement and preventative spend, international learning and the draft plan. The plan structure and Three Horizons engagement approach have been drafted, using the 4Ps framework of People, Place, Procurement/Public Purse and Partnerships with an explicit equity lens. Members have been asked to review the completeness of the product scope, the achievability of the proposed timescales and alignment with health board and partner planning cycles. Any material issue affecting delivery of the draft plan will be escalated to the Executive Leads.

- Procurement and preventative spend

A regional procurement workshop in August brought together finance, procurement, public health, value-based healthcare and RJC colleagues. Work is progressing to establish a

structured regional baseline across processes, governance, data, benefit methodologies, controls and current collaborative activity, and to identify practical opportunities for regional alignment. Public sector food procurement remains a shared regional priority and will be supported by baseline work on demand, spend, suppliers, contracts and supply chains. A Regional Public Sector Food Procurement Workshop is scheduled for November focused on agreeing common principles for public-sector food procurement. Preventative-spend mapping is progressing, with an accompanying interpretative note to be developed to support a shared understanding of prevention definitions and their application to the regional mapping.

- Warm and Healthy Homes

Planned hospital in-reach activity will commence across the four Hywel Dda acute hospitals from late September, alongside summer in-reach activity already undertaken in Swansea Bay. Briton Ferry East 2 was identified as the Swansea Bay pilot locality, supported by combined Energy Performance Certificate (EPC) and health data to target potentially eligible households. Nest funding and delivery support have been confirmed. Evaluation arrangements, including the status of potential HAPS match funding and wider evaluation support, remain in development and are due to return to the subgroup in November.

- International learning and partnerships

Page 2 of 4

The international learning webinar held on 22 July 2026 was completed and the recording and insights report were circulated. The subgroup agreed to continue exploring learning opportunities through the WHO Regions for Health Network, Healthy Places approaches and the Wales and WHO Special Initiative on Health and the Wellbeing Economy. The programme is also linking with emerging WHO wellbeing economy outcomes and indicator work to inform the regional outcomes framework.

- Cross-programme alignment

The programme continues to strengthen links with other RJC workstreams. Population health and inequalities evidence is being positioned to inform established regional clinical service programmes through the appropriate governance routes. Workforce input is informing the People chapter of the long-term plan, while finance and procurement collaboration is supporting the Procurement/Public Purse strand. The subgroup has emphasised that regional activity should add value, avoid duplication of local work and remain proportionate to available capacity.

Assure (to note)/ Sicrhau (i nodi)

The Regional Health Economy Group wishes to assure members of the RJC that:

- The subgroup has maintained oversight of the programme, with a clear action trail and escalation route supporting delivery across the workstreams.

- The Regional Health Intelligence Scoping Document has been endorsed in principle, with a

proportionate initial product identified and the principal delivery dependencies clearly recorded.

- A shared regional health equity framework has been agreed as the preferred direction, balancing common regional principles and methods with delivery adapted to local needs and arrangements.

The long-term plan is supported by a visible product roadmap. Completed outputs include the

strategic analysis, Place workshop outputs, procurement workshop outputs and international learning outputs, with an initial draft of the plan scheduled for consideration by the subgroup in November.

Review of Risks/ Adolygiad o Risgiau

- The principal risk is insufficient analytical and public health capacity, together with unresolved ownership and delivery leadership, which may delay the Regional Health Intelligence Profile and related frameworks. Wider risks include scope expansion, duplication with local work, engagement fatigue and delivery plans exceeding available resource. Mitigation includes phased delivery, use of the product roadmap to prioritise work, alignment with existing planning and governance routes, and escalation of material delivery issues to the Executive Leads.

Sharing of learning/ Rhannu dysgu

- Learning from the July international webinar, the Place workshop, the regional procurement workshop and the development of health intelligence and equity products is being incorporated into the emerging long-term plan. The agreed direction is to use the regional space to connect intelligence, align priorities, share and adapt effective practice, support selected joint prevention activity and embed equity, while retaining local delivery where population needs or organisational arrangements differ.

Recommendation/ Argymhelliad

That RJC members:

Page 3 of 4

- RECOGNISE the progress made since April 2026, including the development of the phased Regional Health Intelligence approach, shared regional health equity framework and long-term plan product roadmap.

- SUPPORT the continued phased and proportionate development of the programme, prioritising activity that provides clear regional added value and RECOGNISE the current analytical, public health and health intelligence capacity constraints, together with the identified ownership and delivery dependencies which may affect the pace and scope of delivery.

- Date of next meeting/ Dyddiad y cyfarfod nesaf: Regional Health Economy Subgroup 23 November 2026

Page 4 of 4

- Subgroup Summary

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

RJC Subgroup Work Programme Summary Template

Blank subgroup-level reporting template for completion

| Reporting Period | July – September 2026 |
| --- | --- |
| Subgroup Name | Regional Health Economy Sub-Group |
| Stage | Define / Delivery |
| Version | 0.2 |
| Executive Lead(s) | Ardiana Gjini (SRO) and Hugo Van Woerden |
| Operational Lead(s) | N/A |
| Clinical Lead(s) | N/A |
| Programme Lead | Sophie Marr |
| Reports To | RJC |
| Receives Reports From | Subgroup Programmes/Projects |
| Meeting Frequency | Bimonthly |
| ToR Agreed | Yes Refreshed Terms of Reference supported in principle on 14 September 2026, subject to final amendments and RJC approval. |

Hywel Dda / Swansea Bay University Health Boards | Byrddau Iechyd Prifysgol Hywel Dda / Bae Abertawe

Subgroup Scope

Subgroup Scope

| 4P theme | Programme / initiative coverage |
| --- | --- |
| People | Workforce development aligned to current and future population need, local pathways to health and social care employment, schools/colleges, FE/HE links, apprenticeships, anchor responsibilities and the People chapter of the long-term plan. |
| Place | Warm and Healthy Homes, Welsh Veg in Schools, Local Development Plan / place engagement, Pride in Place opportunities, housing quality, community assets, climate resilience and local wider determinants. |
| Procurement / Preventative Spend | Public sector food procurement, Health Anchors Learning Network, regional procurement workshop, prevention spend baseline mapping, value-based healthcare, health economics and use of procurement as a policy lever for local economic and health improvement. |
| Partnerships | Health Intelligence, Health Inequalities, PHW support, PSBs, FGCO, WHO / international learning, cross-subgroup collaboration and stakeholder engagement for the long-term RHE Strategic Plan. |

- Ambition Statement(s)

Ambition Statement(s)

The Regional Health Economy Programme aspires to create a thriving, equitable health economy that serves almost 800,000 people across South West Wales by aligning strategies, amplifying existing efforts, and accelerating innovation. Through a collaborative population health approach rooted in the Marmot Principles and Social Model for Health and Wellbeing, the programme will scale up proven practice, foster regional learning, and drive sustainable systems change to maximise impact, investment and health equity across the region.

- Objective / Output Statements

| Objective / Output | Target Date | RAG |
| --- | --- | --- |
| Increase the number of people accessing eligible funding to increase warmth (such as Nest) | Oct 2026 |  |
| Develop and agree a measurable outcome objective relating to avoidable healthcare demand affecting the 20% most deprived communities in the region, including an agreed baseline, measure and boundaries of subgroup influence. | TBC following agreement of the final wording and baseline |  |

- Milestones & Deliverables

| RJC Subgroup Objective | Milestone / Deliverable | Target Date | This Period (RAG) | Comments / Notes |
| --- | --- | --- | --- | --- |
| 3.2.1 Seek assurance that a long‑term Regional Health Economy Strategic Plan is produced that provides a shared regional direction and enables coordinated, equitable system change. | Maintain and agree the Product Development Roadmap, including products, leads, dependencies, timescales and engagement alignment | September 2026 |  |  |
|  | RJC approval of draft long-term Regional Health Economy Strategic Plan. | March 2027 |  |  |

Hywel Dda / Swansea Bay University Health Boards | Byrddau Iechyd Prifysgol Hywel Dda / Bae Abertawe

| RJC Subgroup Objective | Milestone / Deliverable | Target Date | This Period (RAG) | Comments / Notes |
| --- | --- | --- | --- | --- |
|  | Translate strategic plan into delivery plan, benefits framework and annual review cycle. | April 2027 |  |  |
| 3.2.2 Seek assurance that a shared regional health profile is established which identifies the key drivers of health inequality and future healthcare demand across the region and is routinely used to inform regional planning. | Develop Regional Health Intelligence Scoping Document. | August 2026 |  | Scoping document endorsed in principle on 14 September; phased approach and ARCH HNA refresh agreed. |
|  | Agree inequalities plan and evaluation approach with Joint Senior Management Teams across both Local Public Health Teams. | September 2026 |  |  |
|  | Develop shared regional health equity framework, including common methodology, regional priorities, pilots, ownership, governance, funding and measures | October 2026 |  |  |
|  | Confirm ownership, delivery leadership, minimum viable scope and available capacity for development of Regional Health Intelligence Profile | October 2026 |  |  |
|  | Produce a shared regional health profile. | March 2027 |  |  |
| 3.2.3 Oversee the required preparatory work enabling the regional health economy to become a designated WHO sub regional health network so that the RJC can benefit from the shared learning opportunities afforded by participation in the network. | Hold International Learning Webinar hosted by WHO Europe Regions for Health Network and WHO Europe Healthy Cities Network | July 2026 |  | Complete. Webinar Recording and Insights Report circulated. |
|  | Continue ongoing engagement events with WHO Europe Regions for Health Network and Healthy Cities Network | January 2027 |  |  |
|  | Explore and scope WHO Europe Regions for Health Network in-person visit to Wales with RJC members | March 2027 |  |  |

- Resource / Funding Considerations

| Resource / Funding Requirement | Description | Impact / Mitigation |
| --- | --- | --- |
| RESOURCE ANALYSIS / ASSUMPTIONS / REQUIREMENTS / IMPACT / GAPS | The work is based on existing public health team capacity, PHW input, RJC PMO coordination and partner support. Delivery will require clear prioritisation because the ambition is broader than current dedicated capacity. No dedicated analytical resource or single delivery lead has yet been confirmed for the Regional Health Intelligence Profile. Existing public health and analytical teams are managing competing priorities and reduced capacity. Scope and | Confirming ownership and delivery leadership, agreeing a minimum viable scope and realistic timetable, prioritising outputs through the product roadmap, and maintaining RHE subgroup / RJC PMO oversight. Where capacity gaps remain, existing PHW, public health, analytical, academic and partner support will be explored, with unconfirmed activity treated as future opportunity rather than committed delivery. |

Hywel Dda / Swansea Bay University Health Boards | Byrddau Iechyd Prifysgol Hywel Dda / Bae Abertawe

| Resource / Funding Requirement | Description | Impact / Mitigation |
| --- | --- | --- |
|  | timescales must therefore remain proportionate until accountable ownership, leadership and available capacity are agreed. |  |
| FUNDING ASSUMPTIONS / REQUIREMENTS / IMPACT / GAPS | No specific funding source identified. Delivery is dependent on prioritising existing resource and connecting to prevention, value and wider determinant funding opportunities where available. Potential regional pilots, external health economics or academic support, poverty training and evaluation activity must not be treated as commitments until a funding, commissioning and governance route is agreed. | Prioritising delivery within existing resources, using the product roadmap to focus activity on agreed RHE objectives, and exploring external, academic, prevention, value-based healthcare or partner funding routes. Any pilots, training, evaluation or health economics input will only progress where a clear funding, commissioning and governance route is agreed; otherwise they will be recorded as future opportunities rather than committed deliverables. |

- Risks

| Ref | Risk Description | Mitigation | Action Owner | RAG | Risk Owner | Residual Risk |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | If analytical/public health capacity and delivery leadership are not confirmed, the Regional Health Intelligence Profile and outcomes framework may be delayed or reduced in scope. | Prioritise scope and capacity through agreed governance. | Ardiana Gjini/Hugo Van Woerden | + | Ardiana Gjini/Hugo Van Woerden | - |
| 2. | If the RHE programme scope is not actively prioritised, the volume of products and partner expectations may exceed available capacity and affect quality or delivery timescales. | Agree scope, sequencing and priorities through RHE governance. | Ardiana Gjini/Hugo Van Woerden | - | Ardiana Gjini/Hugo Van Woerden | - |
| Su3. | If regional activity is not clearly differentiated from local health board and partner work, the programme may duplicate existing activity rather than demonstrate distinct regional value. | Manage through agreed RHE governance and prioritisation. | Ardiana Gjini/Hugo Van Woerden | - | Ardiana Gjini/Hugo Van Woerden | - |

- Dependencies

| Description | How Dependency is Managed | Action Owner | Dependency Owner |
| --- | --- | --- | --- |
| Confirmed analytical and public health capacity | The scope and sequencing of the Regional Health Intelligence Profile will be kept proportionate to confirmed capacity, using a phased approach beginning with a refresh of the previous ARCH Health Needs Assessment and escalating any material resource constraint through the Executive Leads. | Ardiana Gjini/Hugo Van Woerden | Ardiana Gjini/Hugo Van Woerden |

Hywel Dda / Swansea Bay University Health Boards | Byrddau Iechyd Prifysgol Hywel Dda / Bae Abertawe

| Description | How Dependency is Managed | Action Owner | Dependency Owner |
| --- | --- | --- | --- |
| Confirmed accountable ownership and programme leadership | Executive Leads will agree the accountable owner and delivery lead for the Regional Health Intelligence Profile before the detailed scope, delivery timetable and allocation of work are finalised. | Ardiana Gjini/Hugo Van Woerden | Ardiana Gjini/Hugo Van Woerden |
| Access to current health board, PHW and partner intelligence | Existing intelligence products will be mapped against the agreed regional framework, with information requested from Health Boards, Public Health Wales and partners and any material data gaps or limitations recorded transparently within the refreshed profile. | Ardiana Gjini/Hugo Van Woerden | Ardiana Gjini/Hugo Van Woerden |
| Agreement of indicators, outcomes and baseline measures | A regional outcomes and indicator framework will be developed alongside the refreshed health profile, drawing on available national and WHO work and agreeing a proportionate baseline and measures through the Steering Group before they are incorporated into the long-term plan. | Ardiana Gjini/Hugo Van Woerden | Ardiana Gjini/Hugo Van Woerden |

- Issues

| Ref | Issue Description | Impact | Action Owner | Target Resolution Date | Status |
| --- | --- | --- | --- | --- | --- |
| 1. | Additional ad hoc analytical requests are being added to the programme of work and require ongoing prioritisation within existing resources. | Competing requests are increasing pressure on limited analytical capacity, leading to some slippage against existing programme timescales and requiring active sequencing of outputs. | Ardiana Gjini/Hugo Van Woerden | Ongoing review through RHE governance | Open – being managed through prioritisation and sequencing |
| 2. | Changes to other RJC subgroups and their work programmes may affect the feasibility and deliverability of the Regional Health Economy programme of work. | Any significant changes in related subgroup priorities, deliverables or assumptions could create dependencies, capacity pressures or sequencing issues for RHE programmes and timescales. | Ardiana Gjini/Hugo Van Woerden | Ongoing review through subgroup and RHE governance | Open – to be monitored through routine work programme review |

RAG Definitions and Scoring Guidance

Delivery RAG Definitions

| RAG | Definition |
| --- | --- |
| Black | Activity has yet to commence. |
| Red | Objective/output/milestone will not be delivered within agreed timeline. Immediate corrective action required or formal change action initiated. Report as Advise or Alert. |
| Amber | Forecasting that there is a significant risk that objective/output/milestone will not be delivered. Mitigating action is being taken. |
| Green | Objective/output/milestone forecast to be on time or early. |
| Blue | Task complete. |

Hywel Dda / Swansea Bay University Health Boards | Byrddau Iechyd Prifysgol Hywel Dda / Bae Abertawe

Risk RAG Definitions

| RAG | Definition |
| --- | --- |
| Red | High likelihood and/or high impact risk requiring active management. |
| Amber | Moderate risk requiring monitoring and mitigation. |
| Green | Low risk with routine monitoring. |

Risk Scoring Matrix

| Likelihood / Impact | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| Almost Certain (5) | 5 | 10 | 15 | 20 | 25 |
| Likely (4) | 4 | 8 | 12 | 16 | 20 |
| Possible (3) | 3 | 6 | 9 | 12 | 15 |
| Unlikely (2) | 2 | 4 | 6 | 8 | 10 |
| Rare (1) | 1 | 2 | 3 | 4 | 5 |

Hywel Dda / Swansea Bay University Health Boards | Byrddau Iechyd Prifysgol Hywel Dda / Bae Abertawe

5

11:20 AM, 15 Mins

## - RJC/39a: Research, Innovation and Excellence Subgroup Update

Mark Henwood (Hywel Dda UHB - Executive Medical

Director)

Attachments

RJC 39a Research, Excellence and Innovation Subgroup (AAA) Update Report.pdf

RJC 39b Research, Excellence and Innovation Subgroup Work Programme Summary.pdf

#### REGIONAL RESEARCH, EXCELLENCE AND INNOVATION UPDATE REPORT/ ADRODDIAD DIWEDDARU’R PWYLLGOR

#### Regional Joint Committee

Date of last meeting/ Dyddiad y cyfarfod diwethaf: 6th August 2026 Quoracy/ Cworwm: Yes

Report by/ Adroddiad gan: Leighton Phillips, Regional director for Research and Innovation/Liz Wonnacott, Head of Service – Medical Director, Swansea Bay

KEY DISCUSSION POINTS AND MATTERS FROM THE DISCUSSION AT THE MEETING/ PWYNTIAU TRAFOD ALLWEDDOL A MATERION I’W

HUWCHGYFEIRIO O’R DRAFODAETH YN Y CYFARFOD:

Alert1 (may require discussion. e.g. include significant risks, issues, decisions required, change requests for timescales, scope or milestones within subgroup work programmes and matters requiring escalation.)/ Rhybuddio (efallai y bydd angen trafodaeth)

- There are no matters requiring an ‘alert’ status.

Advise2 (to monitor)/ Cynghori (i fonitro)

- Improving Patient Access to Cancer Trials: confirmation has been received from Welsh Government that the bid for VPAG (Voluntary Scheme for Branded Medicines Pricing, Access, and Growth) monies to develop a regional approach to oncology trials has been successful. This will provide sufficient monies over the next three years to implement several key recommendations, including bolstering capacity to co-ordinate trials across the region and investment in Swansea Bay to undertake the additional activity this generates. As part of sustainability plans, aligned work supported by Directors of Finance, is considering the best mechanism to ensure financial flows across both organisations to meet the additional work generated by this activity and avoid clinical capacity or cost pressures. Advancing this is essential to securing equitable access to trials, improved outcomes, and an attractive research environment in an increasingly competitive UK and internationally environment.

- Scaling Cardiovascular Disease Innovation Project. The Predict and Prevent project, supported by Amgen, was a collaborative cardiovascular (CVD) initiative involving Hywel Dda, Swansea Bay and Swansea University, designed to move the system from reactive treatment to earlier, prevention-focused care. It combined population health analytics with service redesign, using the SAIL databank and wider informatics infrastructure to identify and

1 There is a lack of confidence that any action in place is sufficient to address the issue satisfactorily and/or within the scope of the operational team or executive to resolve. Engagement, action or intervention required. 2 There are areas of concern where assurance has been taken on actions in place but requires close monitoring. An early warning of an emerging and potentially serious concern.

Page 1 of 3

stratify patients at highest risk of future cardiovascular events. Building on this intelligence, the project tested targeted, high‑intensity interventions,

particularly pharmacist-led prevention clinics, focused on lipid optimisation, blood pressure control and lifestyle support, to close the treatment gap and improve outcomes. Hywel Dda has agreed to fund a pathfinder project to move the model towards sustainability and Swansea Bay is appraising how a sustainability plan could be situated in primary care but remains open to working regionally.

- Discussions are continuing with executives in relation to the South West Wales Corporate Joint Committee around supporting a coordinated, regionally led approach to developing the life sciences sector as a core economic priority. South West Wales has strong but fragmented assets across the NHS, universities and industry, and aligning these through a shared regional framework could position the area as a nationally significant health innovation and life sciences testbed. There is an opportunity to move from isolated activity to a connected pipeline spanning research, evaluation, adoption and scale, supported by better access to skills, funding,

infrastructure and industry engagement. A cross-partner programme is being explored, which would develop a clear regional proposition and delivery model, with defined leadership and a prospectus to attract investment and support long-term economic growth and improved health outcomes. Further updates will be provided as the work progresses.

Assure3 (to note)/ Sicrhau (i nodi)

- Regional Research and Innovation Director: Dr Leighton Phillips successfully appointed as the Regional Research and Innovation Director, taking up post on 21st September 2026, for an initial period of 12 months.

During this time a review of both organisations’ structures will be undertaken to develop a strategy and approach to working more regionally. Initials findings will be shared with the workstream towards the end of calendar year.

- A strategic discussion was held between the Chief Executives and Chairs of the two Health Boards and the Vice-Chancellors of the region's three universities to explore how NHS and University Partnership could be used to create a stronger regional health economy and healthier communities. There was strong support for a renewed partnership, with a clear emphasis on moving beyond previous arrangements towards a more purposeful, delivery-focused approach. Universities highlighted the strengths they could bring to shared regional priorities, particularly around developing a healthy, skilled and resilient workforce, recognising that learning is a lifelong endeavour, and the opportunity to influence educational commissioning and workforce development collectively. Cardiovascular disease emerged as a potential unifying challenge around which partners could align their research, education, clinical, public health and innovation capabilities. It was recognised that improving heart health requires coordinated action on the wider determinants of health. All partners identified significant opportunities to align

3 There is confidence that actions are robust and will be sufficient to address the issue or generally operating effectively. Routine monitoring.

Page 2 of 3

with the wider regional economic development arrangements, recognising the combined influence of health boards, universities and regional partners in supporting both health improvement and inclusive economic growth. It was agreed that a framework for ongoing partnership would be developed and brought back for further discussion early in the new calendar year, supporting the RJC's ambition to improve population outcomes through stronger regional collaboration and collective leadership.

- This year’s regional research and innovation symposium will take place on 19th November 2026 at Pentre Awel. The morning session will focus on showcase presentations from research active staff, highlighting work across the local, regional and innovation spheres, while the afternoon will be focussed either on workshops or panel-based discussions.

Review of Risks/ Adolygiad o Risgiau

- There are currently no significant risks to raise.

Sharing of learning/ Rhannu dysgu

- The regional Research and Innovation symposium in November 2026 is an opportunity to share learning across the two health boards.

- Several of the examples provided within the paper demonstrate regional working having an impact on research and innovation and the benefits associated with the same.

Recommendation/ Argymhelliad

Members are asked to:

- BE ASSURED BY the positive response approved bid for funding for the regional oncology trial task and finish group’s report and recommendations and the ongoing work for a funding bid; and ongoing work to sustain a CVD innovation model that has proven impact on health outcomes and addresses a pressing issue across the region.

- BE ASSURED BY the recruitment of the Regional Director of Research and Innovation post.

- BE ASSURED BY the growing programme of regional research and innovation work.

- ACKNOWLEDGE the commencement of work to support life sciences in the region and the co-ordinated involvement of both organisations in several wider regional symposia and partnership development opportunities.

- ACKNOWLEDGE the commencement of work to support a regional approach to NHS and University Partnership.

Date of next meeting/ Dyddiad y cyfarfod nesaf: 8th October 2026

Page 3 of 3

- Subgroup Summary

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

RJC Subgroup Work Programme Summary

For use by Regional Programmes, Projects, Initiatives and Other Activities

| Reporting Period | September 2026 |
| --- | --- |
| Subgroup Name | Regional Research, Innovation and Excellence |
| Subgroup Lead(s) | Mr Mark Henwood and Dr Raj Krishnan (Interim), Executive Medical Directors |
| Operational Lead(s) | Liz Wonnacott, Head of Service – Medical Director |
| Clinical Lead(s) | - |
| Programme Lead | Dr Leighton Phillips, Regional Research and Innovation Director |
| Reports To | Regional Research, Innovation and Excellence Oversight Group |
| Receives Reports From | Regional oncology task and finish group |
| Meeting Frequency | Bi-monthly |
| ToR Agreed | Yes |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

- Subgroup Scope

Subgroup Scope

To scope and implement a regional approach to research, innovation and excellence.

- Ambition Statement(s)

Ambition Statement(s)

To create the South-West Wales Regional Research and Innovation Partnership

- Objective / Output Statements

| Objective / Output | Target Date | RAG |
| --- | --- | --- |
| Strategy for implementing a regional approach to research and innovation | 1st September 2027 |  |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

| Objective / Output | Target Date | RAG |
| --- | --- | --- |

- Milestones & Deliverables

| RJC Subgroup Objective | Milestone / Deliverable | Target Date | This Period (RAG) | Comments / Notes |
| --- | --- | --- | --- | --- |
| Appointment of Regional Director | Completed recruitment process | 31st July 2026 |  | Completed |
| Review of current structures | 100-day review findings | 31st January 2027 |  |  |
| Strategy for regional working | Presentation to oversight group including recommendations | 31st August 2027 |  |  |

- Resource / Funding Considerations

| Resource / Funding Requirement | Current Position | Impact / Mitigation |
| --- | --- | --- |
| Director Post | Recruited | 12-month secondment funded through commercial income. Longer-term arrangements to be agreed as project progresses. |
| Project management support | Not currently in place | Would require commercial income to fund to avoid increasing the run rate of either organisation. |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

- Risks

| Ref | Risk Description | Mitigation | Action Owner | RAG | Risk Owner | Residual Risk |
| --- | --- | --- | --- | --- | --- | --- |
|  | No risks to highlight |  |  |  |  |  |

- Dependencies

| Description | How Dependency is Managed | Action Owner | RAG | Dependency Owner |
| --- | --- | --- | --- | --- |
| No dependencies to highlight |  |  |  |  |

- Issues

| Ref | Issue Description | Impact | Action Owner | Target Resolution Date | Status |
| --- | --- | --- | --- | --- | --- |
|  | No issues to highlight |  |  |  |  |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

| Ref | Issue Description | Impact | Action Owner | Target Resolution Date | Status |
| --- | --- | --- | --- | --- | --- |

RAG Definitions and Scoring Guidance

Delivery RAG Definitions

| RAG | Definition |
| --- | --- |
| Black | Activity has yet to commence. |
| Red | Objective/output/milestone will not be delivered within agreed timeline. Immediate corrective action required or formal change action initiated. Report as Advise or Alert. |
| Amber | Forecasting that there is a significant risk that objective/output/milestone will not be delivered. Mitigating action is being taken. |
| Green | Objective/output/milestone forecast to be on time or early. |
| Blue | Task complete. |

Risk RAG Definitions

| RAG | Definition |
| --- | --- |
| Red | High likelihood and/or high impact risk requiring active management. |
| Amber | Moderate risk requiring monitoring and mitigation. |
| Green | Low risk with routine monitoring. |

Risk Scoring Matrix

| Likelihood / Impact | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| Almost Certain (5) | 5 | 10 | 15 | 20 | 25 |
| Likely (4) | 4 | 8 | 12 | 16 | 20 |
| Possible (3) | 3 | 6 | 9 | 12 | 15 |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

| Unlikely (2) | 2 | 4 | 6 | 8 | 10 |
| --- | --- | --- | --- | --- | --- |
| Rare (1) | 1 | 2 | 3 | 4 | 5 |

Regional Joint Committee | Cyd-bwyllgor Rhanbarthol

#### 5.1	11:35 AM, 0 Mins

5.1 - RJC/37c: Outline Programme		Leighton Phillips (Hywel Dda UHB -

Interim Regional Director for Research

and Innovation (South West Wales))

Attachments

RJC 39c Research, Innovation and Excellence Subgroup Outline Programme.pdf

JOINT HYWEL DDA/SWANSEA BAY UNIVERSITY HEALTH BOARD COMMITTEE CYD-BWRDD IECHYD PRIFYSGOL HYWEL DDA/BAE ABERTAWE PWYLLGOR

| DYDDIAD Y CYFARFOD: DATE OF MEETING: | 13 October 2026 |
| --- | --- |
| TEITL YR ADRODDIAD: TITLE OF REPORT: | Developing a Regional Approach to Research and Innovation |
| CYFARWYDDWR ARWEINIOL: LEAD DIRECTORS: | Executive Medical Directors, Hywel Dda and Swansea Bay University Health Boards |
| SWYDDOG ADRODD: REPORTING OFFICER: | Director for Research and Innovation (South West Wales) |

Pwrpas yr Adroddiad (dewiswch fel yn addas) Purpose of the Report (select as appropriate)

Er Sicrwydd/For Assurance

ADRODDIAD SCAA SBAR REPORT

Sefyllfa / Situation This paper presents a formative work plan for the Research, Innovation and Excellence workstream and describes several practical steps towards a more coherent regional approach to research and innovation. The programme and proposed activities are intended to strengthen collaboration across the NHS and with academic, industry and wider regional partners, ensuring that research and innovation make a meaningful contribution to improving the health and wellbeing of the population of South West Wales. The Regional Joint Committee is asked to take assurance from the emerging programme.

Cefndir / Background The Regional Joint Committee’s Research, Innovation and Excellence work stream strongly aligns to growing national interest, championed by the Chief Medical Officer, in strengthening Wales' research and innovation ecosystem, with increasing emphasis on research participation, innovation adoption, data-driven improvement and collaboration across health, academia and industry. Over the past year, an emerging programme of regional activity has been overseen by the Executive Medical Directors and Research and Development leaders from both organisations, with progress and achievements reported through the associated 3As report, including tangible activities to improve access to cancer research studies and work to understand and respond to cardiovascular disease risk factors. The recent appointment of an Interim Director for Research and Innovation (South West Wales), who started on 21 September, provides an opportunity to move from a series of individual initiatives towards a more coherent regional programme. The Assessment section provides an outline work programme that will be refined over the coming months to support the Committee's ambitions for regional collaboration in research, innovation, life sciences and wider partnership development.

Page 1 of 5

Asesiad / Assessment The programme scope includes research and development activity (including commercial), innovation adoption, university partnerships, and wider opportunities to contribute to regional economic development through life sciences. The objectives set out below are intended to establish an evidence base for future decision-making, strengthen regional partnerships, explore opportunities for greater collaboration and demonstrate the benefits of regional working through practical delivery. They are formative and, as such, will benefit from further refinement over the coming weeks. - Develop the Foundations for Regional Research and Innovation Collaboration A comprehensive assessment of research, innovation and university partnership arrangements within Swansea Bay and Hywel Dda University Health Boards will be undertaken to identify opportunities to strengthen collaboration, increase impact, improve organisational resilience and inform future regional decision-making. This will include: - Reviewing how research, innovation and university partnership functions are organised and managed in both health boards. As part of this process, R&D and Innovation teams will be offered opportunities to visit and observe arrangements within neighbouring organisations, supporting relationship development and the transfer of learning and good practice. - Working with internal and external stakeholders to understand strengths, challenges, opportunities and priorities. - Assessing the current governance, leadership, financial, workforce, infrastructure, performance, partnerships and delivery arrangements. - Identifying opportunities to strengthen alignment between the Research, Innovation and Excellence work programme and other Regional Joint Committee priorities, particularly Regional Health Economy and Service Change programmes, such as the Regional Cellular Pathology Centre of Excellence and potential for on-site and aligned pathology research activity. - Seeking expert input and advice to provide constructive challenge, independent perspective and insight from relevant experience elsewhere. This may include a peer review or other forms of external expert support. The outputs will include a concise assessment report setting out key findings and recommendations, shared learning across participating organisations and stakeholders, and a robust evidence base to inform the development of a future regional model for research, innovation and excellence. Target: January 2027 - Develop a Preferred Future Regional Model There are a range of potential options for regional working across research, innovation and excellence, spanning from greater alignment of activity around services that increasingly operate on a regional basis, through to deeper integration of leadership and delivery functions. Building on the findings from the assessment phase, structured work will be undertaken to evaluate these options and identify the arrangements most likely to strengthen

Page 2 of 5

collaboration, increase impact, improve resilience and support the long-term ambitions of the region. This will include: - Assessing relevant national and international examples of integrated research and innovation systems, identifying the lessons most applicable to South West Wales. This will explore: - Regional innovation ecosystems such as the Capital of Life model in Denmark, Academic Health Science Systems and place-based health innovation partnerships that successfully align healthcare, universities, industry, research infrastructure and economic development partners behind shared objectives. - The lessons from recent national and international reviews into research and innovation, including how health systems have responded to recommendations arising from the O'Shaughnessy Review and other initiatives aimed at improving clinical trial delivery, innovation adoption, industry engagement and research sustainability. - Identifying and evaluating, through cost-benefit analysis or equivalent, a range of potential models for regional leadership, governance, delivery and support arrangements. - Working closely with stakeholders to assess how these different models could support regional priorities, including service transformation, workforce development, research performance, innovation adoption and economic growth. - Developing recommendations and arriving at a preferred model for consideration by the Regional Joint Committee. The ultimate output will be a concise options appraisal describing potential approaches, the lessons derived from national and international exemplars, stakeholder feedback and insights, together with a proposed implementation roadmap to inform a decision about the way forward. Target: March 2027 3) Strengthen University and Health Board Partnerships A recent discussion involving both health boards and the region's three universities identified a strong appetite for a renewed partnership, with an emphasis on moving beyond historical arrangements towards a more purposeful, delivery-focused approach centred on shared regional priorities. This will seek to leverage remarkable diversity and opportunity apparent in south west Wales. From vibrant urban centres and university communities to rural heartlands and coastal towns, the region brings together populations with different needs, experiences and strengths. It is home to areas of innovation and growth, alongside communities facing significant health inequalities and challenges in accessing services. This diversity is one of the region's greatest assets, creating a unique environment in which universities, health systems, industry and communities can work together to improve lives, reduce inequalities and generate sustainable economic growth through research, innovation and life sciences. Work will be undertaken to develop a regional university partnership framework that supports the ambitions of South West Wales across research and development, education and learning, and enterprise and innovation. The development process will include:

Page 3 of 5

- Bilateral discussions with the Vice Chancellors of each institution and their teams to identify shared priorities for future collaboration. As part of this process, each partner's capabilities, priorities and strategic ambitions across research and development, education and learning, and enterprise and innovation will be explored to identify opportunities for greater alignment and collective impact. - Identifying one or two areas where bringing together three universities and two health boards is likely to deliver greater benefit than could be achieved by any organisation working in isolation. Whilst the starting point may be a shared health challenge, such as improving cancer outcomes or cardiovascular health, the intention will be to develop whole-system approaches spanning research. education, innovation, workforce development and wider societal outcomes. - Identifying opportunities to strengthen alignment between university partnerships, regional economic development priorities and the wider ambitions of the Regional Joint Committee. The outputs will include a regional university partnership framework setting out shared priorities, partnership principles and governance arrangements, together with an agreed programme of collaborative activity across research and development, education and learning, and enterprise and innovation. Target: January 2027 (outline for discussion) 4) Explore Opportunities for Life Sciences and Economic Development Recent discussions have identified an opportunity to consider how a regional approach to research and innovation could support the wider ambition of making South West Wales a place where the life sciences sector flourishes, contributing to improved health outcomes, investment, skills development and economic growth. While the primary purpose of the programme is to improve research and innovation outcomes, there is increasing recognition that high-performing research and innovation healthcare systems can also make a significant contribution to economic growth, inward investment and workforce development. The region already has a good reputation and strong industry networks through initiatives including the Joint Clinical Research Facility and the TriTech Institute. Discussions are underway with officers supporting the South West Wales Corporate Joint Committee to explore how the region's research, innovation and health assets could form part of a more coherent regional proposition, helping to strengthen investment attraction, support innovation adoption, promote commercial research and reinforce South West Wales' contribution to the life sciences sector. Consideration will also be given to how health, research, innovation and economic development priorities can be better aligned to maximise regional impact. This work will include discussions with industry partners in the region. The outputs will include an assessment of opportunities for regional collaboration and recommendations to inform future discussions with regional partners regarding the contribution that research, innovation and life sciences could make to the future economic development of South West Wales. Target: November 2026 (regional commitment)

Page 4 of 5

5) Demonstrate the Value of Regional Working Alongside the development of medium to longer-term regional arrangements, a small number of existing regional priorities will be used to demonstrate the practical benefits of collaboration across organisational boundaries. Initial focus will be placed on improving access to cancer research studies across South West Wales and supporting the continued development and spread of a regional cardiovascular disease innovation programme, both of which have already demonstrated the value of cross-organisational working and align with wider regional priorities. Importantly, both programmes have existing investment, established governance arrangements and clearly defined deliverables, providing an opportunity to demonstrate early progress and tangible benefits from regional working. Work will be undertaken to support delivery, remove barriers to collaboration and maximise the impact of both programmes on patient outcomes, research participation, innovation adoption and service improvement. The outputs will include demonstrable progress in regional cancer research and cardiovascular innovation, together with practical learning regarding the opportunities, challenges and benefits associated with regional working. Separate work programmes with associated timelines are available. Detailed work will now be undertaken to develop more granular actions for these areas. In respect of bullet points 3-5, the 3As report illustrates the practical activities already being undertaken. Taken together, this formative programme aims to take practical steps towards a more regional approach to research, innovation and excellence across South West Wales. Through coordinated activity involving the NHS, universities, industry and wider regional partners, it will seek to strengthen collaboration, accelerate the adoption of innovation, increase research opportunities and support sustainable economic growth, with the ultimate goal of improving health and wellbeing across the region.

Argymhelliad / Recommendation The Regional Joint Committee are asked to take assurance from this report this report.

Page 5 of 5

6

11:35 AM, 10 Mins

## - RJC/40: Workforce and OD Subgroup Update

Lisa Gostling (Hywel Dda UHB - Director of Workforce & OD/Deputy CEO)

Attachments

RJC 40a Workforce and OD Subgroup (AAA) Update Report.pdf

#### WORKFORCE & OD UPDATE REPORT/ ADRODDIAD DIWEDDARU’R PWYLLGOR

Regional Joint Committee Date of last meeting/ Dyddiad y cyfarfod diwethaf: Quoracy/ Cworwm: Met

Report by/ Adroddiad gan: Lisa Gostling, Executive Lead

KEY DISCUSSION POINTS AND MATTERS FROM THE DISCUSSION AT THE MEETING/ PWYNTIAU TRAFOD ALLWEDDOL A MATERION I’W

HUWCHGYFEIRIO O’R DRAFODAETH YN Y CYFARFOD:

Alert1 (may require discussion. e.g. include significant risks, issues, decisions required, change requests for timescales, scope or milestones within subgroup work programmes and matters requiring escalation.)/ Rhybuddio (efallai y bydd angen trafodaeth)

Advise2 (to monitor)/ Cynghori (i fonitro)

The Workforce & OD RJC Sub-Group/Work Programme have no issues to advise

members of the RJC to.

- work is progressing with regards to staff wellbeing with a collaboration framework agreed. Work progresses but not at the pace expected due to capacity issues in both teams to drive further work. This will be reviewed at the next meeting.

Assure3 (to note)/ Sicrhau (i nodi)

The Workforce & OD RJC Sub-Group/Work Programme wish to assure members of the RJC that a draft protocol for approval and oversight of regional posts has been drafted and the team will be refining over coming weeks with a view to adoption for any new roles to be introduced.

1 There is a lack of confidence that any action in place is sufficient to address the issue satisfactorily and/or within the scope of the operational team or executive to resolve. Engagement, action or intervention required. 2 There are areas of concern where assurance has been taken on actions in place but requires close monitoring. An early warning of an emerging and potentially serious concern.

3 There is confidence that actions are robust and will be sufficient to address the issue or generally operating effectively. Routine monitoring.

Page 1 of 2

Work continues on the workforce planning workstream and a draft outline will be discussed in the next joint meeting.

The teams will also be looking at benchmarking workforce and OD functions across NHS Wales organisations.

Review of Risks/ Adolygiad o Risgiau

Risk to delivery is linked to capacity for all members of the WOD teams.

Sharing of learning/ Rhannu dysgu

nil

Recommendation/ Argymhelliad

nil

Date of next meeting/ Dyddiad y cyfarfod nesaf: 27th October 2026

Page 2 of 2

7

11:45 AM, 0 Mins

## - Governance

#### 7.1	11:45 AM, 5 Mins

## 7.1 - RJC/41: Annual Review of Terms of Reference

Hazel Lloyd (Swansea Bay UHB -

Corporate Governance), Joanne Wilson (Hywel Dda UHB - Director of

Corporate Governance/Board

Secretary)

-RJC

-RJC Subgroups

Attachments

RJC 41a Draft RJC ToR.pdf

RJC 41b Regional Clinical Services Planning Subgroup ToR.pdf

RJC 41c Draft Research, Innovation and Excellence Subgroup ToR.pdf RJC 41d Draft RFCDDG Group ToR v0.4.pdf

RJC 41e Draft Regional Worforce and OD Subgroup ToR.pdf RJC 41f Regional Health Economy Subgroup ToR.pdf

Regional Joint Committee of Swansea Bay and Hywel Dda University Health Boards

Hywel Dda University Health Board

Swansea Bay University Health Board

REGIONAL JOINT COMMITTEE OF

SWANSEA BAY AND HYWEL DDA UNIVERSITY HEALTH BOARDS

TERMS OF REFERENCE

| Version | Issued To | Date | Comments |
| --- | --- | --- | --- |
| V1.0 | Inaugural meeting of the Regional Joint Committee of Swansea Bay and Hywel Dda University Health Boards | 15/01/2025 | For Comment |
| V.1 | The Boards of Swansea Bay and Hywel Dda University Health Boards | 30/01/2025 | Approved |
| V.2 | The Boards of Swansea Bay and Hywel Dda University Health Boards | 29/05/2025 | Approved |
| V.3 | Regional Joint Committee of Swansea Bay and Hywel Dda University Health Boards | 16/04/2025 | For Comment |
| V.4 | Co-Chairs, Regional Joint Committee of Swansea Bay and Hywel Dda University Health Boards | 05/05/2026 | For Agreement via Chairs Action |
| V.5 | The Boards of Swansea Bay and Hywel Dda University Health Boards | 28/05/2026 | Approved |
| V.6 | Regional Joint Committee of Swansea Bay and Hywel Dda University Health Boards | 13/10/2026 | For Review |
| V.6 | The Boards of Swansea Bay and Hywel Dda University Health Boards | 26/10/2026 | For Approval |

1

1. Constitution

REGIONAL JOINT COMMITTEE OF

SWANSEA BAY AND HYWEL DDA UNIVERSITY HEALTH BOARDS

The Regional Joint Committee (RJC) has been established under Ministerial Direction as a Joint Committee of Swansea Bay and Hywel Dda University Health Boards and constituted from 15 January 2025.

  - The RJC is therefore accountable to the Cabinet Minister for delivering the remit of the Committee.

2. Purpose

  - The RJC has been established to:

    - Provide joint leadership for the regional planning, commissioning, and delivery of services for Swansea Bay University Health Board and Hywel Dda University Health Board taking into account the service challenges, financial challenges and population health needs of both organisations and the work previously undertaken through ARCH.

    - Establish a regional approach to the development of clinical services planning, aligned to regional population health needs assessments, to develop and deliver sustainable services in terms of achieving quality and outcome measures, workforce and financial sustainability.

    - Prioritise in-year efficiencies and identify priorities for the Integrated Medium Term Plans (IMTPs) for both organisations, where a regional approach will deliver benefit in the short term.

    - Explore how the benefits of a regional health economy are harnessed to best serve a population of over 800,000.

      - In the short term focus on intensifying baseline work, supporting the in-year financial position of both Boards, impacting also on cost effectiveness, and waiting list management.

      - In the medium term expand on the short-term gains in the IMTP process, developing the West Wales regional health economy concept, using a ‘discovery’ approach through use of a broader data set and benchmarking against other UK/International models and becoming a designated WHO Sub regional health network.

      - Within the next three two years, have an integrated approach to services across the regional health economy, with an embedded population health and needs assessment that centres on health improvement and health inequities reduction. Both Boards, organisations, populations, and partners would be signed up to a Regional Health Economy long term strategy.

3. Objectives

The following objectives are within the scope of the RJC:

2

  - Core Objectives

    - Develop plans that are aligned to Health Board plans to ensure the benefits of a regional health economy for a population of circa 800,000 are realised.

    - Bring together in one place all the projects, which will deliver significant in-year progress and pace in delivery in the health and care system for the region.

    - Drive forward a range of projects that have been identified by partner organisations as priorities for joint working at pace to deliver Ministerial Priorities as part of a suite of integrated RJC subgroup programmes that deliver against the strategic aims and objectives agreed by the RJC and ratified by both sovereign Boards.

    - Oversee system-wide and strategic matters (including assurance beyond any individual RJC subgroups and programmes), consistent with the Ministerial Direction issued and the expectations of a Regional Joint Committee.

    - Seek assurance that all the RJC subgroups and programmes are aligned with respective University Health Board strategic priorities, clinical service plans, the strategic direction of Welsh Government and other partners (Powys Teaching Health Board, other University Health Boards, Mid Wales Joint Committee, remaining cognisant of, and responding to the changing requirements within the wider environment of the Health Service in Wales.

    - Maximise the use of digital technology and data to transform the delivery services and improve patient experience.

    - Seek assurance that all RJC subgroup programmes are aligned with the RJC programme of work, endorsing Business Cases pre–Sovereign Bodies approval, and identifying and agreeing any further projects to be included in the RJC programme.

    - Seek assurance that RJC subgroups deliver against their outcomes and timescales, and deliver against the quality measures and benefits, as identified in the RJC subgroups portfolios and plans.

    - Manage high-level interdependencies and risks associated with all the RJC subgroups and projects and consider in the context of the wider strategic regional plan, ensuring consistency, compatibility, and co-ordination between RJC subgroups and programmes of work.

    - Progress RJC subgroup work programmes within the remit of the RJC without unnecessary recourse elsewhere to ensure pace.

    - Seek assurance integrated impact assessments are undertaken of all planned service change and embedded in the ways of working.

    - Seek assurance that all subgroups’ plans and resources are prioritised and coordinated to deliver the Clinical Services Planning subgroup’s clinical transformation programmes and improved outcomes for patients to ensure the RJC’s delivery is aligned with expectations set by Senedd Ministers, Welsh Government officials, and the Health Boards’ Annual Plans.

3

  - Regional Health Economy

    - Seek assurance that a long‑term Regional Health Economy Strategic Plan is produced that provides a shared regional direction and enables coordinated, equitable system change.

    - Seek assurance that a shared regional health profile is established which identifies the key drivers of health inequality and future healthcare demand across the region and is routinely used to inform regional planning.

    - Oversee the required preparatory work enabling the regional health economy to become a designated WHO sub regional health network so that the RJC can benefit from the shared learning opportunities afforded by participation in the network.

  - Clinical Services Planning

    - Seek assurance that regional clinical service programmes and models are developed and delivered, which improve resilience, equity of access and outcomes across South West Wales.

    - Seek assurance that processes and governance are in place where SBUHB and HDdUHB work in partnership to commission and deliver a wide range of services-contracting arrangements via the Long Terms Agreements (LTAs) or Service Level Agreements (SLAs) on a regional basis, including work commissioned by the Joint Commissioning Committee and to explore opportunities for joint commissioning from other providers.

    - Seek assurance that a consistent, intelligence‑led approach to regional clinical service planning and investment decisions is in place.

    - Seek assurance that the Health Boards Clinical Services Strategic Plans are aligned

in line with Ministerial Priorities in delivering ‘A Healthier Wales’.

    - Seek assurance that regional Cellular Pathology and SWW Cancer capital planning programmes are delivered to plan and cost, aligned with and deliver regional priorities, efficiency gains, and positively impact on patient services and outcomes.

  - Research, Innovation and Excellence

    - Drive research, innovation, excellence, and training opportunities across the regional health economy through working with all Universities within the region and consider partnership with other Universities, outside of the region, where there is benefit to our population.

    - Develop a joint research development and innovation strategic plan and bring together joint capability and capacity to deliver the plan. This should include an equitable approach to trials access across the region and enhanced industry links to benefit research and innovation.

  - Workforce & OD

    - Develop a joint 3-5 year workforce plan for the region utilising the Health Education and Improvement Wales (HEIW) framework to stabilise fragile services where

4

possible and to ensure the workforce is developed and recruited for our services of the future considering new and changes roles which includes enhanced digital skills.

    - Develop a regional leadership network to support leaders to plan and develop future services in collaboration and ensure future programmes embrace the soon to be launched Management and Leadership Competency framework.

    - Scope opportunities for joint working across Workforce & OD teams to maximise contribution creating greater efficiency and consistency of approach.

  - Finance, Contracting, Data and Digital

    - Seek assurance that a regional financial framework is in place enabling transparent reporting of the utilisation and allocation of resources within and between the two Boards, with explicit treatment of risk-share, cross-boundary activity, capital, and potential sharing of services.

    - Oversee the development and operation of joint commissioning arrangements, including the Long Term Agreements and Service Level Agreements governing cross-boundary services, so that contracting reflects regional priorities and the work of the Joint Commissioning Committee.

    - Seek assurance that opportunities for value and efficiency across the regional health economy are systematically identified and tracked, with delivery aligned to the IMTPs of both Boards.

    - Develop coordinated financial planning and reporting across the RJC subgroups that supports both organisations’ statutory financial duties and informs Welsh Government engagement on regional investment.

    - Seek assurance that digital solutions enable service transformation and systematically remove sources of friction in how staff and patients interact with services, including reliance on manual and paper-based processes.

    - Develop a regional approach to data sharing and interoperability, ensuring information flows between the two Boards and with wider partners are appropriately governed and aligned to all-Wales architecture and standards.

    - Oversee joint digital infrastructure and procurement decisions, reducing duplication and supporting consolidation onto common platforms where this serves regional priorities.

    - Seek assurance that AI, automation, and advanced analytics capability is developed across the region with appropriate governance, evaluation, and a clear line of sight to clinical and operational benefit.

4.  Engagement

  - The RJC will take a ‘people first' approach – putting patients, our communities and our Health Boards’ colleagues at the centre of our work.

5

  - The RJC will, in respect of the joint projects, initiatives or developments, consider the patient, public and stakeholder engagement requirements, and provide assurance and advice to the respective Health Boards on engagement and communication activities.

  - Promote patient and public engagement in the review and redesign of NHS services ensuring that the RJC can evidence where patient experience has influenced change.

  - The RJC will ensure team colleagues are fully engaged, and our clinical service redesign work is clinically led, with a multi-disciplinary approach, based on co-production and organisational development principles.

  - Promote understanding of the aims, objectives, and deliverables of the RJC programme.

  - Ensure continued engagement with Llais in both partner organisations.

  - Develop a communications plan ensuring stakeholder updates are provided after each RJC meeting.

5. Governance

  - The RJC will operate in accordance with the design principles (agreed set of rules defining purpose through intention and behaviour) which have been agreed by both Boards in November 2024. The benefits of using design principles are as follows:

    - They will embed our values in our behaviours and actions;

    - They will provide a compass point when conflict or disagreement occurs;

    - They will ensure we are consistent in what we say and do; and

    - They are universally understood and accepted.

The design principles agreed by both Boards are:

| Mindset | Trusting each other to do the right thing and to act with courage and conviction. |
| --- | --- |
| Process | Driven by data and evidence and embracing opportunities to re- imagine, redesign and innovate Sustainability of the architecture |
| Outcome | Building sustainable and future proofed services that have the greatest impact and are in the best interests of all communities and patients |

  - Ensure an effective governance framework is in place to govern the work of the RJC, which facilitates and enables the ambitions and design principles set out by the RJC.

  - Pro-actively manage the appropriate risks identified within the RJC programme, being accountable to the respective University Health Boards.

  - Develop a work programme that underpins the work of the RJC.

  - The RJC Chairs will maintain a formal reporting link to Welsh Government, to include the submission of assurance products to the Cabinet Secretary e.g. the Committee’s annual self assessment as part of the RJC’s continuous improvement, governance and assurance responsibilities, including its role in evidencing maturity and effectiveness.

6

  - The RJC Chairs will also provide assurance and feedback on regional matters to the Cabinet Minister as part of their annual appraisals and regular meetings with the Cabinet Minister.

6.  Membership

  - To ensure the RJC undertakes its role effectively, its members are asked to:

    - Attend quarterly meetings.

    - Adopt an open and constructively challenging approach within meetings.

    - Promptly follow up on actions and commitments; and

    - Participate in electronic and virtual channels established to allow a continuous flow of information between committee members.

  - Membership of the RJC shall comprise:

| Member | Organisation |
| --- | --- |
| Chair (RJC Joint Chair) | Swansea Bay University Health Board |
| Chair (RJC Joint Chair) | Hywel Dda University Health Board |
| Independent Member (Finance) | Swansea Bay University Health Board |
| Independent Member (Quality University) | Hywel Dda University Health Board |
| Independent Member (Governance) | Swansea Bay University Health Board |
| Independent Member (Planning Digital) | Hywel Dda University Health Board |
| Independent Member (Digital) | Swansea Bay University Health Board |
| Independent Member (Community) | Hywel Dda University Health Board |
| In Attendance |  |
| Vice Chair | Swansea Bay University Health Board |
| Vice Chair | Hywel Dda University Health Board |
| Chief Executive Officer | Swansea Bay University Health Board |
| Chief Executive Officer | Hywel Dda University Health Board |
| Chief Operating Officer | Swansea Bay University Health Board |
| Chief Operating Officer | Hywel Dda University Health Board |
| Executive Director of Strategy and Planning | Swansea Bay University Health Board |
| Executive Director of Strategy and Planning | Hywel Dda University Health Board |
| Executive Director of Finance | Swansea Bay University Health Board |
| Executive Director of Finance | Hywel Dda University Health Board |
| Executive Director of Workforce and OD | Swansea Bay University Health Board |
| Executive Director of Workforce and OD | Hywel Dda University Health Board |
| Executive Medical Director | Swansea Bay University Health Board |
| Executive Medical Director | Hywel Dda University Health Board |
| Director of Public Health | Swansea Bay University Health Board |
| Director of Public Health | Hywel Dda University Health Board |
| Governance Advice |  |
| Director of Corporate Governance | Swansea Bay University Health Board or Hywel Dda University Health Board |
| Associate Member |  |
| Chair | Powys THB |
| Observer Members |  |
| Director of Operations | Welsh Government’s Health, Social Care, and Early Years Executive Directors Team |

7

| Director of Planning | Welsh Government’s Health, Social Care, and Early Years Executive Directors Team |
| --- | --- |
| Invitation to attend to discuss work programme areas requiring wider collaboration (as and when required) |  |
| As and when required |  |

  - The RJC will be jointly chaired by the Chairs from Swansea Bay and Hywel Dda University Health Boards.

  - Membership of the RJC will be reviewed on an annual basis.

  - The RJC will be supported by a dedicated Programme Management Office (PMO).

7. Quorum and Attendance

  - A quorum shall consist of a Chair and Independent Member from both partner organisations plus a third of the in-attendance membership.

  - The membership of the RJC shall be determined by each partner organisation, considering the balance of skills and expertise necessary to deliver the Joint Committee’s remit, and subject to any specific requirements or directions made by Welsh Government.

  - Any senior officer of the UHBs or partner organisation may, where appropriate, be invited to attend, for either all or part of a meeting to assist with discussions on a particular matter.

  - The RJC may also co-opt additional independent external “experts” from outside the

organisation to contribute to specialised areas of discussion.

  - Should any member be unavailable to attend, they may nominate a deputy to attend in their place, subject to the agreement of both Co-Chairs.

  - The RJC may ask any or all of those who normally attend but who are not members to withdraw to facilitate open and frank discussion of particular matters.

8.  Agenda and Papers

  - The Committee Secretary is to hold an agenda setting meeting with the Chair at least six weeks before the meeting date.

  - The agenda will be based around the RJC’s work plan, identified risks, matters arising from previous meetings, issues emerging throughout the year, and requests from members.

  - All papers must be approved by the Lead/ relevant Director.

  - The agenda and papers for meetings will be distributed seven days in advance of the meeting.

  - The minutes and action log will be circulated to members within seven days to check the accuracy, prior to sending to Members (including the RJC Chair) to review within the next seven days.

8

  - Members must forward amendments to the Committee Secretary within the next seven days. The Committee Secretary will then forward the final version to the RJC Chair for approval.

9. In Committee

9.1	The RJC can operate with an In Committee function to receive updates on the management of sensitive and/or confidential information.

10. Frequency of Meetings

  - The RJC will meet quarterly and shall agree an annual schedule of meetings. Any additional meetings will be arranged as determined by the Chair of the RJC.

  - The Chair of the RJC, in discussion with the Committee Secretary, shall determine the time and the place of meetings of the RJC and procedures of such meetings.

11. Accountability, Responsibility and Authority

  - Although, as set out within these terms of reference, each University Health Board has delegated authority to the RJC for the exercise of certain functions, it retains overall responsibility and accountability for ensuring the quality and safety of healthcare for its citizens, through the effective governance of the organisation.

  - The RJC is directly accountable to the respective University Health Board’s for its performance in exercising the functions set out in these terms of reference.

  - The requirements for the conduct of business as set out in each University Health Board’s Standing Orders are equally applicable to the operation of the RJC.

  - The RJC will operate in accordance with the principles approved by both sovereign bodies.

12. Reporting

  - The RJC may establish sub-committees, groups or task and finish groups to carry out on its behalf specific aspects of RJC business. The RJC will receive an update following each group’s meetings detailing the business undertaken on its behalf.

  - The RJC will report through the RJC updates to respective Boards, and for HDdUHB align to the work programme of Committee responsible for planning.

  - Regular joint updates will be provided to respective Llais organisations which will be

based upon the committee’s work programme and meetings.

  - The Directors of Corporate Governance, on behalf of the RJC, shall oversee a process of regular and rigorous self-assessment and evaluation of the RJC’s performance and operation, including that of any sub-committees established.

13. Secretarial Support

13.1	The Committee Secretariat shall be provided by the RJC PMO.

9

14. Review Date

14.1	These terms of reference and operating arrangements shall be reviewed on at least an annual basis by the RJC for approval by the respective University Health Boards.

10

Regional Clinical Services Planning Subgroup

Regional Joint Committee of Swansea Bay and Hywel Dda University Health Boards

Hywel Dda

University Health Board

Swansea Bay

University Health Board

REGIONAL CLINICAL SERVICES PLANNING SUBGROUP

TERMS OF REFERENCE

| Version | Issued To | Date | Comments |
| --- | --- | --- | --- |
| V1.0 | Regional Clinical Services Planning Subgroup | 20/05/2025 | Agreed by Regional Clinical Services Planning Subgroup |
| V.2 | Regional Clinical Services Planning Subgroup | 04/08/2026 | Updated to align with revised RJC Terms of Reference and Clinical Services Planning Objectives |
| V.2 | Regional Joint Committee | 13/10/2026 | For Approval |

1

1	Constitution

CLINICAL SERVICES PLANNING SUBGROUP

The Regional Joint Committee (RJC) has been established under Ministerial Direction as a Joint Committee of Swansea Bay and Hywel Dda University Health Boards and constituted from 15 January 2025.

  - The Regional Clinical Services Planning Subgroup (RCSPS) has been established as a Subgroup of the RJC, and held its inaugural meeting on 20 May 2025.

2	Purpose

The RCSPS has been established to:

  - Provide joint leadership for the regional planning, commissioning and delivery of clinical services for Swansea Bay University Health Board and Hywel Dda University Health Board, taking into account service challenges, financial challenges and population health needs across both organisations.

  - Establish a regional approach to the development of clinical services planning, aligned to the national approach, regional population health needs assessments, to support sustainable services that achieve quality and outcome measures, workforce sustainability and financial sustainability.

  - Prioritise efficiencies and identify longer-term priorities for both organisations where a regional approach will deliver benefit, including those reflected through annual planning and the 2027-28 planning horizon.

3	Objectives

The following objectives are within the scope of the RCSPS:

  - Develop and maintain regional clinical services plans that are aligned to Health Board plans and support delivery of the benefits of a regional health economy for a population of circa 800,000.

  - Bring together, through the RCSPS work programme, clinical service projects that will deliver significant in-year progress and pace in delivery for the regional health and care system.

  - Drive forward clinical service priorities identified by partner organisations for joint working at pace, ensuring alignment with Ministerial Priorities, the strategic aims agreed by the RJC, and ratification requirements of both sovereign Boards.

  - Manage high-level interdependencies and risks associated with the RCSPS portfolio, ensuring consistency, compatibility and co-ordination with other RJC subgroup programmes and regional plans.

  - Provide assurance that integrated impact assessments are undertaken for planned service change and embedded in the ways of working.

  - Provide assurance that regional clinical service programmes and models are developed and delivered to improve resilience, equity of access and outcomes across South West Wales.

  - Provide assurance that processes and governance are in place for Swansea Bay University Health Board and Hywel Dda University Health Board to work in partnership to commission and deliver services on a regional basis, including through Long Term Agreements, Service

2

Level Agreements, work commissioned by the Joint Commissioning Committee, and exploration of opportunities for joint commissioning from other providers.

  - Provide assurance that a consistent, intelligence-led approach to regional clinical service planning and investment decisions is in place.

  - Provide assurance that the Health Boards’ Clinical Services Strategic Plans are aligned with

Ministerial Priorities and the delivery of A Healthier Wales.

  - Provide assurance that regional Cellular Pathology and South West Wales Cancer capital planning programmes are delivered to plan and cost, aligned with regional priorities, deliver efficiency gains, and positively impact patient services and outcomes.

4	Engagement

  - The RCSPS will take a ‘people first' approach – putting patients, our communities and our

Health Boards’ colleagues at the centre of our work.

  - The RCSPS will, in respect of the joint projects, initiatives or developments, consider the patient, public and stakeholder engagement requirements, and provide assurance and advice to the respective Health Boards on engagement and communication activities.

  - Promote patient and public engagement in the review and redesign of NHS services ensuring that the RCSPS can evidence where patient experience has influenced change.

  - The RCSPS will ensure team colleagues are fully engaged, and our clinical service redesign work is clinically led, with a multi-disciplinary approach, based on co-production and organisational development principles.

5	Governance

  - The RCSPS will operate in accordance with the Regional Joint Committee design principles (agreed set of rules defining purpose through intention and behaviour) which have been agreed by both Boards in November 2024. The benefits of using design principles are as follows:

    - They will embed our values in our behaviours and actions;

    - They will provide a compass point when conflict or disagreement occurs;

    - They will ensure we are consistent in what we say and do; and

    - They are universally understood and accepted.

  - The design principles agreed by both Boards are:

| Mindset | Trusting each other to do the right thing and to act with courage and conviction. |
| --- | --- |
| Process | Driven by data and evidence and embracing opportunities to re-imagine, redesign and innovate Sustainability of the architecture |
| Outcome | Building sustainable and future proofed services that have the greatest impact and are in the best interests of all communities and patients |

  - Ensure an effective governance framework is in place to govern the work of the RCSPS, which facilitates the ambitions and design principles set out by the RJC and provides clear routes for assurance, escalation and decision-making (see Appendix 1 Regional Governance)

3

  - Pro-actively manage the appropriate risks identified within the RCSPS portfolio/programme, escalating strategic risks and interdependencies to the RJC as required and remaining accountable to the respective University Health Boards.

  - Develop and maintain a work programme that underpins the work of the RCSPS and aligns with the RJC programme of work, the Health Boards’ Annual Plans and relevant Ministerial Priorities.

6	Membership

  - To ensure the RCSPS undertakes its role effectively, its members will:

    - Attend meetings.

    - Adopt an open and constructively challenging approach within meetings.

    - Promptly follow up on actions and commitments; and

    - Participate in electronic and virtual channels established to allow a continuous flow of information between committee members.

  - Membership of the RCSPS shall comprise:

| Member | Organisation |
| --- | --- |
| Executive Director of Planning and Partnerships (RCSPS Co-Chair) | Swansea Bay University Health Board |
| Executive Director of Strategy and Planning | Hywel Dda University Health Board |
| Chief Operating Officer (RCSPS Co-Chair) | Swansea Bay University Health Board |
| Chief Operating Officer | Hywel Dda University Health Board |
| In Attendance |  |
| Regional Clinical Services Programme Chairs | NHS Regional Clinical Services |
| Deputy Director Planning and Partnerships | Swansea Bay University Health Board |
| Director of Delivery, Planning, Performance and Commissioning | Hywel Dda University Health Board |
| Executive Director of Allied Health Professions and Health Science | Hywel Dda University Health Board |
| Assistant Director of Operations - Planned Care | Swansea Bay University Health Board |
| Director of Operational Planning & Performance | Hywel Dda University Health Board |
| Service Director for Planned and Specialist Care | Hywel Dda University Health Board |
| Head of Strategy & Service Planning | Regional Programme Team |
| Senior Project Manager/Business Manager | Regional Programme Team |
| Senior Project Support Officer | Regional Programme Team |
| Invitation to attend to discuss work programme areas requiring wider collaboration (as and when required) |  |
| As and when required |  |
| Director of Performance & Business Intelligence | Swansea Bay University Health Board |
| Project Clinical Leads | NHS Regional Clinical Services |
| Project Service Group/Specialty Managers | NHS Regional Clinical Services |
| Assistant Director Strategy, Capital Planning | Swansea Bay University Health Board |
| Head of Capital Planning | Hywel Dda University Health Board |

  - The RCSPS will be chaired by one of the members. Chairing shall rotate between partner organisations on an annual basis unless otherwise agreed.

  - Membership of the RCSPS will be reviewed on an annual basis.

4

  - The RCSPS will be supported by a Committee Secretary.

7	Quorum and Attendance

  - At least 50% of members from Hywel Dda UHB (or deputies) At least 50% of members from Swansea UHB (or deputies)

  - All members should inform the RJC PMO one week in advance of the meeting if deputies will be attending, unless exceptional short-term circumstances arise.

  - Should any member be unavailable to attend, they may nominate a deputy to attend in their place, subject to the agreement of both Co-Chairs.

  - Delegation to deputies is expected to be kept to a minimum and specific approval should be sought from the Co-Chairs for instances where more than two consecutive meetings are expected to involve the nominated deputy.

  - The RCSPS may ask any or all of those who normally attend but who are not members to withdraw to facilitate open and frank discussion of particular matters.

8	Agenda and Papers

  - The RJC PMO is to hold an agenda setting meeting with the Co-Chairs at least two weeks before the meeting date.

  - The agenda will be based around the RCSPS’s work plan, identified risks, matters arising

from previous meetings, issues emerging throughout the year, and requests from members.

  - All papers must be approved by the Lead/ relevant Director.

  - The agenda and papers for meetings will be distributed seven days in advance of the meeting.

  - A draft Table of Actions will be issued within seven days of the meeting. The minutes and action log will be circulated to members within seven days to check the accuracy, prior to sending to Members (including the RCSPS Co-Chairs) to review within the next seven days.

  - Members must forward amendments to the RJC PMO within the next seven days. The RJC PMO will then forward the final version to the RCSPS Co-Chairs for approval.

9	Frequency of Meetings

  - The RCSPS will meet monthly and shall agree an annual schedule of meetings. Any additional meetings will be arranged as determined by the Co-Chairs of the RCSPS.

  - The Co-Chairs of the RCSPS, in discussion with the RJC PMO, shall determine the time and the place of meetings of the RCSPS and procedures of such meetings.

10	Accountability, Responsibility and Authority

  - The RCSPS will be accountable to the RJC for its performance in exercising the functions set out in these terms of reference.

  - The requirements for the conduct of business as set out in each university health board’s

standing orders are equally applicable to the operation of the Subgroup.

5

11	Reporting

  - The Regional Clinical Services Planning Subgroup, supported by the RJC PMO, shall:

    - Report formally, regularly and on a timely basis to the RJC on the RCSPS’s activities, in the

format prescribed by the RJC PMO.

    - Bring to the RJC’s specific attention any significant matters under consideration by the

RCSPS.

    - The Regional Clinical Services Planning Subgroup may establish programmes, projects or task and finish groups to deliver agreed clinical service change. The RCSPS will receive updates from programmes, projects or task and finish groups through highlight reports and exception reporting.

12	Secretarial Support

12.1	The RCSPS Secretariat shall be provided by the RJC PMO.

13	Review Date

13.1	These terms of reference and operating arrangements shall be reviewed on at least an annual basis by the RCSPS for approval by the RJC.

6

Appendix 1 – Regional Governance – South West Wales Regional Joint Committee

7

Regional Research, Innovation and Excellence Subgroup

Regional Joint Committee of Swansea Bay and Hywel Dda University Health Boards

Hywel Dda

University Health Board

Swansea Bay

University Health Board

REGIONAL RESEARCH, INNOVATION AND EXCELLENCE SUBGROUP

TERMS OF REFERENCE

| Version | Issued To | Date | Comments |
| --- | --- | --- | --- |
| V1.0 | Regional Joint Committee | 16/04/2026 | For Discussion |
| V.2 | Executive Medical Director(s) | 15/09/2026 | Updated to align with revised RJC Terms of Reference |
| V.2 | Regional Joint Committee | 13/10/2026 | For Approval |

1

1	Constitution

REGIONAL RESEARCH, INNOVATION AND EXCELLENCE SUBGROUP

The Regional Joint Committee (RJC) has been established under Ministerial Direction as a Joint Committee of Swansea Bay and Hywel Dda University Health Boards and constituted from 15 January 2025.

  - The Regional Research, Innovation and Excellence Subgroup has been established as a Subgroup of the RJC.

2	Purpose

2.1	The purpose of the Regional Research, Innovation and Excellence Subgroup is to drive forward the work needed to establish a regional approach to research, innovation and excellence as part of the Regional Joint Committee workstream.

3	Objectives

The Regional Research, Innovation and Excellence Subgroup will:

  - Develop and oversee the implementation of a regional approach to research and innovation, including providing strategic leadership and developing strategies for approval.

  - Identify specialities to prioritise for regional working and develop focussed plans, monitoring the delivery.

  - Receive progress reports and act as an escalation point for issues.

  - Consider the risks associated with taking a regional approach to research and innovation and the mitigating actions, as well as the risk to not developing a regional way of working, aiming to balance the positions.

  - Maximise the role partners can have in this agenda, including universities, industry and government through, for example, national policy initiatives and events.

4	Engagement

4.1	The Regional Research, Innovation and Excellence Subgroup will take a ‘people first' approach – putting patients, our communities and our Health Boards’ colleagues at the centre of our work.

5	Governance

  - The Regional Research, Innovation and Excellence Subgroup will operate in accordance with the Regional Joint Committee design principles (agreed set of rules defining purpose through intention and behaviour) which have been agreed by both Boards in November 2024. The benefits of using design principles are as follows:

-	They will embed our values in our behaviours and actions;

2

- They will provide a compass point when conflict or disagreement occurs;

- They will ensure we are consistent in what we say and do; and

- They are universally understood and accepted.

  - The design principles agreed by both Boards are:

| Mindset | Trusting each other to do the right thing and to act with courage and conviction. |
| --- | --- |
| Process | Driven by data and evidence and embracing opportunities to re-imagine, redesign and innovate Sustainability of the architecture |
| Outcome | Building sustainable and future proofed services that have the greatest impact and are in the best interests of all communities and patients |

  - Ensure an effective governance framework is in place to govern the work of the Regional Research, Innovation and Excellence Subgroup, which facilitates the ambitions and design principles set out by the RJC, and provides clear routes for assurance, escalation and decision-making.

  - Pro-actively manage the appropriate risks identified within the Regional Research, Innovation and Excellence Subgroup portfolio/programme, escalating strategic risks and interdependencies to the RJC as required and remaining accountable to the respective University Health Boards.

  - Develop and maintain a work programme that underpins the work of the Regional Research, Innovation and Excellence Subgroup and aligns with the RJC programme of work, the Health Boards’ Annual Plans and relevant Ministerial Priorities.

6	Membership

  - To ensure the Regional Research, Innovation and Excellence Subgroup undertakes its role effectively, its members will:

    - Attend meetings.

    - Adopt an open and constructively challenging approach within meetings.

    - Promptly follow up on actions and commitments; and

    - Participate in electronic and virtual channels established to allow a continuous flow of information between committee members.

  - Membership of the Regional Research, Innovation and Excellence Subgroup shall comprise:

| Member | Organisation |
| --- | --- |
| Executive Medical Director (Co-Chair) | Swansea Bay University Health Board |
| Executive Medical Director (Co-Chair) | Hywel Dda University Health Board |
| Regional Director for Research and Innovation | Swansea Bay University Health Board/ Hywel Dda University Health Board |
| Associate Medical Director for Research and Development | Swansea Bay University Health Board |
| Clinical Director for Research and Innovation | Hywel Dda University Health Board |
| Executive Director of Allied Health Professionals and Health Science* |  |
| Executive Director of Nursing* |  |

3

| Finance representative* |  |
| --- | --- |
| Workforce representative* |  |
| Digital representative* |  |
| Public Health Wales representative* |  |

Members marked with a * can be represented by either Swansea Bay or Hywel Dda university health board colleagues, rather than both.

  - The Regional Research, Innovation and Excellence Subgroup will be co-chaired by the Executive Medical Directors/chairing shall rotate between partner organisations on an annual basis unless otherwise agreed.

  - Membership of the Regional Research, Innovation and Excellence Subgroup will be reviewed on an annual basis.

  - The Regional Research, Innovation and Excellence Subgroup will be supported by a Secretary nominated through the Co-Chairs.

7	Quorum and Attendance

  - A quorum will be achieved by four members, which must include one of the Executive Medical Directors, and a representative of both health boards’ research and development teams.

  - All members should inform the Co-Chairs one week in advance of the meeting if deputies will be attending, unless exceptional short-term circumstances arise.

  - Should any member be unavailable to attend, they may nominate a deputy to attend in their place, subject to the agreement of both Co-Chairs.

  - Delegation to deputies is expected to be kept to a minimum and specific approval should be sought from the Co-Chairs for instances where more than two consecutive meetings are expected to involve the nominated deputy.

  - The Regional Research, Innovation and Excellence Subgroup may ask any or all of those who normally attend but who are not members to withdraw to facilitate open and frank discussion of particular matters.

8	Agenda and Papers

  - An agenda setting meeting is to be held with the Co-Chairs at least two weeks before the meeting date.

  - The agenda will be based around the Regional Research, Innovation and Excellence Subgroup’s work plan, identified risks, matters arising from previous meetings, issues emerging throughout the year, and requests from members.

  - All papers must be approved by the Lead/relevant Director/Chair.

  - The agenda and papers for meetings will be distributed seven days in advance of the meeting.

  - A draft Table of Actions will be issued within seven days of the meeting. The minutes and action log will be circulated to members within seven days to check the accuracy, prior to sending to Members (including the Regional Research, Innovation and Excellence Subgroup Co-Chairs) to review within the next seven days.

4

  - Members must forward amendments to the Chair within the next seven days. The Subgroup Secretary will then forward the final version to the Regional Research, Innovation and Excellence Subgroup Co-Chairs for approval

9	Frequency of Meetings

  - The Regional Research, Innovation and Excellence Subgroup will meet bi-monthly and shall agree an annual schedule of meetings. Any additional meetings will be arranged as determined by the Co-Chairs of the Regional Research, Innovation and Excellence Subgroup.

  - The Co-Chairs of the Regional Research, Innovation and Excellence Subgroup shall determine the time and the place of meetings of the Regional Research, Innovation and Excellence Subgroup and procedures of such meetings.

10 Accountability, Responsibility and Authority

  - The Regional Research, Innovation and Excellence Subgroup will be accountable to the RJC for its performance in exercising the functions set out in these terms of reference and will provide assurance on delivery of the objectives within the RJC Terms of Reference.

  - The requirements for the conduct of business as set out in each university health board’s

standing orders are equally applicable to the operation of the Subgroup.

11 Reporting

  - The Regional Research, Innovation and Excellence Subgroup shall:

    - Report formally, regularly and on a timely basis to the RJC on the Regional Research, Innovation and Excellence Subgroup’s activities, in the format prescribed by the RJC PMO.

    - Bring to the RJC’s specific attention any significant matters under consideration by the Regional Research, Innovation and Excellence Subgroup, including matters requiring strategic direction, escalation, endorsement or approval.

    - The Regional Research, Innovation and Excellence Subgroup may establish programmes, projects or task and finish groups to scope and take forward specific pieces of work to deliver on agreed objectives. The Regional Research, Innovation and Excellence Subgroup will receive updates from programmes, projects or task and finish groups through highlight reports and exception reporting.

12 Secretarial Support

12.1	The Regional Research, Innovation and Excellence Subgroup secretariat shall be provided through the Co-Chairs.

13 Review Date

13.1	These terms of reference and operating arrangements shall be reviewed on at least an annual basis by the Regional Research, Innovation and Excellence Subgroup for approval by the RJC.

5

Regional Finance, Contracting, Data & Digital Group

Regional Resources, Value and Digital Group ?

Regional Joint Committee of Swansea Bay and Hywel Dda University Health Boards

Hywel Dda

University Health Board

Swansea Bay

University Health Board

REGIONAL FINANCE, CONTRACTING, DATA & DIGITAL GROUP

TERMS OF REFERENCE

| Version | Issued To | Date | Comments |
| --- | --- | --- | --- |
| V1.0 |  | 01.08.2026 |  |
| V.1 | Regional Joint Committee | 13.10.2026 | For Approval |

1

1. Constitution

REGIONAL FINANCE, CONTRACTING, DATA & DIGITAL GROUP

The Regional Finance, Contracting, Data & Digital Group (RFCDDG) has been established as a Sub-Group of the Regional Joint Committee between Swansea Bay and Hywel Dda University Health Boards and constituted from 1 August 2026.

  - The RFCDDG has been established from the previously separate Finance & Contracting and Data & Digital Groups, merging the responsibilities of the former in terms of the phased regional finance collaboration between Hywel Dda and Swansea Bay University Health Boards in response to Welsh Government’s Finance Operating Model and the move towards a more value-based contracting approach to long term agreements, with the responsibilities of the latter in terms of the operational collaboration in place in areas including digital eyecare, theatres systems, preoperative assessment, shared infrastructure and regional cellular pathology, alongside a regional view of artificial intelligence (AI) readiness, and a strategic partnership approach with an external digital partner to include the future consideration of a Patient Services Centre.

2. Purpose

  - The purpose of the RFCDDG is to:

    - Provide assurance on the regional financial framework in place within and between Hywel Dda and Swansea Bay University Health Boards.

    - Provide assurance that opportunities for value and efficiency across the regional health economy are identified and tracked.

    - Provide assurance that digital solutions enable service transformation for staff and patients interaction with services.

    - Provide assurance that AI, automation, and advanced analytics capability is developed across the region with the appropriate governance, evaluation, and benefits realisation in place.

    - Provide assurance on the work to exploit regional value in the procurement strategies.

3. Objectives

The following objectives are within the scope of the RFCDDG:

  - Finance & Contracting

    - Ensure work is progressed on the phased regional finance collaboration between the two Health Boards, with transparent reporting of the utilisation and allocation of resources, cross-boundary activity, capital, and potential sharing of services and risks.

2

    - Ensure support is in place for Phase 1 of the shared regional operating model, Discovery and Design, baselines current processes across both organisations, defining where a once for region approach adds value before moving on to Phase 2, Develop and Deploy.

    - Oversee the development and operation of joint commissioning arrangements, including the Long Term Agreements and Service Level Agreements governing cross-boundary services, in order that contracting reflects regional priorities and the work of the Joint Commissioning Committee.

    - Ensure long term agreements are moved towards a value-based healthcare approach with proposals to be progressed for consideration by the Regional Joint Committee.

    - Systematically identify and track opportunities for value and efficiency across the regional health economy, with delivery aligned to the IMTPs of both Boards.

    - Develop coordinated financial planning and reporting across the RJC subgroups that supports both organisations’ statutory financial duties and informs Welsh Government engagement on regional investment.

  - Data & Digital

    - Ensure digital solutions are progressed to enable service transformation and systematically remove sources of friction in how staff and patients interact with services, including reliance on manual and paper-based processes.

    - Develop a regional approach to data sharing and interoperability, ensuring information flows between the two Health Boards and with wider partners are appropriately governed and aligned to all-Wales architecture and standards.

    - Oversee joint digital infrastructure and procurement decisions, reducing duplication and supporting consolidation onto common platforms where this serves regional priorities.

    - Ensure the development of AI, automation, and advanced analytics capability across the region with appropriate governance, evaluation, and a clear line of sight to clinical and operational benefit.

    - Ensure risks around data security, clinical safety and variation in practice are managed to enable AI to be progressed to a safe scale.

4.  Engagement

4.1	The RFCDDG will take a ‘people first' approach – putting patients, our communities and our Health Boards’ colleagues at the centre of our work.

5. Governance

  - The RFCDDG will operate in accordance with the Regional Joint Committee design principles (agreed set of rules defining purpose through intention and behaviour) which have been agreed by both Boards in November 2024. The benefits of using design principles are as follows:

3

    - They will embed our values in our behaviours and actions;

    - They will provide a compass point when conflict or disagreement occurs;

    - They will ensure we are consistent in what we say and do; and

    - They are universally understood and accepted.

The design principles agreed by both Boards are:

| Mindset | Trusting each other to do the right thing and to act with courage and conviction. |
| --- | --- |
| Process | Driven by data and evidence and embracing opportunities to re- imagine, redesign and innovate Sustainability of the architecture |
| Outcome | Building sustainable and future proofed services that have the greatest impact and are in the best interests of all communities and patients |

  - Ensure an effective governance framework is in place to govern the work of the RFCDDG which facilitates and enables the ambitions and design principles set out by the RJC.

  - Pro-actively manage the appropriate risks identified within the RFCDDG programme, being accountable to the respective University Health Boards.

  - Develop a work programme that underpins the work of the RFCDDG.

6.  Membership

  - To ensure the RFCDDG undertakes its role effectively, its members will:

    - Attend meetings.

    - Adopt an open and constructively challenging approach within meetings.

    - Promptly follow up on actions and commitments; and

    - Participate in electronic and virtual channels established to allow a continuous flow of information between committee members.

  - Membership of the RFCDDG shall comprise:

| Member | Organisation |
| --- | --- |
| Executive Director of Finance (RFCDDG Joint Chair) | Swansea Bay University Health Board |
| Executive Director of Finance (RFCDDG Joint Chair) | Hywel Dda University Health Board |
| Digital Director | Hywel Dda University Health Board |
| Director of Digital |  |
| Director of Performance and Business Intelligence | Swansea Bay University Health Board |
| In Attendance |  |

4

| Deputy Head of Operational Procurement | NWSSP |
| --- | --- |
| Deputy Director of Finance | Swansea Bay University Health Board |
| Deputy Director of Finance | Hywel Dda University Health Board |
| Assistant Director of Finance Strategy | Swansea Bay University Health Board |
| Invitation to attend to discuss work programme areas requiring wider collaboration (as and when required) |  |
| As and when required |  |

  - The RFCDDG will be jointly chaired by the Executive Directors of Finance from Hywel Dda and Swansea Bay University Health Boards.

  - Membership of the RFCDDG will be reviewed on an annual basis.

  - The RFCDDG will be supported by the Committee Secretary.

7. Quorum and Attendance

  - At least 50% of members from Hywel Dda UHB At least 50% of members from Swansea UHB

  - All members should inform the RJC PMO one week in advance of the meeting if deputies will be attending, unless exceptional short-term circumstances arise.

  - Should any member be unavailable to attend, they may nominate a deputy to attend in their place, subject to the agreement of both Co-Chairs.

  - Delegation to deputies is expected to be kept to a minimum and specific approval should be sought from the Co-Chairs for instances where more than two consecutive meetings are expected to involve the nominated.

  - The RFCDDG may ask any or all of those who normally attend but who are not members to withdraw to facilitate open and frank discussion of particular matters.

8.  Agenda and Papers

  - The Committee Secretary is to hold an agenda setting meeting with the Co-Chairs at least two weeks before the meeting date.

5

  - The agenda will be based around the RFCDDG’s work plan, identified risks, matters arising from previous meetings, issues emerging throughout the year, and requests from members.

  - All papers must be approved by the Lead/ relevant Directors.

  - The agenda and papers for meetings will be distributed seven days in advance of the meeting.

  - A draft Table of Actions will be issued within seven days of the meeting. The minutes and action log will be circulated to members within seven days to check the accuracy, prior to sending to Members (including the RFCDDG Co-Chairs) to review within the next seven days.

  - Members must forward amendments to the Committee Secretary within the next seven days. The RJC PMO will then forward the final version to the RFCDDG Co-Chairs for approval.

9. Frequency of Meetings

  - The RFCDDG will meet monthly and shall agree an annual schedule of meetings. Any additional meetings will be arranged as determined by the Co-Chairs of the RFCDDG.

  - The Co-Chairs of the RFCDDG, in discussion with the Committee Secretary, shall determine the time and the place of meetings of the RFCDDG and procedures of such meetings.

10. Accountability, Responsibility and Authority

10.1	The RFCDDG will be accountable to the Regional Joint Committee for its performance in exercising the functions set out in these terms of reference.

11. Reporting

  - The RFCDDG may establish programmes, projects or task and finish groups to deliver service change. The RFCDDG will receive updates from programmes, project or task and finish groups via a monthly highlight report.

  - The RFCDDG, supported by the regional PMO, shall:

    - Report formally, regularly and on a timely basis to the Regional Joint Committee on the RFCDDG’s activities.

    - Bring to the Regional Joint Committee’s specific attention any significant matters

under consideration by the RFCDDG.

12. Secretarial Support

12.1	The Committee Secretary shall be jointly determined by Swansea Bay and Hywel Dda University Health Boards.

13. Review Date

6

13.1	These terms of reference and operating arrangements shall be reviewed on at least an annual basis by the RFCDDG for approval by the Regional Joint Committee.

7

Regional Workforce & OD Subgroup

Regional Joint Committee of Swansea Bay and Hywel Dda University Health Boards

Hywel Dda

University Health Board

Swansea Bay

University Health Board

REGIONAL WORKFORCE & OD SUBGROUP

TERMS OF REFERENCE

| Version | Issued To | Date | Comments |
| --- | --- | --- | --- |
| V.1 | Executive Director(s) of Workforce & OD | 17/09/2026 | For Agreement |
| V.2 | Regional Joint Committee | 13/10/2026 | For Approval |

1

1	Constitution

REGIONAL WORKFORCE & OD SUBGROUP

The Regional Joint Committee (RJC) has been established under Ministerial Direction as a Joint Committee of Swansea Bay and Hywel Dda University Health Boards and constituted from 15 January 2025.

  - The Regional Workforce & OD Subgroup has been established as a Subgroup of the RJC

and held its inaugural meeting on XXXX 2025.

2	Purpose

2.1	The purpose of the Regional Workforce & OD Subgroup is to drive forward the work needed to establish a regional approach to workforce and OD as part of the Regional Joint Committee workstream.

3	Objectives

The Regional Workforce & OD Subgroup will:

  - Develop/create a coordinated, sustainable regional (strategic) workforce plan/model across both Health Boards, aligning service and workforce plans to reduce duplication and strengthen priority specialties.

  - Develop a regional health & well-being (Occupational Health) operating model, with services aligned or shared where appropriate, that improve staff health outcomes, reduces absence and turnover and delivers consistent, high quality support across both Health Boards while maximising efficiency and value for money.

  - Work on a co-ordinated Regional Leadership Development Offer that brings senior leaders together in a collaborative way to enhance opportunities for joint learning, consistent skill development and collective ways of working across the Health Boards.

4	Engagement

4.1	The Regional Workforce & OD Subgroup will take a ‘people first' approach – putting

patients, our communities and our Health Boards’ colleagues at the centre of our work.

5	Governance

  - The Regional Workforce & OD Subgroup will operate in accordance with the Regional Joint Committee design principles (agreed set of rules defining purpose through intention and behaviour) which have been agreed by both Boards in November 2024. The benefits of using design principles are as follows:

    - They will embed our values in our behaviours and actions;

    - They will provide a compass point when conflict or disagreement occurs;

    - They will ensure we are consistent in what we say and do; and

    - They are universally understood and accepted.

2

  - The design principles agreed by both Boards are:

| Mindset | Trusting each other to do the right thing and to act with courage and conviction. |
| --- | --- |
| Process | Driven by data and evidence and embracing opportunities to re-imagine, redesign and innovate Sustainability of the architecture |
| Outcome | Building sustainable and future proofed services that have the greatest impact and are in the best interests of all communities and patients |

  - Ensure an effective governance framework is in place to govern the work of the Regional Workforce & OD Subgroup, which facilitates the ambitions and design principles set out by the RJC, and provides clear routes for assurance, escalation and decision-making.

  - Pro-actively manage the appropriate risks identified within the Regional Workforce & OD Subgroup portfolio/programme, escalating strategic risks and interdependencies to the RJC as required and remaining accountable to the respective University Health Boards.

  - Develop and maintain a work programme that underpins the work of the Regional Workforce & OD Subgroup and aligns with the RJC programme of work, the Health Boards’ Annual Plans and relevant Ministerial Priorities.

6	Membership

  - To ensure the Regional Workforce & OD Subgroup undertakes its role effectively, its members will:

    - Attend meetings.

    - Adopt an open and constructively challenging approach within meetings.

    - Promptly follow up on actions and commitments; and

    - Participate in electronic and virtual channels established to allow a continuous flow of information between committee members.

  - Membership of the Regional Workforce & OD Subgroup shall comprise:

| Member | Organisation |
| --- | --- |
| Executive Director of Workforce & OD (-Chair) | Swansea Bay University Health Board |
| Executive Director of Workforce & OD (Co-Chair) | Hywel Dda University Health Board |
| Assistant Director of People Management | Hywel Dda University Health Board |
| Assistant Director of People Planning | Hywel Dda University Health Board |
| Assistant Director of Organisational Development | Hywel Dda University Health Board |
| Assistant Director of Workforce & OD (specialist support) | Hywel Dda University Health Board |
| Assistant Director of Workforce & OD - Workforce | Swansea University Health Board |
| Head of Staff Health & Wellbeing | Swansea University Health Board |
| Assistant Director of workforce & OD – Workforce Development | Swansea University Health Board |
| Assistant Director of workforce & OD – Workforce Development | Swansea University Health Board |
| In Attendance |  |

3

| Invitation to attend to discuss work programme areas requiring wider collaboration (as and when required) |  |
| --- | --- |

  - The Regional Workforce & OD Subgroup will be co-chaired by the Executive Directors of Workforce & OD/chairing shall rotate between partner organisations on an annual basis unless otherwise agreed.

  - Membership of the Regional Workforce & OD Subgroup will be reviewed on an annual basis.

  - The Regional Workforce & OD Subgroup will be supported by a Secretary nominated through the Co-Chairs.

7	Quorum and Attendance

  - A quorum will be achieved by four members, which must include one of the Executive Directors of Workforce & OD, and a representative of both health boards’ Workforce & OD teams.

  - All members should inform the Co-Chairs one week in advance of the meeting if deputies will be attending, unless exceptional short-term circumstances arise.

  - Should any member be unavailable to attend, they may nominate a deputy to attend in their place, subject to the agreement of both Co-Chairs.

  - Delegation to deputies is expected to be kept to a minimum and specific approval should be sought from the Co-Chairs for instances where more than two consecutive meetings are expected to involve the nominated deputy.

  - The Regional Workforce & OD Subgroup may ask any or all of those who normally attend but who are not members to withdraw to facilitate open and frank discussion of particular matters.

8	Agenda and Papers

  - An agenda setting meeting is to be held with the Co-Chairs at least two weeks before the meeting date.

  - The agenda will be based around the Regional Workforce & OD Subgroup’s work plan, identified risks, matters arising from previous meetings, issues emerging throughout the year, and requests from members.

  - All papers must be approved by the Lead/relevant Director/Chair.

  - The agenda and papers for meetings will be distributed seven days in advance of the meeting.

  - A draft Table of Actions will be issued within seven days of the meeting. The minutes and action log will be circulated to members within seven days to check the accuracy, prior to sending to Members (including the Regional Workforce & OD Subgroup Co-Chairs) to review within the next seven days.

4

  - Members must forward amendments to the Chair within the next seven days. The Subgroup Secretary will then forward the final version to the Regional Workforce & OD Subgroup Co-Chairs for approval.

9	Frequency of Meetings

  - The Regional Workforce & OD Subgroup will meet monthly and shall agree an annual schedule of meetings. Any additional meetings will be arranged as determined by the Co-Chairs of the Regional Workforce & OD Subgroup.

  - The Co-Chairs of the Regional Workforce & OD Subgroup shall determine the time and the place of meetings of the Regional Workforce & OD Subgroup and procedures of such meetings.

10 Accountability, Responsibility and Authority

  - The Regional Workforce & OD Subgroup will be accountable to the RJC for its performance in exercising the functions set out in these terms of reference and will provide assurance on delivery of the objectives within the RJC Terms of Reference.

  - The requirements for the conduct of business as set out in each university health board’s

standing orders are equally applicable to the operation of the Subgroup.

11 Reporting

  - The Regional Workforce & OD Subgroup shall:

    - Report formally, regularly and on a timely basis to the RJC on the Regional Workforce & OD Subgroup’s activities, in the format prescribed by the RJC PMO.

    - Bring to the RJC’s specific attention any significant matters under consideration by the Regional Workforce & OD Subgroup, including matters requiring strategic direction, escalation, endorsement or approval.

    - The Regional Workforce & OD Subgroup may establish programmes, projects or task and finish groups to scope and take forward specific pieces of work to deliver on agreed objectives. The Regional Workforce & OD Subgroup will receive updates from programmes, projects or task and finish groups through highlight reports and exception reporting.

12 Secretarial Support

12.1	The Regional Workforce & OD Subgroup secretariat shall be provided through the Co-Chairs.

13 Review Date

13.1	These terms of reference and operating arrangements shall be reviewed on at least an annual basis by the Regional Workforce & OD Subgroup for approval by the RJC.

5

Regional Health Economy Subgroup

Regional Joint Committee of Swansea Bay and Hywel Dda University Health Boards

Hywel Dda

University Health Board

Swansea Bay

University Health Board

REGIONAL HEALTH ECONOMY SUBGROUP

TERMS OF REFERENCE

| Version | Issued To | Date | Comments |
| --- | --- | --- | --- |
| V1.0 |  | 16/07/2025 | Drafted |
| V.1 | RHE Subgroup | 14/10/2025 | Revised |
| V.2 | RHE Subgroup | 17/11/2025 | Revised |
| V.3 | RHE Subgroup | 12/01/2026 | Approved by RHE Subgroup |
| V.4 | RHE Subgroup | 14/09/2026 | Revised |
| V.5 | Regional Joint Committee | 13/10/2026 | For Approval |

1

1.	Constitution

REGIONAL HEALTH ECONOMY SUBGROUP

The Regional Joint Committee (RJC) has been established under Ministerial Direction as a Joint Committee of Swansea Bay and Hywel Dda University Health Boards and constituted from 15 January 2025.

  - The Regional Health Economy Subgroup (RHES) has been established as a Subgroup of the RJC, and held its inaugural meeting on 10 November 2025.

  - For the purposes of these Terms of Reference, the Regional Health Economy is defined as the combined health, care, public service, community and economic system whose collective actions determine the health of the population and the sustainability of services.

2.	Purpose

  - The purpose of the RHES is to support the RJC by providing strategic leadership, coordination and assurance for the development of the Regional Health Economy.

  - To fulfil this purpose, the RHES will:

    - Set and align regional strategic plans for the Regional Health Economy, ensuring consistency with the strategic priorities of the Regional Joint Committee and both University Health Boards.

    - Align relevant programmes and workstreams across the region to support a coherent approach, maximise collective impact and avoid duplication.

    - Lead and coordinate Regional Health Economy work on behalf of the Regional Joint Committee, including the development and oversight of the agreed work programme.

    - Provide assurance to the Regional Joint Committee on progress, delivery, outcomes, risks and issues relating to the Regional Health Economy work programme.

3.	Objectives

The following objectives are within the scope of the RHES:

  - Produce a long-term Regional Health Economy Strategic Plan that provides a shared regional direction, enables coordinated and equitable system change, and sets out the intended population outcomes and measures through which regional impact will be assessed.

  - Establish a shared regional health profile which identifies the key drivers of health inequality and future healthcare demand across the region and is routinely used to inform regional planning.

  - Undertake the required preparatory work enabling the regional health economy to become a designated WHO sub regional health network so that the RJC can benefit from the shared learning opportunities afforded by participation in the network.

4.	Engagement

4.1.	The RHES will take a ‘people first' approach – putting patients, our communities and our Health Boards’ colleagues at the centre of our work.

5.	Governance

2

  - The RHES will operate in accordance with the Regional Joint Committee design principles (agreed set of rules defining purpose through intention and behaviour) which have been agreed by both Boards in November 2024. The benefits of using design principles are as follows:

    - They will embed our values in our behaviours and actions;

    - They will provide a compass point when conflict or disagreement occurs;

    - They will ensure we are consistent in what we say and do; and

    - They are universally understood and accepted.

  - The design principles agreed by both Boards are:

| Mindset | Trusting each other to do the right thing and to act with courage and conviction. |
| --- | --- |
| Process | Driven by data and evidence and embracing opportunities to re- imagine, redesign and innovate. |
| Outcome | Building sustainable and future proofed services that have the greatest impact and are in the best interests of all communities and patients |

  - Ensure an effective governance framework is in place to govern the work of the RHES, which facilitates the ambitions and design principles set out by the RJC and provides clear routes for assurance, escalation and decision-making (see Appendix 1 Regional Governance).

  - Pro-actively manage the appropriate risks identified within the RHES portfolio/programme, escalating strategic risks and interdependencies to the RJC as required and remaining accountable to the respective University Health Boards.

  - Develop and maintain a work programme that underpins the work of the RHES and aligns with the RJC programme of work, the Health Boards’ Annual Plans and relevant Ministerial Priorities.

  - Ensure that the RHES work programme is ambitious, proportionate and deliverable within the collective capacity and resources available across partner organisations.

6.	Membership

  - To ensure the RHES undertakes its role effectively, its members will:

    - Attend meetings.

    - Adopt an open and constructively challenging approach within meetings.

    - Promptly follow up on actions and commitments; and

    - Participate in electronic and virtual channels established to allow a continuous flow of information between committee members.

  - Membership of the RHES shall comprise:

| Member | Organisation |
| --- | --- |
| Executive Director of Public Health | Hywel Dda University Health Board |
| Interim Executive Director of Public Health | Swansea Bay University Health Board |
| Executive Representative | Public Health Wales |
| Representative | Future Generations Commissioner’s Office |
| In Attendance |  |
| Representation from Swansea Bay Public Health Team | Swansea Bay University Health Board |

3

| Representation from Hywel Dda Public Health Team | Hywel Dda University Health Board |
| --- | --- |
| Representation from Policy and International Health, WHO Collaborating Centre | Public Health Wales |
| Representation from Research, Data and Digital Directorate, Public Health Wales | Public Health Wales |
| Programme Management Office | Regional Joint Committee |
| Representation from PSBs within the region | PSBs within the region. |
| Representation from RJC Finance & Contracting Subgroup | Swansea Bay University Health Board Hywel Dda University Health Board |
| Representation from RJC Workforce & OD Subgroup | Swansea Bay University Health Board Hywel Dda University Health Board |
| Representation from RJC Data & Digital Subgroup | Swansea Bay University Health Board Hywel Dda University Health Board |
| Representation from RJC Research, Innovation & Excellence Subgroup | Swansea Bay University Health Board Hywel Dda University Health Board |
| Invitation to attend to discuss specific subject areas/ work programme areas requiring wider collaboration (as and when required) |  |
| As and when required | e.g. RPBs, FE Colleges, etc |

  - The RHES will be chaired on a rotational basis by the Executive Directors of Public Health, Swansea Bay and Hywel Dda University Health Boards.

  - Membership of the RHES will be reviewed on an annual basis.

  - The RHES will be supported by the RJC PMO.

7.	Quorum and Attendance

  - At least one member (or deputy) each from Swansea Bay UHB, Hywel Dda UHB, and Public Health Wales.

  - All members should inform the RJC PMO one week in advance of the meeting if deputies will be attending, unless exceptional short-term circumstances arise.

  - Should any member be unavailable to attend, they may nominate a deputy to attend in their place, subject to the agreement of the Chair.

  - Delegation to deputies is expected to be kept to a minimum and specific approval should be sought from the Chairs for instances where more than two consecutive meetings are expected to involve the nominated deputy.

  - The RHES may ask any or all of those who normally attend but who are not members to withdraw to facilitate open and frank discussion of particular matters.

8.	Agenda and Papers

  - The RJC PMO is to hold an agenda setting meeting with the Chair at least two weeks before the meeting date.

  - The agenda will be based around the RHES’ work plan, identified risks, matters arising from previous meetings, issues emerging throughout the year, and requests from members.

  - All papers must be approved by the Chair.

  - The agenda and papers for meetings will be distributed seven days in advance of the meeting.

4

  - A draft Table of Actions will be issued within seven days of the meeting. The minutes and action log will be circulated to members within seven days to check the accuracy, prior to sending to Members (including the RHES Chair) to review within the next seven days.

  - Members must forward amendments to the RJC PMO within the next seven days. The RJC PMO will then forward the final version to the RHES Chair for approval.

9.	Frequency of Meetings

  - The RHES will meet every other month and shall agree an annual schedule of meetings. Any additional meetings will be arranged as determined by the Chair of the RHES.

  - The Chair of the RHES, in discussion with the RJC PMO, shall determine the time and the place of meetings of the RHES and procedures of such meetings.

10.	Accountability, Responsibility and Authority

  - The RHES will be accountable to the RJC for its performance in exercising the functions set out in these terms of reference.

  - The requirements for the conduct of business as set out in each university health board’s

standing orders are equally applicable to the operation of the Subgroup.

11.	Reporting

  - The RHES, supported by the RJC PMO, shall:

    - Report formally, regularly and on a timely basis to the RJC on the RHES’ activities, in the format prescribed by the RJC PMO.

    - Bring to the RJC’s specific attention any significant matters under consideration by the RHES.

    - The RHES may establish programmes, projects or task and finish groups. The RHES will receive updates from programmes, project or task and finish groups through highlight reports and exception reporting.

12.	Secretarial Support

1.1	The RHES Secretariat shall be provided by the RJC PMO.

13.	Review Date

  - These terms of reference and operating arrangements shall be reviewed on at least an annual basis by the RHES for approval by the RJC.

5

##### Appendix 1

6

#### 11:50 AM, 5 Mins

  - - RJC/42: Board to Board Proposal		Hazel Lloyd (Swansea Bay UHB -

Corporate Governance), Joanne Wilson (Hywel Dda UHB - Director of

Corporate Governance/Board

Secretary)

Verbal

#### 11:55 AM, 5 Mins

## - RJC/43: RJC Internal Audit Report and Response

Hazel Lloyd (Swansea Bay UHB -

Corporate Governance), Joanne Wilson (Hywel Dda UHB - Director of

Corporate Governance/Board

Secretary)

Attachments

RJC 43a IA Advisory Review SBAR Report.pdf

RJC 43b RJC Governance Arrangements Final Advisory Report 2025-26.pdf RJC 43c IA RJC Governance Management Response.pdf

JOINT HYWEL DDA/SWANSEA BAY UNIVERSITY HEALTH BOARD COMMITTEE CYD-BWRDD IECHYD PRIFYSGOL HYWEL DDA/BAE ABERTAWE PWYLLGOR

| DYDDIAD Y CYFARFOD: DATE OF MEETING: | 13 October 2026 |
| --- | --- |
| TEITL YR ADRODDIAD: TITLE OF REPORT: | Regional Joint Committee Governance Arrangements - Internal Audit Final Advisory Report 2025/26 |
| CYFARWYDDWR ARWEINIOL: LEAD DIRECTOR: | Joanne Wilson, Director of Corporate Governance/Board Secretary, HDdUHB Hazel Lloyd, Director of Corporate Governance, SBUHB |
| SWYDDOG ADRODD: REPORTING OFFICER: | Alison Gittins, Head of Special Projects, Corporate Governance |

Pwrpas yr Adroddiad (dewiswch fel yn addas) Purpose of the Report (select as appropriate)

Er Sicrwydd/For Assurance

ADRODDIAD SCAA SBAR REPORT

Sefyllfa / Situation During the final quarter of 2025/26 and the first quarter of 2026/27, Internal Audit undertook an advisory review to assess the governance arrangements in place to support effective partnership working between Swansea Bay and Hywel Dda University Health Boards through the Regional Joint Committee (RJC). This paper shares the Final Advisory Report and also the Management Response to the recommendations made for the purposes of RJC oversight and assurance.

Cefndir / Background The advisory review focused on the design, clarity, and coherence of the governance framework established to support the RJC and its subgroups. While the review identified a number of established and effective elements within the RJC governance framework i.e. a clearly defined governance structure supported by approved Terms of Reference, subgroups operating in line with their intended strategic oversight role, developing work programmes aligned to regional priorities, and consistent and reliable reporting arrangements to both Health Boards through the AAA framework – it also identified opportunities to further strengthen consistency and maturity across the governance landscape, in particular: - Subgroup governance arrangements continue to evolve, with some inconsistency in the development, approval and alignment of Terms of Reference and supporting documentation. - The work programmes in place across subgroups vary in coverage and maturity, with some being only indicative in nature and with a less consistent defining of outputs, milestones and outcomes. - The intention to develop an RJC strategic risk register could be strengthened by a programme-wide approach to risk management, to ensure delivery risks at subgroup and workstream level are consistently identified, recorded and managed.

Page 1 of 4

Asesiad / Assessment The management response has identified the following proposed actions against each of the review’s recommendations:

Page 2 of 4

Actions in response to three of the advisory review’s recommendations will be complete by the 13 October 2026 RJC meeting with the annual review of the Terms of Reference for the RJC and those of its subgroups presented to the RJC for approval, together with the refreshed Annual Work Programme and the RJC Strategic Risk Register. The action in response to the final recommendation will be complete by the date of the next RJC meeting on 5 February 2027 when any remaining subgroup programmes will be baselined, and performance reported to the RJC using the maturity matrix agreed as part of the advisory review’s second recommendation, to inform RJC’s oversight.

Page 3 of 4

Argymhelliad / Recommendation The Regional Joint Committee is asked to receive assurance on the actions proposed in response to the advisory review’s recommendations.

Page 4 of 4

Regional Joint Committee Governance Arrangements

Final Advisory Report

2025/26

Swansea Bay University Health Board Hywel Dda University Health Board

Contents

Executive Summary	1

Findings & Agreed Action Plan	3

Appendix A: RJC Work Programme Status (August 2025)	8

Appendix B: RJC Work Programme Status (May 2026)	9

Appendix C: Assurance Opinion & Prioritisation of Findings	10

Review Reference	SBU-2526-03 / HDU-2526-01

Fieldwork	March 2026 – May 2026

Executive Sign Off	11 June 2026

Audit Committee	23 June 2026 (HDdU) / 16 July 2026 (SBU)

Executive Lead	Hazel  Lloyd  (SBU)  &  Joanne  Wilson  (HDdU),

Directors of Corporate Governance

Audit Team	Osian Lloyd & James Johns, Heads of Internal Audit Felicity Quance & Sophie Corbett, Deputy Heads of Internal Audit

Page 174

# Executive Summary

Purpose

In March 2024, Welsh Government directed Swansea Bay University Health Board (SBUHB) and Hywel Dda University Health Board (HDdUHB) to establish a Regional Joint Committee (RJC) to strengthen collaboration in the planning and delivery of services in response to shared clinical, financial and population health challenges. This direction recognised the need for a coordinated regional approach to support the long-term safety, quality and sustainability of key services.

This advisory review assessed the governance arrangements in place to support effective partnership working between SBUHB and HDdUHB through the RJC. The review focused on the design, clarity, and coherence of the governance framework established to support the RJC and its subgroups. An assessment of the operational effectiveness of these arrangements will be undertaken as part of a subsequent review within both Health Boards’ 2026/2027 internal audit plans.

Overview

The review identified a number of established and effective elements within the RJC governance framework. In particular, there is a clearly defined governance structure supported by approved Terms of Reference, subgroups operating in line with their intended strategic oversight role, developing work programmes aligned to regional priorities, and consistent and reliable reporting arrangements to both Health Boards through the AAA framework. These arrangements provide a strong foundation for regional partnership working, collective oversight and informed Board-level assurance.

The RJC has made clear progress in establishing its operating model and defining regional priorities. Governance arrangements are functioning as intended at a structural level, with evidence of Board scrutiny, effective escalation processes, and flexible decision-making where required, including for time-critical regional decisions.

As the committee transitions from establishment to delivery, there is an opportunity to further strengthen consistency and maturity across the governance landscape. Variation in maturity across subgroups reflects, in part, the transition from legacy ARCH1 arrangements and differing stages of programme development. This variation is particularly evident in the consistency and completeness of governance documentation, the clarity and alignment of subgroup objectives and Terms of Reference, the articulation of outputs, outcomes and success measures within work programmes, and the ability to demonstrate progress, interdependencies and impact at a whole‑programme level. In particular:

- Subgroup governance arrangements continue to evolve, with some inconsistency in the development, approval and alignment of Terms of Reference and supporting documentation.

- Work programmes are in place across subgroups but vary in coverage and maturity. While more developed areas (e.g. CSP) demonstrate structured, delivery-focused approaches, others remain more indicative in nature, with less consistent defining of outputs, milestones and outcomes. In some cases (e.g. Finance and Contracting), supporting documentation was not available for review, limiting visibility of delivery expectations and contribution to regional objectives.

- There is an intention to develop an RJC strategic risk register and this could be strengthened by a programme-wide approach to risk management, to ensure delivery risks at subgroup and workstream level are consistently identified, recorded and managed.

Notwithstanding these areas for development, governance arrangements are operating effectively in supporting oversight, reporting and decision-making across both Health Boards.

Page 175

Addressing the areas identified will support the RJC in transitioning from a developing governance model to a more mature, consistently applied framework, capable of demonstrating clear delivery, effective oversight, and measurable impact across its full remit.

1 A Regional Collaboration for Health (ARCH) was a long‑term, tri‑partite partnership between Swansea Bay University Health Board, Hywel Dda University Health Board and Swansea University.

1

Scope & Actions Summary

Objectives	Related Actions

    - The Regional Joint Committee has a clearly defined and approved governance structure, supported by terms of reference and work programmes aligned to its purpose and objectives.

    - Regional Joint Committee subgroups are established with clear roles, responsibilities and reporting arrangements to support the effective delivery of regional outputs.

    - The Health Boards receive sufficient information to enable effective oversight, decision-making and escalation of key risks and issues.

1, 2, 3

3

4

Management Actions	Themes	Risk Types

4

Governance

1

2

Planning, Delivery &

Deadline Management

1

Risk Management

Public Perception & Reputational Risk

Choose an item. Choose an item. Choose an item.

Page 176

2

Findings & Agreed Actions

Objective 1: The Regional Joint Committee has a clearly defined and approved governance structure, supported by terms of reference and work programmes aligned to its purpose and objectives.

Terms of Reference

The RJC has been formally established in line with ministerial direction issued in March 2024 and is intended to operate at a level equivalent to a Board Assurance Committee within both Health Boards. Its first meeting was held in January 2025. The Committee operates with a clearly articulated purpose and scope, supported by approved Terms of Reference (ToR), which set out its objectives, membership, quorum, meeting arrangements, and reporting lines.

The RJC ToR were approved by the respective Health Boards in May 2025, and have been subsequently reviewed in April 2026, which included strengthening self‑assessment arrangements, clarifying the Committee’s system‑wide oversight role, and reinforcing reporting expectations to Welsh Government. Review of the RJC Terms of Reference identified varying levels of maturity across the RJC’s supporting subgroups2, with the objectives of the Clinical Services Planning (CSP) and Regional Health Economy (RHE) subgroups being the most clearly articulated. We note that this variation was acknowledged in the April 2026 review of ToR, with the RJC agreeing that further work was required to develop and align objectives of the Finance and Contracting, and Workforce and Organisational Development (WOD) subgroups to improve consistency.

Review of RJC papers (January 2025 to April 2026) confirms that meetings have consistently achieved quorum. While the expectation is for quarterly meetings, the planned October 2025 meeting was stood down to allow greater focus on subgroup development, including clarifying ambition, scope, and delivery expectations. An extraordinary meeting was convened in February 2026, aligned to Health Board reporting cycles, to enable timely consideration, endorsement, and submission of the Regional Cellular Pathology business case to Welsh Government.

Although the RJC has received updates on the development of subgroup ToR, formal approval has not been consistently undertaken beyond that of the Research Innovation and Excellence (RIE) subgroup (see Action 1). Our review of subgroup and workstream ToR (see objective 2) identified that there could be greater consistency and alignment with the overarching RJC ToR (see Action 1 & 3).

Work Programme

The RJC work programme has evolved from an initial consolidation of legacy ARCH arrangements into a more structured articulation of regional priorities aligned to its core objectives. Comparison of the 2026/27 work programme with both Health Boards’ Annual Plans confirms alignment between regional priorities and organisational commitments, providing a clear line of sight between regional planning and local delivery.

Page 177

Earlier iterations of the work programme incorporated a subgroup maturity assessment (see Appendix A), providing a structured view of relative development across the RJC portfolio. This enabled clearer differentiation between established delivery areas and those still in scoping or development phases, supporting more informed oversight by the RJC. We have prepared an updated maturity assessment (see Appendix B), based on a review of supporting documentation for each subgroup, which provides a current view of their development.

2 Regional Health Economy Subgroup, Regional Clinical Services Planning Subgroup, Regional Workforce & OD Subgroup, Regional Digital & Data Subgroup, Regional Finance and Contracting Subgroup, Regional Research Innovation & Excellence Subgroup.

3

Page 178

Review of the RJC work programme, delivered through its constituent sub‑groups, demonstrates clear progression since establishment, with increasing clarity around intended outputs and areas of focus. This is most evident within the CSP subgroup, where outputs and priorities are articulated in a more structured and delivery-focused manner, reflecting a more mature programme of work.

In contrast, other subgroups remain at an earlier stage of development, with plans articulated more at the level of intention or direction. There is less consistent sequencing of activities and articulation of corresponding deliverables, timescales and outcome measures. While this is consistent with their stage of development, it could contribute to variation in how activity, outputs, and outcomes are monitored (see Action 2).

Similarly, this was recognised by the RJC through its self-assessment of its first year of operation, which identified a need for clearer measurement of effectiveness and impact. An action plan has been developed to address this, which includes expanding reporting to provide clearer outline of timescales, outputs, and outcomes rather than activity alone.

Action 1: RJC

Improving consistency across subgroup and respective workstream Terms of Reference would support clearer roles, defined responsibilities, and more robust governance accountability.

Action 2: RJC Work Programme

Further development of the RJC work programme would support consistent articulation of expected outputs and delivery contributions across all subgroups. This could be strengthened through periodic use of a subgroup maturity assessment or view to inform Committee‑level oversight and self‑assessment.

4

Objective 2: Regional Joint Committee subgroups are established with clear roles, responsibilities and reporting arrangements to support the effective delivery of regional outputs.

Work programmes are in place across the RJC substructure and are broadly aligned at a strategic level to RJC objectives. Acknowledging there are differing levels of maturity across these programmes, there is variation in both the level of detail and the way in which they are articulated and reported to the RJC.

The CSP subgroup has a more developed portfolio approach, supported by structured AAA and highlight reporting, with a clear linkage between programme activity, risk, prioritisation and executive decision-making. This includes decisions taken to pause specific workstreams, such as Urgent and Emergency Care, in recognition of programme resource constraints. While evidence was available to support the decision-making process at the point of pause, including consideration of capacity and prioritisation of resources, limited supporting documentation was available to demonstrate the progress of this workstream prior to this decision.

In contrast, other subgroups are at earlier stages of development, with variation in maturity reflecting the transition from legacy ARCH arrangements to newer RJC-established structures. The RHE subgroup reports progress using narrative-based highlight summaries, with a strong emphasis on partnership working and activity; however, this is not consistently supported by clearly defined outputs or success criteria. This has been recognised by management and is a key focus within the Health Intelligence and Health Inequalities workstreams as the subgroup develops its longer-term strategic plan.

The REI subgroup structure has established short-term milestones and supporting documentation; however, given its delayed implementation, longer-term outcomes and benefits realisation remain under development. Similarly, the WOD subgroup has made positive progress through the introduction of “plan on a page” documentation; however, this approach is not yet been consistently applied across all workstreams.

A more structured approach is evident within the Data and Digital subgroup, where a defined delivery plan was presented to the RJC in April 2026, incorporating clearly articulated workstreams, milestones, outputs and intended benefits. This reflects a response to challenge from RJC members for greater clarity on near-term priorities and delivery expectations.

In contrast, while the Finance and Contracting Subgroup is referenced within the RJC structure and work programme, no supporting documentation or defined work programme was available for review. This restricts visibility of its role, delivery expectations and contribution to wider regional objectives (see Action 3).

Structured reporting is undertaken to the RJC, primarily through the Alert, Advise and Assure (AAA) framework, which supports visibility of key activity and provides an established mechanism to escalate issues.

In addition to formal subgroups, the Regional Drive and Delivery Group (RDDG) operates as an Executive-level operational and steering forum. Chaired jointly by the Chief Executives and comprising senior executive representation from both Health Boards, the RDDG provides coordination and oversight of delivery across the RJC portfolio. Meeting cycles are aligned with those of the RJC, enabling the group to review progress, coordinate inputs and monitor actions in advance of and following formal RJC reporting.

Page 179

Evidence from action logs and meeting notes indicates that the RDDG is actively tracking and progressing RJC actions across subgroup workstreams, such as the Orthopaedics programme within CSP. The decision to step down the October RJC meeting provided additional operational focus at RDDG level, enabling subgroups to refine their plans, clarify intended outputs and outcomes, and consider key risks and dependencies ahead of subsequent RJC reporting.

5

Page 180

Variation in maturity and coverage of work programmes is, in part, reflective of wider programme capacity and resource constraints. Evidence from CSP and RDDG indicates that conscious decisions are being made to focus available programme management and operational resource on areas of greatest strategic importance and readiness.

The RJC Programme Management Office (PMO) capacity is directed towards the CSP and RHE portfolios and delivered through a small core team. Engagement with national programmes is ongoing to identify additional resources to support its operation.

Action 3: Strengthen formal governance and documentation discipline

Formalising and standardising governance arrangements across all subgroups would strengthen documentation discipline. This includes ensuring Terms of Reference are approved, documentation is maintained and up to date, and consistent standards (such as version control and clear articulation of purpose, outputs and responsibilities) are applied.

This is particularly relevant where documentation is limited or not fully developed, for example within the Finance and Contracting sub-group, where work programme documentation does not consistently set out defined outputs, milestones or delivery timescales. This could also include updating legacy references (e.g. ARCH within CSP documentation) and ensuring governance documentation accurately reflects current operating arrangements.

6

| Objective 3: The Health Boards receive sufficient information to enable effective oversight, decision-making and escalation of key risks and issues. |  |  |
| --- | --- | --- |
| Review of RJC meeting papers (January, May and August 2025; and January 2026), minutes, and corresponding AAA subgroup reports confirmed that Board papers accurately reflect the content, decisions, assurances, and matters requiring escalation arising from RJC meetings across all periods tested. Where AAA reports indicated “no alerts” or “no risks”, this was fully consistent with the underlying RJC documentation. Comparison of reporting across both Health Boards confirms consistency in the format, structure and content of information presented. The same AAA reports, containing identical core assurance content, including decisions and risks, were submitted to both Boards at the next scheduled Board meeting following each RJC meeting. One instance of variation was identified in March 2025, where additional narrative context relating to the developing governance architecture of the RJC was provided to Hywel Dda but not to Swansea Bay. However, this did not affect the consistency of assurance or decision-making information and has not recurred in subsequent reporting cycles. Evidence of Board scrutiny and challenge when receiving RJC AAA reports was evident, particularly in relation to complex or high-impact matters such as the progression of the Regional Cellular Pathology business case. We did not identify any instances where issues were formally referred back to the RJC. Where RJC and Board meeting cycles did not fully align, appropriate flexibility was applied to ensure that Boards received complete and accurate updates at the earliest available opportunity. The use of extraordinary RJC meetings and Special Board meetings, particularly in relation to significant regional clinical decisions, demonstrates that governance arrangements are sufficiently flexible to respond to time‑critical requirements. The RJC does not maintain a standalone risk register, although subgroup reporting includes references to a range of workstream and project risks. As part of this review, a mapping exercise against Health Board risk registers confirmed that regional and RJC‑relevant risks are appropriately captured. This includes recognition of cross‑organisational and system-wide dependencies, particularly in areas such as workforce sustainability, diagnostics and cancer pathways, digital resilience, financial sustainability, and the delivery of regional clinical services. At its April 2026 meeting, the RJC considered its approach to identifying and managing system‑wide risks arising from regional working. An action was agreed for the Directors of Corporate Governance of both Health Boards to jointly develop and present a proportionate and pragmatic RJC strategic risk register, identifying system‑wide risks aligned to RJC objectives, an initial high-level outline is to be presented to the RJC in July 2026. Review of subgroup agendas identified that risks are routinely referenced within highlight reports, with some evidence of workstream or project-level risk registers (for example, within the CSP subgroup at individual project level). However, there is no clearly defined programme-wide approach to risk management to ensure that delivery risks are identified, recorded and managed consistently across subgroups and workstreams. (see Action 4). |  |  |
|  | Action 4: Programme Risk Management Completion of the strategic risk register should be followed by the definition and implementation of a programme-wide approach to risk management, to ensure delivery risks are consistently identified, recorded and escalated across all subgroups and workstreams. |  |

Page 181

7

# Appendix A: RJC Work Programme Status (August 2025)

Page 182

The following summary was presented at the Regional Joint Committee meeting (18 August 2025)

8

# Appendix B: RJC Work Programme Status (May 2026)

Page 183

This programme status was developed as part of an exercise undertaken by Audit & Assurance, based on a review of supporting documentation for each of the sub-groups:

| Subgroup | ToR’s agreed by Sub-group | Programme Defined | Ambition Agreed | Agreed Sub-group Work Programme | Objectives/ Outcomes agreed | Resources agreed | Risks Understood | Dependencies Understood | Key Milestones | Detailed Plans |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Regional Health Economy |  | In progress |  |  |  | In progress | In progress | In progress | In progress | In progress |
| Clinical Services Planning |  |  |  |  |  | In progress |  | In progress |  |  |
| Workforce & OD | No |  |  | Partial |  |  |  | In progress | In progress | In progress |
| Data & Digital | No |  |  |  |  |  |  | In progress |  |  |
| Finance & Contracting | No | In progress | In progress | In progress | In progress | In progress | Unclear | Unclear | Unclear | Unclear |
| Research, Innovation & Excellence |  |  |  |  |  | In progress | In progress | In progress | In progress | In progress |

9

# Appendix C: Assurance Opinion & Prioritisation of Findings

##### Assurance Opinion	Disclaimer

Substantial

Few matters require attention and are compliance or advisory in nature.

Low impact on residual risk exposure.

Some	matters	require	management

Reasonable	attention in control design or compliance.

Low to moderate impact on residual risk

exposure until resolved.

More	significant	matters	require

Limited

management attention.

Unsatisfactory

Advisory

Moderate impact on residual risk exposure until resolved.

Action is required to address the whole control framework in this area.

High impact on residual risk exposure until resolved.

Given to reviews and support provided to management which form part of the internal audit plan, to which the assurance definitions are not appropriate.

These reviews are still relevant to the evidence base upon which the overall opinion is formed.

This audit report has been prepared for internal use only. Audit and Assurance Services reports are prepared, in accordance with the agreed audit brief, and the Audit Charter as approved by the Audit Committee.

Audit reports are prepared by the staff of the NHS Wales Audit and Assurance Services and addressed to Independent Members or officers including those designated as Accountable Officer. They are prepared for the sole use of Hywel Dda and Swansea Bay University Health Boards and no responsibility is taken by the Audit and Assurance Services Internal Auditors to any director or officer in their individual capacity, or to any third party.

The report is based on the review work undertaken and is not necessarily a complete statement of all weaknesses that exist or potential improvements. Whilst every care has been taken to ensure that the information provided in this report is as accurate as possible, no complete guarantee or warranty can be given with regard to the advice and information contained.

Our work does not provide absolute assurance that material errors, loss or fraud do not exist. Responsibility for a sound system of internal controls and the prevention and detection of fraud and other irregularities rests with management of Hywel Dda and Swansea Bay University Health Boards. Work performed by internal audit should not be relied upon to identify all strengths and weaknesses in internal controls, or all circumstances of fraud or irregularity. Effective and timely implementation of recommendations is important for the development and maintenance of a reliable internal control system.

##### Prioritisation of Findings	Public Sector Internal Audit Standards

| Priority | Explanation |
| --- | --- |
| High | Significant risk to achievement of a system objective OR evidence present of material loss, error, or misstatement. Poor system design OR widespread non-compliance. |
| Medium | Some risk to achievement of a system objective. Minor weakness in system design OR limited non-compliance. |

Audit work undertaken by NHS Wales Audit and Assurance Services conforms with the International Standards for the Professional Practice of Internal Auditing and associated Public Sector Internal Audit Standards as validated through the external quality assessment undertaken by the Chartered Institute of Public Finance & Accountancy in April 2023.

Page 184

Website: Audit & Assurance Services - NHS Wales Shared Services Partnership

10

ACTION PLAN / DEVELOPMENT OF MANAGEMENT RESPONSES

Process

Within one month of receipt of report, please complete the table below to confirm:

      - If the recommendation is accepted or not (justification must be documented if not accepted);

      - A management response to the accepted recommendations detailing:

        - how it will be implemented, ie the actions that will be undertaken to fully implement the recommendation. Consideration must be given to what is within the means and capacity of the service in order to deliver, with any barriers to its implementation, or additional resource requirements clearly documented

        - who will own this recommendation.

      - A realistic and achievable completion date, taking into account your capacity;

      - The evidence/documentation that will demonstrate the recommendation has been fully implemented as this will need to be uploaded to AMAT before it will be fully approved as completed; and

      - Any recommendation that cannot be fully implemented must be escalated through the relevant management structure and action plans must be signed off by the relevant Clinical Care Group.

      - Management responses to recommendations in these reports should be SMART (Specific, Measurable, Achievable, Realistic/Relevant and Time-Bound).

| S | Specific | What is the recommendation – is it achievable? Your response should be clear and well defined to ensure that you able to achieve the outcome set out in the recommendation. |
| --- | --- | --- |
| M | Measurable | What documentation can you provide to evidence that the recommendation has been completed to a satisfactory standard? Do you need to create/amend policies, processes etc? |
| A | Achievable | Can we as a Health Board achieve the outcome needed – are there any factors (internal and external) that need to be taken into account to be able to achieve the outcome i.e Financial implications, workforce capacity, specific equipment etc? |

1

| R | Realistic/Relevant | Are you able to complete the action - Do you have the correct resources? Do you have enough workforce capacity to complete the action? |
| --- | --- | --- |
| T | Time-bound | Ensure that you set yourself realistic and achievable completion dates. Give yourselves enough time to be able to complete the action – and maybe add some extra time such as a month or so on top of that in case of any unforeseen circumstances which may cause delays. |

After sign off by Clinical Care Group/Director, action plans must be reviewed by IQFPDG prior to onward submission to Formal Executive Team for approval. Once approved, action plans should be sent to the Head of Assurance and Risk for initial upload to AMaT.

The report and action plans will then be presented to QSEC (or other Board level Committee) at its next meeting to provide assurance that the management response will address the areas of concern/improvement detailed in the report.

Progress against recommendations must be regularly provided on AMaT by the relevant recommendation owners, with monitoring of their delivery undertaken by the relevant Clinical Service Group, with oversight from the Clinical Care Group. Any exceptions to the implementation of recommendations are required to be reported to IQFPD.

Non-compliance of implementing recommendations within agreed timescales is one of the criteria considered within the Governance domain within the

Health Board’s Improving Together Framework

2

Report: Regional Joint Committee Governance Arrangements Final Advisory Report 2025/26 Swansea Bay University Health Board Hywel Dda University Health Board

Issued By: Internal Audit Issued On: 11/06/2026

Lead Officer: Hazel Lloyd (SBUHB) & Joanne Wilson (HDdUHB), Directors of Corporate Governance Suggested Overseeing Committee: Regional Joint Committee

| Recommendation | Management Response | Recommendation Owner (name, job title and CCG) | Completion Date - Please enter a specific implementation date for your action. For recommendations that are reliant on factors external to the Health Board, please note as “External” | Expected Evidence of Implementation |
| --- | --- | --- | --- | --- |
| Action 1: RJC Improving consistency across subgroup and respective workstream Terms of Reference would support clearer roles, defined responsibilities, and more robust governance accountability. | RJC Terms of Reference Agree. Consistency will be introduced across Sub-Group and respective workstream Terms of Reference to support clearer roles, defined responsibilities and more robust governance accountability. Terms of Reference are currently being crafted for the newly merged, Finance, Contracting, Digital and Data Sub-Group for approval at the RJC meeting on 13 October 2026. An annual review of the remaining Sub-Groups and respective workstreams Terms of Reference has been scheduled for the RJC meeting on 13 October 2026 to | Joanne Wilson | 13/10/2026 | RJC approved Terms of Reference for all RJC Sub-Groups |

3

|  | approve the suite of RJC Sub-Group Terms of Reference. |  |  |  |
| --- | --- | --- | --- | --- |
| Action 2: RJC Work Programme Further development of the RJC work programme would support consistent articulation of expected outputs and delivery contributions across all subgroups. This could be strengthened through periodic use of a subgroup maturity assessment or view to inform Committee-level oversight and self-assessment | RJC Work Programme and RJC Work Plan The RJC PMO will produce a Work Programme for each RJC meeting setting out expected outputs and delivery contributions. This will include a maturity assessment or view to inform Committee-level oversight and self-assessment, as identified in Appendix A and B of the Internal Audit RJC Governance Arrangements Advisory Report. A further strengthening of key outputs and delivery reporting will be achieved by using the Regional Joint Committee – Annual Work Plan 2026/27 to schedule specific performance reports from Sub-Groups for key outputs, outcomes and anticipated performance improvements. | RJC PMO | 13/10/2026 | RJC Work Programme presented to RJC RJC Annual Work Plan 2026/27 used to schedule specific performance reports |
| Action 3: Strengthen formal governance and documentation discipline Formalising and standardising governance arrangements across all subgroups would strengthen documentation discipline. This includes ensuring Terms of Reference are approved, documentation is maintained and up to date, and consistent standards (such as version control and clear articulation of | PowerPoint Programme Summaries linked to AAA Update Reports Documentation discipline will be addressed through a clear articulation of workstream purpose, outputs and responsibilities through the regular and routine Work Programme Summary (PP Slides) capturing scope; ambition statement; objective | RJC PMO | 05/02/2027 | Completed Work Programme Summary (PP Slides) for each RJC Sub-Group. Performance routinely reported for each RJC meeting. |

4

| purpose, outputs and responsibilities) are applied. This is particularly relevant where documentation is limited or not fully developed, for example within the Finance and Contracting sub-group, where work programme documentation does not consistently set out defined outputs, milestones or delivery timescales. | statement; key milestones; resource analysis/ assumptions/ requirements /impacts/ gaps; funding assumptions/ requirements/ gaps; risks; issues; dependencies (see PP template embedded below). RJC Subgroup Work Programme Summar The action in response to the final recommendation will be complete by the date of the next RJC meeting on 5 February 2027 when any remaining subgroup programmes will be baselined, and performance reported to the RJC using the maturity matrix agreed as part of the advisory review’s second recommendation, to inform RJC’s oversight. AAA Update Reports will be used to report performance as follows: Assurance – programmes are proceeding as baselined; outputs and outcomes will be delivered as scheduled. Advisory – action is required/being taken to ensure programmes are proceeding as baselined; outputs and outcomes will be delivered as scheduled / within tolerance. Alert – outputs and outcomes will not be delivered as scheduled; immediate action |  |  | Major issues and risks to output and outcome delivery discussed at RJC, with mitigating actions agreed. |
| --- | --- | --- | --- | --- |

5

| This could also include updating legacy references (e.g. ARCH within CSP documentation) and ensuring governance documentation accurately reflects current operating arrangements. | or a change to programme baseline is required Legacy references have been updated to ensure governance documentation accurately reflects current operating arrangements. |  |  |  |
| --- | --- | --- | --- | --- |
| Action 4: Programme Risk Management Completion of the strategic risk register should be followed by the definition and implementation of a programme-wide approach to risk management, to ensure delivery risks are consistently identified, recorded and escalated across all subgroups and workstreams | A jointly developed and standalone RJC strategic risk register will be presented to the RJC on 13 October 2026, identifying system‑wide risks aligned to each of the RJC’s objectives. These risks will be aligned to each relevant Sub-Group and workstream and identified on their Work Programme Summary (PP Slides) with their owner, impact and mitigating action clearly articulated. These risks will also be referenced within each of the Sub-Groups AAA Update Reports to the RJC providing assurance on how risks are being managed. | Hazel Lloyd | 13/10/2026 | RJC strategic risk register presented to the RJC on 13 October 2026 |

Prepared By: …………………………………………………………………………………………………………………………………………….. Prepared On: …………………………………………………………………………………………………………………………………………….. Approved By: …………………………………………………………………………………………………………………………………………….. Approved On:  ……………………………………………………………………………………………………………………………………………..

6

#### 12:00 PM, 5 Mins

  - - RJC/44: RJC Strategic Risk Register		Hazel Lloyd (Swansea Bay UHB -

Corporate Governance), Joanne Wilson (Hywel Dda UHB - Director of

Corporate Governance/Board

Secretary)

Attachments

RJC 44 RJC Strategic Risk Register.pdf

Page 191

#### SBAR Report: Regional Joint Committee Strategic Risk Register

| Report title | Regional Joint Committee Strategic Risk Register |
| --- | --- |
| Date | October 2026 |
| Purpose | To present draft Regional Joint Committee strategic risks for consideration, comment and agreement; to discuss and agree Director level ownership for individual risks; and to set out next steps to develop the risks into a fuller risk register and to establish management and reporting processes. |
| Author | Hazel Lloyd, Director of Corporate Governance |
| Executive lead | Joint Chief Executives / RJC Chair |
| Action required | The Regional Joint Committee members are asked to consider the outline strategic risks in Appendix 1 and agree them as the basis for further register development, and/or provide comments to develop them further. |

Situation

The Regional Joint Committee is developing its approach to strategic risk oversight as its regional work programme matures. A strategic risk register would provide a structured basis for identifying, overseeing and escalating the key risks that could affect

delivery of the Committee's objectives across the regional health economy, clinical services planning, corporate enablers, research and innovation, governance, and external system alignment. This report proposes a set of draft risks as a basis on which to build a strategic risk register for the RJC.

1

Background

The RJC has approved terms of reference, an emerging 2026/27 work programme, subgroup arrangements and reporting routes to both sovereign Boards. Recent reporting has highlighted the need to strengthen strategic risk ownership, subgroup work programme discipline, escalation routes, benefits realisation and the alignment of assurance reporting with the 3A reporting cycle.

A listing of draft, strategic risks has therefore been developed as a basis on which to build a pragmatic Board Assurance-style strategic risk register. The register when fully developed will be intended to help the RJC focus on the key risks to delivery of its

strategic objectives; consider the adequacy of controls; assess the assurances available; identify gaps; and determine what further action may be required to support delivery and escalation.

Assessment

The listing attached with this report identifies six, draft strategic risks. These focus on the risks to achieving the RJC objectives: the delivery of a coherent regional health economy model; timely and evidence-based regional clinical services planning; the availability of corporate enablers; the translation of research and innovation into scaled improvement; the maturity of governance, accountability and assurance arrangements; and the ability to secure external support and system alignment for major regional change. Indicative content is also provided indicating high level control mechanisms, sources of assurance, gaps, and areas for

action.

In addition to the agreement the risks themselves, clear ownership is important to ensure the ongoing management and update of register content required to support effective monitoring and reporting. While the register will be overseen by the RJC, it is recommended that each risk is assigned a single Director-level risk owner from either of the health boards, who will be accountable for the management and update of the risk entry. Lead managers can be nominated to support the risk owner in the further development of risk register content and ongoing administration of the risk register when adopted.

The agreement of a set of strategic risks and risk owners is a prerequisite to further development of a risk register for the RJC. This report is seeking agreement to the risks presented and/or the identification of areas for adjustment / further development,

Following agreement of risks and Director-level ownership, the next steps will be:

- Further develop risk register format and content

- Development and agreement of a common approach to risk assessment

2

- Assessment of listed risks in accordance with the agreed approach

- Further consideration to be given to risk appetite; responsibilities and processes for updating the risk register; and arrangements for monitoring and reporting.

Recommendations

The Regional Joint Committee Members are asked to:

    - Consider and agree the strategic risks as outlined in Appendix 1, and/or provide suggestions for enhancement.

    - Consider and agree Executive ownership for each strategic risk and where possible lead officer arrangements for maintaining the register.

    - Note the next steps proposed, following agreement of 1 & 2.

3

Appendix 1

| Ref | Strategic objective | Strategic risk | Key controls in place | Sources of assurance | Assurance gaps | Further actions required | Exec Risk Owner | Mgt Support Lead | Current risk score | Target risk score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SR01 | Develop a coherent and deliverable regional health economy model. | There is a risk that the Regional Joint Committee's emerging ambition for a more integrated regional health economy is not translated into a clear and deliverable strategic programme. This is caused by a lack of agreed long- term priorities, defined benefits realisation measures, and a comprehensive assessment of the opportunities and impacts of regional working. This could lead to limited strategic impact, duplication of effort, reduced collective influence across partner organisations, and an inability to deliver the scale of transformation required to improve outcomes, sustainability and value across the region. | Approved Terms of Reference; RJC annual work programmes; Regional Health Economy Subgroup; Regional Drive and Delivery Group; programme management support; regular reporting to sovereign Boards; development of regional business cases and opportunity assessments. | RJC Key Issues Reports; RJC work programme reports; Regional Drive and Delivery Group updates; subgroup work programme summaries; milestone reporting; Board update reports; review of decisions and actions. | Further assurance is needed on risk appetite, measurable outcomes, delegated authority, quantified opportunity and impact, benefits realisation, and how regional health economy priorities will be prioritised within available capacity. | Agree a small number of measurable regional outcomes; quantify opportunity and impact; clarify accountability and escalation routes; establish benefits realisation reporting; align subgroup reporting with the RJC work programme and 3A reporting cycle. | TBC | TBC | TBC | TBC |
| SR02 | Deliver timely and evidence-based regional | There is a risk that regional clinical service planning does not deliver timely, evidence-based and | Clinical Services Planning Subgroup; priority service workstreams for | Quality and performance dashboards; waiting list and demand data; | Further assurance is needed on clinical consensus, implementation | Define priority service changes, milestones and decision points; complete demand | TBC | TBC | TBC | TBC |

4

| Ref | Strategic objective | Strategic risk | Key controls in place | Sources of assurance | Assurance gaps | Further actions required | Exec Risk Owner | Mgt Support Lead | Current risk score | Target risk score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | clinical service planning. | sustainable decisions on the future configuration and delivery of priority services, including cancer, stroke, orthopaedics, ophthalmology, pathology and radiotherapy. This is caused by the complexity of securing agreement across organisations, insufficient pace of decision-making, capacity constraints, competing priorities, and challenges in translating strategic intent into actionable regional service models. This will lead to continued unwarranted variation in care, service fragility, workforce vulnerabilities, inequalities in access and outcomes, reduced quality and sustainability of services, and an inability to realise the benefits of regional working required to meet current and future | cancer, stroke, orthopaedics, ophthalmology and pathology; baseline service reviews; demand and capacity modelling; alignment to national standards; escalation through the RJC and Regional Drive and Delivery Group. | service reviews; workforce data; exception reports from priority programmes; clinical standards; business case status reports; Regional Drive and Delivery Group minutes and action logs. | capacity, workforce and capital dependencies, financial flows, cross-boundary pathways, programme management support, and whether plans are reducing variation and improving outcomes. | and capacity modelling for orthopaedics; strengthen oncology and cancer roadmap alignment with the National Cancer Programme; clarify stroke and ophthalmology delivery assumptions; align workforce, capital, digital and contracting dependencies. |  |  |  |  |

5

| Ref | Strategic objective | Strategic risk | Key controls in place | Sources of assurance | Assurance gaps | Further actions required | Exec Risk Owner | Mgt Support Lead | Current risk score | Target risk score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | population health needs. |  |  |  |  |  |  |  |  |
| SR03 | Ensure corporate enablers support regional delivery at pace and scale. | There is a risk that the Regional Joint Committee is unable to deliver its strategic ambitions for regional integration, service transformation and system sustainability. This is caused by the enabling infrastructure required to support regional delivery, including digital, data, workforce, organisational development, financial and contracting capabilities, not being developed at the pace, scale or maturity necessary to underpin regional models of care and ways of working. This will lead to delays in the implementation of regional priorities, reduced organisational readiness for transformation, an inability to realise the anticipated benefits of regional collaboration, inefficient use of resources, and a diminished capacity to improve population | Finance, contracting, data and digital workstreams; proposal to combine finance/contractin g and data/digital arrangements; workforce and OD collaboration; regional finance operating model discovery work; shared programme support arrangements; escalation through senior leadership structures. | Digital maturity and readiness assessments; finance operating model outputs; workforce plans; financial monitoring reports; contracting updates; dashboard development; delivery reports from enabling workstreams; gateway review outputs. | Assurance is limited on interoperability, reporting consistency, transformation capacity, affordability, management bandwidth, scope control, standardisation, and whether enabling plans are sufficiently integrated with clinical priorities. | Agree the future operating model for finance, contracting, data and digital workstreams; update Terms of Reference where required; produce a consolidated enabling plan linked to each regional priority; identify critical dependencies; report delivery confidence, affordability, capacity gaps and benefits. | TBC | TBC | TBC | TBC |

6

| Ref | Strategic objective | Strategic risk | Key controls in place | Sources of assurance | Assurance gaps | Further actions required | Exec Risk Owner | Mgt Support Lead | Current risk score | Target risk score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | outcomes, service resilience and long-term system sustainability. |  |  |  |  |  |  |  |  |
| SR04 | Promote research, innovation, and excellence to improve regional outcomes. | There is a risk that the region does not fully realise the benefits of its research, innovation and academic partnerships to drive transformational improvement in health and care outcomes. This is caused by an inability to translate research, innovation and life sciences opportunities, including those relating to cancer, cardiovascular care, digital innovation and academia-industry collaboration, into coordinated, scalable and sustainable service improvement at pace. This will lead to reduced opportunities to improve population outcomes, slower adoption of evidence-based innovation, diminished system productivity and resilience, and a reduced ability to attract investment, research funding, high- | Research, Innovation and Excellence Subgroup; emerging regional operating model; university and life sciences partnerships; innovation and training initiatives; inclusion of research and innovation within regional planning discussions. | Reports from research and innovation programmes; subgroup work programme updates; Welsh Government support for regional clinical trials; partnership updates; benefits realisation reporting; workforce and training metrics. | Limited assurance remains on pipeline maturity, implementation capacity, leadership capacity pending appointment, spread and adoption of innovation, alignment with regional clinical priorities, and measurable impact on service quality and outcomes. | Confirm the regional research and innovation operating model; complete appointment and mobilisation of regional leadership arrangements; develop an innovation pipeline with prioritisation criteria; identify adoption barriers; report measurable benefits and spread across the region. | TBC | TBC | TBC | TBC |

7

| Ref | Strategic objective | Strategic risk | Key controls in place | Sources of assurance | Assurance gaps | Further actions required | Exec Risk Owner | Mgt Support Lead | Current risk score | Target risk score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | calibre staff and strategic partners to the region. |  |  |  |  |  |  |  |  |
| SR05 | Maintain effective governance, accountability , and assurance for regional joint working. | There is a risk that the Regional Joint Committee is unable to provide effective leadership, oversight and assurance for the delivery of its strategic ambitions and regional programmes. This is caused by governance, accountability and assurance arrangements not maturing at the pace required to support collective decision-making, robust performance oversight, effective action management, timely escalation of issues and risks, and clear lines of responsibility across the regional partnership landscape. This will lead to reduced organisational and Board confidence, weakened oversight of regional priorities, delayed decision- making, ineffective management of risks and dependencies, reduced transparency | Approved and updated Terms of Reference; reporting to both Boards; committee action tracking; RJC PMO support; Regional Drive and Delivery Group; programme governance arrangements; annual self-assessment; internal audit advisory review and management response. | RJC risk register; internal audit advisory review; management response actions; action logs; subgroup work programme summaries; Board assurance reports; annual self-assessment and improvement actions. | Assurance gaps remain around subgroup Terms of Reference, discipline and consistency of subgroup work programme summaries, clarity of respective responsibilities, strategic risk ownership, escalation thresholds, and the maturity of the committee assurance framework. | Implement the internal audit management response actions: review subgroup Terms of Reference, develop the RJC work programme, strengthen subgroup work programme summaries, complete and approve the strategic risk register by October 2026, and align reporting with sovereign Board assurance needs. | TBC | TBC | TBC | TBC |

8

| Ref | Strategic objective | Strategic risk | Key controls in place | Sources of assurance | Assurance gaps | Further actions required | Exec Risk Owner | Mgt Support Lead | Current risk score | Target risk score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | and accountability, and an increased likelihood that intended benefits and outcomes from regional collaboration are not realised. |  |  |  |  |  |  |  |  |
| SR06 | Secure the external support and system alignment needed for major regional change. | There is a risk that the Regional Joint Committee is unable to secure the resources, policy support, stakeholder commitment and system-wide alignment necessary to deliver its long-term ambitions for regional transformation. This is caused by limited influence over external funding decisions, competing national and organisational priorities, uncertainty in capital and revenue investment, and insufficient alignment of partners, programmes and policy frameworks around a shared regional agenda. This will lead to delays or failure in delivering major service transformation programmes, including cancer, radiotherapy, orthopaedics, stroke | Engagement with Welsh Government, NHS Performance and Improvement, national programmes and partners; development of regional business cases; stakeholder engagement; alignment to ministerial priorities, IMTP planning, National Cancer Programme and national clinical standards. | Business case status reports; stakeholder feedback; funding decisions; IMTP submissions; National Cancer Programme engagement; programme support updates; exception reporting on dependencies and constraints. | Further assurance is needed on deliverability where changes depend on national funding, capital approval, revenue consequences, programme management support, data and digital alignment, or wider stakeholder agreement outside direct RJC control. | Make external dependencies explicit within reporting; escalate constraints early through the 3A route; agree contingency planning where critical assumptions are uncertain; secure national programme alignment and programme support for priority regional changes. | TBC | TBC | TBC | TBC |

9

| Ref | Strategic objective | Strategic risk | Key controls in place | Sources of assurance | Assurance gaps | Further actions required | Exec Risk Owner | Mgt Support Lead | Current risk score | Target risk score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | and other critical enabling infrastructure, resulting in reduced service sustainability, slower improvement in population outcomes, missed opportunities to realise the benefits of regional collaboration, and an inability to meet future health and care needs effectively. |  |  |  |  |  |  |  |  |

10

#### 12:05 PM, 10 Mins

## - RJC/45: RJC 2026/2027 Work

## Programme and Maturity Matrix

Abigail Harris (Swansea Bay UHB - CEO), Philip Kloer (Hywel Dda UHB - Chief Executive)

Attachments

RJC 45a RJC Work Programme 2026-2027.pdf RJC 45b RJC Subgroup Maturity Matrix.pdf

AGENDA ITEM/ISSUE

INTRODUCTIONS

Apologies

Declaration of Interests

LEARNING & GOVERNANCE

Minutes from Previous Meeting

Matters Arising and Table of Actions

Matters Arising not on Agenda

REGIONAL JOINT COMMITTEE WORK PROGRAMME

Regional Health Economy

Updated Regional Health Economy Terms of Reference agreed (for assurance and endrosement)

Regional Health Inequalities Action Plan agreed (for assurance and endrosement)

Regional Health Intelligence and Inequalities findings incorporated into strategic priorities and implementation roadmap (for endorsement/approval)

Progress report on preparatory work towards WHO Sub-Regional Health Network participation and associated learning opportunities (for assurance and endrosement)

RJC approval of draft long-term Regional Health Economy Strategic Plan.

Translate strategic plan into delivery plan, benefits framework and annual review cycle.

Explore and scope WHO Europe Regions for Health Network in-person visit to Wales with RJC members

Clinical Services Planning Group

Updated Clinical Services Planning Group Terms of Reference agreed (for assurance and endrosement)

Pathology Update - capital timeline, financial modelling options, service revenue implications, D&C baselining activity update (assurance and endorsement)

Renewed Orthopaedic Plans (for assurance and endrosement) - PID

Eye Care Plans (for assurance and endrosement) - PID

Regional Stroke Plans - Conslutant Rota (for assurance and endrosement) - PID

SWW Cancer Centre Update (6/7 Bunker)

Orthopaedics: develop strategic regional solution supporting 36-week waits by 2030 and Regional Surgical Hub response

Regional Cancer Services Proposal for dicsussion

Regional Cancer Services Proposal update and sense check

Regional Cancer Services Proposal for endorsement

Cellular Pathology: submit fully tendered business case to Welsh Government

South West Wales Cancer Centre: deliver radiotherapy capacity pathway including 5th Linac, future bunker capacity and seven-Linac model / satellite centre scoping

Data and Digital

Governance proposal for combining the Finance and Contracting and Data and Digital Subgrous

Ophthalmology system live, early analytics benefits realised

EPMA optimisation, AI pilots, cyber uplift delivered

Digital baseline, AI governance and national compact agreed

Finance and Contracting

Governance proposal for combining the Finance and Contracting and Data and Digital Subgrous

Finance and Contracting Renewed Plans Submitted for agreement

Discovery and design - understand, challenge and define

Workforce and OD

Regional governance and agreed roles/responsibilities established

Priority services & models, complete baseline workforce data analysis & benchmark identifies

Alternative service and workforce models/ solutions benchmarked/ identified/ appraised

Plans for joint workforce solutions and implement early actions for priority areas developed

Implement joint workforce solutions

Regional Leadership Development Offer - Roadmap agreed and shared

Discovery and needs assessment completed

Sponsors confirmed and cross HB governance agreed

Initial design options developed and reviewed

Roadmap agreed and shared

Research, Innovation, and Excellence

Revised governance arrangements in place

Review of both organisations R&D structures complete

Regional strategy and implementation plan update and sense check

Regional strategy and implementation plan

Appoint Regional Director for Research & Innovation

Regional Governance

RJC Internal Audit Report

Terms of Reference All Subgroups

RJC ToR Agreement Update

AGENDA ITEM/ISSUE

All Subgroups - AAA reports (including workprogramme summary reports) and SBARs

| SUBGROUP/ LEAD | 16-Apr-26 | 23-Jul-26 | 13-Oct-26 |
| --- | --- | --- | --- |
|  |  | CANCELLED |  |
| Chair(s) |  | x |  |
| All |  | x |  |
| Chair(s) |  | x |  |
| Chair(s) |  | x |  |
| Chair(s) |  | x |  |
| Regional Health Economy |  | x |  |
| Regional Health Economy |  | x |  |
| Regional Health Economy |  | x |  |
| Regional Health Economy |  | x |  |
| Regional Health Economy |  | x |  |
| Regional Health Economy |  | x |  |
| Regional Health Economy |  | x |  |
| Clinical Services Planning |  | x |  |
| Clinical Services Planning |  | x |  |
| Clinical Services Planning |  | x |  |
| Clinical Services Planning |  | x |  |

| Clinical Services Planning |  | x |  |
| --- | --- | --- | --- |
| Clinical Services Planning |  | x |  |
| Clinical Services Planning |  | x |  |
| Clinical Services Planning |  | x |  |
| Clinical Services Planning |  | x |  |
| Clinical Services Planning |  | x |  |
| Clinical Services Planning |  | x |  |
| Clinical Services Planning |  | x |  |
| Data and Digital |  |  |  |
| Data and Digital |  | x |  |
| Data and Digital |  | x |  |
| Data and Digital |  | x |  |
| Finance and Contracting |  |  |  |
| Finance and Contracting |  | x |  |
| Finance and Contracting |  |  |  |
| Workforce and OD |  | x |  |
| Workforce and OD |  | x |  |
| Workforce and OD |  | x |  |
| Workforce and OD |  | x |  |

| Workforce and OD |  | x |  |
| --- | --- | --- | --- |
| Workforce and OD |  | x |  |
| Workforce and OD |  | x |  |
| Workforce and OD |  | x |  |
| Workforce and OD |  | x |  |
| Workforce and OD |  | x |  |
| Research, Innovation and Excellence |  | x |  |
| Research, Innovation and Excellence |  | x |  |
| Research, Innovation and Excellence |  | x |  |
| Research, Innovation and Excellence |  | x |  |
| Research, Innovation and Excellence |  | x |  |
|  |  | x |  |
| Regional Governance |  | x |  |
| Regional Governance |  | x |  |
| Regional Governance |  | x |  |
|  |  | x |  |
|  |  | x |  |

| 05-Feb-27 | 15-Apr-27 | 22-Jul-27 | 14-Oct-27 | 13-Jan-28 |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

| Q1 April 28 | Q2 July 28 | Q3 October 28 |
| --- | --- | --- |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

|  |  |  |
| --- | --- | --- |

|  |  |  |
| --- | --- | --- |
|  |  |  |

,

c

RJC Subgroup Maturity Matrix

| Subgroup | ToRs agreed by Sub- Group | Programme Defined | Ambition Agreed | Agreed Subgroup Work programme | Objectives/ Outcomes Agreed | Resources Agreed* | Risks Understood | Dependencies Understood | Key Milestones | Detailed Plans |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Regional Health Economy |  |  |  |  |  |  |  |  |  |  |
| Clinical Services Planning |  |  |  |  |  |  |  |  |  |  |
| Workforce & OD |  |  |  |  |  |  |  |  |  |  |
| Data and Digital |  |  |  |  |  |  |  |  |  |  |
| Finance and Contracting |  |  |  |  |  |  |  |  |  |  |
| Research, Innovation & Excellence |  |  |  |  |  |  |  |  |  |  |

*resources agreed and understood at a subgroup level but issues persist at a programme/project delivery level

Page 244

8

12:15 PM, 0 Mins

## 8 - Minutes and Actions, Closing Remarks and Future Meetings

#### 8.1	12:15 PM, 5 Mins

## - RJC/46: Minutes of Previous Meeting held on 16th April 2026

Jan Williams (Swansea Bay UHB - Corporate), Neil Wooding (Hywel Dda UHB - Chair of Hywel Dda University Health Board)

Attachments

RJC 46 DRAFT Minutes Swansea Bay and Hywel Dda University Health Boards Re~.pdf

Hywel Dda University Health Board and Swansea Bay University Health Board

Regional Joint Committee Meeting DRAFT Minutes

Beacon Centre of Enterprise, Dafen, Llanelli

Thursday 16th April 2026 9.30am-12.30pm Conference Room,

| SWANSEA BAY UNIVERSITY HEALTH BOARD |  |  |
| --- | --- | --- |
| Present: |  |  |
| Jan Williams | (JW) | Chair (Joint Chair of the meeting) |
| Jean Church | (JC) | Independent Member |
| In Attendance: |  |  |
| Abigail Harris | (AH) | Chief Executive |
| Marie Davies | (MD) | Executive Director of Planning and Partnerships |
| Deb Lewis | (DL) | Chief Operating Officer |
| Matt John | (MJ) | Director of Digital |
| Claire Osmundsen-Little | (COL) | Interim Finance Director |
| Hugo Van Woerden | (GR) | Interim Executive Director of Public Health |
| Kimberley Cann | (KC) | Consultant in Public Health |
| Apologies: |  |  |
| Andrew Griffiths | (AG) | Independent Member |
| Steve Spill | (SS) | Vice Chair |
| Christine Morrell | (CM) | Executive Director of Therapies and Health Science |
| Tina Ricketts | (TR) | Executive Director of Workforce and Organisational Development |
| Hazel Lloyd | (HL) | Director of Corporate Governance |

| HYWEL DDA UNIVERSITY HEALTH BOARD |  |  |
| --- | --- | --- |
| Present: |  |  |
| Neil Wooding | (NW) | Chair |
| Sarah Harraway | (SH) | Independent Member |
| In Attendance: |  |  |
| Philip Kloer | (PK) | Chief Executive |
| Andrew Carruthers | (AC) | Chief Operating Officer |
| Ardiana Gjini | (AG) | Executive Director of Public Health |
| Lisa Gostling | (LG) | Deputy Chief Executive and Executive Director of Workforce and Organisational Development |
| Huw Thomas | (HT) | Executive Director of Finance |

Page 1 of 11

| Lee Davies | (LD) | Executive Director of Strategy and Planning |
| --- | --- | --- |
| Mark Henwood | (MH) | Executive Medical Director |
| Joanne Wilson | (JWi) | Director of Corporate Governance/Board Secretary |
| Anthony Tracey | (AT) | Director of Digital |
| Apologies: |  |  |
| Maynard Davies | (MD) | Independent Member |
| Chantal Patel | (CP) | Independent Member |
| Eleanor Marks | (NW) | Vice Chair (Joint Chair of the meeting) |

| Other Organisations |  |  |
| --- | --- | --- |
| In Attendance: |  |  |
| Samia Edmonds (Observer Member) | (SE) | Planning Programme Director, Health and Social Services Group, Welsh Government |
| Mary Sherwood | (MS) | Fairer Future (Poverty Workshop Only) |
| Siôn Charles | (SC) | RJC Head of Strategy and Service Planning |
| Sophie Marr | (SM) | RJC Senior Project & Business Manager (Secretariat) |
| Carolyn Dart | (CD) | RJC Senior Project Support Officer |
| Apologies: |  |  |
| Carl Cooper (Associate Member) | (CP) | Chair, Powys Teaching Health Board |
| Jeremy Griffith | (JG) | Director of Operations, Health and Social Care Early Years, Welsh Government |

| WORKSHOP SESSION |  |  |
| --- | --- | --- |
| RJC/20 | WHAT DRIVES POVERTY? IMPLICATIONS ACROSS RJC PORTFOLIOS NW introduced Mary Sherwood (MS) to the Committee as someone highly recommended with a background and specialisation in poverty and inequality in the UK, advising that the workshop session would consider the drivers of poverty and how these interact with the work carried out by both Health Boards. MS commenced the workshop by asking Members to discuss one of two questions in groups: - We should focus on reducing poverty because that will improve health - We should focus on improving health because that will reduce poverty |  |

Page 2 of 11

|  | Groups were asked which feels most accurate and possible? Define the terms. Justify your choice of group and what success measures would you use? MS asked the groups to define who the “we” is – whether that is a group you are thinking of or the whole of society; define poverty and to define health. The group could also discuss a third choice of: 3. We should focus on because that will The group who discussed Question 1 shared their thoughts on this being a generational issue with tackling societal challenges particularly around education, basic life skills and access to good food through a collective society wide approach being paramount. The group discussed an emphasis on early education as a key lever for long term change. Success would likely be measured through educational attainment and improved equity. A major challenge was identified as who “we” are. The group who discussed Question 2 explored the relationship between health, poverty and inequality focusing on practical actions that organisations can take. These included the argument that improving health can directly reduce poverty as better health leads to improved employment, life choices and economic outcomes. A key issue is unequal access to healthcare services particularly among disadvantaged groups, and improving access would be a key measure of success. Large organisations can influence poverty through various measures including employment, local procurement and staff acting as community ambassadors. Early intervention is critical, especially childhood health and early years support to prevent long term inequality. The group spoke about how defining poverty is multi-dimensional and includes a lack of resources and other barriers to achieving potential, not only income. The group who discussed Question 3 spoke about how the health boards have some influence on poverty with hiring practices but are not consistently designing services to be “poverty aware”. One example used would be outpatient appointments as people on hourly pay or insecure work may lose income by attending appointments. Services are often designed by assuming people can |  |
| --- | --- | --- |

Page 3 of 11

|  | afford to take time off from work, which disadvantages lower income groups. There are concerns that waiting lists may disproportionately include poorer patients as it is thought more wealthy individuals increasingly opt for private care. The group concluded that the health service often unintentionally causes disadvantage to poorer people due to how services are designed and called for a more nuanced “poverty aware” approach that considers both economic and wider wellbeing factors. MS spoke about the poverty rates and the drivers around low income and high housing costs. To have a high standard of living in the UK the consensus is you should be able to afford certain things including a special occasion and a hobby. Society judges how people living in poverty spend their money. MS presented a scenario to the Committee to consider an example of single parent family with two teenage children and to work out a budget for this family. The group discussed the need to include budgeting for birthdays and Christmas, as well as domestic emergencies and debt repayment, noting that if a homeowner takes out a loan the APR will be much lower than someone living in rented accommodation. Having a low income and high living costs means that people are missing out on enrichment in their lives and are not able to connect with the wider community if they are not able to have hobbies. The stress and anxiety levels are constant, worrying about paying bills and not having any money for “luxuries”. Poverty means lives with low enrichment, low inspirational experiences, low connection to community and low social and support networks. MS was thanked for her informative presentation helping the Committee to explore more fully its role in relation to poverty and the contribution Health Boards can make. |  |
| --- | --- | --- |

Page 4 of 11

| PART 1: PRELIMINARY MATTERS |  |  |
| --- | --- | --- |
| RJC/21 | Welcome and Apologies |  |
|  | JW and NW welcomed members, attendees and observers to the meeting. Apologies were received and noted as recorded. Members were reminded of the Committee’s decision-making principles and the expectation that updates are framed using the Triple A (Alert, Advise, Assure) methodology, with clear mitigations where required. |  |
| PART 2: TO RECEIVE SUB-GROUP ASSURANCE REPORTS |  |  |
| RJC/22 | Regional Clinical Services Planning Subgroup - Pathology Programme Update An update was provided on progress across the Regional Clinical Service Planning programmes, with particular focus on pathology, vascular services, orthopaedics and stroke. Key points included: - Continued progress made on the Regional Cellular Pathology Programme, with risks being actively managed and ongoing engagement with Welsh Government. - Vascular service alignment remains subject to national considerations, with monitoring of dependencies in place. - Orthopaedic work is progressing on a regional basis, particularly around workforce and Patient Tracking List management. - Stroke services are entering a critical phase, with emerging national standards recently issued and the need for clarity on the current baseline position against the standards. Summary of Discussion Members welcomed the progress to date and emphasised: - The need for clearer baseline data to support assurance and future decision-making, particularly for stroke services. - The importance of not undermining local public consultations within HDdUHB while still maintaining a strategic regional view, in particular regional planning for stroke services. |  |

Page 5 of 11

|  | - That narrative updates must increasingly be supported by measurable outcomes and shared intelligence. Actions/Agreements Agreement: Members endorsed the direction of travel for the Regional Clinical Services Planning Sub-Group, recognising the progress made to date. Agreement: Members supported the proposal to pause the Urgent and Emergency Care (UEC) programme for 2026/27; consolidate diagnostics activity under the Pathology programme; and actively monitor the situation in relation to regional priorities and to re-start programmes when resources allow. ACTION: RJC PMO supported by Local Public Health Teams, to produce a clear baseline position on current stroke services (projections, activity, outcomes) across both Health Boards and ensure this demonstrates how HDdUHB CSP proposals benefit the regional service model, using baseline data. To include as a presentation on the RJC agenda for July 2026. ACTION: AC to provide a briefing outside of the RJC meeting to SE outlining planned regional work to progress Urgent and Emergency Care improvement as an alternative, given the closure of the formal programme. ACTION: DL to investigate the progress on updating the Vascular Long-Term Agreement. |  |
| --- | --- | --- |
| RJC/23 | Regional Health Economy Subgroup Update The Committee received an update on progress across the Regional Health Economy programme, structured around the Four Ps: People, Place, Procurement and Partnerships. Key developments included: - Progress on Healthy Weight, food systems work and Public Services Boards (PSB) engagement. - Ongoing work with Public Health Wales (PHW) on inequalities profiles and analytical support. - Alignment with population health, prevention and wellbeing economy approaches. Summary of Discussion Members welcomed the direction of travel and emphasised: - The importance of quantifying opportunity and impact to support system investment arguments. |  |

Page 6 of 11

|  | - The reliance on national analytical capacity and the need to prioritise effectively. - It was agreed to amend the Terms of Reference to include providing strategic leadership and developing strategies for approval as well as including points on national policy initiatives and events. Actions/Agreements Agreement: The Committee noted the continued progress made across all programme areas. Agreement: The Committee approved the REI Terms of Reference, subject to the changes agreed. |  |
| --- | --- | --- |
| RJC/24 | Data and Digital Subgroup Update An update was provided on the emerging regional digital vision, emphasising capability-based development rather than system-specific solutions. Key themes included interoperability, Artificial Intelligence (AI), data sharing, workforce readiness and managing legacy system constraints. Summary of Discussion Members stressed the need to: - Translate strategic intent into time-bound deliverables. - Avoid locking in decisions that limit future regional capability. - Align digital priorities with poverty, access and inequality considerations. - Understand the potential role of the Centre for Social Innovation, University of Wales Trinity Saint David (UWTSD) in supporting complex system challenges, including digital inclusion and poverty‑related issues. It was suggested that a future RJC seminar or workshop could explore how the Centre might support RJC priorities. Chairs agreed this should be considered further from a governance perspective. - Further investigation is required to clarify the contractual arrangements with CGI ahead of any regional work where they may be involved. Actions/Agreements |  |

Page 7 of 11

|  | Agreement: The Committee supported the approaches outlined in the report. |  |
| --- | --- | --- |
| RJC/25 | Research, Innovation and Excellence Subgroup Update An update was provided on progress towards a regional approach to research and innovation, including oncology research and governance proposals. Summary of Discussion Members discussed governance proportionality, university involvement, strategic leadership and the need for a clearer articulation of ambition and benefit. Actions/Agreements Action: The Committee supported the revised regional research, innovation and excellence operating model and Terms of Reference (ToR) subject to amendments to include reference to: strategic leadership and developing strategies for approval; and reference to national policy initiatives and events. Approval via RJC Chairs on behalf of the Committee. |  |
| RJC/26 | Workforce and OD Subgroup Update An update was provided on Occupational Health joint working, collaborative workforce planning, leadership development, Electronic Staff Record (ESR) alignment and legislative readiness. Summary of Discussion Members noted: - The scale and pace of ambition and the importance of prioritisation. - The significant workforce implications of digital transformation and the importance of ensuring alignment between digital initiatives and workforce planning. - The importance of aligning regional workforce activity with Mid Wales where appropriate. Actions/Agreements Agreement: The Committee noted the continued progress being made. |  |

Page 8 of 11

|  | ACTION: LG, through the Workforce and OD Subgroup, to identify priority specialties and critical workforce risks requiring accelerated regional action, and to report these back to the RJC. |  |
| --- | --- | --- |

| PART 3: GOVERNANCE |  |  |
| --- | --- | --- |
| RJC/27 | RJC 2026/27 Work Programme The Committee discussed priorities for the coming year, including Regional Health Economy, Research & Innovation, Cellular Pathology and Diagnostics; noted that the regional work programme had been developed based on discussions at the Committee in January 2026 and that the plan had been agreed by both Health Boards through their Annual Planning processes and governance. Summary of Discussion Members emphasised the need to: - Demonstrate tangible progress. - Be explicit about prioritisation alongside existing commitments. - Align with Welsh Government expectations. - Take a more explicit, RJC‑level view of strategic risks, distinct from individual programme or subgroup risks. Members agreed this should focus on a small number of system‑level risks (including regional effectiveness and credibility) and that further consideration should be brought back to the Committee. Actions/Agreements: ACTION: JWi and HL to work with RJC Chairs, to develop and present back to the RJC a proportionate and pragmatic RJC strategic risk register, identifying a small number of system‑wide level of risks aligned to RJC objectives. |  |
| RJC/28 | Outcome of Committee Annual Self-Assessment Exercise The Committee received the results of the self-assessment exercise. Members welcomed the findings and agreed this should form part of the assurance and improvement narrative to Boards and Welsh Government. |  |

Page 9 of 11

|  | Actions/Agreements: Agreement: the Committee agreed the actions to be taken to improve its effectiveness. ACTION: JWi to formally share the RJC Committee Annual Self‑Assessment with Welsh Government, including submission to the Cabinet Secretary, as part of ongoing assurance and reporting arrangements. ACTION: the RJC PMO to forward plan a collective conversation on the performance of the Committee at a future RJC meeting. |  |
| --- | --- | --- |
| RJC/29 | Draft RJC Terms of Reference Members considered the proposed updates to the RJC Terms of Reference, including: - The need for the Terms of Reference to explicitly reference the RJC’s annual self‑assessment as part of its continuous improvement, governance and assurance responsibilities, including its role in evidencing maturity and effectiveness to Welsh Government. - For the Terms of Reference to more clearly reflect the role of the RJC Chairs in maintaining a formal reporting link to Welsh Government, including submission of assurance products (such as the Committee self‑assessment) to the Cabinet Secretary. - For the Terms of Reference to better articulate the Committee’s responsibility for overseeing system‑wide and strategic matters (including assurance beyond individual sub‑groups), consistent with the Ministerial Direction and expectations of a Regional Joint Committee. - For the Terms of Reference to be supported by clearer, outcome‑focused objectives. This included agreement that Directors of Governance should work with the Leads for the Finance & Contracting Subgroup and the Workforce & OD Subgroup to develop and align objectives within the RJC Terms of Reference, ensuring consistency across governance, finance and workforce responsibilities. It was agreed that the required minor consequential changes would be made to reflect the above discussions, with final revisions to be agreed by the Chairs outside of the meeting rather than needing to be brought back to a future RJC meeting. |  |

Page 10 of 11

|  | Actions/Agreements: ACTION: JWi and HL to work with the RJC Chairs, to finalise the amendments to the RJC Terms of Reference prior to Health Boards approval, reflecting the discussion held. |  |
| --- | --- | --- |
| PART 4: MINUTES AND ACTIONS, CLOSING REMARKS, & DATES OF RJC NEXT MEETINGS |  |  |
| RJC/30 | Minutes of Previous RJC Meeting held on 22 January 2026, and Extraordinary RJC Meeting held on 16 February 2026 The minutes of the previous meetings were approved as a true and accurate record. |  |
| RJC/31 | Table of Actions All actions were noted as either complete or appropriately closed. |  |
| RJC/32 | RJC Committee Annual Work Plan Received for information. |  |
| RJC/33 | Closing Remarks The Chairs thanked Members for a constructive and wide-ranging meeting and reflected on the increasing maturity of the regional collaboration. JW requested that Members use the lessons learned in the workshop when developing services. Actions/Agreements: Agreement: HT and AG to work with their respective subgroups, to consider how they can provide services that support the work against poverty as an organisation. ACTION: HT to ask the Data and Digital Subgroup to consider what poverty-related data can be appropriately and ethically used to inform service planning and to ask Directors of Public Health to support, where appropriate. |  |
| RJC/34 | Dates of Next RJC Meetings: - 23rd July 2026 - 13th October 2026 - 7th January 2027 |  |

The meeting closed at 12:30

Page 11 of 11

#### 8.2	12:20 PM, 5 Mins

  - - RJC/47: Table of Actions		Jan Williams (Swansea Bay UHB -

Corporate), Neil Wooding (Hywel Dda UHB - Chair of Hywel Dda University Health Board)

Attachments

RJC 47 Regional Joint Committee Table of Actions 13102026.pdf

Table of Actions from Hywel Dda University Health Board and Swansea Bay University Health Board Regional Joint Committee Meeting 16th April 2026

| Minute Ref. | Action | Lead | Timescale | Progress | RAG |
| --- | --- | --- | --- | --- | --- |
| RJC/22 | RJC PMO supported by Local Public Health Teams, to produce a clear baseline position on current stroke services (projections, activity, outcomes) across both Health Boards and ensure this demonstrates how HDdUHB CSP proposals benefit the regional service model, using baseline data. To include as a presentation on the RJC agenda for July 2026. | RJC PMO | Oct 2026 (July 2026 RJC meeting stood down) | Complete. On agenda for RJC 13/10/26 |  |
|  | AC to provide a briefing outside of the RJC meeting to SE outlining planned regional work to progress Urgent and Emergency Care improvement as an alternative, given the closure of the formal programme. | AC | Oct 2026 (July 2026 RJC meeting stood down) |  |  |
|  | DL to investigate the progress on updating the Vascular Long-Term Agreement. | DL | Oct 2026 | Complete. Vascular Programme no longer included within the |  |

|  |  |  | (July 2026 RJC meeting stood down) | Clinical Services Planning Subgroup Work Programme. Action progressing through Regional Vascular Network Programme |  |
| --- | --- | --- | --- | --- | --- |
| RJC/26 | LG, through the Workforce and OD Subgroup, to identify priority specialties and critical workforce risks requiring accelerated regional action, and to report these back to the RJC. | LG | Oct 2026 (July 2026 RJC meeting stood down) |  |  |
| RJC/27 | JWi and HL to work with RJC Chairs, to develop and present back to the RJC a proportionate and pragmatic RJC strategic risk register, identifying a small number of system-wide levels of risks aligned to RJC objectives. | JWi & HL | Oct 2026 (July 2026 RJC meeting stood down) | Complete - RJC Strategic Risk Register to be presented to the RJC meeting on 13 October |  |
| RJC/28 | JWi to formally share the RJC Annual Self Assessment with Welsh Government, including submission to the Cabinet Secretary, as part of ongoing assurance and reporting arrangements. RJC PMO to forward plan a collective conversation on the performance of the Committee at a future RJC meeting. | Jwi RJC PMO | Oct 2026 (July 2026 RJC meeting stood down) Oct 2026 (July 2026 RJC meeting stood down) | Complete – e-mail sent sharing the RJC Annual Self Assessment on 8 May 2026 Complete. Forward planned to a future RJC agenda |  |

| RJC/29 | JWi and HL to work with the RJC Chairs, to finalise the amendments to the RJC Terms of Reference prior to Health Boards approval, reflecting the discussion held. | JWi & HL | Oct 2026 (July 2026 RJC meeting stood down) | As part of the scheduled annual review of the RJC Terms of Reference and those of its Subgroups, the RJC Terms of Reference will be presented to the RJC on 13 October 2026 for agreement, prior to seeking respective Health Board approval |  |
| --- | --- | --- | --- | --- | --- |
| RJC/25 | The Committee supported the revised regional research, innovation and excellence operating model and Terms of Reference (ToR) subject to amendments to include reference to: strategic leadership and developing strategies for approval; and reference to national policy initiatives and events. Approval via RJC Chairs on behalf of the Committee. | NW & JW | Oct 2026 (July 2026 RJC meeting stood down) | As part of the scheduled annual review of the RJC Terms of Reference and those of its Subgroups, the REI Terms of Reference will be presented to the RJC on 13 October 2026 for approval |  |

Key

| Initials | Name |
| --- | --- |
| AC | Andrew Carruthers |
| LD | Lee Davies |
| MD | Marie Davies |
| SE | Samia Edmonds |
| RE | Richard Evans |
| AG | Ardiana Gjini |

| LG | Lisa Gostling |
| --- | --- |
| MH | Mark Henwood |
| MJ | Matt John |
| DL | Deb Lewis |
| HL | Hazel Lloyd |
| GR | Gill Richardson |
| TR | Tina Ricketts |
| HT | Huw Thomas |
| AT | Anthony Tracey |
| JW | Jan Williams |
| JWi | Jo Wilson |
| NW | Neil Wooding |

#### 8.3	12:25 PM, 5 Mins

  - - RJC/48: Closing Remarks		Jan Williams (Swansea Bay UHB -

Corporate), Neil Wooding (Hywel Dda UHB - Chair of Hywel Dda University Health Board)

#### 8.4	12:30 PM, 0 Mins

  - - RJC/49: Date of Next RJC Meetings:	Jan Williams

(Swansea Bay UHB -

Corporate), Neil Wooding (Hywel Dda UHB - Chair of Hywel Dda University Health Board)

-5 February 2027

-15 April 2027