| Meeting Date | 12 December 2023 |  | Agenda Item |  |  | 4.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Management Report |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Interim Director of Corporate Governance |  |  |  |  |  |
| Presented by | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to inform the Workforce OD & Digital Committee of the risks within the Health Board Risk Register (HBRR) assigned to the Committee for scrutiny. |  |  |  |  |  |
| Key Issues | - The HBRR was last received by the Workforce OD & Digital Committee (WODC) in July 2023. - Since then risks have been subject to update by Executive Directors on a monthly basis. The HBRR for Oct 2023 was received by the Board in November 2023. This paper presents an extract of risks assigned to the WODC from that register. - The number of risks overseen by Workforce OD & Digital Committee is six in open session (an additional sensitive risk has been identified for review within closed session). |  |  |  |  |  |
|  | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Workforce OD & Digital Committee. - CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any. |  |  |  |  |  |

HEALTH BOARD RISK REPORT

- INTRODUCTION

The purpose of this report is to inform the Workforce OD & Digital Committee of the risks within the Health Board Risk Register (HBRR) assigned to the Committee for scrutiny.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular HBRR update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

Risk Register management is supported by a Risk Management Group (RMG) which meets quarterly and is responsible for overseeing the operational management of risk, ensuring local systems and processes are in place and are operating effectively to ensure appropriate reporting and escalation. The Group last met in July 2023.

Additionally, a Risk Scrutiny Panel is responsible for ensuring there is an appropriate and robust risk management system in place and working throughout the organisation. It is responsible for moderating new risks and risks escalated to the Health Board Risk Register (HBRR) and Board Assurance Framework (BAF) and recommending and advising the Management Board on the escalation and de-escalation of risks. The Panel last met in October 2023.

2.2 Risk Appetite

Risk appetite and tolerance provide clarification on the level of risk the Board is prepared to accept.

The health board approved a risk appetite statement in November, setting out a new approach to expressing the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, requiring risks scoring 16 or above to be overseen at committee level. The mechanism for reporting risk is developing to support this for board and committee updates.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

- GOVERNANCE AND RISK

3.1 Management of Health Board Risk Register (HBRR)

The HBRR was last received by the Workforce OD & Digital Committee (WODC) in July 2023. Since then risks have been subject to update by Executive Directors on a monthly basis. The full HBRR for October 2023 was received by the Board in November 2023. This paper is based on an extract from the same HBRR as attached at Appendix 1.

The number of risks overseen by Workforce OD & Digital Committee in open session is now six:

- HBR 3	Workforce Recruitment of Medical & Dental Staff

- HBR 27	Digital Transformation to Deliver Sustainable Services

- HBR 36	Electronic Patient Record (Paper Record Storage)

- HBR 37	Operational & Strategic Decisions are not Data Informed

- HBR 51	Nurse Staffing Levels Act

- HBR 90	GDPR Subject Access Requests

In addition, the following risk is deemed sensitive and will be overseen in closed session:

- HBR 60	Cyber Security

A further two risks are overseen by other Committees, but reported to the Workforce OD & Digital Committee for information:

- HBR 81 	Midwifery: Critical Staffing Levels

- HBR 82 	Closure of Burns Service

The profile of risk scores for seven risks assigned to WODC is as follows:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 |
| --- | --- | --- | --- | --- | --- |
| Number of Risks | 1 | 0 | 3 | 3 | 0 |

3.2 Risks Exceeding Appetite

Section 2.2 above indicated the risk level thresholds associated with the health board risk appetite statement approved in November 2022. There are 4 risks currently meeting or exceeding the Health Board’s appetite thresholds, for which action is required so that they may be reduced to acceptable levels. The tables below highlight recent changes / actions of note since the last meeting of the Committee for those risks that are currently meeting or exceeding the thresholds:

| HBR3: Workforce Recruitment Risk of failure to recruit medical & dental staff |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Workforce and Operational Development | 20 | 20 | 12 |  |
| Ongoing Actions: Action 1: Medical training initiatives pursued in a number of specialties to ease junior doctor recruitment Action 2: The Medical Workforce Board continues to monitor recruitment and junior doctor’s rotas. Action 3: Continue to recruit internationally. Action 4: Continue to work with head hunters (Target Date: 31/03/2024) Additional Notes/Updates: It was previously reported to the Committee that the costs associated with overseas recruitment had become more visible in the last financial year once central reserves were not able to keep pace with the changes to how the Health Board recruits due to UK market forces. The introduction of the single lead employer has further complicated this element. Since last meeting, an allocation of £350K had been made available to supplement funds from Month 4 onwards. It has been indicated that this is unlikely to be sufficient but there are non-recurring underspends in the WOD budget which will mitigate any likely overspends in this area for the remainder of this financial year. The stability of this funding however needs to be resolved for the next financial year. |  |  |  |  |

| HBR 51: Non Compliance with Nurse Staffing Levels Act (2016) There is a risk that we might not be able to maintain safe staffing levels due to staff unavailability, vacancies and sickness levels. The potential impact of this maybe avoidable harm, suspension of services, non-compliance with the Nurse Staffing Act. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Executive Director of Nursing | 20 | 16 | 12 |  |
| Ongoing Actions: - Action 1 (monthly ongoing): Student Streamlining and Overseas recruitment (Target Date: 31/12/2023) - Action 2 (expanded): Review of workforce, considering more diverse skill mix, including development of Band 3 and Band 4 roles. Bi-annual re-calculations of inpatient wards have resulted in the addition of Band 3 and 4 roles within the NSA templates. These posts are being recruited into but there is a need for training and supervision for these new posts. (Target Date: 31/12/2023 refreshed) Rationale for assessment at October 2023: - Pressures at Morriston and Singleton Hospitals remain high. There were 27 areas with staff unavailability over 40% across all service groups, during roster period 27th August to 23rd September 2023. (Breakdown of service groups: MH – 4, NPTSH – 11, MH/LD – 10, PCT – 2) - For comparison, previous reporting periods: 30th July to 26th August (includes school holiday time and CAMHS team) had 30 areas; 2nd July to 29th July 2023 had 21 areas. - Nurse vacancies reported through ESR on 19th September 2023 were 299 Band 5 and 171 Band 2; 23rd October were 229 Band 5 and 169 Band 2. - Skill mix related to internal promotion, newly qualified and international nurses recruitment and subsequent induction plans continues to impact on wards, although to a lesser extent than 2-3 months ago. New/Refreshed Controls & Actions Taken include: - Workforce Plans have been developed by Service Group Nurse Directors & each Service Group to agree staffing, with consideration of all reasonable steps. - Workforce planning & redesign, training and development: Recruitment and retention continues. A Health Board Workforce Group has been set up and this links with the Health Education & Improvement Wales (HEIW) Retention Workstream, The Health Board representatives on the HEIW Group are Associate Head of Human Resources, Recruitment and Retention Manager and Matron (Corporate Recruitment). - Work assessing the impact of the 'Team around the Person' is underway currently led by HEIW. - Patient Information available on all Section 25B wards; Service Groups have access to all HEIW documents via a SharePoint. - SafeCare has been implemented. An All Wales Standard Operating procedure has been supported by All Wales NSA Group and remains a working document as understanding evolves. Support has been given to help embed the system into everyday use. Use of SafeCare linked to daily staffing huddles. - The Health Board Nursing and Midwifery Safe Staffing Assurance and Improvement Group (NMSSAIG – formally the Nurse Staffing Act Steering Group, amended July 2023) meets on a bi-monthly basis, ensuring risks from all service groups are represented at each meeting and escalated appropriately as required. This group is chaired by the Associate Director of Nursing and reports to Nursing and Midwifery Board and this Committee. Terms of reference are agreed, and membership extended to provide further assurance and a forum for learning and improvement. - Service Group risk assessments have been updated and segregated into different areas for clear escalation of any risks, supporting clearer governance. Additional Notes/Updates: Next bi-monthly NMSSAIG (November 2023) will further discuss reported risks and will look to separate risk into areas, for example: Section 25B wards only in Mental Health & Learning Disabilities (MHLD) Service Group. Surgical re-design is planned within MHLD Service Group – phased implementation starting from w/c 5th November 2023. Successful recruitment of international nurses (for adults, paediatric and neonatal areas) and student streamlining has resulted in decreased vacancies. Reported vacancies above are higher than current position due to time taken to on-board and update ESR reporting. |  |  |  |  |

| HBR 90: Non-compliance with UK-GDPR Article 15 regarding Subject Access Requests (SARs), along with other health records requests for disclosure of personal data The Health Board does not have adequate resources to deal with the sustained increase in volume and complexity of subject access /access to health records requests received from requestors. The ICO are already involved with a number of breaches and complaints in this area and there is the potential for future enforcement action if significant improvements are not made. Misfiling and redaction are major issues for Health Records, IG and Health Professionals. SAR breaches have led to successful compensation claims and media interest. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Digital | 16 | 16 | 12 |  |
| Actions: - Action 1: Implement key tasks outlined within the action plan within agreed timescales (Target date: April 2024) - Action 2: Data Protection Officer to Review all Subject Access Request documentation across the Health Board (Target date: End December 2023) Additional Notes/Updates: Following interview in August, the new Subject Access Request lead start date was agreed for 30th October 2023. |  |  |  |  |

Further detail on the above risks can be found at Appendix 1.

In addition, HBR50 Cyber Risk exceeds the Board’s risk appetite with a score of 20 currently. The full risk entry is reported separately within Closed session to the Committee.

3.3 Other Risks Assigned to this Committee

When the Board’s risks appetite was agreed in November 2022, it was the Board’s aspiration that thresholds could be reduced in the future. In view of this, additional risks assigned to this Committee which are not currently meeting the appetite threshold are presented below for information:

| HBR 27 Digital Transformation Inability to deliver sustainable clinical services due to lack of Digital Transformation. There are insufficient resources to: - Invest in the delivery of the ABMU Digital strategy, - Support the growth in utilisation of existing and new digital solution - Replace existing technology infrastructure and the end of its useful life. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Digital | 16 | 20 | 12 |  |
| Ongoing Action: Continue to develop the 10 year investment plan that has been submitted to Welsh Government, which will inform the Health Board IMTP submission. (Target Date: 31/12/2023 refreshed) Additional Notes/Updates: An assessment was completed of the impact of COVID on the resources required to support the increase in devices and software and the change in complexity of the support model required. This highlighted the need for four additional on-site engineers and two service desk staff. The Head of Service Delivery has raised an SBAR. It was agreed within Digital Services to review the score after the end of the financial year. |  |  |  |  |

| HBR 36 Paper Record Storage Lack of a single electronic record means there is greater reliance on the provision of the paper record. If we fail to provide adequate storage facilities for paper records, then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. There is an increased fire risk where medical records are stored outside of the medical record libraries. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Digital | 16 | 20 | 9 |  |
| Ongoing Actions (targets refreshed): - Action 1: Re-develop a joint outline Business Case for centralisation of the health records and the scanning model. (Target date: 30/11/2023 refreshed while awaiting building costs for new centralised unit which has been found. Once costs are realised the business case can be re-submitted to Business Case Assurance Group). - Action 2: Welsh Government sign off for long term conditions retention of records (Target Date: 29/11/2023) Additional Notes/Updates: New targets and milestones are to be developed. |  |  |  |  |

| HBR 37 Operational and strategic decisions are not data informed - Business intelligence and information already available is not utilised - Users are unable to access the information they require to make decisions at the right time - Gaps in information collection including patient outcome measures |  |  |  |  |
| --- | --- | --- | --- | --- |
| Exec Lead | Current Rating | Appetite Threshold | Target Rating | Change |
| Director of Digital | 12 | 20 | 8 |  |
| Actions Completed: - Establishment & delivery of data literacy programme educating users on data concepts, skills and tools. - Establishment of certified training programme for trained users to create their own dashboards. - Commencement of Digital and Data Module for Managers. New Actions: - Additional development of self-service dashboards (Target: 31/01/2024) - Create Community of Practice for Power BI knowledge sharing across Health Board (Target: 28/02/2024) - Appointments of BI partners to vacant posts (Target: 31/03/2024) - Start of 2nd tranche of Data Literacy Module Manager’s Pathway program (Target: 31/05/2024) - Certified Analytical Programme with access to self-service datasets (Target: 30/06/2024) |  |  |  |  |

Further detail on the above risks can be found at Appendix 1.

3.4 For Information – Risks Assigned to Other Committees

There are two  risks which are assigned to other Committees in terms of overseeing actions to mitigate the risks, as outlined in the table below, noted here for information. As noted earlier, the detailed HBRR entries are also included in Appendix 1 for information.

| Ref | Description of Risk Identified (Summarised) | Exec Lead | Committee | Current Score |
| --- | --- | --- | --- | --- |
| 81 (2788) | Critical staffing levels – Midwifery: Unplanned absence resulting from Covid-19 related sickness, shielding and isolation, alongside other current absences, has resulted in critical staffing levels, further reductions in which could result in unsafe service provision, poor patient outcomes and/or experience. In turn, poor service quality or reduction in services could impact on organisational reputation. | Executive Director of Nursing | Q&S Committee | 25 |
| 82 (2554) | Risk of closure of Burns service if Burns Anaesthetic Consultant cover not sustained There is a risk that adequate Burns Consultant Anaesthetist cover will not be sustained, potentially resulting in closure to this regional service, harm to those patients would require access to it when closed and the associated reputational damage. This is caused by: • Significant reduction in Burns anaesthetic consultant numbers due to retirement and long-term sickness • Inability to recruit to substantive burns anaesthetic posts • The reliance on temporary cover by General intensive care consultants to cover while building work is completed in order to co-locate the burns service on General ITU • Reliance on capital funding from Welsh Government to support the co-location of the service | Executive Medical Director | P&F Committee Also Q&S Committee for information | 12 (Reduced from 16) |

3.5 Operational Workforce OD & Digital Risks

Each Service Group and Directorate hold their own risk registers, which outline the operational risks facing them. Any operational risks relating to Workforce OD & Digital services can be escalated to the Risk Scrutiny Panel which may co-opt a member of the Workforce team or seek the views of an Executive Director to consider the risk, controls in place and action to be taken to mitigate the risk, and whether the risk should be considered for inclusion on the Health Board Risk Register.

- FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information.

- RECOMMENDATIONS

Members are asked to:

- NOTE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Workforce OD & Digital Committee.

- CONSIDER the risks exceeding the Board’s stated appetite levels, the associated actions and timescales identified, and consider whether further action / assurance is required in respect of any.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | - The last WODC risk report was received in July 2023. This report reflects risks recorded in the October 2023 Risk Register, received by the Board in November 2023. |  |
| Appendices |  | - Appendix 1 – Health Board Risk Register (HBRR) extract |  |