| # Swansea Bay University Health Board Report: # Business Continuity Incident: Loss of British Telecom Services: Impact on Health Board Digital Systems: 25.04.23 # FINAL # V2: 05.07.2023 |  |
| --- | --- |
| Sensitive |  |
| Debrief Date: Report Date: | 10th May 2023 5th July 2023 |
| Author: | Completed by: Karen Jones, Head of EPRR Damian Jones, EPRR Manager |

# Introduction

On Tuesday the 25th April at approximately 08:30 hours, Swansea Bay University Health Board (SBUHB) started to experience issues with network access across all sites. This was effecting internet access, the ability to access e-mails, Microsoft Teams and SBUHB patient recording / information and data systems (WPAS etc.).

The Health Board (HB) must have robust business continuity management processes in place in order to plan, respond and recover from any potential disruption of services and this includes loss of digital services. The Civil Contingencies Act, (2004) requires Category One Responder organisations, including the NHS, to demonstrate that they are capable of dealing with such incidents. All having to be achieved during a time when demand and available resources need to be managed and delivery of safe care is required.

The HB established the Command, Control and Coordination arrangements that would be essential to deal with the impacts of the BCI during this period. These are listed below.

The C3 arrangements that were established are aligned to the Health Board Emergency response procedures.

1.1 Digital Services Silver

- 09:05 – Digital Silver established

- Included key system owners (Pathology and Radiology)

- Included key Service Delivery Group (SDG) Leads

- Included Emergency Preparedness Resilience and Response (EPRR) Team

- Digital Services Bronzes were established on each site

- Agreed requirement to establish Health Board (HB) wide Silver

- 17:30 – Digital Silver

- Included Digital site Bronzes

1.2 Health Board Silver Meetings

- 10:10 – Health Board Silver meetings established (chaired by Matt John - Director of Digital)

- Included all Service Delivery Group (SDG) Silvers

- Included Chief Operating Office (COO) / representation

- Included Gold representation

- Included Emergency Preparedness Resilience and Response (EPRR) Team

- Included key representatives from Digital Health Care Wales (DHCW)

- Included key representatives from British telecom (BT)

- 11:30 – Health Board Silver meeting (chaired by Matt John - Director of Digital)

- Included all Service Delivery Group (SDG) Silvers

- Included Emergency Preparedness Resilience and Response (EPRR) Team

- Included key system owners

- Included Chief Operating Office (COO) representation

- Included Gold representation

- Included key representatives from Digital Health Care Wales (DHCW)

- Included key representatives from British telecom (BT)

- 14:00 - Health Board Silver meeting (chaired by Matt John - Director of Digital)

- Included all Service Delivery Group (SDG) Silvers

- Included Emergency Preparedness Resilience and Response (EPRR) Team

- Included key system owners

- Included Chief Operating Office (COO) representation

- Included Gold representation

- Included key representatives from Digital Health Care Wales (DHCW)

- Included key representatives from British telecom (BT)

- 16:00 - Health Board Silver meeting (used internal safety huddle meeting)

- Included all Service Delivery Group (SDG) Silvers

- Included Emergency Preparedness Resilience and Response (EPRR) Team

- Included normal safety huddle meeting representatives

- Included Chief Operating Office (COO) representation

- Included Gold representation

- 20:00 - Health Board Silver meeting (used internal safety huddle meeting)

- Included all Service Delivery Group (SDG) Silvers

- Included normal safety huddle meeting representatives

- Included Gold on call representation

1.3 Digital health Care Wales (DHCW), British Telecom (BT) & Health Board (HB) Silver Meetings

- 11:00 - Silver meeting (chaired by Matt John - Director of Digital)

- Included Morriston SDG Silver

- Included Emergency Preparedness Resilience and Response (EPRR) Team

- Included key representatives from Digital Health Care Wales (DHCW)

- Included key representatives from British telecom (BT)

- 12:00 - Silver meeting (chaired by Matt John - Director of Digital)

- Included Morriston SDG Silver

- Included Emergency Preparedness Resilience and Response (EPRR) Team

- Included key representatives from Digital Health Care Wales (DHCW)

- Included key representatives from British telecom (BT)

- 13:30 - Silver meeting (chaired by Matt John - Director of Digital)

- Included Morriston SDG Silver

- Included Emergency Preparedness Resilience and Response (EPRR) Team

- Included key representatives from Digital Health Care Wales (DHCW)

- Included key representatives from British telecom (BT)

- 15:30 - Silver meeting (chaired by Matt John - Director of Digital)

- Included Morriston SDG Silver

- Included Emergency Preparedness Resilience and Response (EPRR) Team

- Included key representatives from Digital Health Care Wales (DHCW)

- Included key representatives from British telecom (BT)

- 17:00 - Silver meeting (chaired by Matt John - Director of Digital)

- Included Morriston SDG Silver

- Included Emergency Preparedness Resilience and Response (EPRR) Team

- Included key representatives from Digital Health Care Wales (DHCW)

- Included key representatives from British telecom (BT)

- Business Continuity Incident: Loss of British Telecom Services Debrief

Following the response to any disruptive incident, there should always be an opportunity to look back and debrief the response, perusing what went well and also identifying the challenges in order to highlight lessons that could be learned, noting further risk mitigation, vulnerability reduction and resilience building to support this. The requirement to remain prepared, to plan, exercise, capture lessons and good practice remains extant. We must plan fiercely together, to be prepared and put in place the mitigations and prevent escalation of harm during these incidents.

A debrief was held on the 10th May. This was attended by HB representatives that were involved in the response to the BCI. Following this debrief any highlighted areas of good practice, challenges and learning will be reflected and will shape the HB response to any future BCI’s.

It is deemed extremely important that lessons are identified and measures put in place to evidence that learning has taken place. The lessons themes that are identified will be included on the EPRR lessons identified spreadsheet.

# Debrief Aim and Objectives

# Aim

To provide staff with an opportunity to reflect on the operational preparedness, response and recovery following the Health Boards response to the BCI: Loss of BT Services, Impact on Health Board Digital Systems.

Objectives

1. To discuss and examine areas of good practice and to identify the key lessons during both the response and recovery phases of the Loss of British Telecom Services BC Incident by:

- Identifying the key learning and forwarding observations or recommendations for change to support, preparedness, response and recovery to BC incidents in the future, (Main focus)

- To collate the discussions as observations, conclusions and recommendations to improve/Feedback:

  - General Business Continuity Management of the preparedness, response and recovery phases for any escalating or declared BC incident in the future.

  - Forward recommendations to improve business continuity management processes

  - Improve Health Board resilience.

# 2.2. Methodology/Format

The debrief approach is based on allowing participants to capture their personal experiences from a positive perspective as well as allowing for challenges to be identified.

The debrief was facilitated and chaired by the EPRR Manager and supported by the Assistant Director of Digital services.

# The Debriefs format involved an agenda with a specific debrief section which included, looking back on what went well, what were the challenges and looking forward to consider any key learning points for the Health Board to consider to:

# Adapt

- Adopt

- Abandon

- Amplify

# 2.3 Debrief Agenda (Appendices 1)

A debrief agenda had been created to structure the meeting, which included looking forward in order to prepare the Health Board for any future BCI’s.

# 2.4 Debrief Themes (Appendix 2)

Some themes were pre-identified to aid the debrief discussions and facilitate the report write up and these are included as part of the summary of the learning. It was emphasised that the themes were not exhaustive and the participants could raise anything pertinent to help inform the debrief process.

- Health Board Command, Control and Coordination, (C3), Service Group C3 structures and associated battle rhythm

- Response

- Communications, engagement and information flows: Internally and Externally

- Interdependencies

- Risks

- Escalation process

- Service impact

- Business continuity arrangements

- Recovery:

- Operational

- Financial

The purpose of this report therefore, is to identify:

- The most significant incident learning points derived from the identified good practice as well as the challenges in terms of preparedness, response and recovery to BCI response.

- Recommendations and consequent actions required for future improvements.

- Participants Feedback

Feedback was requested from those involved in the BCI response, Gold & Silver Commanders, Senior Corporate members and other key Service stakeholders during the debrief process.

- Observations and Recommendations

The consolidation included in this report is intended as a brief reflection of the risks and key actions required at the time and as noted in the debriefs scribe notes, (Appendix 3; debrief scribe notes).

Recommendations are included but based on generic recommendations and these will be actions taken forward as appropriate within the Chief Operating Office, Workforce Organisational Development and EPRR, in order to further inform business continuity preparedness for dealing with BCI response and overall business continuity management and hence Health Board resilience.

- Acknowledgements

It is imperative to note that the Health Board, together with some multi-agency partners (Digital Health care Wales, British telecom) involved in the response was excellent, attributed to all the personnel concerned for their actions. The responses included a number of disciplines working together, at strategic, tactical and operational levels to deliver successful outcomes. Staff quickly thought through the key risks/issues, undertaking the most appropriate actions at that time, as well as identifying the planning that remained; this was invaluable. This is particularly pertinent during a time when operational business has been extremely challenged.

- Appendices

- Interim Debrief Agenda BCI: Loss of BT Services

- Debrief Themes

- Debrief scribe notes

- Debrief presentation

# Observations and Recommendations

All comments have been collated, from the debrief meeting notes. These have been summarised and themed according to the most appropriate classifications and are not attributed to one person. Included in the following themes are both the key challenges and also the positive aspects of the preparedness, response and recovery.

| Themes | Comments | Recommendation Number |
| --- | --- | --- |
| Preparedness, Contingencies and Actions Prior to BCI declaration |  |  |
| - Business Continuity Procedures - EPRR support - Outpatient Departments - HEPMA BCI Documents - Digital resilience | - The response to the incident ran smoothly and was dealt with in a controlled manor. Business Continuity Procedures (BCP) were utilised throughout the Health Board (HB) both prior and following the BCI declaration. - The Head of EPRR and EPRR Manager were at Morriston Hospital when the issues occurred and were able to provide support. - Outpatient departments always print off the following day’s clinic lists the day before, this meant there was less disruption as paper copies of the day’s lists were available. - Unable to contact using the normal general number. Need to review documents and clarify a specific contact number instead. - Each Hospital (Site) is connected to Digital Health Care Wales (DHCW) and the Internet. The way the HB resilience is setup is that if any traffic is lost across any site, the traffic reroutes automatically to a different one (4 layers of resilience). Therefore 3 of the 4 sites could be lost and still run seamlessly. However in this incident all resilience was lost. | 10, 6, 5, |
| Escalation processes; internal, general and specialty/regional/national |  |  |
| - British Telecom (BT) - Radiology Support - Command and Control Structures - Business Continuity Procedures | - It was confirmed very early on that the issues reported were due to BT services and they were already working to find and repair the fault / issue. External Network Traffic was impacted across all main Hospital Sites. - Additional Radiologist support was identified early, in the event that high volumes of reporting where required. - A Critical Incident was declared prior to the BCI declaration and the H/ICC were established early on in the incident. - Business Continuity Procedures were utilsed early on in the incident (prior to the BCI declaration). |  |
| Declaration Processes |  |  |
| - Command and Control Structures | - Command and Control Structures were established quickly throughout the HB to deal with the incident. All Hospital / Incident Co-ordination Centre’s (H/ICC) were established. Bronze teams fed regular information and updates from across all services back into Silver Command which increased situational awareness throughout the incident. |  |
| Common Language |  |  |
| - JESIP Interoperability Principles | - JESIP Principles were utilised and adhered to which ensured common language was used throughout the incident. |  |
| Command, Control and Coordination |  |  |
| - JESIP Interoperability Principles - Battle Rhythm | - JESIP Principles and the Joint Decision Model (JDM) were utilised and adhered to, which maintained excellent Situational Awareness throughout the incident. - Early on in the incident, the battle rhythm was not fully aligned and there was not enough time between meetings to achieve the required outcomes. This did improve throughout the day. The Digital National/ Internal meetings were scheduled at the same time. | 11, |
| Response: Internal/Regional/National |  |  |
| - Teamwork - Bank staff rosters - Command & Control | - Good teamwork was evident across the HB and throughout all service delivery groups (SDG). - Access to health Rosters were an issue and this needs to be reviewed as to the process of requesting and allocating Bank staff moving forward. - Command & Control structures worked well throughout the incident. | 7, |
| Communications: W&I, Engagement & Information Flows: Internally & Externally |  |  |
| - Teleconference facilities - Public messaging - Internal communications - IT support desk - Internal / External | - The lack of a pre-arranged Teleconference number made it more difficult to initially arrange our internal meetings. - There was a lack of public messaging to alert the public of possible Clinic disruption. Aneurin Bevan and Cwm Taff Morgannwg Health Boards shared messages via Social Media platforms. - This incident highlighted that should they have been required, there were not enough Radios available within the Morriston Coordination Centre. Portering Services had to collect additional radios from Morriston Estates department. However, the radios were not all fully charged. - When Staff were logging calls. Service Point had an automated message to say staff were all on training. - Digital Bronze Teams were on Site feeding back to Silver and DHCW. Local Communications remained working as staff were able to use Virgin services. National Calls Held throughout day with Silver Leads. | 1, 2, 3, 4, |
| Risks and Harm Reduction processes |  |  |
| - Command & Control - Staff expectations - WPAS system | - Digital Bronze Teams were on Sites feeding back into Silver Command. - Managers managed staff expectations well throughout the incident. MH/LD Service: Staff kindly volunteered to stay on to update systems (CAHMS Crisis referrals). - No function to merge patient numbers via WPAS post BCI Incident. (Speak with WPAS Product Specialist). | 12, 8, |
| Mutual Aid/Stakeholder involvement |  |  |
| - External | - All key stakeholders were involved and engaged in the response to the incident. These included: - Welsh Government - BT - DHCW - Virgin |  |
| Current Business Continuity Arrangements: Service, Service group and Strategic Levels |  |  |
| - Business Continuity Management / Procedures | - The incident has highlighted that across all SDG, services accessed and utilised their BCP as soon as issues were occurring and systems were being lost. - Digital Services need to look into solutions on how to aid with future Digital reliance (Having Diverse lenders for Digital Systems, not reliant on one lender). Virgin, Sky etc. Then test procedures to gain assurance. Arrange a task and finish group to allow mitigation | 5, |
| Recovery |  |  |
| - Recovery from incident | - Update Digital Systems / platforms with preemptive Information regarding what do in the event of loss of IT systems. - The health board is heavily reliant on TEAMS usage. Digital to look into finding some alternative solutions. - Playing Catch Up – Assigning Staff to upload data / patient information back onto systems was very labor intensive and proved challenging to assign staff to do this whilst also continuing with normal business. MH/LD had an urgent backlog of CAHMS referrals and had to pay overtime to staff to ensure they were completed. - Any planned system downtimes were pushed back to allow for appropriate recovery time. - Due to the difference in experienced issues reported across health board sites and backlog of digital data that required uploading back onto systems, it was hard to establish an approximate recovery period. - Digital prioritised the whole Health Board issues before their own. Whilst this was obviously important they should also focus on their internal issues as noted in their business continuity procedures to ensure that they can still function appropriately. | 9, 5, |

Key Learning Points

The following are specific key learning points derived from the above summary, where further detail is contained.

| Item | Comments | Recommendation Number |
| --- | --- | --- |
| - Command, Control and Coordination | Utilising the Health Board standardised C3 approach to emergency response, including the JESIP Programme and Joint Decision Making Model allows for full oversight of risks, safe management and reduces harm. This includes operation of Incident/Hospital Coordination Centres for tactical and operational oversight. | 11, |
| - Preparedness | A continued focus on preparedness has ensured that the Health Board (HB) responded well and maintained its critical services throughout the incident. | 12, |
| - Teamwork | A positive and collaborative approach allowed for safe working. Staff across the HB adjusted to working without some of the required Digital services. |  |
| - Business Continuity Management (BCM) | Business Continuity Procedures (BCP) were utilised throughout the HB both prior and during the BCI. This has highlighted the importance of the HB having good BCM processes in place. |  |
| - Risks and Harm Reduction processes | Look into non Digital contingencies to reduce risk on future incidents. | 5, |
| - Reliance on Digital services | Look into non Digital contingencies to further enhance HB resilience. | 5, |
| - Recovery management | Recovery management processes need to be seen as an integral part of the response. | 12, |

# Observations/Recommendations/Actions

| No. | Theme | Recommendations | Actions/Lead | Timescales |
| --- | --- | --- | --- | --- |
| 1. | Communication | Identify a Teleconference number for use in any future loss of IT systems. Explore alternative platforms that could be used instead of Microsoft Teams for communications. | Digital services | 31 August 2023 |
| 2. |  | Ensure appropriate & timely warning and informing information is cascaded to the public. | DICE | 31 August 2023 |
| 3. |  | Review the required numbers and locations of radios on Morriston site. This will also be part of the ongoing HB wide work with all SDG having radios and the ability to communicate between sites. | Morriston SDG | 31 August 2023 |
| 4. |  | When Staff were trying to log calls. Service Point had message to say staff were all on training. | Digital services | 31 August 2023 |
| 5. | Business Continuity Management | Arrange a task and finish group to look at SBUHB reliance on Digital services. Following any changes, test BCP to gain assurance. | Digital services / EPRR / All SDG’s | 30 September 2023 |
| 6. |  | HEPMA BCI Documents: Require review. Including contact numbers. | Medicines Management | 31 August 2023 |
| 7. |  | Review process of requesting and allocating Bank staff in the event of loss of digital services. | Nurse Bank Pete Matthews | 31 August 2023 |
| 8. |  | Explore WPAS functionality to see if it can merge patient numbers from other systems. | Deb Usher (Digital) & SDG | 31 August 2023 |
| 9. |  | Update SharePoint / Digital Systems / platforms with pre-emptive Information regarding what do in the event of loss of IT systems. This will be pre-emptive for in readiness. | Digital services | 31 August 2023 |
| 10. |  | Where appropriate (departmental / services), print off any clinic / patient information the day before. | All SDG | 31 August 2023 |
| 11. | Command, Control and Coordination (C3) | Ensure Battle rhythm is aligned with national meetings. This is included in both the SBUHB and Local resilience Forum (LRF) Multi Agency Gold / Silver Commander training. All Gold / Silver Commanders to ensure they complete the appropriate command level training. | SBUHB Gold / Silver Commanders | 31 August 2023 |
| 12. | Risk / recovery | Agree a pre-determined process for updating CAHMS Crisis referrals with patient information and include in BCP. | MH/LD | 31 August 2023 |

# Conclusion

Overall the Health Board response to this incident went very well and all critical services were maintained during a very challenging period. Moving forward, this is an excellent opportunity for all SDG / Service areas to review their Business Continuity Procedures and make any required amendments.

This Report will be used to extract the key learning and inform further preparedness requirements and assurance processes. The key learning points will be referenced to further improve preparedness. The development and agreement of actions will be taken forward and monitored by the Chief Operating Office, Digital Services and EPRR.

Appendices

| No. | Title | Document |
| --- | --- | --- |
|  | Debrief Agenda: Loss of BT Services |  |
|  | Debrief Themes | Included in Appendices 4 (debrief presentation) |
|  | Debrief Scribe notes |  |
|  | Debrief Presentation |  |