This form is for use by staff for recording and assessing risks affecting their service. As many fields as possible and applicable should be completed and the form then escalated to their line manager. All risks scoring 9 or above should be considered for inclusion within the service risk register in Datix. Lower scoring risks may also be included. Fields marked with an asterisk are mandatory for completion within the Datix Risk Module – there are additional fields required to be entered in Datix at that point by the Risk Owner.

1. SERVICE AFFECTED & LOCATION

| SERVICE GROUP / CORPORATE DIRECTORATE | Workforce & OD |  |
| --- | --- | --- |
| DIVISION (optional) |  |  |
| SPECIALTY |  |  |
| WARD / DEPARTMENT |  |  |
| SITE (if applicable) |  |  |

2. RESPONSIBILITIES

| RISK OWNER * | Interim Director of Workforce & OD |
| --- | --- |
| MANAGER OF SERVICE |  |

3. RISK TITLE (Just a few words to identify the risk)*

Service Group capacity to meet delivery requirements of National Speaking Up Safely Framework in agreed timeframes.

4. RISK DESCRIPTION*

A brief description of the risk, entering facts not opinions.

Do not enter the names of people. Try to be as concise and clear as possible.

In your description, consider what is the risk, what is its main cause(s) and what is its main consequence(s).

What are the risks and causes? There is a risk that the organisation will not deliver the section 6 requirements of the national speaking up safely framework, because of Service Group capacity to be able to respond and deliver in the agreed timeframes, which may result in delayed improvements towards a culture that enables staff to raise concerns and a continued limited assurance assessment. Following the Lucy Letby verdict in August 2023, the NHS Chief Executive wrote to all NHS Wales organisations with a call to action and requirement to self-assess against section 6 of the national Speaking Up Safely Framework. Following on from this was the need to develop an action plan to close any gaps in meeting the section 6 requirements which were to be submitted to Welsh Government on 30th October 2023. Whilst this action had been completed, an internal audit report published in January 2025 issued a limited assurance rating, recognising the need for organisation-wide ownership of the agenda. Engagement with and from Service Groups and wider stakeholders is essential to successful delivery of the recommendations set out in the Internal Audit Report. Service pressures mean capacity across Service Groups is significantly stretched and is a potential risk to the ability to respond to, and deliver the requirements of the framework in the agreed timeframes. Until Service Groups complete a local self-assessment against the section 6 Framework requirements, we cannot confirm what the gaps are to inform local action plans and so the level of risk. Consquences The ultimate consequences of the risks outlined above are that the Health Board will not deliver on the requirements of section 6 of the national Speaking Up Safely framework, a continued limited assurance assessment and delayed improvements towards a culture that enables staff to raise concerns.

7. SUMMARY OF CONTROLS IN PLACE(*)

What are the key measures already in place to manage the risk?

Engagement with stakeholders for collective ownership and delivery of the action plan for delivery of the Framework requirements has commenced via the HR BPs, Workforce & OD Delivery Group (scheduled on 25th March 2025 agenda) and through the set-up of the Speaking Up Safely Working Group during November 2024, which currently meets bi-monthly. We will work with Service Groups in collaboration to agree a proposal for the reporting process for Speaking Up Safely on a rotational basis. Reports from Service Groups are to amalgamate the detail of concerns raised (themes, trends, actions taken, lessons learned) and be reported to Workforce & OD Delivery Group and Workforce & OD Committee a minimum of twice yearly, as part of the overarching Speaking Up Safely Monitoring and Reporting schedule, providing assurance that the national Framework Requirements are being adhered to. There is an opportunity to align with the existing Quality & Safety reporting structure and mechanisms that Service Groups are already engaged with. The action plan against the section 6 requirements of the national framework will be revisited / refreshed to ensure the actions remain appropriate and timeframes realistic.

9. ADDITIONAL SUPPORTING INFORMATION

Please add any further detail that may assist other understand the nature of the risk.

As detailed in section 4.

10. RISK ASSESSMENT

Risks are scored according to their potential consequences and likelihood of occurring. Insert a cross “X” in the tables below to indicate your assessment of the current risk:

|  | 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Critical |
| --- | --- | --- | --- | --- | --- |
| CURRENT RISK CONSEQUENCE |  |  | x |  |  |

|  | 1 Rare | 2 Unlikely | 3 Possible | 4 Probable | 5 Expected |
| --- | --- | --- | --- | --- | --- |
| CURRENT RISK LIKELIHOOD |  |  | x |  |  |

Calculate the total current risk score by multiplying: Consequence x Likelihood, in the table below. Then do the same for the risk level you want to achieve – the target risk score:

|  | CONSEQUENCE (C) (1-5) | LIKELIHOOD (L) (1-5) | TOTAL RISK SCORE (CxL) (1-25) |
| --- | --- | --- | --- |
| CURRENT SCORE | 3 | 3 | 9 |
| TARGET SCORE | 2 | 2 | 4 |

11. RISK DECISION

What do you intend doing about the risk?

Treat

12. ADEQUACY OF CONTROLS

Are the current measures in place to manage the risks designed appropriately and operating effectively to address the risk?

Adequate

13. ACTIONS PLANNED

Please indicate any further actions you intend to take to address the risk:

| Action | Lead Officer Responsible | Target Date for implementation |
| --- | --- | --- |
| Complete the development of the Raising Concerns’ page of the Staff Intranet to include the national branding and Framework for Speaking Up Safely in NHS Wales. | Director of Workforce & OD | 31.03.25 - Completed |
| Develop training resources for employees and managers on how to speak up safely and embed these within the Brilliant Basics platform. | Director of Workforce & OD | June 2025 |
| Create an action plan template for Service Groups to use, to demonstrate improvement against the self-assessment of the national framework section 6 requirements. | Director of Workforce & OD | June 2025 |
| Create a template for Service Groups to self-assess performance against Section 6 of the national Speaking up Safely Framework. | Director of Workforce & OD | June 2025 |
| Integrate Speaking Up Safely measures into the Workforce Performance Scorecard when this is developed. | Director of Workforce & OD | March 2026 |

14. TARGET SCORE DATE

By when do you expect to achieve the target risk score?

March 2026, aligned to the Management Response to the IA Report and Delivery Actions agreed for 2025-26.

15. ASSESSMENT ESCALATED TO:

| Name | Title | Date |
| --- | --- | --- |
| Sarah Jenkins | Interim Director of WOD | 21-03-25 |

16. ASSESSMENT COMPLETED BY:

| Name | Title | Date |
| --- | --- | --- |
| Julie Lloyd | Head of Culture, OD & Staff Experience | 21-03-25 |

NOTES

The Risk Owner or Handler is the person responsible for managing the overall control of the risk such as updating it and ensuring that the risk record is regularly reviewed and updated in Datix.

The Manager is the person accountable for ensuring that risks within the service affected are managed and controlled. The Risk Owner and Manager may be the same person.

Please refer to the Simple Guide to Risk Assessment & Management on the Intranet for guidance on how to assess consequence and likelihood.

Consequence is graded as follows:

| 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Critical |
| --- | --- | --- | --- | --- |

Likelihood is graded as follows:

| 1 Rare | 2 Unlikely | 3 Possible | 4 Probable | 5 Expected |
| --- | --- | --- | --- | --- |

Current Risk Score is the score of the risk taking into account the effect of all the controls currently in operation (but not including those planned or not yet fully implemented).

Target Risk Score is the score you aim to achieve. If the current risk score is higher than the target risk score then additional action would need to be identified if you wished to reduce it towards the target.

Options for Risk Decision are:

Tolerate = accept the risk at its current level with no further action

Treat = take action to reduce the likelihood of the risk occurring or to mitigate is consequences

Terminate = stop undertaking the activity or service that is exposed to the risk

Transfer = take out insurance / share the risk with partners

Tolerate and Treat are the most common options.

SCORING GUIDANCE

Please See Risk Management Policy and Simple Guide to Risk Assessment & Management for further guidfenac on how to apply this guidance: