The 2025 NHS Wales Staff Survey – Next Steps and Timelines

| Action | Timeline | Who |
| --- | --- | --- |
| Executive Team: |  |  |
| Collaborative workshop with the Board and Trade Union Partners | April 2026 | Board Services |
| Staff Survey Results shared through Team Brief | April 2026 | Director of WOD |
| Results, top 3 priority areas and ask of services shared through governance channels i.e. Workforce & OD Committee | April 2026 | Director of WOD and Head of Culture, OD & Staff Experience |
| Sharing of Health Board Staff Survey Results, Action Plan and engagement through Ask Abi | April/May 2026 | Chief Executive and Director of WOD |
| Continuation of “We Said, We’re Delivering Together” campaign and top 3 priorities to wider organisation via Team Brief | May 2026 onwards | Chief Executive and Interim Director of WOD |
| Quarterly communication, engagement and reporting of progress on top 3 priorities, informed by local service monitoring. Progress reporting via existing communication mechanisms i.e. Ask Abi, Midweek message, Team Brief | Quarterly starting from June 2026 | CEO, Director of DICE and Interim Director of WOD |
| Service Groups / Corporate Directorates: |  |  |
| Nominate leads to access Survey dashboard along with HR BPs and send details to Head of Culture, OD & Staff Experience | COMPLETED | Service Group/Corporate Directors |
| Nominated leads to request access to new Staff Survey Dashboard for 2025 results via link: NHS Wales Staff Survey Dashboard - Power BI | April 2026 | Nominated Leads and HRBPs |
| Reporting and monitoring of top 3 priorities and action plans linked to People Strategy Aims via WOD Delivery Group & WOD Committee | Quarterly starting from June 2026 | Service Groups/Corporate Directors |
| Workforce & OD: |  |  |
| Share dashboard link for Nominated Leads and HRBPs to request access and approve access to anyone within SBU that would like access to the data. | March 2026 onwards | Culture, OD & Staff Experience |
| Work in partnership with DICE re communications and engagement plan to cascade results and actions i.e. ‘we said, we’re delivering together’ | April-May 2026 | Culture, OD & Staff Experience and DICE |
| Draft Action Plan template supporting consistency of monitoring and reporting to be shared with nominated leads in Service Groups and Corporate Directorates. | April 2026 | Director of WOD |