Key

|  | Exceeding Review Date |
| --- | --- |
|  | Due to be reviewed in next 6 months – 2025 |
|  | All Wales Policies |
|  | Within Review Date |

| Policy No. | Policy Name | Executive Lead/Policy Lead | Review Date | Lead | Comments | Actions/Next Steps | Deadline | RAG (on track) Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| s170 | Registration Policy | Director of Therapies, Director of Nursing, Director of Workforce &OD | Jun-24 | SJ | This is a jointly owned policy. It has been reviewed and will shortly be shared with staff side for comment | To be shared with staff side for comment / approval. Will require translation. Expected by end of October 2025 | October 2025 | GREEN- ON TRACK |
| 68 | Study Leave Policy | Director of Workforce & OD | Sep-23 | LJ | Work underway to develop Education Strategy which will incorporate Study Leave. National work is underway linked to CPD elements of pay deal as this will directly impact policy. Date to be confirmed. | Suggest we link this to work around our People Strategy & WOD5 as next stage of ‘academy’ development and governance structures | On hold pending AW discussions | AMBER- ON HOLD- PENDING AW WORK |
| 69 | Extreme Weather Conditions Policy | Director of Workforce & OD | Feb-21 | SJ | Work is required with the Emergency Preparedness Team to ensure it is in line with their policy | Meeting arranged with the EPT to understand wider policy to cover broader emergency preparedness | March 2026 | GREEN- ON TRACK |
| 78 | Partnership Working Agreement | Director of Workforce & OD | May-21 | SJ | Partnership Working agreement was reviewed in 2023. Compact created and issued as part of the outcomes of our big conversation. | Refresh and reset now required which will include a review of the agreement. Meeting to be scheduled to review in partnership. | March 2026 | GREEN – ON TRACK |
| 96 | Induction Policy | Director of Workforce & OD | Mar-24 | LJ | Induction programme under review. | Bench marking across Wales and elsewhere being undertaken. Task and Finish group- to include staff side representative established to review. | December 2025 | GREEN – ON TRACK |
| 107 | Staff Stress and Emotional Wellbeing Policy | Director of Workforce & OD | Dec-23 | LJ | Policy will be finalised by end August 2025 and thereafter taken through | Finalised policy to be submitted for approval | October 2025 | GREEN – ON TRACK |
| 109 | Alcohol & Substance Misuse Policy | Director of Workforce & OD | Jul-17 | SJ | Scoping required | To seek information / advice regarding content and comment from policy users to identify issues. | March 2026 | AMBER |
| 122 | Annual Leave Policy | Director of Workforce & OD | Apr-18 | SJ | Annual leave is covered within National Terms and Conditions. Policy not required. | Guidance to be developed to replace this policy | March 2026 | AMBER |
| 125 | Shared Parental Leave Policy | Director of Workforce & OD | Jun-22 | SJ | This is covered within national terms and conditions. Policy unnecessary | User friendly guidance to be developed | March 2026 | GREEN – ON TRACK |
| 129 | Redeployment Policy | Director of Workforce & OD | Jun-23 | SJ | Local policy | Policy under review by Operational Team | January 2026 | AMBER |
| 131 | Bilingual Skills Strategy | Director of Workforce & OD | Jan-20 |  | This was historically managed within the WFOD portfolio, but that was before the establishment of the Welsh Language Team- This is not a WF document so may be more appropriate to be held by Corporate Services | Identify appropriate owner for this document | September 2025 | AMBER- OWNERSHIP TO BE IDENTFIED |
| 143 | Personal Relationships at Work | Director of Workforce & OD | Sep-20 | SJ | minor refresh required | to be signed off at sub group | October 2025 | GREEN |
| 160 | Home Working Policy | Director of Workforce & OD | Aug-22 | SJ | There is work underway on a national basis looking at updating/refreshing the Agile Working Framework. It may be sensible to wait to see the outcome of that work to ensure nothing in this policy is contradictory | Pending issue of AW Agile Working Policy |  | AMBER_ PENDING AW WORK |
| 171 | Disclosure & Barring Policy | Director of Workforce & OD | Nov-24 | SJ | Minor review required | Policy circulated for comment with interested parties before sharing with staff side. No major change expected. | November 2025 | GREEN |