Health Education and Improvement Wales - Medicine Action Plan

| Report: | Medicine action plan to HEIW |
| --- | --- |
| Date of visit: | Monday 30th June 2025 |
| Action plan sent to HEIW: | Wednesday 13th August |

| Recommendation | Service Action | Responsible Officer | Timescale |
| --- | --- | --- | --- |
| 1.The Health Board should conduct a review of departmental rotas with the aim of equitably distributing on call commitments across Medicine specialities, to ensure ward staffing levels remain robust and consistent. | Undertake a 2-week audit to review: - How many doctors are on a ward on a given day. - Determine whether multiple doctors from the same team have on-call commitments on the same day. - Review what the allocate system displays against the reality and amend where necessary. | Abi Landeg | November 2025 |
| 2.The Health Board should ensure that residents returning to work after extended periods of leave are provided with an appropriately managed phased return to work plan. | Develop and circulate a return-to-work guidance document that clearly articulates the health boards responsibilities and the responsibility of individuals. Continue to review sickness/extended periods of leave at weekly medical staffing meetings and highlight any hot spot areas. Undertake a deep dive to review extended periods of leave (over a week), the process, what was provided and highlight any hot spot areas. | Bethany Jones & Diane Williams Rhodri Edwards Abi Landeg & Diane Williams | September 2025 Ongoing September 2025 |
| 3.The Health Board should consider the inclusion of reverse ward rounds for higher grade Speciality Training residents in Acute Medicine settings. | Circulate recommendations for reverse ward rounds to all supervisors and higher-grade resident doctors. | Rhodri Edwards | October 2025 |
| 4.The Health Board should make efforts to improve the handover process for patients transferring from the Same Day Emergency Care unit to the Acute Medical Unit, ensuring patients are tracked appropriately and information provided to the on-call registrar is up to date and robust. | Develop and implement a Standing Operating Procedure (SOP) for handover of patients between SDEC and AMU. | Rhodri Edwards & Lucy Thomas | October 2025 |
| 5.The Health Board should make efforts to clarify and encourage communication channels amongst on call teams to ensure efficient distribution and movement of staff within Medicine areas. | The weekly medical staffing meeting will regularly review distribution of resident doctors across the acute medicine footprint (AMU/ED/Acute Frailty/Ward Cover) to ensure it reflects demand. Review of medical handovers processes to ensure staff are distributed fairly to compensate for absence etc. Engagement of resistant doctors at various forums (e.g trainee forums, weekend handover meetings) | Medical staffing team. | Complete and will be ongoing |
| 6.The Health Board should build upon previous efforts to provide an equitable balance between Speciality and General Internal Medicine commitments for residents in dual training programmes to ensure curriculum requirements are accessible and achievable. | Regular engagement at trainee forums to ensure appropriate balance between speciality medicine and General Internal Medicine. Regularly encourage trainees to discuss any curriculum requirements/concerns with Educational Supervisors – reiterated at Induction. Educational representation at monthly clinical leads meeting to ensure appropriate balance of training reflected. | Education Faculty Education Faculty Rhodri Edwards, Sophie Henson, Educational Faculty | Ongoing |