Upper Valleys Health Cluster

Integrated Medium Term Plan

(IMTP)

Annual Plan 2022 – 2023

Contents

1.	CLUSTER OVERVIEW – PLAN ON A PAGE	1

2. FORWARD LOOK	2

SWOT ANALYSIS	4

3. VISION/MISSION STATEMENT	5

4. STRATEGIC BACKGROUND & PRIORITY AREAS	6

CLUSTER IMTP STRATEGIC PRIORITY AREAS	9

5. CLUSTER NEEDS HIGHLIGHTS	11

SUMMARY	11

LOCALITY KEY FACTS	15

6. ACTION PLAN	16

7. GOVERNANCE ARRANGEMENTS	24

MEMBERS	24

8. CLUSTER ASSETS PROFILE	25

Community Assets	25

9. CLUSTER WORKFORCE PROFILE	26

10. CLUSTER FINANCIAL PROFILE	28

# CLUSTER OVERVIEW – PLAN ON A PAGE

| IMPROVING PLANNED CARE | IMPROVING CANCER & PALLIATIVE CARE | IMPROVING UNSCHEDULED CARE |
| --- | --- | --- |
| Improve diagnosis and management of Hypertension Maintain essential services in responding to COVID 19 Engage in prescribing management schemes & further improve antimicrobial stewardship and pain management | Improve EOL for patients and patient’s family Support patients with USC referrals to make lifestyle changes | Reduce demand on outpatients and support improved referral to treatment times. Provide more care in the community Ensure the provision of Signposting, information and assistance for all |
| IMPROVING MENTAL HEALTH & LEARNING DIFFICULTIES | CHILDREN, YOUNG PEOPLE & MATERNITY | PREVENTION & REDUCING HEALTH INEQUALITIES |
| Develop services to improve mental health and wellbeing of patients. Identify and support patients experiencing domestic violence | Develop strategies to support parents of children with behavioural problems Improve outcomes for the most vulnerable families within the NPT clusters | Improve uptake of childhood vaccinations Encourage uptake of Public Health screening programmes Deliver an enhanced Flu vaccination Programme Develop a consistent approach to reduce smoking prevalence Support patients to manage their weight To improve patient awareness and self management of Type 2 diabetes within the Cluster population, Identify and manage patients who have pre diabetes Develop strategies which contribute to the decarbonisation of the environment to help with the current climate emergency |

The plan is actioned using enablers; technological, workforce, communication and engagement, financial. Click Here

# 2. FORWARD LOOK

The last year has presented unimaginable challenges to the whole health and social care system. Primary care, as the front door to health services, has taken a beating but has shown immense resilience in rising to the pressures and demands placed on it.  These pressures and demands continue in an unrelenting fashion, as the nation adjusts to a world with endemic COVID infection.  Primary Care is digging deep to face the challenges.

Maintaining essential services had been a key priority for the cluster, the introduction of new systems, processes and technology have helped achieve this.  Cluster members have continued to deliver services to all, including the most vulnerable, whilst learning on the job how manage COVID 19.

Cluster practices worked hard to support the mass vaccination centre (MVC) to ensure timely delivery of COVID vaccines to citizens, including those unable to travel to the MVC, in many cases vaccines were delivered in citizens homes where they were housebound.  Whilst vaccination has helped to prevent hospitalisations and death the virus remains with us and continues to cause illness and disruption.  Despite this we need to take the opportunity to pause and reset, ensuring that we acknowledge pressures and backlogs and put in place strategies to manage these.

Swansea Bay University Health Board (SBUHB) has reviewed Cluster membership so that we are in a stronger position to work with key partners across Health, Social Care and the Voluntary Sector.  Working together, we will identify priorities and review pathways across the whole system. Work is ongoing to align our Cluster Plans with Health Board and Welsh Government priorities, while ensuring that priorities identified at Cluster Level inform the wider strategic Plans. The cluster’s intention is to work smarter on a small number of areas, which will have the greatest impact in meeting the health needs of the cluster population while maintaining COVID 19 resilience.

There is no doubt that COVID 19 has exacerbated problems with mental health and wellbeing, the cluster is prioritising a rapid review of provision of services., for those with mental health needs in the cluster, with a view to commissioning appropriate services to bridge any gaps.   The Cluster is working with a social prescriber to work with citizens in a holistic way to address their non-medical needs and help them take greater control of their health and well-being. The Cluster has also identified the need for individual Counselling and group therapy and is currently undergoing a procurement process.

Dr Rebecca Jones, Upper Valleys Cluster Lead

The cluster has been keen to develop Cluster wide Multi-Disciplinary Teams (MDT) to ensure that citizens see the most appropriate Health Care Professional.  The cluster has effective first contact physiotherapy, a community Occupational Therapist and supports first contact audiology service.  The intention is to strengthen this way of working.  The cluster is actively promoting the Common Ailments Scheme so that citizens are aware they can seek advice from local pharmacies for many complaints rather than their GP.

Establishing an MDT virtual ward (VW) during the COVID pandemic helped to support the most vulnerable and frail citizens in the community and thus avoided unnecessary hospital admissions.   The cluster is working with SBUHB transformation to strengthen this approach and deliver the benefits of this way of working to more citizens.

Citizens are placing ever-increasing demands on Health Services whilst staff are tired and vulnerable to these pressures, having worked so hard during the pandemic. Primary Care provision in the cluster is vulnerable and so supporting GP practices to remain sustainable is a key priority.

We plan to build on our successes in 2022-23, while meeting the challenges still posed by COVID 19. We will have the additional challenge of beginning to implement the Accelerated Cluster Development programme, which aims to align cluster work with regional priorities of all our partners

## SWOT ANALYSIS

| STRENGTHS - Good working relationship between cluster practices and with partners - Strengthened TOR - Successful delivery of cluster projects - Committed and experienced Cluster leads - Sharing of good practice and skills | WEAKNESSES - Cluster geography makes close working difficult - Fragmentation of services due to cross border issues - No legal structure resulting in lack of autonomy and complete reliance on HB to employ staff, manage and release finances, procure goods and services - Lack of workforce and services e.g. obesity, Mental Health - Unrealistic projects, differing business objectives, different challenges being faced - Lack of opportunity for engagement with cluster individuals due to COVID 19 - Lack of capacity within Cluster to deliver programmes |
| --- | --- |
| OPPORTUNITIES - To increase collaboration - To further develop MDTs and novel shared services - To align policies, procedures and services - To explore sources of external funding - To develop business plans based on evaluation - To implement Accelerated Cluster Development | THREATS - Increasing demand on services resulting in risks to service sustainable - Consequences of inability to bring the COVID pandemic under control - Increasing Backlogs and Work overload in primary care - Staff fatigue, isolation and burnout due to COVID 19 - Programmes largely dependent on WG annual funding - Disengagement if successful projects are not absorbed into core business, funded or rolled out by the Health Board |

# 3. VISION/MISSION STATEMENT

Our Vision

In 2018, Upper Valleys Cluster jointly agreed a Cluster Vision for the coming years. The Vision sets out how our Cluster sees its role in providing Health, Social Care and Wellbeing, with and for, the population of the Upper Valleys Cluster area:

To enable communication between the right people at the right time, leading to cohesive working for the betterment of the population with provision of equitable services across the Network that are safe, timely and accessible

Purpose and Values

- Delivery of primary, community and integrated services

- Planning and management of services best delivered at the Cluster level

- Delivery of Care Closer to Home where this is safe to do so and adds value to patient outcomes and experience

- Providing innovative alternatives to traditional outpatient or inpatient models of care

- Support whole populations to develop healthy lifestyles, through preventative programmes, self-care and out of hospital care.

- Integrating primary and community based services between health, social and voluntary sectors, physical and mental health services, with our partners

- Supporting the transition of care out of hospital into the community

- Promoting University Research and Undergraduate and Postgraduate Education in a vibrant community setting

# 4. STRATEGIC BACKGROUND & PRIORITY AREAS

The Primary Care Model for Wales sets out how primary care will work within the whole system to deliver a place based approach. Our Cluster working is at the core of this to ensure care is better co-ordinated to promote the wellbeing of individuals and communities and will continue to be taken forward through the multi-disciplinary, multi-agency cluster planning teams reflecting all partner contributions.

The Cluster continues to focus resources on delivering the aims and aspirations of the Primary Care Model for Wales and to accommodate the delivery of improvements, our plan is flexible and will be underpinned by ongoing work to develop implementation and performance plans against the stated Goals, Methods and Outcomes Action Plan.

.The 2022/23 Cluster IMTP is developed in alignment with national, regional and local strategic context and to address:

- COVID 19 Resilience

- Ministerial Delivery Milestones

- Local Primary Care Cluster Priorities

- Local Priorities influenced by Health Board IMTP, Regional Partnership Board, National Strategic Programmes and the Primary Care Model for Wales

- NHS Wales Planning Framework

- Framed within the context of the Well-being of Future Generations Act

- Social Services and Wellbeing Act 2014

- NHS Wales Decarbonisation Strategic Delivery Plan 2021-2030

As part of the process to develop this IMTP we have worked closely with Health Board colleagues to integrate with the Health Board IMTPs and planning arrangements, such as delivery plans for Cancer and Mental Health services, and under the context of The Clinical Services Plan (CSP) . The CSP remains the primary roadmap for the long-term delivery of services for our communities and Cluster planning and delivery remains aligned to the four CSP principles:

In Swansea Bay, Primary Care Clusters aim to:

- Work towards the Primary Care Model for Wales

- Prevent ill health

- Develop a range and quality of services in the community

- Ensure services in the community are better co-ordinated

- Improve communication and information sharing between professionals

- Facilitate closer working between community based and hospital services

- Support sustainability of primary care

Additionally, Cluster work is structured to encompass the Health Board’s overall Organisational Strategy as set out below in summary:

The organisational strategies and priorities of a number of key regional partnerships are also accounted in our planning including:

- Swansea & Neath Port Talbot Wellbeing Plans

- The West Glamorgan Regional Partnership

- The Adult’s Transformation Board

- The Children and Young Adults’ Transformation Board

- The Integrated Transformation Board

## CLUSTER IMTP STRATEGIC PRIORITY AREAS

During the planning process, SBUHB Cluster leads considered the range of Health Board strategic priority areas, and agreed to focus their Cluster planning on a key range of six priority areas from those:

Improving Unscheduled Care

Improving Planned Care

Improving Cancer and Palliative Care

Prevention and Reducing Health Inequalities

Children, Young People and Maternity

Improving Mental Health and Learning Disabilities and the 7 goals

In addition the Cluster has mapped throughout its GMO Action Plan where work is undertaken which overlaps with the remaining HB Strategic Priority Areas, Ministerial Priorities (July 2021) and addressing the Four Harms of Covid.

Other SBUHB Strategic Priority Areas

- Responding to Covid  (including addressing the four harms of Covid)

- Improving Patient Quality and the 5 Q&S goals

- Improving Planned Care

- Increasing Digital Capability

- Improving primary, community and therapy services

Ministerial priorities refreshed in July 2021:

- A Healthier Wales - as the overarching policy context

- Population health

- Covid - response

- NHS recovery

- Mental Health and emotional wellbeing

- Supporting the health and care workforce

- NHS Finance and managing within resources

- Working alongside Social Care

Clusters have also given consideration to the enablers and programmes in place which will support facilitation of the plan and wider priorities set out above and have set these out at the end of the GMO action plan in section 6 below.

Finally, Clusters have also taken account of the Four Strategic Programme priorities and will continue to address these throughout the year:

-  Accelerated Cluster Development;

-  Urgent Primary Care;

-  Community Infrastructure and

-  Mental Well-being

Taking account of these priority areas ensures a robust approach to delivering safe, quality services and improving health population whilst maintaining the lighter touch approach requested for the development of the IMTPs in the annual delivery period prior to the implementation of the national Accelerated Cluster Development Programme. The ACD outline specification discussed nationally is currently being considered by Cluster Leads to identify key requirements and constraints into 2022-23 as an ongoing process, alongside Health Board and Local Authority discussions in the region.

# 5. CLUSTER NEEDS HIGHLIGHTS

An extensive cluster needs profile has been developed for all 8 clusters within the SBUHB. This document is available separately, the content of the needs profile was considered for Upper Valleys Cluster with highlights set out below:

## SUMMARY

Obesity:

- The obesity prevalence (2019/20) for the Cluser GP registered population is 9.4%, above both the SBUHB average (8.2%) and the Wales average (8.3%). For Patients 16+ the prevelance is 11.5% (SBUHB 10%; Wales 10.2%)

Alcohol:

- Swansea Bay UHB has the highest percentage (21.1%) along with residents of Cardiff and Vale UHB area who drink more than the recommended guidelines. Consumption is above the Welsh average of 19% - Swansea (20.8%) and Neath Port Talbot (21.3%).

- Swansea Bay UHB also has the highest percentage (3.8%) of harmful drinkers compared to other health boards, with Neath Port Talbot having the highest level of harmful drinkers of all the Welsh Local Authorities.

- Neath Port Talbot has a slightly higher percentage (22.1%) of heavy binge drinkers than Swansea (20.6%). Both counties are above the Welsh average (20.0%)

- In 2017/18, Neath Port Talbot had a slightly higher proportion of alcohol specific hospital admissions (497 per 100,000) compared to the Wales average (477 per 100,00).

- Neath Port Talbot also had 1,846 per 100,000 acohol-attributable hospital admissions, higher than both the SBUHB and Wales averages (1,757 & 1,743 per 1000,00 respectively)

- With regards to Alcohol-specific mortality and Alcohol-attributable mortality (crude rates per 100,000 [2015-17]), Neath Port Talbot was above both the SBUHB and Wales Average

Screening:

Upper Valleys Cluster was

- below the bowel-screening target of 60% at 55.8% (2017/18)

- below the Cervical-screening target of 80% at 71.6% (2018-19

- below the Abdominal Aortic Aneurysm screening target of 80% at 71.6% (2018-19)

- above the Breast Screening target 70% at 72.9% (2019/20)

Influenza Vaccinations:

65 and older

- 78.6% were vaccinated, above the WG target of 75%. 3 practices met the target (Cluster range 72.3% – 83.7%)

6 months to 65 in at risk group

- 56.7% were vaccinated, above the WG target of 55% (range 51.4% – 62%)

  - year olds

- 58.1% were vaccinated (range 40.9 – 78.1% - 3 practices achieved  over 50% range 48.8 - 63.2%

50-64 year olds

- 43.2% were vaccinated (range 30.5% – 52.4%)

Diabetes:

- The prevalence of Diabetes in SBUHB (6.32%) is slightly below the Wales average (6.33%). Upper Valleys Cluster has a higher prevalence (6.92%)

Heart Failure:

- The prevalence of Heart Failure in SBUHB (1.18%) is slightly above the Wales average (1.11%). Upper Valleys Cluster prevalence is 1.45%

Mental Health and Wellbeing:

Mental Wellbeing

Swansea Bay UHB respondents reported highest level of low wellbeing in Wales. Adults aged 65 and over reported higher levels of wellbeing than younger age groups.

Sense of worthwhile- Swansea local authority had one of the lowest overall rating scores at 81.5. Individuals residing in Neath Port Talbot local authority reported a higher percentage than Swansea at 84.0

Low Sense of Anxiety: Swansea being the lowest (60.0) and lower than Wales (62.8). Age groups 55-64, 65-74 and 75+ were more likely to have a low sense of anxiety

High Sense of Life Satisfaction – Overall Swansea Bay UHB showed a moderately lower percentage (79.7) than Wales (81.3). Individuals in Swansea reported the highest percentage (80.4) within the region. The lowest being in Neath Port Talbot (79.2). Age groups 65-74, 25-34 and 16-24 were more likely to have a high sense of satisfaction.

High Sense of Happiness – Swansea Bay UHB showed the lowest percentage (72.0) than the rest of Wales and the Wales average (74.7). Swansea residents reported the highest percentage (73.5) within the region and compared to the Wales average (74.7). The lowest being in Neath Port Talbot (69.5) and lower than Wales (74.7). Age groups 65-74 and 75+ were more likely to have a high sense of satisfaction.

Impact of COVID

During the period immediately before the pandemic, 11.7% of Welsh people suffered severe mental health issues. This share climbed to 28.1% in April 2020. This means mental health conditions in Wales during the first lockdown almost tripled compared to the period before the onset of the pandemic. The deterioration in average mental health was equivalent to that associated with an individual moving from being employed to unemployed during the pre-COVID-19 period.

Young people experienced the largest deterioration as a result of COVID-19 at the beginning of the pandemic. The average GHQ score among those aged 16-24 in November 2020 rose by 3 points, or 24%, relative to the pre-pandemic period.1

On average, women exhibited worse levels of mental health after the onset of the pandemic, with the gap between reported wellbeing between men and women increasing from 9.9% to 14.1%.

Between April 2019-March 2021 there were604 referrals from Upper Valleys Cluster to the LPMHSS

Dementia

The prevalence of Dementia in SBUHB (.73%) is slightly above the Wales average (.070%). Neath Cluster prevalence is 0.92%

From a public health perspective, it is important to remember that while dementia usually affects older people it is not an inevitable part of the ageing process (WHO; 2012. Dementia: a public health priority). It may therefore, be amenable to primary prevention, awareness raising to reduce stigma and reducing barriers to early diagnosis and support for cares to reduce the economic burden and improve quality of life

Suicide:

Between 2014 and 2018 the suicide rate for Swansea Bay UHB was 12.3 per 100,000 population, equating to 208 recorded deaths by suicide. This is in line with the Wales average at 12.3 per 100,000. Additional analysis undertaken in early 2019 showed that during 2008-17 suicide rates were higher in males than females in both Swansea and Neath Port Talbot, which is in line with the national average. Among males, the rates were highest in the 35 – 64 year age group in Neath Port Talbot and the 25 – 54 years age group in Swansea.

There were 40 suicides in SBUHB between April 2020 - March 2021 with 12 being in NPT

Smoking

The percentage of adults (over 16 years old) who smoke (self-reported) is as follows:

- 17% in Swansea Bay UHB

- 18% in Swansea

- 17% in Neath Port Talbot

- 17% across Wales

The adult smoking prevalence in SBUHB (19.7%) is slightly higher than the Wales average (19.2%). Upper Valleys Cluster has a higher prevalence (19.8%). Neath Port Talbot has higher smoking-attributable admissions rate (1,578 EASR/100,000) than the Health Board average 1,498 EASR/100,000 ). Smoking attributable mortality is higher in persons aged 35+ in NPT (325/100,000 EASR) than SBUHB average (295/100,000) and the Wales Average (284/100,000)

Childhood immunisations

Upper Valleys Cluster achieved over 95% uptake in all childhood vaccinations for the 1 year; 2 years, 5 years and 14 years age groups. Areas for improvement are in the areas where performance was below 90% (teenage booster for 16 year olds, 4 in 1 pre-school booster and MMR (2 doses) for 4 year olds)

## LOCALITY KEY FACTS

- The Upper Valleys Cluster servers a (GP registered) population of 31,088 (as at 01.04.2021) and is the smallest cluster by registered population in the Health Board Area. (Source – NHS Wales Shared Services Partnership)

- It is 1 of 3 clusters within the county of Neath Port Talbot.

- Of the 20% most deprived LSOAs in Wales, 14 are within Neath Port Talbot, with 3 found within the Upper Valleys Cluster (Source - https://wimd.gov.wales/geography/la/W06000012?lang=en#&min=0&max=10&domain=overall)

- This area consists of 22 LSOAs. 11.8% of the cluster population live in a Lower Super Output Area (LSOA) classified as rural. (Source – IMTP 2020-2023)

- The Cluster geographically covers the wards: Lower Brynamman, Gwaun-Cae-Gurwen, Cwmllynfell, Pontardawe, Ystalyfera, Allt-wen, Rhos, Trebanos, Crynant, Seven Sisters, Resolven, Onllwyn, Glynneath and Blaengwrach(Source Upper Valleys IMTP)

- Based on the projected population growth in Neath Port Talbot, provided in section 2, there is a forecast of 5.91% increase in population between 2018 – 2043. Based on the resident population in the Upper Valleys cluster area of 35,031 (as at 2018) --Population projections by local authority and year (gov.wales)) this could increase to 37,101

- The Upper Valleys Cluster has approximately 10,940 people over the age of 65 years and over (18.7%) which is lower than the Welsh average of 21%. (Primary Source – Mid 2018 Population estimates (Source: Small area population estimates (2018), ONS) Secondary Source - Cluster IMTP

- The Cluster area has 4 GP practices (1 of which operates branch practices).

- The locality has 10 community pharmacies.

- There are 4 dental practices that offer NHS treatment and 3 optometric practices.

- There are 6 care homes (Source – GP Care Homes DES)

- There are 4 pharmacies in the Upper Valleys Cluster where spoken languages in addition to English, Welsh is noted.

- According to the 2011 Census 15.3% of people aged 3 years and above in Neath Port Talbot are able to speak Welsh (Source: https://statswales.gov.wales/Catalogue/Welsh-Language/Census-Welsh-Language/welshspeakers-by-localauthority-gender-detailedagegroups-2011census)

- According to Neath Council Local Development Plan (2010-2026) there are no homes that will be built in the Upper Valley Cluster during the 5-year period of this PNA from October 2021

- There are no developments that are likely to have an impact on the pharmaceutical needs of the locality

# 6. ACTION PLAN

How we developed this plan

Our plan is a flexible plan, informed by the strategic background and range of priorities, together with consideration of local needs highlighted above. It will be underpinned by ongoing work to develop implementation and performance plans against the stated Goals, Methods and Outcomes Action Plan. Future programmes of work such as those around Obesity Prevention, Diabetes prevention and Cancer, among others will be considered as the programme details evolve.

Key:

| SBUHB Strategic priority Areas | Addressing Ministerial Priorities |
| --- | --- |
| Responding to COVID | A Healthier Wales – overarching policy context |
| Improving Patient Quality and the 5 Q&S goals | Population Health |
| Improving Staff Experience | Covid Response |
| Improving Unscheduled Care | NHS Recovery |
| Improving Planned Care | Mental Health and Emotional Wellbeing |
| Increasing Digital Capability | Supporting the Health and Care Workforce |
| Improving Cancer and Palliative Care | NHS Finance and Managing within Resources |
| Prevention and Reducing Health Inequalities | Working Alongside Social Care |
| Children, Young People and Maternity |  |
| Improving primary, community and therapy services and the 6 priorities Primary and Community |  |
| Improving Mental Health and Learning Disabilities and the 7 goals |  |

| - IMPROVING PLANNED CARE |  |  |  |
| --- | --- | --- | --- |
|  | GOALS | METHODS | OUTCOMES |
|  | Provide more care in the community | - Implement the trial without Catheter (TWOC) project to manage patients in their own homes | - Better patient care. - Patient satisfaction - % of successful TWOCs - Length of time between referral and TWOC |
|  | Improve diagnosis and management of Hypertension | - Support patients to self-monitor their BP when necessary | - Early diagnosis of Hypertension - Management of blood pressure in patients with Diabetes and hypertension - No of patients’ blood pressure in target range - No of patients started/changed medication as a result of the monitoring |
|  | Maintain essential services in responding to COVID 19 | - Maintain up to date Business Continuity Plans. - Initiate Business Continuity Plans in response to significant events e.g. surges and outbreak - Review IPC measures in line with national guidance. | - Essential services are delivered in a safe environment. - Escalation of risk been managed effectively to maintain patient safety |
|  | Engage in prescribing management schemes & further improve antimicrobial stewardship and pain management | - Engage in the Prescribing Management Scheme (PMS) for 2022-23 - Ensure prescribing of antibiotics is in line with SBU HB recommendations where appropriate - Review prescribing data (which will be provided by Medicines Management to Clusters / Practices) on a regular basis to monitor progress - Continue to utilise CRP POC for the management of LRTI - Utilise supportive packages for QI work around UTI management / prophylaxis and 4Cs where appropriate - Ensure that analgesic agents are only prescribed where the benefits outweigh the risks and that patients are appropriately monitored and reviewed - Further develop the Cluster Pharmacists and medicines management technician roles | - Increased assurance that antibiotics are being prescribed appropriately - Maintenance of current low prescribing with aim of further reduction in prescribing of Co-amoxiclav, cephalosporin, fluoroquinolone and clindamycin items prescribed per 1,000 patients and a reduction in overall antibiotic prescribing - Aim for a reduction in the prevalence of healthcare associated infection (HCAI), including Clostridioides difficile infection and Staphylococcus aureus bacteraemia - Management of patient expectation in relation to antibiotic prescribing and pain management - Increased assurance that patients are prescribed analgesic therapy where the benefits outweigh the risks and that they are appropriately reviewed and monitored - Reduction in the prescribing of gabapentin, pregabalin, tramadol and other opioids. |
|  | Improved management of patients with diabetes | - Encourage uptake of diabetes education programme for patients newly diagnosed with diabetes | - Increased attendance at Diabetes education Programmes To improve patient awareness and self management of Type 2 diabetes within the Cluster population, Identify and manage patients who have pre diabetes |
|  | Reduce demand on outpatients and support improved referral to treatment times. | - Increase the use of Consultant Connect. - Increase the use of GPTR - Participate in the Extended Minor Surgery Service for transfer of low risk Basal Cell Carcinoma excisions from secondary care dermatology to the Cluster | - % of practices with bypass numbers on consultant connect - Improved communication between primary and secondary care - Patients can be treated in primary and community care - Reduced emergency admissions. |

|  | IMPROVING CANCER & PALLIATIVE CARE |  |  |
| --- | --- | --- | --- |
|  | GOALS | METHODS | OUTCOMES |
|  | Improve EOL for patients and patient’s family | - Engage with Compassionate Communities Programme. - Support Dying Matters weeks. - Pilot roll of ‘message in a bottle’ scheme | - Patients and their families experience better EOLC services. - Number of ‘message in a bottle’ distributed - Fewer people dying in hospital |
|  | Support patients with USC referrals to make lifestyle changes | - Explore engaging in the Cancer pre-habilitation project | - Patients benefit at the time of referral with suspected cancer, from interventions to maximise outcomes of treatment |

| - IMPROVING UNSCHEDULED CARE |  |  |  |
| --- | --- | --- | --- |
|  | GOALS | METHODS | OUTCOMES |
|  | Reduce demand on outpatients and support improved referral to treatment times. | - Increase the use of Consultant Connect. - Increase the use of GPTR | - Improved communication between primary and secondary care - Patients can be treated in primary and community care - Reduced emergency admissions. |
|  | Provide more care in the community | - Expand the Virtual Ward (Home First approach and reduce risk of readmission) - Review Virtual Ward performance | - Reduced unnecessary admissions - Support discharge from hospital - Vulnerable patients supported. |
|  | Ensure the provision of Signposting, information and assistance for all | - Raise awareness of ‘Choose Pharmacy’ and the common ailments service (CAS) | - Information, advice or assistance to signpost people who want – or need - urgent support or treatment to the right place, first time. - Appropriate treatment for minor ailments in a timely manner from the community pharmacy, preventing the need for presentation at GP practices |

| - IMPROVING MENTAL HEALTH & LEARNING DISABILITIES |  |  |  |
| --- | --- | --- | --- |
|  | GOALS | METHODS | OUTCOMES |
|  | Develop services to improve mental health and wellbeing of patients. | - Commission Low Level Mental Health Support Services from the 3rd Sector - Continue to work with LPMHSS to develop a cluster specific service with the aim of having more streamlined access. - Develop Social prescriber and Cluster Mental Health Practitioner roles. | - Reduction in demands on GP services, medicines. - Reduction in impact on Mental Health Services, Social Care. - Improved patient reported outcome measures. |
|  | Identify and support patients experiencing domestic violence | - Engage in the primary care IRIS project | - Patients experiencing domestic abuse are supported and kept safe |

| - CHILDREN, YOUNG PEOPLE & MATERNITY |  |  |  |
| --- | --- | --- | --- |
|  | GOALS | METHODS | OUTCOMES |
|  | Develop strategies to support parents of children with behavioural problems | - Review the ‘Understanding Why’ parenting Project - Consider continuing to implement the‘Understanding Why’ Parenting Pilot project. - Telephone support of parents of children with behavioural problems. - Virtual peer support groups working with local schools. | - Reduced isolation and Early identification of need for parental support - Reduce anxieties of parents and young people and family wellbeing - Peer interaction and support |
|  | Improve outcomes for the most vulnerable families within the NPT clusters | - Review the Specialist Health Visiting pilot service - Support the recruitment of a Specialist health visitor - Provide specialist Health Visiting advice and service to the Child and Family Team across the age span | - Integrated approach to assessments, thresholds and referrals. - Improved outcomes for the most vulnerable families - Improved communication between health, social services and third-party agencies - Improved education for health partners - Effective and efficient referral pathway for health partners - Improved safeguarding of children and Young people |

| - PREVENTION & REDUCING HEALTH INEQUALITIES |  |  |  |
| --- | --- | --- | --- |
|  | GOALS | METHODS | OUTCOMES |
|  | Improve uptake of childhood vaccinations | - Continue to maintain performance in the uptake of childhood immunisations in areas where targets have been achieved. - Build on existing working relationships with Health Visitors - Continue to educate parents and encourage vaccination uptake. | - Improved uptake of childhood imms - Improved health and wellbeing of children. Reduced morbidity & mortality - Reduced variation across cluster, Health Board and all Wales Position |
|  | Encourage uptake of Public Health screening programmes | - Provide opportunities to attend cervical screening in GP practices or sexual health clinics - Encourage patients to engage with screening programmes opportunistically - Review data as it becomes available | - Increased screening uptake - Reduced cancer rates |
|  | Deliver an enhanced Flu vaccination Programme | - Regularly review IVOR data for flu vaccination when available - Develop and implement a seasonal flu plan aimed at early administration of the flu vaccine to eligible at risk patients and increasing uptake | - Increased uptake of influenza vaccine in target groups - Reduced mortality / hospital admissions due to influenza. |
|  | Develop a consistent approach to reduce smoking prevalence | - Develop and implement sustainable processes/initiatives that lead to increased referrals to the Help Me Quit local smoking cessation services - Increase engagement with the local Pharmacies Level 3 service. | - Increased referrals to “Help Me Quit” - Reduced local prevalence of smoking – reduced morbidity / mortality |
|  | Support patients to manage their weight | - Develop local services to support the HB Obesity Programme | - Patients are supported to manage their weight. |
|  | To improve patient awareness and self management of Type 2 diabetes within the Cluster population, Identify and manage patients who have pre diabetes | - Delivery of the two year All Wales Diabetes Prevention Programme (AWDPP). | - National evaluation based on a core set of patient clinical outcomes to be finalised. |
|  | Develop strategies which contribute to the decarbonisation of the environment to help with the current climate emergency | - Engage with pharmacists and prescribers to build upon and support existing efforts to encourage responsible disposal of inhalers through discussions with patients, information leaflets, posters and media | - An increase in carbon friendly disposal of inhalers |
|  | To support individuals who are frail, socially isolated or at risk of falls and empower individuals with long term health conditions with a timely and responsive service | - A timely responsive Occupational Health Review | - Reduction in Patient and carer distress - Improved participation in activites and stabilisation of health and wellbeing - Positive patient feedback |

| - ACTION PLAN ENABLERS |  |  |  |
| --- | --- | --- | --- |
| Technological | Workforce | Communication & Engagement | Finance |
| Ask My GP | Business Implementation and Development Manager | Twitter; Facebook and Websites information | WG Funding |
| My Health Online | Cluster admin support officer | Patient Engagement Surveys | Health Board funding for Virtual Ward |
| Vision 360 | Occupational Therapist | Emergency Planning Response and Resilience Plan |  |
| My Surgery App | Social Prescriber |  |  |
| Microsoft Teams | Counsellors |  |  |
| Consultant Connect | Virtual Ward staff |  |  |
|  | Paediatric Occupational Therapist |  |  |
|  | Specialist health Visitor |  |  |
|  | Audiologist |  |  |
|  | Cluster Lead |  |  |
|  | Cluster Members |  |  |
|  | Health Board Primary Care Support Staff |  |  |
|  | Induction Pack for New Cluster members |  |  |

# 7. GOVERNANCE ARRANGEMENTS

The Cluster members meet 5 times a year at formal Cluster Board meetings, to plan and review progress and strategic direction related to the Cluster IMTP and to routinely address: Cluster Plan and associated planning actions, Cluster Spending Plan, Risk Register Update, Sustainability and Finance. Declarations of interest are addressed as standing items.

Welsh Government and Health Board allocated Cluster Funds are spent and allocated in accordance with Swansea Bay University Health Board’s Standing Financial Instructions. Non-Welsh Government funds are administered on behalf of the Cluster in accordance with agreed Cluster and funding body policies and procedures.

## MEMBERS

The core membership of the Primary Care Cluster shall comprise of representation from all local services involved in health and social care within the cluster area and shall include:

- Cluster Lead (Chair)

- Representation for each GP Practice* In Upper Valleys Cluster there will be representation from 4 GP Practices. This will include as a minimum a GP* and will also extend to Practice Manager.

- One representative from Community Pharmacy - to represent all community pharmacies within the cluster

- One representative from Dental - to represent dental services within the cluster

- One representative from Optometry - to represent optometry services within the cluster

- Primary, Community & Therapies Services Senior Manager

- Cluster Development Manager

- Nominated representative for Adult Nursing and Children’s Nursing

- Medicines Management Representation

- Nominated representative for Therapies; two members to represent the breadth of therapies services

- Representation from Mental Health

- Third Sector / Community Voluntary Service

# 8. CLUSTER ASSETS PROFILE

## Community Assets

Primary Care Estate is used to support the development and implementation to community based clinics e.g. spirometry and counselling clinics in the Upper Valleys.

The cluster is mainly semi-rural with beautiful countryside and natural features. It has a number of public footpaths and cycling trails, woodlands, rivers and canals, bridle paths and an abundance of wildlife, flora and fauna. There are also a number of former coal mining villages in the cluster area. The cluster has:

- 4 GP practices. One of which holds 2 contracts; 1 with Swansea bay Health Board and the other with Hywel Dda Health Board.

- 3 Dental Practices

- 10 community pharmacies

- 2 Leisure Centres

- 6 Libraries (4 community libraries and 2 local authority run libraries)

- Several Community centre

- 15 primary schools, 2 secondary schools

- Voluntary Sector organisations including mental health, physical activity and other charities aimed at supporting health and wellbeing

# 9. CLUSTER WORKFORCE PROFILE

Whilst outlining the planned Upper Valleys Cluster actions for 2022/23, the following roles have been identified as either required or to be considered, to enable implementation of the Cluster Action Plan:

| Role | WTE | Outcomes / Impact |
| --- | --- | --- |
| Occupational Therapist | 1 | To establish and deliver an early intervention OT service in primary care for those who are frail, socially isolated, at risk of falls and/or struggle to manage activities of daily living secondary to symptoms of a chronic condition. - Reduce the number of avoidable primary care consultations, thereby increasing GP capacity and allowing patients to be seen by the right professional, at the right time and in the right place. - Minimise crisis situations that may lead to presentation to hospital and secondary service dependency, by proactively resolving health and social issues at an earlier stage. - Empower individuals to manage their own health and well-being through working co-productively with patients to increase self-management skills. - Reduce physical and mental health decline and promote independence through the provision of a flexible service delivering early, responsive support. - Identify regular users and those who may be frail and aim to resolve or minimise potential underlying issues. |
| Paediatric Occupational Therapist | .2 | To provide emotional and wellbeing support and guidance to parents who have concerns about their child’s development/ behaviour/ wellbeing/ sleep hygiene etc. - Support for families during COVID pandemic - Reduced isolation and Early identification of need for parental support - Referral pathway for GPs and front line workers for parents/ young people to, who present with concerns around child development/ behaviour/ wellbeing/ sleep hygiene - Advice on developmental concerns - Family wellbeing - Direct links with education - Improved communication with parents and schools |
| Social prescriber | 1 | (.5 WTE funded by the Cluster and .5 WTE from the HB MH Transformation Fund) To provide Mental Health and wellbeing support for patients with low to moderate mental health issues. - Timely access and robust referral pathways for patients - Direct intervention and onward referral where appropriate - Improved outcomes for patients including less medication intervention - Saving of GP time by patients receiving the right care at the right time from the right Health Care professional |
| Specialist health visitor | 1 | (1WTE part funded by the cluster as a shared resource between Afan, Neath and Upper Valleys) To Provide specialist Health Visiting advice and service to the Child and Family Team across the age span - Integrated approach to assessments, thresholds and referrals. - Improved outcomes for the most vulnerable families - Improved communication between health, social services and third-party agencies - Improved education for health partners - Effective and efficient referral pathway for health partners - Effective evaluation will ensure longevity of the service |
| Audiologist |  | (Cluster contribution to an SBUHB – wide roll out of audiology services in primary care) To provide a wax removal and first contact hearing and tinnitus service for the population of the cluster within the community - First contact assessment and advice in primary care - Reduced consultations required with GPs (increase in GP capacity) - Reduced pathway complexity and length - Patients receive specialist hearing and tinnitus assessment and advice closer to home - Patients receive specialist tinnitus advice at first contact Quicker identification and time sensitive treatment of Sudden Sensorieneural hearing loss for patients reporting sudden hearing loss |
| Cluster Support Officer | .25 | To provide administrative support to the cluster lead and for cluster projects - Effective admin support for the cluster lead - Efficient data collection for cluster projects and activities - Support for cluster planning and project delivery |
| Business Implementation and Development Manager | .6 | To provide support to the cluster lead and members as well as leadership for implementation of cluster projects - Effective project implementation, monitoring, evaluation and reporting - Support for the planning process including robust needs assessments - Implementation of the cluster IMTP |

# 10. CLUSTER FINANCIAL PROFILE

Upper Valleys - 2022/23

| BUDGET 22/23 |  |
| --- | --- |
| WG allocation 22/23 | £ 224,786.00 |
| Brokerage from 21/22 | £ - |
| Total available for 22/23 | £ 224,786.00 |

|  | 2022 - 2023 |
| --- | --- |
| Project | Agreed Total Spend |
| Social Prescriber |  |
| Business Implementation Manager | £33,768.00 |
| CRP POC Testing | £4,840.00 |
| INPS - V360 support contract | £3,930.00 |
| Parenting in a Pandemic | £4,132.00 |
| OT in primary Care | £61,864.00 |
| Cluster support officer | £1,920.00 |
| Specialist Health Advice and Advocacy | £10,458.00 |
| Clinical Summarisers | £39,672.00 |
| Mental Health Counselling | £34,999.50 |
| Audiology | £6,799.00 |
|  | £202,382.50 |

The Cluster will continue to develop initiatives designed to meet the health and wellbeing needs of the local population and is considering significant spend around extending the Social prescriber role, increased Point of Care testing, and an enhanced flu vaccination programme.

RETURN TO TOP

Source PCIP http://gig01srvisdlogi/pcip/rdPage.aspx?rdReport=Prevalence.Default#clusters

Source SBUHB PNA

Source https://phw.nhs.wales/services-and-teams/screening/

Source PHW Ivor Data at 23/3/21 Vaccine Preventable Disease Programme | Swansea Bay UHB IVOR (wales.nhs.uk)

Source PCIP (2019/20) http://gig01srvisdlogi/pcip/rdPage.aspx?rdReport=Prevalence.Default#clusters

Source PCIP (2019/20) http://gig01srvisdlogi/pcip/rdPage.aspx?rdReport=Prevalence.Default#clusters

(Source PHW Mental Wellbeing in Wales Tool 2018 reported in SBUHB PNA)

Source Mental Health in Wales during COVID-19 Source COVID-19-Mental-health-FINAL-08-07-2021.pdf (cardiff.ac.uk) accessed 20/8/21)

SBUHB mental health directorate data intelligence

Source PCIP (2019/20) http://gig01srvisdlogi/pcip/rdPage.aspx?rdReport=Prevalence.Default#clusters

Taken from Cwm Tawe (check source)

https://statswales.gov.wales/Catalogue/National-Survey-for-Wales/Population-Health/Adult-Lifestyles/adultlifestyles-by-localauthority-healthboard 2018/19-2019/20

Source PNA

COVER data (check date)

Source - https://www.npt.gov.uk/media/7321/ldp_written_statement_jan16.pdf?v=20170727124344)