| Meeting Date | 30 January 2025 |  | Agenda Item |  |  | 6.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Health Board |  |  |  |  |  |
| Report Title | Gold Command for Maternity and Neonatal Services Progress Report |  |  |  |  |  |
| Report Author | Liz Wonnacott, Head of Service – Medical Director Kathryn Greaves, Clinical Director for Midwifery Dr Raj Krishnan, Deputy Executive Medical Director |  |  |  |  |  |
| Report Sponsor | Dr Richard Evans, Executive Medical Director Hazel Powell, Interim Director of Nursing and Patient Experience |  |  |  |  |  |
| Presented by | Dr Raj Krishnan, Deputy Executive Medical Director |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of the report is to set out the progress discussed as part of the gold command arrangements established for scrutiny and assurance of improvement within maternity and neonatal services. |  |  |  |  |  |
| Key Issues | - In December 2023, the health board’s maternity and neonatal services were placed by Welsh Government into enhanced monitoring; - The escalation status followed an unannounced inspection by Healthcare Inspectorate Wales (HIW) in September 2023 during which seven areas of immediate action were identified; - An action plan was shared with HIW, with a follow-up unannounced visit in April 2024 to review progress; - Alongside this are other external reports and inspections which require action, as well as open incidents to be closed; - To scrutinise and seek assurance that the work required is being undertaken, a gold command structure has been established; - The report sets out the latest reported position against all areas of focus. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - ACKNOWLEDGE the work to close additional actions raised during enhanced monitoring meetings; - BE ASSURED the maternity and neonatal dashboards will be in place by 1st April 2025; - BE ASSURED progress against the HIW improvement plans is on track with all to be closed by the end of January 2025; - BE ASSURED the actions to address the Health Education and Improvement Wales (HEIW) maternity and neonatal specific actions are in progress; - BE ASSURED the group has included within its remit the need to ‘horizon scan’ to look ahead to potential visits and/or reports which may require action. |  |  |  |  |  |

GOLD COMMAND FOR MATERNITY AND NEONATAL SERVICES PROGRESS REPORT

- INTRODUCTION

The purpose of the report is to set out the progress discussed as part of the gold command arrangements established for scrutiny and assurance of improvement within maternity and neonatal services.

- BACKGROUND

In December 2023, the health board’s maternity and neonatal services were placed into enhanced monitoring by Welsh Government. This was because of concerns as to the quality and safety of the care provided raised by members of the Senedd and families who have accessed the services.

The escalation status followed an unannounced inspection by Healthcare Inspectorate Wales (HIW) in September 2023 during which seven areas of immediate action were identified. In addition, the formal report for the visit set out a number of recommendations for improvement, and an action plan was shared with HIW. HIW undertook a follow-up unannounced visit in undertaken in April 2024 to review progress and while some of work had been completed, there were still improvements required.

Alongside this are two Health Education and Improvement Wales (HEIW) targeted inspections of obstetrics and gynaecology in February and July 2024 as part of HEIW’s quality framework to identify areas working well or in need of improvement, as well as national reports which identify areas of improvement for maternity and neonatal services across the UK.

To scrutinise and seek assurance that the work required is being undertaken, a gold command structure has been established, led by the Deputy Medical Director as the senior responsible officer, supported by the Chief Operating Officer and Interim Director of Nursing and Patient Experience. Meetings are attended by members of the Singleton/Neath Port Talbot Service Group’s senior team under which sit maternity and neonatal services.

- GOVERNANCE AND RISK ISSUES

The main areas of focus for the group are enhanced monitoring, inspection action plans, open incidents, national reports and horizon scanning. Progress includes:

- Enhanced Monitoring

Senior members of the service group along with key members of the executive team meet with Welsh Government on a monthly basis to share progress to achieve de-escalation. During these meetings, actions additional to the criteria already set by Welsh Government can be allocated and these are reviewed within the gold command meetings to ensure completion. There is one outstanding action:

- Maternity dashboard – work is progressing to build and populate dashboards for maternity and neonatal services for use by the department and service group’s quality and safety groups. This will allow data to be triangulated and any themes identified for onward escalation to the health board’s quality and safety forums. The dashboard will be in place for 1st April 2025.

Work has commenced to complete the framework which sets out the criteria for de-escalation. A baseline and gap analysis has been established which show progress as it is made and will form part of the presentations to the enhanced monitoring meetings with Welsh Government from February 2025.

- Inspection Action Plans

- HIW Inspections

As part of the work to address the recommendations made by HIW, the 2019 HIW improvement plan and 2019 Birth Centre Improvement Plan were revisited, and both have been closed in full.

In relation to the improvement plans for 2023 and 2024, the following progress has been made:

| Report | Actions |  |  |  |
| --- | --- | --- | --- | --- |
|  | Total | Open | Due in Jan. 2025 | Overdue |
| 2023 Singleton Hospital Immediate Improvement Plan | 41 | 0 | 0 | 0 |
| 2023 Singleton Hospital General Improvement Plan | 118 | 1 | 1 | 0 |

| Report | Actions |  |  |  |
| --- | --- | --- | --- | --- |
|  | Total | Open | Due in Jan. 2025 | Overdue |
| 2024 Singleton Hospital Immediate Improvement Plan | 6 | 0 | 0 | 0 |
| 2024 Singleton Hospital General Improvement Plan | 37 | 0 | 0 | 0 |

There had been one action due for closure in December 2024 which was delivered:

- The health board should review and improve feedback mechanisms for staff to feedback on leadership team.

Café conversations and other engagement events have enabled a thematic analysis of feedback mechanisms to be established, supported by an action plan. This has now been signed off within the service and will be taken through the service group’s Workforce Retention and Engagement Group to agree timescales for delivery.

The original target had been to complete all the improvements plans by December 2024 with the exception of two recommendations, one of which was the recruitment of a women’s experience midwife recommendation.

Previous reports advised of a deadline of April 2025 for completion of this action. However, on reviewing the ask, it was for the potential to recruit to be considered. As funding has been identified and the job description completed, with just the recruitment of a suitable candidate to be undertaken, it was agreed by the gold command in January 2025 that this is closed. The group would be kept apprised of the recruitment process progress. The job description has been through the job evaluation and Welsh translation process and is awaiting the publication of the job advert on the Trac system by the recruitment team for appointment by April 2025.

The completion of both of these actions means that the 2024 Singleton Hospital General Improvement Plan is now closed.

Only one action across all the improvement plans remains and this is on the 2023 General Singleton Hospital Improvement Plan:

- 95% compliance with Breast Feeding Initiative (BFI) training

The BFI’s target of 80% has already been achieved however the recommendation from HIW was for 95% compliance. Staff have been rostered to undertake the training, and the final training session took place week commencing 13th January 2025. The compliance figures are in the process of being validated which will provide the evidence to close the action.

Therefore, by the end January 2025, all HIW improvement plans will be closed and correspondence sent outlining the evidence to demonstrate this. It is anticipated HIW will return to review the progress made but no formal arrangements have been made to date.

- Health Education and Improvement Wales (HEIW)

Following the two visits earlier in 2024, an action plan is place the majority of which has already been delivered and spans obstetrics and gynaecology.

There is only one outstanding area relevant to obstetrics, which is job planning for consultants and the following progress has been made:

|  | Number of Consultants | Signed off | With Consultant to Sign Off | Booked |
| --- | --- | --- | --- | --- |
|  | 18 | 4 | 10 | 4 |

The timescales for completion are currently being worked through as they are dependent on when the meetings take place and the consultants subsequently sign-off their job plans.

Since the two visits, a new cohort of trainees have rotated to the service and no concerns have been raised, with a visit taking place by the Deputy Medical Director and Associate Medical Director for Children and Young People in November 2024 to seek assurance. Some of work to improve the experience of trainees has included:

- Providing feedback to resident doctors based on ‘You Say, We did’;

- Multi-disciplinary team to be appointed;

- Associate Medical Director for Children and Young People to attend multi-disciplinary team meetings;

- Team lunches and time to come together to talk.

Appendix one and two set out the actions completed to date.

HEIW have indicated they will return in March or April 2025 and the exact date is in the process of being confirmed.

- Open Incidents

The HIW action to continue the work to reduce the backlog of open Datix incidents in a timely manner and monitor progress has been closed on the 2024 general improvement plan as the work to reduce the backlog is ongoing.

The service is now in a position where it is closing more incidents each month than are opened. For example, in November 2024, 127 incidents were reported, and 162 closed. This demonstrates the backlog is reducing.

|  | Maternity |  | Neonatal |  |
| --- | --- | --- | --- | --- |
|  | Open | Overdue | Open | Overdue |
| Incidents | 152 | 98 | 21 | 8 |
| Duty of Candour | 10 |  | 0 |  |
| Concerns | 12 | 11 | 0 | 0 |
| Redress | 38 |  | 3 |  |
| Claims | 57 |  | 5 |  |

Sprint sessions are taking place to close incidents as soon as possible where no harm has occurred, while the more serious are investigated by the midwifery team. Of those incidents which are overdue, the majority are from August 2024 onwards, with the few prior to this complex and some subject to legal proceedings.

The clinical leads for maternity and neonatal continue to prioritise the responses to concerns, redress and claims to sign-off the responses, but the majority of the ones open are complex and part of legal proceedings, with 22 of the 38 redress claims originating from incidents.

Two main themes have been identified from the incidents and/or concerns being raised:

- Delayed induction of labour – work to address this is taking place on a national level as it is a result of changes to the NICE (National Institute for Clinical Excellence) guidance. A local task and finish group led by an obstetric consultant will consider any improvements that can be made locally and will report into gold, including the timescales once agreed at a national level.

- Communication – work has been undertaken through the weekly communication meetings to remind staff of the importance of providing consistent information across antenatal clinics and ward rounds as women often see different staff members over the course of their care.

- National Reports

- MBRRACE-UK (Mothers and Babies: Reducing Risk through Audits and Confidential Enquiries across the UK)

There are two reports from MBRRACE-UK currently being worked though by the service.

The first being the ‘State of the Nation Report Saving Lives, Improving Mothers’ Care October 2024 Surveillance findings and lessons learned to inform maternity care from the UK and Ireland Confidential Enquiries into Maternal Deaths from thrombosis and thromboembolism, malignancy and ectopic pregnancy 2020-2022, and morbidity findings for recent migrants with language difficulties’. The service has benchmarked itself against the findings and no immediate causes for concern have been identified. A report and action plan has been populated and is now under review by the senior midwifery team to identify any gaps or areas for improvement and timescales for these. The final version will be shared with the gold command at its next meeting.

The national MBRRACE-UK report setting out how many stillbirths and neonatal deaths have occurred is published two years in arrears, so the report published in 2024 provided data from 2022. The data for 2023 will likely be published later in 2025. However, maternity and neonatal services have worked through health board data to ascertain how many cases there have been. So far, there is nothing to suggest the health board is an outlier and all cases had been reviewed for learning and closure using the perinatal mortality review tool (PRMT).

- Audit Wales Review of Operational Governance

The service has considered the recommendations made within the report around governance and leadership as these were the ones most relevant to the current work. The service group has recently undergone an organisational change process, resulting in a new leadership and governance structure, which address the findings of the report. These have been shared with the members of the gold command for assurance.

The service group reviewed the report more widely across all of its services and developed an action plan to address the recommendations but there were no concerns directly related to maternity or neonatal services.

- NNAP (National Neonatal Audit Programme)

NNAP identified the neonatal intensive care unit at Singleton Hospital as an outlier for late onset sepsis in 2023. A quality improvement programme has been delivered and the gold command was assured that no further issues have been identified. The learning from the quality improvement programme was presented to the Clinical Outcomes and Effectiveness Group in January 2025 and there was confidence that the health board would not be an outlier in the next iteration.

- VON (International Vermont Oxford Network)

The VON report, which is a neonatal quality improvement review and is similar to NNAP has been received and has identified the health board as within the national average with no concerns raised.

- Horizon Scanning

As part of the gold command’s role, it looks ahead to any potential reviews or reports relating to maternity or neonatal services. These could be regular national reports which are issued as standard or external reviews being undertaken either of the health board itself or other maternity and neonatal services from which there could be learning. Only one is expected, which is the report from Llais, an independent statutory body set up by Welsh Government for people to have their say in relation to health and social services. Llais undertook an assurance visit to the maternity services towards the end of 2024 and a report on its findings is expected. Any actions required will be discussed through the gold meetings.

- Other Areas of Discussion

As progress continues to be made, the agenda for the gold meetings is extending more widely than the initial areas first outlined to provide further assurance:

- Leadership Proposal

The service group approved an options appraisal to establish a leadership programme to support the maternity and neonatal leadership team to develop further as compassionate leaders as well as a robust and sustainable well-functioning team. The preferred option agreed was shared with the gold command group and includes:

- Psychometric testing using ‘Insights Discovery;

- The ‘Team Journey’ development programme;

- 360 feedback mechanism (linked to the ‘Team Journey’ programme);

- Action Learning Sets (ALS);

- PADR (personal and development review)/Appraisal – Leaders that Live our Values;

- Bite-size learning sessions;

- Teams-based quality improvement (QI) training;

- Individual coaching/mentoring.

Outline proposals were set out for each of the sections which will now be expanded to create the formal leadership programme including timeframes and expected outcomes. This will be implemented over a two-year period from January 2025.

- Workforce Availability

A key recommendation by HIW and enhanced monitoring was to improve staff availability. Although there was an improvement in sickness absence with a decrease from 11.99% to 6.5% between September 2023 to August 2024, a small spike in absences was seen in the autumn months, but this was in-keeping with absences across all services due to high flu, Covid and other virus rates, and was not unique to maternity and neonatal services. The maternity management team continues to work through the planned improvements to effectively manage sickness absence across the service. A progress report will be shared with the Workforce and OD Committee early in 2025.

- Risk

The health board was asked at the October 2024 enhanced monitoring meeting to provide an updated risk register at its next meeting. This was delivered in November 2024 and a discussion undertaken as to reducing the risk scores based on the progress which has been made. There are three risks currently on the health board risk register relating to maternity and neonatal services

- Screening for Fetal Growth Assessment in line with Gap-Grow (G&G) – risk score 12

- Inability for maintaining Birthrate Plus ® complaint rosters – risk score 16

- High Quality Choices in Place of Birth – risk score 16

These have been reviewed by the service group to consider reducing the two with a score of 16 to 12 to reflect progress made. The service submitted a paper to the risk scrutiny panel following the gold command meeting indicating intent to reduce scores and de-escalate, but it was felt it needed wider engagement. While this is undertaken, an updated narrative has been included that does not reduce the scores, but presents an improved situation. The revised scorecards will be shared with the gold command meeting once the risk scores and mitigating actions have been agreed by the panel.

- Internal Quality Assurance Visit

The health board’s quality improvement team undertook a review of the services against internal quality assurance indicators. Ward managers and the site matron have developed an intense programme for collating evidence to demonstrate closure of the recommendations raised following the visit. Progress will be monitored through the gold command meetings.

- FINANCIAL IMPLICATIONS

There are no financial implications associated with this report.

- RECOMMENDATION

Members are asked to:

- ACKNOWLEDGE the work to close additional actions raised during enhanced monitoring meetings;

- BE ASSURED the maternity and neonatal dashboards will be in place by 1st April 2025;

- BE ASSURED progress against the HIW improvement plans is on track with all to be closed by the end of January 2025;

- BE ASSURED the actions to address the Health Education and Improvement Wales (HEIW) maternity and neonatal specific actions are in progress;

- BE ASSURED the group has included within its remit the need to ‘horizon scan’ to look ahead to potential visits and/or reports which may require action.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| The health board is dedicated to ensuring that pregnancy and childbirth is a safe and positive experience for all service users in order to support healthy life choices and to give children the best start in life. This requires safe and effective maternity and neonatal services. The actions identified by the reviews and external bodies will support the improvements needed to achieve this. |  |  |  |
| Financial Implications |  |  |  |
| There are no financial implications associated with the report. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| There are no legal implications associated with the report. |  |  |  |
| Staffing Implications |  |  |  |
| There are no staffing implications associated with the report. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The health board has a 10-year vision to be a high-quality organisation. Work being undertaken to address the concerns raised and to de-escalate from enhanced monitoring will not only support that vision but develop maternity and neonatal services which are safe and sustainable in the longer-term. |  |  |  |
| Report History |  | Regular report |  |
| Appendices |  | Appendix One – HEIW action plan Appendix Two – actions following Deputy Medical Director visit to obstetrics and gynaecology |  |